## KPIs
KPI | Value
As of | 15 Oct 2026 (reports up to 14 Oct)
Open POs | 412
Open qty (pcs) | 1900020
Open FOB value (USD) | 18601449.36
October POs (planned ex-factory in Oct) | 160
October shipped so far | 60
October shipped on time | 56
October open, predicted on time | 82
October predicted on-time % | 0.8625
October open, predicted late (excl. already late) | 13
Already late (past ex-factory, not shipped) | 7
Value at risk (USD) = FOB of At risk + Critical + Late | 2400006.24
POs at risk (At risk + Critical + Late) | 48
Top 3 factories by value at risk | GRL 774,059, IRB 477,578, SLM 428,400
Top 3 share of value at risk | 0.7
Air-freight exposure (USD) | 539720.28
Factories reported today | 18 of 22
Band counts | On track: 354, At risk: 28, Critical: 13, Watch: 10, Late: 7
Shipping rest of October (POs / pcs / USD) | 95 / 455,364 / 4,879,805

## Open PO Predictions
PO No | Factory Code | Factory Name | Department | Style No | Style Name | Gauge | Order Qty | FOB Value USD | Planned Ex-factory | State | Bottleneck Stage | Bottleneck Rate pcs/day | Required Rate pcs/day | Projected Finish (WD) | Completion Day N | Available WD | Slack WD | Projected Ex-factory | Slip Days | Score Schedule | Score T&A | Score Factory OTD | Score Quality | Score Freshness | Risk Score | Band | On-time Probability | Value at Risk USD | Air-freight Exposure USD | Drivers | Merchandiser | Seed Scenario
71008823 | IRB | Ironbridge Sweaters Ltd. | Women | KAW26-W-3510 | Wool-blend Turtle-neck Pullover | 7 | 4560 | 42088.8 | 2026-09-28 | In production | Washing | 108.4 |  | 1.5 | 2 | 0 | -2 | 2026-10-18 | 20 | 50 | 16 | 1500% | 10 | 0 | 91 | Late | 2% | 42088.8 | 14797.2 | Yarn in-house 5 days late; PP sample approval 6 days late; Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | late
71009027 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-2874 | Wool-blend Long Cardigan | 5 | 2412 | 31597.2 | 2026-09-24 | In production | Linking | 51.7 |  | 5.5 | 6 | 0 | -6 | 2026-10-22 | 28 | 50 | 20 | 1500% | 0 | 0 | 85 | Late | 2% | 31597.2 | 12470.04 | Yarn in-house 8 days late; PP sample approval 6 days late; Factory OTD 68% (12 months) | Farhana Rahman | late
71009183 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-8278 | Merino V-neck Pullover | 12 | 3888 | 61119.36 | 2026-10-06 | In production | Linking | 114.1 |  | 2.51 | 3 | 0 | -3 | 2026-10-19 | 13 | 50 | 16 | 1420% | 0 | 5 | 85 | Late | 2% | 61119.36 | 8339.76 | Yarn in-house 7 days late; PP sample approval 5 days late; Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | late
71009071 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-3594 | Acrylic Shawl-collar Cardigan | 5 | 9120 | 73416 | 2026-10-08 | In production | Trimming & Mending | 279.1 |  | 1.5 | 2 | 0 | -2 | 2026-10-18 | 10 | 50 | 12 | 1500% | 5 | 0 | 82 | Late | 2% | 73416 | 39124.8 | Yarn in-house 9 days late; Factory OTD 70% (12 months) | Tanvir Hasan | late
71010360 | GRL | Greyloom Knitwear Ltd. | Men | KHO26-M-5174 | Cotton-blend Shawl-collar Cardigan | 5 | 2172 | 22545.36 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-12-01 | 6 | 44 | 20 | 1500% | 0 | 0 | 79 | Critical | 2% | 22545.36 | 10273.56 | Yarn in-house revised to 19 Oct (8 days late); PP sample approval 5 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009831 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KAW26-K-3080 | Kids Acrylic Jacquard Jumper | 7 | 2772 | 12917.52 | 2026-10-31 | In production | Knitting | 106.9 | 122.2 | 14.51 | 15 | 13 | -2 | 2026-11-02 | 2 | 38 | 12 | 1420% | 10 | 5 | 79 | Critical | 15% | 12917.52 | 2591.82 | Knitting 107 pcs/day vs 122 needed; Yarn in-house 8 days late; Factory OTD 72% (12 months); Last inspection failed; No report since 12 Oct | Nusrat Jahan | pred_late
71010686 | IRB | Ironbridge Sweaters Ltd. | Kids | KHO26-K-9338 | Kids Wool-blend Jacquard Jumper | 7 | 3420 | 24384.6 | 2026-11-19 | Pre-production | [5 empty] | 30 |  | 2026-11-26 | 7 | 45.5 | 12 | 1500% | 5 | 0 | 78 | Critical | 2% | 24384.6 | 3573.9 | Yarn in-house revised to 12 Oct (10 days late); Factory OTD 70% (12 months) | Tanvir Hasan | pred_late
71009470 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-1995 | Lambswool V-neck Pullover | 7 | 5052 | 71233.2 | 2026-10-20 | In production | Linking | 162.2 | 608 | 9.5 | 10 | 4 | -6 | 2026-10-27 | 7 | 45.5 | 8 | 1500% | 10 | 0 | 78 | Critical | 2% | 71233.2 | 18338.76 | Linking 162 pcs/day vs 608 needed; Yarn in-house 5 days late; Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | pred_late
71008741 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-6776 | Merino V-neck Pullover | 7 | 2808 | 49785.84 | 2026-10-03 | In production | Knitting | 65.1 |  | 5.49 | 6 | 0 | -6 | 2026-10-22 | 19 | 50 | 12 | 1500% | 0 | 0 | 77 | Late | 2% | 49785.84 | 8803.08 | Yarn in-house 8 days late; Factory OTD 68% (12 months) | Farhana Rahman | late
71010305 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-1736 | Lambswool V-neck Cardigan | 7 | 9600 | 158400 | 2026-10-29 | In production | Linking | 411.1 | 680 | 18.54 | 19 | 12 | -7 | 2026-11-07 | 9 | 48.5 | 12 | 1500% | 0 | 0 | 76 | Critical | 2% | 158400 | 38016 | Linking 411 pcs/day vs 680 needed; Yarn in-house 8 days late; Factory OTD 68% (12 months) | Farhana Rahman | hero
71008973 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-5042 | Recycled Crew-neck Pullover | 12 | 5172 | 36255.72 | 2026-10-20 | In production | Knitting | 189.2 | 504 | 6.5 | 7 | 4 | -3 | 2026-10-24 | 4 | 41 | 20 | 1500% | 0 | 0 | 76 | Critical | 2% | 36255.72 | 10809.48 | Knitting 189 pcs/day vs 504 needed; Yarn in-house 9 days late; PP sample approval 3 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71010120 | GRL | Greyloom Knitwear Ltd. | Kids | KAW26-K-2568 | Kids Cotton-blend Cardigan | 7 | 4572 | 27386.28 | 2026-11-10 | In production | Knitting | 137 | 182.9 | 28.54 | 29 | 22 | -7 | 2026-11-18 | 8 | 47 | 12 | 1500% | 0 | 0 | 74 | Critical | 2% | 27386.28 | 4777.74 | Knitting 137 pcs/day vs 183 needed; Yarn in-house 8 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71010013 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-4107 | Merino V-neck Pullover | 7 | 6384 | 100228.8 | 2026-10-29 | In production | Knitting | 193.9 | 312.3 | 17.5 | 18 | 12 | -6 | 2026-11-05 | 7 | 45.5 | 8 | 1500% | 5 | 0 | 74 | Critical | 2% | 100228.8 | 20013.84 | Knitting 194 pcs/day vs 312 needed; Yarn in-house 7 days late; Factory OTD 70% (12 months) | Tanvir Hasan | pred_late
71009789 | GRL | Greyloom Knitwear Ltd. | Kids | KAW26-K-8070 | Kids Acrylic Cardigan | 7 | 3636 | 18470.88 | 2026-11-14 | In production | Trimming & Mending | 120 | 146.5 | 30.3 | 31 | 25 | -6 | 2026-11-21 | 7 | 45.5 | 12 | 1500% | 0 | 0 | 72 | Critical | 2% | 18470.88 | 3399.66 | Trimming & Mending 120 pcs/day vs 146 needed; Yarn in-house 8 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009371 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KAW26-K-2261 | Kids Merino Crew-neck Jumper | 7 | 3324 | 34702.56 | 2026-10-15 | In production | Linking | 112.2 |  | 4.5 | 5 | 0 | -5 | 2026-10-21 | 6 | 44 | 8 | 1420% | 0 | 5 | 71 | At risk | 2% | 34702.56 | 2925.12 | Yarn in-house 5 days late; Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | pred_late
71010707 | GRL | Greyloom Knitwear Ltd. | Men | KHO26-M-2771 | Wool-blend V-neck Pullover | 12 | 3876 | 41744.52 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-16 | 6 | 44 | 12 | 1500% | 0 | 0 | 71 | At risk | 2% | 41744.52 | 8740.38 | Yarn in-house revised to 04 Nov (9 days late); Factory OTD 68% (12 months) | Arif Chowdhury | pred_late
71011029 | GRL | Greyloom Knitwear Ltd. | Kids | KHO26-K-9874 | Kids Acrylic Cardigan | 7 | 4668 | 19372.2 | 2026-12-16 | Pre-production | [5 empty] | 53 |  | 2026-12-22 | 6 | 44 | 12 | 1500% | 0 | 0 | 71 | At risk | 2% | 19372.2 | 4364.58 | Yarn in-house revised to 09 Nov (8 days late); Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009631 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-7080 | Recycled V-neck Pullover | 12 | 4356 | 30099.96 | 2026-10-19 | In production | Knitting | 138.2 | 1384 | 7.51 | 8 | 3 | -5 | 2026-10-25 | 6 | 44 | 12 | 1500% | 0 | 0 | 71 | At risk | 2% | 30099.96 | 8864.46 | Knitting 138 pcs/day vs 1,384 needed; Yarn in-house 9 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71010806 | GRL | Greyloom Knitwear Ltd. | Kids | KSS27-K-9477 | Kids Cotton-blend Crew-neck Jumper | 12 | 3240 | 18176.4 | 2026-12-31 | Pre-production | [5 empty] | 66 |  | 2027-01-06 | 6 | 44 | 12 | 1500% | 0 | 0 | 71 | At risk | 2% | 18176.4 | 2138.4 | Yarn in-house revised to 25 Nov (9 days late); Factory OTD 68% (12 months) | Imran Hossain | pred_late
71009462 | HMR | Highmoor Sweaters Ltd. | Women | KAW26-W-5684 | Merino Turtle-neck Pullover | 7 | 4944 | 83355.84 | 2026-10-13 | In production | Knitting | 165 |  | 3.5 | 4 | 0 | -4 | 2026-10-20 | 7 | 45.5 | 12 | 910% | 0 | 3 | 70 | Late | 2% | 83355.84 | 15227.52 | Yarn in-house 9 days late; No report since 13 Oct | Imran Hossain | late
71009600 | IRB | Ironbridge Sweaters Ltd. | Women | KAW26-W-3605 | Cotton-blend Long Cardigan | 5 | 9168 | 109374.24 | 2026-10-19 | In production | Knitting | 323.5 | 1294 | 4.5 | 5 | 3 | -2 | 2026-10-21 | 2 | 38 | 12 | 1500% | 5 | 0 | 70 | At risk | 12% | 109374.24 | 47398.56 | Knitting 323 pcs/day vs 1,294 needed; Yarn in-house 9 days late; Factory OTD 70% (12 months) | Tanvir Hasan | pred_late
71010853 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KHO26-W-3467 | Acrylic Crew-neck Pullover | 7 | 3612 | 21635.88 | 2026-11-28 | Pre-production | [5 empty] | 37 |  | 2026-12-01 | 3 | 39.5 | 16 | 1420% | 0 | 0 | 70 | At risk | 10% | 21635.88 | 9933 | Yarn in-house revised to 20 Oct (6 days late); PP sample approval 4 days late; Factory OTD 72% (12 months) | Imran Hossain | pred_late
71010721 | GRL | Greyloom Knitwear Ltd. | Kids | KHO26-K-2262 | Kids Recycled Crew-neck Jumper | 7 | 2328 | 11174.4 | 2026-11-23 | Pre-production | [5 empty] | 33 |  | 2026-11-28 | 5 | 42.5 | 12 | 1500% | 0 | 0 | 70 | At risk | 2% | 11174.4 | 1920.6 | Yarn in-house revised to 17 Oct (9 days late); Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009741 | IRB | Ironbridge Sweaters Ltd. | Women | KAW26-W-3063 | Acrylic Cropped Pullover | 7 | 8760 | 56852.4 | 2026-10-21 | In production | Linking | 424.9 | 121.7 | 2.5 | 3 | 5 | 2 | 2026-10-19 | -2 | 25 | 20 | 1500% | 10 | 0 | 70 | At risk | 77% | 56852.4 | 0 | Yarn in-house 8 days late; PP sample approval 5 days late; Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | tight
71010695 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KHO26-W-4481 | Acrylic Crew-neck Pullover | 12 | 6168 | 48110.4 | 2026-12-05 | Pre-production | [5 empty] | 43 |  | 2026-12-10 | 5 | 42.5 | 12 | 1420% | 0 | 0 | 69 | At risk | 2% | 48110.4 | 11534.16 | Yarn in-house revised to 29 Oct (8 days late); Factory OTD 72% (12 months) | Arif Chowdhury | pred_late
71009547 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-6156 | Lambswool Turtle-neck Pullover | 7 | 2496 | 41408.64 | 2026-10-31 | In production | Linking | 97.3 | 128.4 | 16.51 | 17 | 13 | -4 | 2026-11-04 | 4 | 41 | 8 | 1420% | 0 | 5 | 68 | At risk | 2% | 41408.64 | 8923.2 | Linking 97 pcs/day vs 128 needed; Yarn in-house 7 days late; Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | pred_late
71010217 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-3514 | Lambswool Crew-neck Pullover | 7 | 4620 | 68699.4 | 2026-11-04 | In production | Linking | 141.7 | 193.6 | 22.5 | 23 | 17 | -6 | 2026-11-11 | 7 | 45.5 | 8 | 1500% | 0 | 0 | 68 | Critical | 2% | 68699.4 | 15500.1 | Linking 142 pcs/day vs 194 needed; Yarn in-house 4 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009437 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-7508 | Wool-blend Crew-neck Pullover | 7 | 2508 | 26283.84 | 2026-10-22 | In production | Knitting | 88.4 | 132.7 | 7.5 | 8 | 6 | -2 | 2026-10-25 | 3 | 39.5 | 12 | 1500% | 0 | 0 | 66 | At risk | 10% | 26283.84 | 7724.64 | Knitting 88 pcs/day vs 133 needed; Yarn in-house 8 days late; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71010354 | HMR | Highmoor Sweaters Ltd. | Men | KAW26-M-7288 | Wool-blend Shawl-collar Cardigan | 3 | 4164 | 54756.6 | 2026-11-12 | In production | Ironing | 138 | 171.3 | 29.67 | 30 | 24 | -6 | 2026-11-19 | 7 | 45.5 | 8 | 910% | 0 | 3 | 66 | Critical | 2% | 54756.6 | 22443.96 | Ironing 138 pcs/day vs 171 needed; Yarn in-house 6 days late; No report since 13 Oct | Imran Hossain | pred_late
71009698 | CPL | Copperleaf Knit Ltd. | Women | KAW26-W-1974 | Cotton-blend Turtle-neck Pullover | 12 | 2724 | 25496.64 | 2026-10-11 | In production | Linking | 77.9 |  | 2.49 | 3 | 0 | -3 | 2026-10-19 | 8 | 47 | 16 | 220% | 0 | 0 | 65 | Late | 2% | 25496.64 | 5992.8 | Yarn in-house 4 days late; PP sample approval 4 days late | Mehedi Karim | late
71009490 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-3648 | Recycled Turtle-neck Pullover | 7 | 3780 | 28954.8 | 2026-11-07 | In production | Linking | 148.4 | 161.1 | 20.51 | 21 | 19 | -2 | 2026-11-09 | 2 | 38 | 8 | 1420% | 0 | 5 | 65 | At risk | 15% | 28954.8 | 11018.7 | Linking 148 pcs/day vs 161 needed; Yarn in-house 6 days late; Factory OTD 72% (12 months); No report since 12 Oct | Farhana Rahman | pred_late
71009613 | WSM | Westmere Knitwear Ltd. | Kids | KAW26-K-3647 | Kids Merino Jacquard Jumper | 7 | 5664 | 65192.64 | 2026-10-21 | In production | Linking | 194 | 614 | 11.5 | 12 | 5 | -7 | 2026-10-29 | 8 | 47 | 12 | 590% | 0 | 0 | 65 | Critical | 2% | 65192.64 | 5607.36 | Linking 194 pcs/day vs 614 needed; Yarn in-house 9 days late | Imran Hossain | pred_late
71009517 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-2056 | Acrylic V-neck Pullover | 7 | 4332 | 32706.6 | 2026-11-01 | In production | Linking | 186.6 | 194.1 | 14.5 | 15 | 14 | -1 | 2026-11-02 | 1 | 36.5 | 8 | 1420% | 0 | 5 | 64 | At risk | 18% | 32706.6 | 12866.04 | Linking 187 pcs/day vs 194 needed; Yarn in-house 7 days late; Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | pred_late
71009955 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-1739 | Merino Turtle-neck Pullover | 12 | 5064 | 93380.16 | 2026-10-29 | In production | Knitting | 225.5 | 187.7 | 10.49 | 11 | 12 | 1 | 2026-10-28 | -1 | 25 | 20 | 1420% | 0 | 5 | 64 | At risk | 78% | 93380.16 | 0 | Yarn in-house 8 days late; PP sample approval 5 days late; Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | tight
71009816 | LTF | Lanternfield Sweaters Ltd. | Kids | KAW26-K-6337 | Kids Cotton-blend Jacquard Jumper | 7 | 6048 | 32901.12 | 2026-10-27 | In production | Linking | 201.1 | 331.1 | 15.5 | 16 | 10 | -6 | 2026-11-03 | 7 | 45.5 | 12 | 620% | 0 | 0 | 64 | Critical | 2% | 32901.12 | 6320.16 | Linking 201 pcs/day vs 331 needed; Yarn in-house 8 days late | Rumana Akter | pred_late
71011032 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KSS27-M-9768 | Cotton-blend Knitted Vest | 12 | 7344 | 53464.32 | 2026-12-26 | Pre-production | [5 empty] | 61 |  | 2026-12-29 | 3 | 39.5 | 8 | 1420% | 0 | 0 | 62 | At risk | 10% | 53464.32 | 11713.68 | Yarn in-house revised to 17 Nov (6 days late); Factory OTD 72% (12 months) | Nusrat Jahan | pred_late
71011127 | GRL | Greyloom Knitwear Ltd. | Kids | KSS27-K-2678 | Kids Cotton Crew-neck Jumper | 12 | 10296 | 58172.4 | 2026-12-21 | Pre-production | [5 empty] | 57 |  | 2026-12-23 | 2 | 38 | 8 | 1500% | 0 | 0 | 61 | At risk | 15% | 58172.4 | 6795.36 | Yarn in-house revised to 11 Nov (6 days late); Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71009983 | WTH | Wildthorn Sweaters Ltd. | Men | KHO26-M-3980 | Merino V-neck Pullover | 7 | 2280 | 37323.6 | 2026-11-16 | In production | Linking | 81 | 85.1 | 28.27 | 29 | 27 | -2 | 2026-11-18 | 2 | 38 | 16 | 710% | 0 | 0 | 61 | At risk | 18% | 37323.6 | 7147.8 | Linking 81 pcs/day vs 85 needed; Yarn in-house 6 days late; PP sample approval 4 days late | Tanvir Hasan | pred_late
71011048 | BLF | Bluefinch Sweaters Ltd. | Men | KHO26-M-8060 | Merino Half-zip Pullover | 7 | 1440 | 29491.2 | 2026-12-19 | Pre-production | [5 empty] | 55 |  | 2026-12-24 | 5 | 42.5 | 12 | 510% | 0 | 0 | 60 | At risk | 2% | 29491.2 | 4910.4 | Yarn in-house revised to 12 Nov (8 days late) | Sadia Islam | pred_late
71010981 | AMB | Amberline Knit Ltd. | Women | KHO26-W-7598 | Lambswool V-neck Cardigan | 7 | 4440 | 64202.4 | 2026-12-05 | Pre-production | [5 empty] | 43 |  | 2026-12-10 | 5 | 42.5 | 12 | 260% | 0 | 0 | 57 | At risk | 2% | 64202.4 | 16605.6 | Yarn in-house revised to 29 Oct (8 days late) | Arif Chowdhury | pred_late
71010325 | GRL | Greyloom Knitwear Ltd. | Women | KHO26-W-3383 | Wool-blend V-neck Cardigan | 12 | 4896 | 50967.36 | 2026-11-19 | In production | Trimming & Mending | 164 | 166 | 30.35 | 31 | 30 | -1 | 2026-11-21 | 2 | 38 | 4 | 1500% | 0 | 0 | 57 | At risk | 15% | 50967.36 | 11309.76 | Trimming & Mending 164 pcs/day vs 166 needed; Factory OTD 68% (12 months) | Farhana Rahman | pred_late
71010028 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-5610 | Wool-blend Crew-neck Pullover | 7 | 4812 | 52354.56 | 2026-10-25 | In production | Knitting | 198.8 | 99.6 | 5.5 | 6 | 8 | 2 | 2026-10-22 | -3 | 25 | 16 | 1500% | 0 | 0 | 56 | At risk | 84% | 52354.56 | 0 | Yarn in-house 7 days late; PP sample approval 5 days late; Factory OTD 68% (12 months) | Farhana Rahman | tight
71010787 | LTF | Lanternfield Sweaters Ltd. | Women | KHO26-W-9422 | Lambswool Cropped Pullover | 7 | 2556 | 33892.56 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-16 | 4 | 41 | 8 | 620% | 0 | 0 | 55 | At risk | 2% | 33892.56 | 7731.9 | Yarn in-house revised to 04 Nov (7 days late) | Rumana Akter | pred_late
71009330 | WTH | Wildthorn Sweaters Ltd. | Men | KAW26-M-8022 | Cotton-blend V-neck Pullover | 7 | 7788 | 69313.2 | 2026-10-22 | In production | Linking | 282.6 | 376.9 | 7.5 | 8 | 6 | -2 | 2026-10-25 | 3 | 39.5 | 8 | 710% | 0 | 0 | 55 | At risk | 11% | 69313.2 | 25700.4 | Linking 283 pcs/day vs 377 needed; Yarn in-house 6 days late | Tanvir Hasan | pred_late
71009941 | FNS | Fernstitch Knitwear Ltd. | Women | KAW26-W-2384 | Merino Crew-neck Pullover | 12 | 5880 | 108780 | 2026-11-09 | In production | Linking | 191.3 | 236.8 | 25.52 | 26 | 21 | -5 | 2026-11-15 | 6 | 44 | 8 | 180% | 0 | 0 | 54 | At risk | 2% | 108780 | 11642.4 | Linking 191 pcs/day vs 237 needed; Yarn in-house 6 days late | Mehedi Karim | pred_late
71010830 | RVS | Riverstone Sweaters Ltd. | Men | KHO26-M-2899 | Wool-blend Shawl-collar Cardigan | 5 | 3720 | 44379.6 | 2026-12-08 | Pre-production | [5 empty] | 46 |  | 2026-12-10 | 2 | 38 | 8 | 710% | 0 | 0 | 53 | At risk | 29% | 44379.6 | 17595.6 | Yarn in-house revised to 29 Oct (5 days late) | Imran Hossain | pred_late
71009945 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-3727 | Lambswool Half-zip Pullover | 7 | 3192 | 52572.24 | 2026-10-19 | In production | Packing | 144.5 | 24.3 | 0.51 | 1 | 3 | 2 | 2026-10-17 | -2 | 25 | 12 | 1500% | 0 | 0 | 52 | At risk | 79% | 52572.24 | 0 | Yarn in-house 9 days late; Factory OTD 68% (12 months) | Farhana Rahman | tight
71011040 | KST | Kestrel Knitwear Ltd. | Women | KHO26-W-7745 | Wool-blend Crew-neck Pullover | 12 | 6600 | 70884 | 2026-12-14 | Pre-production | [5 empty] | 51 |  | 2026-12-16 | 2 | 38 | 8 | 370% | 0 | 0 | 50 | At risk | 12% | 70884 | 13794 | Yarn in-house revised to 04 Nov (6 days late) | Arif Chowdhury | pred_late
71010153 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-1669 | Cotton-blend Crew-neck Pullover | 7 | 4008 | 32184.24 | 2026-11-04 | In production | Linking | 172.5 | 111.2 | 11.49 | 12 | 17 | 5 | 2026-10-29 | -6 | 12 | 4 | 1500% | 10 | 0 | 41 | Watch | 88% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | watch
71010389 | IRB | Ironbridge Sweaters Ltd. | Women | KAW26-W-7569 | Wool-blend V-neck Cardigan | 7 | 2436 | 27331.92 | 2026-11-12 | In production | Linking | 121.7 | 74.6 | 15.49 | 16 | 24 | 8 | 2026-11-03 | -9 | 0 | 4 | 1500% | 10 | 0 | 29 | Watch | 96% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | ok
71009425 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-6157 | Cotton-blend Half-zip Pullover | 5 | 3924 | 33197.04 | 2026-10-22 | In production | Packing | 171.3 | 14.2 | 0.5 | 1 | 6 | 5 | 2026-10-17 | -5 | 12 | 0 | 1500% | 0 | 0 | 27 | Watch | 87% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71009475 | OKH | Oakhaven Knitwear Ltd. | Women | KAW26-W-6821 | Wool-blend V-neck Cardigan | 12 | 2532 | 23446.32 | 2026-10-22 | In production | Linking | 100.6 | 12.5 | 2.5 | 3 | 6 | 3 | 2026-10-19 | -3 | 12 | 4 | 520% | 0 | 5 | 26 | Watch | 97% | 0 | 0 | No report since 11 Oct | Sadia Islam | watch
71010071 | SVP | Silverpine Knitwear Ltd. | Men | KAW26-M-2514 | Wool-blend V-neck Pullover | 12 | 4308 | 39633.6 | 2026-10-26 | In production | Linking | 178.1 | 89 | 5.5 | 6 | 9 | 3 | 2026-10-22 | -4 | 12 | 0 | 370% | 10 | 0 | 26 | Watch | 97% | 0 | 0 | Last inspection failed | Mehedi Karim | watch
71009642 | AMB | Amberline Knit Ltd. | Kids | KAW26-K-3745 | Kids Merino Cardigan | 7 | 9000 | 105120 | 2026-10-25 | In production | Linking | 421 | 35.2 | 2.5 | 3 | 8 | 5 | 2026-10-19 | -6 | 12 | 0 | 260% | 10 | 0 | 25 | Watch | 98% | 0 | 0 | Last inspection failed | Arif Chowdhury | watch
71008941 | IRB | Ironbridge Sweaters Ltd. | Kids | KAW26-K-1392 | Kids Recycled Crew-neck Jumper | 7 | 4956 | 21855.96 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 1500% | 10 | 0 | 25 | Watch | 70% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | ok
71009654 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-2990 | Merino Half-zip Pullover | 7 | 5412 | 111270.72 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 0 | 1500% | 10 | 0 | 25 | Watch | 70% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | ok
71009779 | IRB | Ironbridge Sweaters Ltd. | Kids | KAW26-K-8575 | Kids Wool-blend Crew-neck Jumper | 7 | 6288 | 33703.68 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 0 | 1500% | 10 | 0 | 25 | Watch | 70% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | ok
71010108 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-6853 | Recycled Half-zip Pullover | 5 | 3948 | 35729.4 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 0 | 1500% | 10 | 0 | 25 | Watch | 70% | 0 | 0 | Factory OTD 70% (12 months); Last inspection failed | Tanvir Hasan | ok
71009281 | HMR | Highmoor Sweaters Ltd. | Men | KAW26-M-9564 | Lambswool V-neck Pullover | 7 | 5400 | 75060 | 2026-10-28 | In production | Knitting | 202 | 113.8 | 7.51 | 8 | 11 | 3 | 2026-10-25 | -3 | 12 | 0 | 910% | 0 | 3 | 24 | On track | 95% | 0 | 0 | No report since 13 Oct | Imran Hossain | watch
71009899 | OKH | Oakhaven Knitwear Ltd. | Women | KAW26-W-7420 | Recycled Cropped Pullover | 7 | 2964 | 18969.6 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 4 | 520% | 10 | 5 | 24 | On track | 90% | 0 | 0 | Last inspection failed; No report since 11 Oct | Sadia Islam | ok
71009854 | HMR | Highmoor Sweaters Ltd. | Women | KAW26-W-9189 | Lambswool Long Cardigan | 3 | 3768 | 67447.2 | 2026-11-04 | In production | Linking | 159.4 | 111.5 | 12.49 | 13 | 17 | 4 | 2026-10-31 | -4 | 12 | 0 | 910% | 0 | 3 | 24 | On track | 98% | 0 | 0 | No report since 13 Oct | Imran Hossain | watch
71010509 | IRB | Ironbridge Sweaters Ltd. | Women | KHO26-W-5139 | Acrylic Long Cardigan | 3 | 2772 | 29272.32 | 2026-11-19 | In production | Linking | 155.3 | 87 | 17.47 | 18 | 30 | 12 | 2026-11-05 | -14 | 0 | 4 | 1500% | 5 | 0 | 24 | On track | 98% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009296 | IRB | Ironbridge Sweaters Ltd. | Women | KAW26-W-8280 | Wool-blend Long Cardigan | 5 | 8652 | 106419.6 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 4 | 1500% | 5 | 0 | 24 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009161 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-3354 | Wool-blend Knitted Vest | 12 | 5916 | 41530.32 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 4 | 1420% | 0 | 5 | 23 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Sadia Islam | ok
71010145 | OKH | Oakhaven Knitwear Ltd. | Men | KAW26-M-7312 | Lambswool V-neck Pullover | 7 | 3672 | 54969.84 | 2026-11-01 | In production | Linking | 179.2 | 127 | 10.51 | 11 | 14 | 3 | 2026-10-28 | -4 | 12 | 0 | 520% | 0 | 5 | 22 | On track | 97% | 0 | 0 | No report since 11 Oct | Sadia Islam | watch
71010174 | BRW | Brightwool Knit Industries Ltd. | Men | KAW26-M-6674 | Acrylic Knitted Vest | 12 | 5364 | 32023.08 | 2026-11-15 | In production | Knitting | 205.4 | 166.1 | 21.51 | 22 | 26 | 4 | 2026-11-10 | -5 | 12 | 4 | 450% | 0 | 0 | 21 | On track | 98% | 0 | 0 |  | Mehedi Karim | watch
71009668 | RSG | Rosegate Sweaters Ltd. | Men | KAW26-M-3638 | Lambswool Shawl-collar Cardigan | 5 | 6144 | 110407.68 | 2026-10-27 | In production | Knitting | 241 | 86 | 5.5 | 6 | 10 | 4 | 2026-10-22 | -5 | 12 | 0 | 910% | 0 | 0 | 21 | On track | 98% | 0 | 0 |  | Arif Chowdhury | watch
71010534 | BRW | Brightwool Knit Industries Ltd. | Men | KAW26-M-3148 | Cotton-blend Crew-neck Pullover | 12 | 5016 | 46197.36 | 2026-11-11 | In production | Linking | 208.2 | 154.9 | 17.5 | 18 | 23 | 5 | 2026-11-05 | -6 | 12 | 4 | 450% | 0 | 0 | 21 | On track | 98% | 0 | 0 |  | Farhana Rahman | watch
71010202 | IRB | Ironbridge Sweaters Ltd. | Men | KHO26-M-1909 | Merino Half-zip Pullover | 7 | 2820 | 48081 | 2026-11-23 | In production | Knitting | 170 | 88.3 | 18.59 | 19 | 33 | 14 | 2026-11-07 | -16 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 98% | 0 | 0 | Factory OTD 70% (12 months) | Nusrat Jahan | ok
71011069 | IRB | Ironbridge Sweaters Ltd. | Women | KHO26-W-9872 | Cotton-blend Crew-neck Pullover | 7 | 4992 | 38288.64 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-12 | 0 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71010634 | IRB | Ironbridge Sweaters Ltd. | Men | KHO26-M-9515 | Lambswool Shawl-collar Cardigan | 5 | 2436 | 42703.08 | 2026-11-24 | Pre-production | [5 empty] | 34 |  | 2026-11-24 | 0 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009949 | IRB | Ironbridge Sweaters Ltd. | Kids | KAW26-K-6933 | Kids Merino Crew-neck Jumper | 7 | 6540 | 71155.2 | 2026-10-22 | In production |  |  |  | 0 | 0 | 6 | 6 | 2026-10-22 | 0 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009013 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-6717 | Lambswool Crew-neck Pullover | 7 | 6072 | 92901.6 | 2026-10-17 | In production |  |  |  | 0 | 0 | 1 | 1 | 2026-10-17 | 0 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Mehedi Karim | ok
71010672 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-4928 | Lambswool V-neck Pullover | 7 | 8988 | 143987.76 | 2026-11-12 | In production | Linking | 472.4 | 268.5 | 14.5 | 15 | 24 | 9 | 2026-11-02 | -10 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 96% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009340 | IRB | Ironbridge Sweaters Ltd. | Men | KAW26-M-4613 | Lambswool Half-zip Pullover | 7 | 6780 | 96208.2 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 0 | 1500% | 5 | 0 | 20 | On track | 70% | 0 | 0 | Factory OTD 70% (12 months) | Tanvir Hasan | ok
71009431 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-2465 | Wool-blend V-neck Pullover | 7 | 2376 | 25637.04 | 2026-10-22 | In production |  |  |  | 0 | 0 | 6 | 6 | 2026-10-22 | 0 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71009622 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-5571 | Acrylic Cropped Pullover | 7 | 4008 | 27414.72 | 2026-11-11 | In production | Linking | 195.7 | 127.4 | 15.5 | 16 | 23 | 7 | 2026-11-03 | -8 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 92% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71010417 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KAW26-K-7353 | Kids Merino Jacquard Jumper | 7 | 2016 | 23567.04 | 2026-11-14 | In production | Linking | 181.2 | 59 | 9.49 | 10 | 25 | 15 | 2026-10-27 | -18 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 98% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71010238 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-2695 | Merino Turtle-neck Pullover | 12 | 3516 | 65608.56 | 2026-11-12 | In production | Knitting | 163.1 | 97 | 15.49 | 16 | 24 | 8 | 2026-11-03 | -9 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 96% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010426 | GRL | Greyloom Knitwear Ltd. | Women | KHO26-W-4555 | Lambswool Long Cardigan | 5 | 3492 | 64113.12 | 2026-11-18 | In production | Trimming & Mending | 194.7 | 113.5 | 17.54 | 18 | 29 | 11 | 2026-11-05 | -13 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 98% | 0 | 0 | Factory OTD 68% (12 months) | Nusrat Jahan | ok
71009664 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-1128 | Merino V-neck Pullover | 7 | 3528 | 66785.04 | 2026-10-18 | In production |  |  |  | 0 | 0 | 2 | 2 | 2026-10-18 | 0 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71009719 | GRL | Greyloom Knitwear Ltd. | Kids | KAW26-K-6094 | Kids Recycled Cardigan | 7 | 2892 | 12291 | 2026-10-22 | In production |  |  |  | 0 | 0 | 6 | 6 | 2026-10-22 | 0 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010112 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-1211 | Merino V-neck Cardigan | 7 | 1704 | 28473.84 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71008860 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KAW26-W-7890 | Recycled Cropped Pullover | 7 | 6624 | 48288.96 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71009055 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KAW26-M-6069 | Recycled Knitted Vest | 12 | 4932 | 31318.2 | 2026-10-22 | In production |  |  |  | 0 | 0 | 6 | 6 | 2026-10-22 | 0 | 0 | 0 | 1420% | 0 | 5 | 19 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months); No report since 12 Oct | Nusrat Jahan | ok
71009214 | GRL | Greyloom Knitwear Ltd. | Kids | KAW26-K-7864 | Kids Wool-blend Cardigan | 7 | 1812 | 12394.08 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71009573 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-8393 | Wool-blend Crew-neck Pullover | 7 | 14400 | 161280 | 2026-11-10 | In production | Linking | 770.8 | 443.1 | 13.5 | 14 | 22 | 8 | 2026-11-01 | -9 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 96% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | donor
71010244 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-1372 | Merino Half-zip Pullover | 7 | 4776 | 79233.84 | 2026-10-29 | In production | Linking | 232 | 57.9 | 4.5 | 5 | 12 | 7 | 2026-10-21 | -8 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 90% | 0 | 0 | Factory OTD 68% (12 months) | Mehedi Karim | ok
71010274 | GRL | Greyloom Knitwear Ltd. | Men | KHO26-M-4891 | Recycled Half-zip Pullover | 7 | 2844 | 22837.32 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Tanvir Hasan | ok
71010614 | WTH | Wildthorn Sweaters Ltd. | Men | KHO26-M-9952 | Acrylic Shawl-collar Cardigan | 3 | 2784 | 24025.92 | 2026-11-17 | In production | Ironing | 112 | 97.2 | 24.36 | 25 | 28 | 3 | 2026-11-14 | -3 | 12 | 0 | 710% | 0 | 0 | 19 | On track | 98% | 0 | 0 |  | Arif Chowdhury | watch
71009129 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-3350 | Merino Crew-neck Pullover | 7 | 4452 | 66601.92 | 2026-10-25 | In production |  |  |  | 0 | 0 | 8 | 8 | 2026-10-25 | 0 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71009861 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-4126 | Wool-blend Long Cardigan | 5 | 5028 | 59732.64 | 2026-11-12 | In production | Linking | 241.4 | 148 | 15.49 | 16 | 24 | 8 | 2026-11-03 | -9 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 96% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010048 | PBB | Pebblebrook Knit Ltd. | Men | KAW26-M-9159 | Recycled Knitted Vest | 12 | 4296 | 25947.84 | 2026-11-11 | In production | Linking | 374.8 | 87.2 | 6.5 | 7 | 23 | 16 | 2026-10-24 | -18 | 0 | 4 | 170% | 10 | 3 | 19 | On track | 98% | 0 | 0 | Last inspection failed; No report since 13 Oct | Sadia Islam | ok
71010621 | GRL | Greyloom Knitwear Ltd. | Kids | KHO26-K-4434 | Kids Lambswool Cardigan | 7 | 9336 | 93453.36 | 2026-11-22 | In production | Knitting | 481 | 290.3 | 20.5 | 21 | 32 | 11 | 2026-11-09 | -13 | 0 | 4 | 1500% | 0 | 0 | 19 | On track | 98% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71009551 | LTF | Lanternfield Sweaters Ltd. | Kids | KAW26-K-4593 | Kids Wool-blend Jacquard Jumper | 7 | 2928 | 19529.76 | 2026-10-24 | In production | Linking | 114.5 | 11.6 | 2.51 | 3 | 7 | 4 | 2026-10-19 | -5 | 12 | 0 | 620% | 0 | 0 | 18 | On track | 98% | 0 | 0 |  | Rumana Akter | watch
71009530 | FNS | Fernstitch Knitwear Ltd. | Kids | KAW26-K-3733 | Kids Cotton-blend Crew-neck Jumper | 12 | 4440 | 24153.6 | 2026-11-05 | In production | Linking | 183.6 | 122.5 | 12.51 | 13 | 18 | 5 | 2026-10-31 | -5 | 12 | 4 | 180% | 0 | 0 | 18 | On track | 98% | 0 | 0 |  | Mehedi Karim | watch
71010035 | FNS | Fernstitch Knitwear Ltd. | Women | KAW26-W-3307 | Wool-blend V-neck Cardigan | 12 | 7200 | 81936 | 2026-10-31 | In production | Linking | 318.6 | 159.4 | 7.5 | 8 | 13 | 5 | 2026-10-25 | -6 | 12 | 4 | 180% | 0 | 0 | 18 | On track | 98% | 0 | 0 |  | Mehedi Karim | watch
71010198 | CPL | Copperleaf Knit Ltd. | Men | KHO26-M-1279 | Merino Knitted Vest | 12 | 3516 | 46516.68 | 2026-11-19 | In production | Linking | 137 | 120.7 | 26.66 | 27 | 30 | 3 | 2026-11-16 | -3 | 12 | 4 | 220% | 0 | 0 | 18 | On track | 96% | 0 | 0 |  | Mehedi Karim | watch
71009523 | LTF | Lanternfield Sweaters Ltd. | Men | KAW26-M-1318 | Cotton-blend Shawl-collar Cardigan | 5 | 3348 | 33915.24 | 2026-11-02 | In production | Linking | 143.3 | 84.9 | 9.5 | 10 | 15 | 5 | 2026-10-27 | -6 | 12 | 0 | 620% | 0 | 0 | 18 | On track | 98% | 0 | 0 |  | Rumana Akter | watch
71010527 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KHO26-W-1220 | Acrylic V-neck Cardigan | 12 | 3612 | 31893.96 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 4 | 1420% | 0 | 0 | 18 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71009864 | AMB | Amberline Knit Ltd. | Men | KAW26-M-9697 | Cotton-blend Half-zip Pullover | 7 | 11292 | 111452.04 | 2026-10-17 | In production |  |  |  | 0 | 0 | 1 | 1 | 2026-10-17 | 0 | 0 | 4 | 260% | 10 | 0 | 17 | On track | 95% | 0 | 0 | Last inspection failed | Arif Chowdhury | ok
71009965 | BRW | Brightwool Knit Industries Ltd. | Kids | KHO26-K-8349 | Kids Acrylic Jacquard Jumper | 7 | 7224 | 32724.72 | 2026-11-23 | In production | Knitting | 267 | 228.1 | 28.56 | 29 | 33 | 4 | 2026-11-18 | -5 | 12 | 0 | 450% | 0 | 0 | 17 | On track | 98% | 0 | 0 |  | Farhana Rahman | watch
71009763 | MDW | Morningdew Knit Ltd. | Men | KAW26-M-4666 | Wool-blend Crew-neck Pullover | 12 | 3012 | 30782.64 | 2026-11-11 | In production | Linking | 117.1 | 97.5 | 19.47 | 20 | 23 | 3 | 2026-11-08 | -3 | 12 | 0 | 520% | 0 | 0 | 17 | On track | 97% | 0 | 0 |  | Nusrat Jahan | watch
71009680 | SVP | Silverpine Knitwear Ltd. | Women | KAW26-W-1105 | Recycled V-neck Cardigan | 12 | 2028 | 15615.6 | 2026-10-25 | In production | Knitting | 82.3 | 14.9 | 3.5 | 4 | 8 | 4 | 2026-10-20 | -5 | 12 | 0 | 370% | 0 | 0 | 16 | On track | 98% | 0 | 0 |  | Mehedi Karim | watch
71009873 | KST | Kestrel Knitwear Ltd. | Women | KHO26-W-7557 | Wool-blend Turtle-neck Pullover | 12 | 3048 | 33131.76 | 2026-11-22 | In production | Knitting | 111.3 | 97.9 | 28.51 | 29 | 32 | 3 | 2026-11-18 | -4 | 12 | 0 | 370% | 0 | 0 | 16 | On track | 95% | 0 | 0 |  | Arif Chowdhury | watch
71009724 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-6752 | Wool-blend V-neck Pullover | 7 | 4764 | 40875.12 | 2026-11-08 | In production | Linking | 231.1 | 147.6 | 13.49 | 14 | 20 | 6 | 2026-11-01 | -7 | 0 | 0 | 640% | 10 | 0 | 16 | On track | 98% | 0 | 0 | Last inspection failed | Rumana Akter | ok
71009905 | CLB | Cloudberry Knit Ltd. | Women | KAW26-W-7642 | Acrylic Crew-neck Pullover | 12 | 2772 | 22730.4 | 2026-11-05 | In production | Knitting | 99 | 76.6 | 14.49 | 15 | 18 | 3 | 2026-11-02 | -3 | 12 | 0 | 440% | 0 | 0 | 16 | On track | 97% | 0 | 0 |  | Rumana Akter | watch
71008967 | PBB | Pebblebrook Knit Ltd. | Kids | KAW26-K-6149 | Kids Acrylic Crew-neck Jumper | 12 | 4488 | 20240.88 | 2026-10-18 | In production |  |  |  | 0 | 0 | 2 | 2 | 2026-10-18 | 0 | 0 | 0 | 170% | 10 | 3 | 15 | On track | 97% | 0 | 0 | Last inspection failed; No report since 13 Oct | Sadia Islam | ok
71011298 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-8612 | Cotton Knitted Vest | 12 | 2268 | 18869.76 | 2027-01-30 | Pre-production | [5 empty] | 91 |  | 2027-01-30 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011470 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-8813 | Organic Cotton Turtle-neck Pullover | 12 | 6036 | 59997.84 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Sadia Islam | ok
71011473 | GRL | Greyloom Knitwear Ltd. | Kids | KSS27-K-1464 | Kids Organic Cotton Crew-neck Jumper | 12 | 5748 | 36097.44 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011267 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-7061 | Organic Cotton Crew-neck Pullover | 12 | 1224 | 13415.04 | 2027-01-24 | Pre-production | [5 empty] | 86 |  | 2027-01-24 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010279 | GRL | Greyloom Knitwear Ltd. | Women | KHO26-W-3469 | Cotton-blend V-neck Cardigan | 7 | 2676 | 26599.44 | 2026-11-29 | Pre-production | [5 empty] | 38 |  | 2026-11-29 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71011377 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-3065 | Cotton Crew-neck Pullover | 12 | 6876 | 56864.52 | 2027-01-14 | Pre-production | [5 empty] | 78 |  | 2027-01-14 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71011215 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-1529 | Cotton Turtle-neck Pullover | 12 | 4140 | 43345.8 | 2027-01-16 | Pre-production | [5 empty] | 79 |  | 2027-01-16 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011165 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-4971 | Cotton-blend Knitted Vest | 12 | 4032 | 25401.6 | 2027-01-16 | Pre-production | [5 empty] | 79 |  | 2027-01-16 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011705 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-2848 | Linen-blend Turtle-neck Pullover | 12 | 5256 | 69274.08 | 2027-02-23 | Pre-production | [5 empty] | 112 |  | 2027-02-23 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011586 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-4803 | Cotton Turtle-neck Pullover | 12 | 10236 | 107375.64 | 2027-02-25 | Pre-production | [5 empty] | 114 |  | 2027-02-25 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011386 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-5918 | Cotton-blend Knitted Vest | 12 | 3396 | 20953.32 | 2027-01-13 | Pre-production | [5 empty] | 77 |  | 2027-01-13 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011305 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-8061 | Organic Cotton Turtle-neck Pullover | 12 | 6876 | 75704.76 | 2027-01-02 | Pre-production | [5 empty] | 67 |  | 2027-01-02 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011084 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-7463 | Organic Cotton V-neck Pullover | 12 | 5136 | 48227.04 | 2027-01-17 | Pre-production | [5 empty] | 80 |  | 2027-01-17 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71009888 | GRL | Greyloom Knitwear Ltd. | Men | KAW26-M-3256 | Wool-blend V-neck Pullover | 12 | 2436 | 21485.52 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011036 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-9149 | Cotton-blend Crew-neck Pullover | 12 | 3480 | 28988.4 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010543 | GRL | Greyloom Knitwear Ltd. | Women | KAW26-W-7221 | Lambswool Cropped Pullover | 7 | 5508 | 76340.88 | 2026-11-15 | In production | Knitting | 251.4 | 169.3 | 18.49 | 19 | 26 | 7 | 2026-11-07 | -8 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 90% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010590 | GRL | Greyloom Knitwear Ltd. | Men | KHO26-M-6687 | Cotton-blend Knitted Vest | 12 | 2064 | 14179.68 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71011627 | GRL | Greyloom Knitwear Ltd. | Women | KSS27-W-2668 | Organic Cotton V-neck Cardigan | 12 | 4536 | 48716.64 | 2027-02-01 | Pre-production | [5 empty] | 93 |  | 2027-02-01 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71011433 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-7777 | Cotton-blend Crew-neck Pullover | 12 | 6996 | 53449.44 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Nusrat Jahan | watch
71010929 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-2504 | Cotton-blend V-neck Pullover | 12 | 2904 | 26629.68 | 2026-12-31 | Pre-production | [5 empty] | 66 |  | 2026-12-31 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Imran Hossain | watch
71011136 | GRL | Greyloom Knitwear Ltd. | Men | KSS27-M-6426 | Organic Cotton Crew-neck Pullover | 12 | 4044 | 36153.36 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71010833 | GRL | Greyloom Knitwear Ltd. | Men | KHO26-M-3441 | Cotton-blend Half-zip Pullover | 5 | 6672 | 59380.8 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | watch
71010942 | GRL | Greyloom Knitwear Ltd. | Kids | KHO26-K-6858 | Kids Recycled Crew-neck Jumper | 7 | 6108 | 26753.04 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 1500% | 0 | 0 | 15 | On track | 68% | 0 | 0 | Factory OTD 68% (12 months) | Farhana Rahman | ok
71010759 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KHO26-W-2139 | Cotton-blend Cropped Pullover | 7 | 4344 | 31884.96 | 2026-11-23 | Pre-production | [5 empty] | 33 |  | 2026-11-23 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Sadia Islam | ok
71011546 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KSS27-W-3987 | Cotton Turtle-neck Pullover | 12 | 1224 | 10832.4 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | watch
71011593 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KSS27-M-5841 | Organic Cotton Knitted Vest | 12 | 3768 | 27883.2 | 2027-02-18 | Pre-production | [5 empty] | 108 |  | 2027-02-18 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | watch
71010732 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KHO26-M-8438 | Merino Crew-neck Pullover | 12 | 3192 | 61254.48 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-12 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71010430 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KHO26-M-3549 | Recycled Crew-neck Pullover | 12 | 4416 | 32855.04 | 2026-11-30 | Pre-production | [5 empty] | 39 |  | 2026-11-30 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71010530 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KHO26-M-2333 | Recycled Crew-neck Pullover | 12 | 3336 | 26120.88 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71010994 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KSS27-K-8261 | Kids Cotton Crew-neck Jumper | 12 | 3288 | 17689.44 | 2027-01-05 | Pre-production | [5 empty] | 70 |  | 2027-01-05 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71011183 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KSS27-K-1373 | Kids Linen-blend Crew-neck Jumper | 12 | 6060 | 39874.8 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71011660 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KSS27-K-4457 | Kids Cotton-blend Crew-neck Jumper | 12 | 2316 | 11927.4 | 2027-02-20 | Pre-production | [5 empty] | 109 |  | 2027-02-20 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Sadia Islam | ok
71011261 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KSS27-M-6467 | Organic Cotton Crew-neck Pullover | 12 | 7752 | 84186.72 | 2027-01-11 | Pre-production | [5 empty] | 75 |  | 2027-01-11 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Farhana Rahman | ok
71011609 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KSS27-K-6910 | Kids Linen-blend Crew-neck Jumper | 12 | 2640 | 16790.4 | 2027-02-09 | Pre-production | [5 empty] | 100 |  | 2027-02-09 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71009478 | OKH | Oakhaven Knitwear Ltd. | Men | KAW26-M-2834 | Acrylic Crew-neck Pullover | 12 | 3684 | 28477.32 | 2026-10-29 | In production | Knitting | 163.8 | 51.7 | 5.5 | 6 | 12 | 6 | 2026-10-22 | -7 | 0 | 4 | 520% | 0 | 5 | 14 | On track | 98% | 0 | 0 | No report since 11 Oct | Sadia Islam | ok
71011190 | SLM | Saltmarsh Knit Fashions Ltd. | Kids | KSS27-K-4098 | Kids Linen-blend Crew-neck Jumper | 12 | 5628 | 34387.08 | 2027-01-13 | Pre-production | [5 empty] | 77 |  | 2027-01-13 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71011670 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KSS27-M-3582 | Cotton Crew-neck Pullover | 12 | 5448 | 56768.16 | 2027-02-08 | Pre-production | [5 empty] | 99 |  | 2027-02-08 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | watch
71010600 | OKH | Oakhaven Knitwear Ltd. | Women | KAW26-W-8580 | Recycled Turtle-neck Pullover | 7 | 3108 | 24304.56 | 2026-11-10 | In production | Linking | 363.3 | 71 | 5.5 | 6 | 22 | 16 | 2026-10-22 | -19 | 0 | 4 | 520% | 0 | 5 | 14 | On track | 98% | 0 | 0 | No report since 11 Oct | Sadia Islam | ok
71011292 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KSS27-W-3614 | Cotton-blend V-neck Cardigan | 12 | 3828 | 40576.8 | 2027-01-19 | Pre-production | [5 empty] | 82 |  | 2027-01-19 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71010712 | OKH | Oakhaven Knitwear Ltd. | Women | KAW26-W-9294 | Wool-blend Crew-neck Pullover | 12 | 4032 | 39513.6 | 2026-11-15 | In production | Linking | 280 | 145.7 | 14.49 | 15 | 26 | 11 | 2026-11-02 | -13 | 0 | 4 | 520% | 0 | 5 | 14 | On track | 98% | 0 | 0 | No report since 11 Oct | Sadia Islam | ok
71011146 | SLM | Saltmarsh Knit Fashions Ltd. | Women | KSS27-W-7705 | Linen-blend Crew-neck Pullover | 12 | 7908 | 89044.08 | 2027-01-07 | Pre-production | [5 empty] | 72 |  | 2027-01-07 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71011284 | SLM | Saltmarsh Knit Fashions Ltd. | Men | KSS27-M-5619 | Linen-blend V-neck Pullover | 12 | 4644 | 55217.16 | 2026-12-26 | Pre-production | [5 empty] | 61 |  | 2026-12-26 | 0 | 0 | 0 | 1420% | 0 | 0 | 14 | On track | 72% | 0 | 0 | Factory OTD 72% (12 months) | Nusrat Jahan | ok
71010267 | HMR | Highmoor Sweaters Ltd. | Men | KHO26-M-3817 | Acrylic V-neck Pullover | 7 | 6564 | 54153 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 4 | 910% | 0 | 0 | 13 | On track | 82% | 0 | 0 |  | Imran Hossain | watch
71009991 | RSG | Rosegate Sweaters Ltd. | Men | KHO26-M-7133 | Acrylic Crew-neck Pullover | 5 | 4980 | 32121 | 2026-11-18 | In production | Linking | 335 | 158.2 | 14.49 | 15 | 29 | 14 | 2026-11-02 | -16 | 0 | 4 | 910% | 0 | 0 | 13 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71009446 | HMR | Highmoor Sweaters Ltd. | Women | KAW26-W-4174 | Wool-blend Long Cardigan | 3 | 6468 | 95079.6 | 2026-11-02 | In production | Linking | 474.7 | 18.3 | 2.5 | 3 | 15 | 12 | 2026-10-19 | -14 | 0 | 0 | 910% | 0 | 3 | 12 | On track | 98% | 0 | 0 | No report since 13 Oct | Imran Hossain | ok
71010180 | HMR | Highmoor Sweaters Ltd. | Men | KHO26-M-7300 | Recycled Half-zip Pullover | 5 | 3048 | 24140.16 | 2026-11-17 | In production | Linking | 253 | 105.5 | 12.55 | 13 | 28 | 15 | 2026-10-31 | -17 | 0 | 0 | 910% | 0 | 3 | 12 | On track | 98% | 0 | 0 | No report since 13 Oct | Imran Hossain | ok
71009626 | HMR | Highmoor Sweaters Ltd. | Women | KAW26-W-8276 | Lambswool Turtle-neck Pullover | 7 | 3120 | 52915.2 | 2026-11-12 | In production | Knitting | 159.5 | 79.9 | 13.52 | 14 | 24 | 10 | 2026-11-01 | -11 | 0 | 0 | 910% | 0 | 3 | 12 | On track | 98% | 0 | 0 | No report since 13 Oct | Nusrat Jahan | ok
71010078 | HMR | Highmoor Sweaters Ltd. | Kids | KAW26-K-3068 | Kids Acrylic Jacquard Jumper | 7 | 3288 | 18971.76 | 2026-11-03 | In production | Linking | 249.5 | 17.2 | 2.5 | 3 | 16 | 13 | 2026-10-19 | -15 | 0 | 0 | 910% | 0 | 3 | 12 | On track | 98% | 0 | 0 | No report since 13 Oct | Imran Hossain | ok
71010074 | HMR | Highmoor Sweaters Ltd. | Kids | KAW26-K-8500 | Kids Cotton-blend Crew-neck Jumper | 7 | 3948 | 17884.44 | 2026-10-26 | In production |  |  |  | 0 | 0 | 9 | 9 | 2026-10-26 | 0 | 0 | 0 | 910% | 0 | 3 | 12 | On track | 82% | 0 | 0 | No report since 13 Oct | Farhana Rahman | ok
71010334 | RVS | Riverstone Sweaters Ltd. | Women | KHO26-W-2642 | Recycled Long Cardigan | 5 | 3348 | 32241.24 | 2026-11-28 | Pre-production | [5 empty] | 37 |  | 2026-11-28 | 0 | 0 | 4 | 710% | 0 | 0 | 11 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71010795 | RVS | Riverstone Sweaters Ltd. | Men | KHO26-M-9779 | Recycled Half-zip Pullover | 7 | 4644 | 40124.16 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 4 | 710% | 0 | 0 | 11 | On track | 86% | 0 | 0 |  | Imran Hossain | watch
71009756 | RVS | Riverstone Sweaters Ltd. | Men | KAW26-M-8914 | Merino Crew-neck Pullover | 12 | 8844 | 163171.8 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 4 | 710% | 0 | 0 | 11 | On track | 86% | 0 | 0 |  | Mehedi Karim | ok
71010256 | RVS | Riverstone Sweaters Ltd. | Kids | KHO26-K-7501 | Kids Wool-blend Jacquard Jumper | 7 | 9924 | 69864.96 | 2026-11-17 | In production | Linking | 466.8 | 332 | 20.49 | 21 | 28 | 7 | 2026-11-09 | -8 | 0 | 4 | 710% | 0 | 0 | 11 | On track | 98% | 0 | 0 |  | Imran Hossain | ok
71009676 | TLG | Tallgrass Knitwear Ltd. | Kids | KAW26-K-2312 | Kids Recycled Cardigan | 7 | 4032 | 18627.84 | 2026-10-20 | In production |  |  |  | 0 | 0 | 4 | 4 | 2026-10-20 | 0 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009811 | TLG | Tallgrass Knitwear Ltd. | Women | KAW26-W-6085 | Lambswool V-neck Cardigan | 7 | 5508 | 85208.76 | 2026-10-20 | In production |  |  |  | 0 | 0 | 4 | 4 | 2026-10-20 | 0 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71010747 | LTF | Lanternfield Sweaters Ltd. | Kids | KHO26-K-2238 | Kids Recycled Jacquard Jumper | 7 | 12420 | 69427.8 | 2026-11-23 | In production | Knitting | 690 | 384.6 | 19.5 | 20 | 33 | 13 | 2026-11-08 | -15 | 0 | 4 | 620% | 0 | 0 | 10 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71009879 | LTF | Lanternfield Sweaters Ltd. | Women | KAW26-W-2629 | Recycled Turtle-neck Pullover | 7 | 3324 | 26492.28 | 2026-10-29 | In production | Linking | 152.1 | 43.5 | 4.5 | 5 | 12 | 7 | 2026-10-21 | -8 | 0 | 4 | 620% | 0 | 0 | 10 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71009974 | TLG | Tallgrass Knitwear Ltd. | Kids | KAW26-K-8618 | Kids Recycled Crew-neck Jumper | 12 | 4020 | 19014.6 | 2026-10-31 | In production | Linking | 208.3 | 18.2 | 2.5 | 3 | 13 | 10 | 2026-10-19 | -12 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71009046 | TLG | Tallgrass Knitwear Ltd. | Kids | KAW26-K-6407 | Kids Recycled Crew-neck Jumper | 12 | 9348 | 42252.96 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009605 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-8848 | Acrylic Knitted Vest | 12 | 2172 | 13618.44 | 2026-10-21 | In production |  |  |  | 0 | 0 | 5 | 5 | 2026-10-21 | 0 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009327 | TLG | Tallgrass Knitwear Ltd. | Women | KAW26-W-1895 | Acrylic Crew-neck Pullover | 7 | 4920 | 32176.8 | 2026-10-19 | In production |  |  |  | 0 | 0 | 3 | 3 | 2026-10-19 | 0 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009845 | WSM | Westmere Knitwear Ltd. | Kids | KAW26-K-1274 | Kids Lambswool Crew-neck Jumper | 7 | 4836 | 42315 | 2026-11-01 | In production |  |  |  | 0 | 0 | 14 | 14 | 2026-11-01 | 0 | 0 | 4 | 590% | 0 | 0 | 10 | On track | 88% | 0 | 0 |  | Arif Chowdhury | ok
71009759 | TLG | Tallgrass Knitwear Ltd. | Kids | KAW26-K-5540 | Kids Acrylic Jacquard Jumper | 7 | 2556 | 14032.44 | 2026-11-08 | In production | Knitting | 159.5 | 27.3 | 5.5 | 6 | 20 | 14 | 2026-10-22 | -17 | 0 | 4 | 640% | 0 | 0 | 10 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71010548 | OKH | Oakhaven Knitwear Ltd. | Men | KHO26-M-8216 | Merino Knitted Vest | 12 | 6480 | 93506.4 | 2026-11-17 | In production | Knitting | 577 | 196 | 11.49 | 12 | 28 | 16 | 2026-10-29 | -19 | 0 | 0 | 520% | 0 | 5 | 10 | On track | 98% | 0 | 0 | No report since 11 Oct | Sadia Islam | ok
71010756 | HMR | Highmoor Sweaters Ltd. | Women | KHO26-W-3477 | Recycled Turtle-neck Pullover | 7 | 10656 | 83969.28 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-10 | 0 | 0 | 0 | 910% | 0 | 0 | 9 | On track | 82% | 0 | 0 |  | Farhana Rahman | ok
71010517 | PBB | Pebblebrook Knit Ltd. | Women | KHO26-W-1095 | Wool-blend Crew-neck Pullover | 12 | 2820 | 28143.6 | 2026-11-16 | In production | Linking | 196 | 98 | 14.51 | 15 | 27 | 12 | 2026-11-02 | -14 | 0 | 4 | 170% | 0 | 3 | 9 | On track | 98% | 0 | 0 | No report since 13 Oct | Sadia Islam | ok
71009797 | MDW | Morningdew Knit Ltd. | Kids | KHO26-K-7881 | Kids Acrylic Jacquard Jumper | 7 | 5604 | 27851.88 | 2026-11-16 | In production | Ironing | 350 | 198.3 | 15.51 | 16 | 27 | 11 | 2026-11-03 | -13 | 0 | 4 | 520% | 0 | 0 | 9 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71011193 | HMR | Highmoor Sweaters Ltd. | Women | KHO26-W-1669 | Cotton-blend Long Cardigan | 5 | 3720 | 37162.8 | 2026-12-19 | Pre-production | [5 empty] | 55 |  | 2026-12-19 | 0 | 0 | 0 | 910% | 0 | 0 | 9 | On track | 82% | 0 | 0 |  | Imran Hossain | ok
71009876 | OKH | Oakhaven Knitwear Ltd. | Women | KHO26-W-7481 | Merino Crew-neck Pullover | 12 | 6168 | 117253.68 | 2026-11-23 | Pre-production | [5 empty] | 33 |  | 2026-11-23 | 0 | 0 | 4 | 520% | 0 | 0 | 9 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010556 | HMR | Highmoor Sweaters Ltd. | Women | KHO26-W-7440 | Acrylic Long Cardigan | 5 | 6144 | 62976 | 2026-12-13 | Pre-production | [5 empty] | 50 |  | 2026-12-13 | 0 | 0 | 0 | 910% | 0 | 0 | 9 | On track | 82% | 0 | 0 |  | Imran Hossain | ok
71010193 | RSG | Rosegate Sweaters Ltd. | Women | KHO26-W-6826 | Lambswool Long Cardigan | 5 | 2844 | 54149.76 | 2026-11-18 | In production | Trimming & Mending | 221 | 88.3 | 12.49 | 13 | 29 | 16 | 2026-10-31 | -18 | 0 | 0 | 910% | 0 | 0 | 9 | On track | 98% | 0 | 0 |  | Tanvir Hasan | ok
71009928 | PBB | Pebblebrook Knit Ltd. | Men | KAW26-M-6623 | Wool-blend Knitted Vest | 12 | 3024 | 24554.88 | 2026-10-24 | In production |  |  |  | 0 | 0 | 7 | 7 | 2026-10-24 | 0 | 0 | 4 | 170% | 0 | 3 | 9 | On track | 97% | 0 | 0 | No report since 13 Oct | Sadia Islam | ok
71010637 | HMR | Highmoor Sweaters Ltd. | Kids | KHO26-K-5059 | Kids Wool-blend Cardigan | 7 | 2880 | 19267.2 | 2026-11-28 | Pre-production | [5 empty] | 37 |  | 2026-11-28 | 0 | 0 | 0 | 910% | 0 | 0 | 9 | On track | 82% | 0 | 0 |  | Imran Hossain | ok
71010380 | PBB | Pebblebrook Knit Ltd. | Kids | KAW26-K-4209 | Kids Acrylic Crew-neck Jumper | 12 | 5508 | 23298.84 | 2026-11-05 | In production | Trimming & Mending | 482 | 14.2 | 1.5 | 2 | 18 | 16 | 2026-10-18 | -18 | 0 | 4 | 170% | 0 | 3 | 9 | On track | 98% | 0 | 0 | No report since 13 Oct | Sadia Islam | ok
71009921 | BRW | Brightwool Knit Industries Ltd. | Women | KAW26-W-5702 | Recycled Crew-neck Pullover | 7 | 2736 | 18385.92 | 2026-10-20 | In production |  |  |  | 0 | 0 | 4 | 4 | 2026-10-20 | 0 | 0 | 4 | 450% | 0 | 0 | 9 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71010041 | BRW | Brightwool Knit Industries Ltd. | Women | KAW26-W-8623 | Merino V-neck Cardigan | 12 | 2688 | 45749.76 | 2026-11-05 | In production | Knitting | 154 | 25.7 | 5.51 | 6 | 18 | 12 | 2026-10-22 | -14 | 0 | 4 | 450% | 0 | 0 | 9 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71010537 | BRW | Brightwool Knit Industries Ltd. | Kids | KAW26-K-3839 | Kids Acrylic Cardigan | 7 | 6024 | 27409.2 | 2026-11-12 | In production | Knitting | 298.2 | 138.7 | 12.5 | 13 | 24 | 11 | 2026-10-31 | -12 | 0 | 4 | 450% | 0 | 0 | 9 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71010170 | BLF | Bluefinch Sweaters Ltd. | Men | KAW26-M-8045 | Wool-blend Crew-neck Pullover | 7 | 7068 | 65732.4 | 2026-11-12 | In production | Knitting | 310.7 | 199.8 | 16.5 | 17 | 24 | 7 | 2026-11-04 | -8 | 0 | 4 | 510% | 0 | 0 | 9 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71010210 | CLB | Cloudberry Knit Ltd. | Women | KAW26-W-6473 | Cotton-blend Crew-neck Pullover | 7 | 2592 | 19232.64 | 2026-10-28 | In production |  |  |  | 0 | 0 | 11 | 11 | 2026-10-28 | 0 | 0 | 4 | 440% | 0 | 0 | 8 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71009156 | SVP | Silverpine Knitwear Ltd. | Men | KAW26-M-7340 | Merino V-neck Pullover | 12 | 9528 | 167121.12 | 2026-10-20 | In production |  |  |  | 0 | 0 | 4 | 4 | 2026-10-20 | 0 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010487 | SVP | Silverpine Knitwear Ltd. | Women | KAW26-W-8095 | Recycled Crew-neck Pullover | 12 | 4248 | 30585.6 | 2026-11-12 | In production | Knitting | 199.6 | 111.4 | 14.5 | 15 | 24 | 9 | 2026-11-02 | -10 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Mehedi Karim | ok
71010309 | KST | Kestrel Knitwear Ltd. | Women | KAW26-W-7353 | Recycled Turtle-neck Pullover | 12 | 7548 | 62421.96 | 2026-11-07 | In production | Linking | 634.2 | 72.5 | 3.5 | 4 | 19 | 15 | 2026-10-20 | -18 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010297 | KST | Kestrel Knitwear Ltd. | Men | KAW26-M-3089 | Merino Half-zip Pullover | 7 | 2280 | 44505.6 | 2026-11-11 | In production | Linking | 168.5 | 44.2 | 7.51 | 8 | 23 | 15 | 2026-10-25 | -17 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71009649 | KST | Kestrel Knitwear Ltd. | Kids | KAW26-K-7278 | Kids Recycled Cardigan | 7 | 5460 | 27463.8 | 2026-10-27 | In production | Linking | 260 | 61.3 | 3.5 | 4 | 10 | 6 | 2026-10-20 | -7 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71009509 | SND | Sundial Knitwear Ltd. | Women | KAW26-W-4457 | Recycled Turtle-neck Pullover | 12 | 4968 | 37905.84 | 2026-10-27 | In production | Linking | 223.3 | 26.2 | 2.5 | 3 | 10 | 7 | 2026-10-19 | -8 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Nusrat Jahan | ok
71009254 | SND | Sundial Knitwear Ltd. | Men | KAW26-M-5427 | Cotton-blend V-neck Pullover | 12 | 4596 | 38560.44 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010677 | SND | Sundial Knitwear Ltd. | Women | KAW26-W-3542 | Merino Cropped Pullover | 7 | 3312 | 53223.84 | 2026-11-14 | In production | Packing | 245 | 122.7 | 12.52 | 13 | 25 | 12 | 2026-10-31 | -14 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71009567 | KST | Kestrel Knitwear Ltd. | Kids | KAW26-K-1584 | Kids Recycled Cardigan | 7 | 4776 | 23545.68 | 2026-11-10 | In production | Knitting | 298.2 | 91.8 | 8.5 | 9 | 22 | 13 | 2026-10-26 | -15 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010162 | KST | Kestrel Knitwear Ltd. | Women | KAW26-W-3985 | Wool-blend V-neck Cardigan | 12 | 3624 | 38813.04 | 2026-11-12 | In production | Linking | 244.1 | 83.2 | 9.5 | 10 | 24 | 14 | 2026-10-27 | -16 | 0 | 4 | 370% | 0 | 0 | 8 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71009748 | WTH | Wildthorn Sweaters Ltd. | Men | KAW26-M-6748 | Merino V-neck Pullover | 7 | 3768 | 59383.68 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71009961 | AMB | Amberline Knit Ltd. | Kids | KAW26-K-5595 | Kids Merino Crew-neck Jumper | 12 | 4188 | 46403.04 | 2026-10-31 | In production |  |  |  | 0 | 0 | 13 | 13 | 2026-10-31 | 0 | 0 | 4 | 260% | 0 | 0 | 7 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011352 | RVS | Riverstone Sweaters Ltd. | Women | KSS27-W-2966 | Linen-blend V-neck Cardigan | 12 | 4188 | 51344.88 | 2026-12-30 | Pre-production | [5 empty] | 65 |  | 2026-12-30 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71009634 | WTH | Wildthorn Sweaters Ltd. | Women | KAW26-W-9687 | Merino Turtle-neck Pullover | 7 | 4164 | 71287.68 | 2026-10-22 | In production |  |  |  | 0 | 0 | 6 | 6 | 2026-10-22 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71009300 | WTH | Wildthorn Sweaters Ltd. | Men | KAW26-M-3691 | Lambswool V-neck Pullover | 7 | 2052 | 31888.08 | 2026-10-19 | In production |  |  |  | 0 | 0 | 3 | 3 | 2026-10-19 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71010139 | AMB | Amberline Knit Ltd. | Kids | KAW26-K-1120 | Kids Merino Crew-neck Jumper | 7 | 5928 | 54537.6 | 2026-11-01 | In production | Packing | 425.2 | 15.1 | 0.5 | 1 | 14 | 13 | 2026-10-17 | -15 | 0 | 4 | 260% | 0 | 0 | 7 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010605 | WTH | Wildthorn Sweaters Ltd. | Men | KAW26-M-2284 | Cotton-blend Crew-neck Pullover | 7 | 3396 | 26556.72 | 2026-11-14 | In production | Linking | 252.2 | 85.8 | 9.5 | 10 | 25 | 15 | 2026-10-27 | -18 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 98% | 0 | 0 |  | Tanvir Hasan | ok
71011091 | RVS | Riverstone Sweaters Ltd. | Women | KSS27-W-5551 | Linen-blend V-neck Cardigan | 12 | 1272 | 16637.76 | 2026-12-21 | Pre-production | [5 empty] | 57 |  | 2026-12-21 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | watch
71010952 | RVS | Riverstone Sweaters Ltd. | Kids | KHO26-K-8750 | Kids Cotton-blend Cardigan | 7 | 6120 | 35679.6 | 2026-12-19 | Pre-production | [5 empty] | 55 |  | 2026-12-19 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71010494 | WTH | Wildthorn Sweaters Ltd. | Kids | KHO26-K-8011 | Kids Cotton-blend Crew-neck Jumper | 7 | 4164 | 18862.92 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | watch
71011222 | RVS | Riverstone Sweaters Ltd. | Women | KSS27-W-1428 | Organic Cotton Crew-neck Pullover | 12 | 3252 | 28780.2 | 2027-01-23 | Pre-production | [5 empty] | 85 |  | 2027-01-23 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71010640 | WTH | Wildthorn Sweaters Ltd. | Men | KHO26-M-1184 | Lambswool Shawl-collar Cardigan | 3 | 4920 | 87723.6 | 2026-12-15 | Pre-production | [5 empty] | 52 |  | 2026-12-15 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71011076 | RVS | Riverstone Sweaters Ltd. | Women | KHO26-W-9718 | Wool-blend Long Cardigan | 3 | 4656 | 60015.84 | 2026-12-16 | Pre-production | [5 empty] | 53 |  | 2026-12-16 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Mehedi Karim | ok
71010128 | AMB | Amberline Knit Ltd. | Women | KHO26-W-2486 | Acrylic V-neck Cardigan | 7 | 4668 | 31322.28 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 4 | 260% | 0 | 0 | 7 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010989 | WTH | Wildthorn Sweaters Ltd. | Women | KHO26-W-6908 | Wool-blend Crew-neck Pullover | 7 | 3264 | 27123.84 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71010357 | AMB | Amberline Knit Ltd. | Women | KHO26-W-8211 | Acrylic Crew-neck Pullover | 7 | 8028 | 48087.72 | 2026-11-22 | In production | Knitting | 334 | 260.8 | 25.54 | 26 | 32 | 6 | 2026-11-15 | -7 | 0 | 4 | 260% | 0 | 0 | 7 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010449 | WTH | Wildthorn Sweaters Ltd. | Men | KHO26-M-1805 | Cotton-blend Crew-neck Pullover | 5 | 2616 | 22706.88 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-12 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71010877 | RVS | Riverstone Sweaters Ltd. | Men | KHO26-M-3394 | Recycled Half-zip Pullover | 5 | 4704 | 41536.32 | 2026-12-03 | Pre-production | [5 empty] | 42 |  | 2026-12-03 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71010725 | WTH | Wildthorn Sweaters Ltd. | Women | KHO26-W-3555 | Acrylic Long Cardigan | 3 | 9348 | 92264.76 | 2026-12-08 | Pre-production | [5 empty] | 46 |  | 2026-12-08 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71011648 | RVS | Riverstone Sweaters Ltd. | Men | KSS27-M-9067 | Linen-blend Knitted Vest | 12 | 3480 | 28222.8 | 2027-02-18 | Pre-production | [5 empty] | 108 |  | 2027-02-18 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71011430 | RVS | Riverstone Sweaters Ltd. | Men | KSS27-M-6417 | Cotton-blend V-neck Pullover | 12 | 7140 | 61832.4 | 2027-01-31 | Pre-production | [5 empty] | 92 |  | 2027-01-31 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Imran Hossain | ok
71011518 | RVS | Riverstone Sweaters Ltd. | Kids | KSS27-K-1785 | Kids Organic Cotton Crew-neck Jumper | 12 | 6012 | 33005.88 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 710% | 0 | 0 | 7 | On track | 86% | 0 | 0 |  | Tanvir Hasan | ok
71011601 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-9745 | Linen-blend V-neck Cardigan | 12 | 5364 | 75203.28 | 2027-02-03 | Pre-production | [5 empty] | 95 |  | 2027-02-03 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71011512 | WSM | Westmere Knitwear Ltd. | Men | KSS27-M-7907 | Cotton-blend Knitted Vest | 12 | 4380 | 31448.4 | 2027-01-25 | Pre-production | [5 empty] | 87 |  | 2027-01-25 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71009594 | LTF | Lanternfield Sweaters Ltd. | Men | KAW26-M-3800 | Cotton-blend Shawl-collar Cardigan | 5 | 2076 | 19369.08 | 2026-10-17 | In production |  |  |  | 0 | 0 | 1 | 1 | 2026-10-17 | 0 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Rumana Akter | ok
71011480 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-5119 | Cotton V-neck Cardigan | 12 | 3144 | 27792.96 | 2027-01-20 | Pre-production | [5 empty] | 83 |  | 2027-01-20 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71011056 | WSM | Westmere Knitwear Ltd. | Men | KHO26-M-5273 | Acrylic Knitted Vest | 12 | 4008 | 20080.08 | 2026-12-19 | Pre-production | [5 empty] | 55 |  | 2026-12-19 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71011253 | WSM | Westmere Knitwear Ltd. | Men | KSS27-M-1145 | Organic Cotton V-neck Pullover | 12 | 3888 | 39346.56 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71010777 | TLG | Tallgrass Knitwear Ltd. | Men | KHO26-M-4880 | Lambswool Crew-neck Pullover | 7 | 4284 | 56463.12 | 2026-12-13 | Pre-production | [5 empty] | 50 |  | 2026-12-13 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | watch
71010563 | TLG | Tallgrass Knitwear Ltd. | Kids | KHO26-K-3127 | Kids Acrylic Jacquard Jumper | 7 | 3432 | 15066.48 | 2026-12-14 | Pre-production | [5 empty] | 51 |  | 2026-12-14 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71010912 | LTF | Lanternfield Sweaters Ltd. | Men | KHO26-M-1281 | Cotton-blend Half-zip Pullover | 5 | 6612 | 60433.68 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-10 | 0 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Rumana Akter | watch
71010581 | TLG | Tallgrass Knitwear Ltd. | Women | KHO26-W-8569 | Lambswool Cropped Pullover | 5 | 9720 | 142884 | 2026-12-03 | Pre-production | [5 empty] | 42 |  | 2026-12-03 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | watch
71010369 | TLG | Tallgrass Knitwear Ltd. | Men | KHO26-M-9803 | Cotton-blend Crew-neck Pullover | 5 | 2160 | 19159.2 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71010817 | WSM | Westmere Knitwear Ltd. | Kids | KHO26-K-5401 | Kids Lambswool Cardigan | 7 | 4020 | 39637.2 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-12 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Sadia Islam | watch
71010135 | LTF | Lanternfield Sweaters Ltd. | Women | KHO26-W-8104 | Acrylic Long Cardigan | 5 | 4644 | 47926.08 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Rumana Akter | ok
71011247 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-4479 | Linen-blend Turtle-neck Pullover | 12 | 6336 | 77299.2 | 2027-01-24 | Pre-production | [5 empty] | 86 |  | 2027-01-24 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71010394 | TLG | Tallgrass Knitwear Ltd. | Men | KHO26-M-8379 | Wool-blend Crew-neck Pullover | 7 | 6156 | 57373.92 | 2026-12-03 | Pre-production | [5 empty] | 42 |  | 2026-12-03 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | watch
71010811 | WSM | Westmere Knitwear Ltd. | Women | KHO26-W-1368 | Lambswool Long Cardigan | 5 | 6264 | 123901.92 | 2026-12-08 | Pre-production | [5 empty] | 46 |  | 2026-12-08 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71010063 | TLG | Tallgrass Knitwear Ltd. | Men | KHO26-M-9998 | Lambswool Half-zip Pullover | 7 | 2904 | 42369.36 | 2026-11-28 | Pre-production | [5 empty] | 37 |  | 2026-11-28 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009554 | TLG | Tallgrass Knitwear Ltd. | Women | KAW26-W-3376 | Merino V-neck Cardigan | 12 | 5952 | 109814.4 | 2026-10-31 | In production | Linking | 310.5 | 70.6 | 4.5 | 5 | 13 | 8 | 2026-10-21 | -10 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71009823 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-8305 | Merino Knitted Vest | 12 | 3552 | 51930.24 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009336 | CPL | Copperleaf Knit Ltd. | Women | KAW26-W-1372 | Merino V-neck Cardigan | 12 | 2460 | 41918.4 | 2026-10-29 | In production |  |  |  | 0 | 0 | 12 | 12 | 2026-10-29 | 0 | 0 | 4 | 220% | 0 | 0 | 6 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010999 | WSM | Westmere Knitwear Ltd. | Men | KSS27-M-4425 | Organic Cotton V-neck Pullover | 12 | 3264 | 33358.08 | 2027-01-05 | Pre-production | [5 empty] | 70 |  | 2027-01-05 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71009179 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-9311 | Recycled Crew-neck Pullover | 12 | 2784 | 21436.8 | 2026-10-28 | In production | Linking | 127.5 | 26.9 | 3.51 | 4 | 11 | 7 | 2026-10-20 | -8 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71011447 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-9627 | Organic Cotton Turtle-neck Pullover | 12 | 1512 | 15225.84 | 2027-01-14 | Pre-production | [5 empty] | 78 |  | 2027-01-14 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71011524 | WSM | Westmere Knitwear Ltd. | Men | KSS27-M-2835 | Cotton Knitted Vest | 12 | 6216 | 40590.48 | 2027-02-06 | Pre-production | [5 empty] | 97 |  | 2027-02-06 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71011502 | TLG | Tallgrass Knitwear Ltd. | Kids | KSS27-K-5642 | Kids Organic Cotton Crew-neck Jumper | 12 | 4800 | 30480 | 2027-02-09 | Pre-production | [5 empty] | 100 |  | 2027-02-09 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009263 | LTF | Lanternfield Sweaters Ltd. | Men | KAW26-M-7330 | Cotton-blend Half-zip Pullover | 5 | 2676 | 22746 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Rumana Akter | ok
71010802 | WSM | Westmere Knitwear Ltd. | Women | KSS27-W-3783 | Cotton-blend Crew-neck Pullover | 12 | 4404 | 32633.64 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71010023 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-5004 | Wool-blend Knitted Vest | 12 | 6972 | 53335.8 | 2026-10-21 | In production |  |  |  | 0 | 0 | 5 | 5 | 2026-10-21 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71010412 | LTF | Lanternfield Sweaters Ltd. | Women | KAW26-W-8022 | Wool-blend Long Cardigan | 5 | 2196 | 24946.56 | 2026-11-08 | In production | Linking | 116.8 | 55.1 | 10.49 | 11 | 20 | 9 | 2026-10-28 | -11 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71010221 | LTF | Lanternfield Sweaters Ltd. | Women | KAW26-W-4774 | Acrylic Turtle-neck Pullover | 7 | 3264 | 22293.12 | 2026-11-11 | In production | Knitting | 162.2 | 79 | 12.49 | 13 | 23 | 10 | 2026-10-31 | -11 | 0 | 0 | 620% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71009396 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-7197 | Wool-blend Shawl-collar Cardigan | 5 | 3384 | 37968.48 | 2026-11-03 | In production | Linking | 202.9 | 7.2 | 2.5 | 3 | 16 | 13 | 2026-10-19 | -15 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Imran Hossain | ok
71011363 | WSM | Westmere Knitwear Ltd. | Women | KSS27-W-2528 | Organic Cotton Crew-neck Pullover | 12 | 3384 | 30862.08 | 2027-01-19 | Pre-production | [5 empty] | 82 |  | 2027-01-19 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71010261 | FNS | Fernstitch Knitwear Ltd. | Women | KHO26-W-9587 | Cotton-blend V-neck Cardigan | 12 | 3288 | 29098.8 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 4 | 180% | 0 | 0 | 6 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010478 | WSM | Westmere Knitwear Ltd. | Women | KHO26-W-5628 | Cotton-blend Long Cardigan | 5 | 8544 | 91591.68 | 2026-12-14 | Pre-production | [5 empty] | 51 |  | 2026-12-14 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Imran Hossain | ok
71010821 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-7368 | Organic Cotton Crew-neck Pullover | 12 | 9396 | 92080.8 | 2026-12-22 | Pre-production | [5 empty] | 58 |  | 2026-12-22 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009918 | TLG | Tallgrass Knitwear Ltd. | Men | KHO26-M-1644 | Merino V-neck Pullover | 7 | 4848 | 77422.56 | 2026-11-16 | In production | Linking | 398.6 | 135.5 | 10.5 | 11 | 27 | 16 | 2026-10-28 | -19 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71010960 | WSM | Westmere Knitwear Ltd. | Women | KSS27-W-6728 | Cotton-blend Crew-neck Pullover | 12 | 2532 | 20382.6 | 2026-12-21 | Pre-production | [5 empty] | 57 |  | 2026-12-21 | 0 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 88% | 0 | 0 |  | Farhana Rahman | ok
71010938 | TLG | Tallgrass Knitwear Ltd. | Men | KSS27-M-6380 | Linen-blend Knitted Vest | 12 | 3396 | 28764.12 | 2026-12-31 | Pre-production | [5 empty] | 66 |  | 2026-12-31 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | watch
71009840 | WSM | Westmere Knitwear Ltd. | Women | KAW26-W-8209 | Merino Cropped Pullover | 7 | 3216 | 52034.88 | 2026-10-31 | In production | Linking | 168.6 | 23 | 3.5 | 4 | 13 | 9 | 2026-10-20 | -11 | 0 | 0 | 590% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Imran Hossain | ok
71009933 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-5464 | Lambswool Crew-neck Pullover | 5 | 6420 | 108498 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Rumana Akter | ok
71009995 | TLG | Tallgrass Knitwear Ltd. | Men | KAW26-M-3993 | Recycled Shawl-collar Cardigan | 5 | 2052 | 16518.6 | 2026-10-24 | In production |  |  |  | 0 | 0 | 7 | 7 | 2026-10-24 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Nusrat Jahan | ok
71011176 | TLG | Tallgrass Knitwear Ltd. | Women | KSS27-W-2131 | Cotton-blend Crew-neck Pullover | 12 | 5964 | 53795.28 | 2026-12-29 | Pre-production | [5 empty] | 64 |  | 2026-12-29 | 0 | 0 | 0 | 640% | 0 | 0 | 6 | On track | 87% | 0 | 0 |  | Arif Chowdhury | watch
71010321 | CPL | Copperleaf Knit Ltd. | Men | KAW26-M-2688 | Merino V-neck Pullover | 12 | 1632 | 28511.04 | 2026-11-10 | In production | Knitting | 75.2 | 41.6 | 13.5 | 14 | 22 | 8 | 2026-11-01 | -9 | 0 | 4 | 220% | 0 | 0 | 6 | On track | 98% | 0 | 0 |  | Mehedi Karim | ok
71009269 | PBB | Pebblebrook Knit Ltd. | Men | KAW26-M-9712 | Wool-blend Crew-neck Pullover | 12 | 5520 | 46478.4 | 2026-10-19 | In production |  |  |  | 0 | 0 | 3 | 3 | 2026-10-19 | 0 | 0 | 0 | 170% | 0 | 3 | 5 | On track | 97% | 0 | 0 | No report since 13 Oct | Sadia Islam | ok
71011345 | OKH | Oakhaven Knitwear Ltd. | Men | KSS27-M-8438 | Cotton-blend Crew-neck Pullover | 12 | 1524 | 13197.84 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011580 | BRW | Brightwool Knit Industries Ltd. | Men | KSS27-M-7596 | Cotton-blend Crew-neck Pullover | 12 | 2688 | 20482.56 | 2027-01-31 | Pre-production | [5 empty] | 92 |  | 2027-01-31 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71011537 | BRW | Brightwool Knit Industries Ltd. | Women | KSS27-W-2607 | Organic Cotton V-neck Cardigan | 12 | 5448 | 54697.92 | 2027-01-26 | Pre-production | [5 empty] | 88 |  | 2027-01-26 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71011507 | OKH | Oakhaven Knitwear Ltd. | Men | KSS27-M-3004 | Cotton Knitted Vest | 12 | 5292 | 36885.24 | 2027-01-28 | Pre-production | [5 empty] | 90 |  | 2027-01-28 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011575 | OKH | Oakhaven Knitwear Ltd. | Women | KSS27-W-9592 | Cotton-blend Crew-neck Pullover | 12 | 2340 | 19000.8 | 2027-01-25 | Pre-production | [5 empty] | 87 |  | 2027-01-25 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Rumana Akter | watch
71011598 | MDW | Morningdew Knit Ltd. | Women | KSS27-W-1672 | Linen-blend Crew-neck Pullover | 12 | 7524 | 93523.32 | 2027-02-18 | Pre-production | [5 empty] | 108 |  | 2027-02-18 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71011424 | BRW | Brightwool Knit Industries Ltd. | Men | KSS27-M-4859 | Linen-blend Knitted Vest | 12 | 4716 | 44141.76 | 2027-01-11 | Pre-production | [5 empty] | 75 |  | 2027-01-11 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Mehedi Karim | ok
71011493 | MDW | Morningdew Knit Ltd. | Men | KSS27-M-4726 | Organic Cotton V-neck Pullover | 12 | 6780 | 72274.8 | 2027-02-08 | Pre-production | [5 empty] | 99 |  | 2027-02-08 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | watch
71009999 | BLF | Bluefinch Sweaters Ltd. | Men | KAW26-M-3451 | Cotton-blend Crew-neck Pullover | 5 | 3168 | 27815.04 | 2026-10-27 | In production | Trimming & Mending | 147.4 | 8.2 | 1.5 | 2 | 10 | 8 | 2026-10-18 | -9 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71011153 | OKH | Oakhaven Knitwear Ltd. | Kids | KSS27-K-3480 | Kids Cotton Crew-neck Jumper | 12 | 4020 | 19939.2 | 2027-01-04 | Pre-production | [5 empty] | 69 |  | 2027-01-04 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011338 | MDW | Morningdew Knit Ltd. | Men | KSS27-M-5543 | Linen-blend Crew-neck Pullover | 12 | 3036 | 33335.28 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71009618 | BLF | Bluefinch Sweaters Ltd. | Women | KAW26-W-3011 | Recycled Long Cardigan | 5 | 4368 | 42762.72 | 2026-10-28 | In production | Knitting | 176.1 | 41.5 | 4.5 | 5 | 11 | 6 | 2026-10-21 | -7 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71010103 | BLF | Bluefinch Sweaters Ltd. | Women | KAW26-W-6552 | Wool-blend Cropped Pullover | 5 | 5328 | 50083.2 | 2026-10-25 | In production |  |  |  | 0 | 0 | 8 | 8 | 2026-10-25 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010082 | BLF | Bluefinch Sweaters Ltd. | Men | KHO26-M-8020 | Acrylic Shawl-collar Cardigan | 5 | 4140 | 33782.4 | 2026-11-18 | In production | Linking | 247.5 | 125.9 | 15.49 | 16 | 29 | 13 | 2026-11-03 | -15 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71009230 | MDW | Morningdew Knit Ltd. | Men | KAW26-M-9181 | Recycled Half-zip Pullover | 7 | 2616 | 21660.48 | 2026-10-19 | In production |  |  |  | 0 | 0 | 3 | 3 | 2026-10-19 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71011139 | BRW | Brightwool Knit Industries Ltd. | Kids | KSS27-K-1700 | Kids Organic Cotton Crew-neck Jumper | 12 | 3504 | 21794.88 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Sadia Islam | ok
71009176 | MDW | Morningdew Knit Ltd. | Women | KAW26-W-1723 | Merino Crew-neck Pullover | 12 | 2220 | 37162.8 | 2026-10-21 | In production |  |  |  | 0 | 0 | 5 | 5 | 2026-10-21 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71011562 | MDW | Morningdew Knit Ltd. | Men | KSS27-M-4680 | Linen-blend Crew-neck Pullover | 12 | 1800 | 21132 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71011565 | BRW | Brightwool Knit Industries Ltd. | Women | KSS27-W-1196 | Linen-blend Crew-neck Pullover | 12 | 4368 | 52940.16 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71010595 | BLF | Bluefinch Sweaters Ltd. | Men | KHO26-M-8061 | Wool-blend Shawl-collar Cardigan | 3 | 7776 | 87013.44 | 2026-12-17 | Pre-production | [5 empty] | 54 |  | 2026-12-17 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011436 | MDW | Morningdew Knit Ltd. | Men | KSS27-M-6394 | Cotton Knitted Vest | 12 | 4608 | 38522.88 | 2027-01-23 | Pre-production | [5 empty] | 85 |  | 2027-01-23 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71010318 | MDW | Morningdew Knit Ltd. | Women | KHO26-W-8578 | Wool-blend Crew-neck Pullover | 7 | 3744 | 36429.12 | 2026-11-24 | Pre-production | [5 empty] | 34 |  | 2026-11-24 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | watch
71010664 | OKH | Oakhaven Knitwear Ltd. | Women | KSS27-W-7893 | Cotton Crew-neck Pullover | 14 | 4776 | 47425.68 | 2026-12-21 | Pre-production | [5 empty] | 57 |  | 2026-12-21 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | watch
71011003 | MDW | Morningdew Knit Ltd. | Men | KHO26-M-7198 | Acrylic V-neck Pullover | 7 | 5268 | 38245.68 | 2026-12-15 | Pre-production | [5 empty] | 52 |  | 2026-12-15 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Rumana Akter | ok
71011063 | BRW | Brightwool Knit Industries Ltd. | Men | KSS27-M-1675 | Linen-blend Knitted Vest | 12 | 5700 | 48564 | 2026-12-23 | Pre-production | [5 empty] | 59 |  | 2026-12-23 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71011115 | OKH | Oakhaven Knitwear Ltd. | Men | KHO26-M-9420 | Merino V-neck Pullover | 12 | 5628 | 100741.2 | 2026-12-16 | Pre-production | [5 empty] | 53 |  | 2026-12-16 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | watch
71010094 | BLF | Bluefinch Sweaters Ltd. | Women | KHO26-W-1593 | Wool-blend V-neck Cardigan | 7 | 7560 | 81270 | 2026-11-28 | Pre-production | [5 empty] | 37 |  | 2026-11-28 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010901 | MDW | Morningdew Knit Ltd. | Kids | KHO26-K-7418 | Kids Acrylic Jacquard Jumper | 7 | 4140 | 19706.4 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71010283 | BLF | Bluefinch Sweaters Ltd. | Kids | KHO26-K-9122 | Kids Cotton-blend Cardigan | 7 | 3960 | 19562.4 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011021 | BLF | Bluefinch Sweaters Ltd. | Kids | KHO26-K-1144 | Kids Merino Cardigan | 7 | 3720 | 39692.4 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-10 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010553 | BRW | Brightwool Knit Industries Ltd. | Men | KHO26-M-5675 | Cotton-blend Half-zip Pullover | 5 | 3408 | 32376 | 2026-11-24 | Pre-production | [5 empty] | 34 |  | 2026-11-24 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71010859 | OKH | Oakhaven Knitwear Ltd. | Women | KHO26-W-2581 | Acrylic V-neck Cardigan | 12 | 5856 | 39645.12 | 2026-12-03 | Pre-production | [5 empty] | 42 |  | 2026-12-03 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010407 | MDW | Morningdew Knit Ltd. | Men | KHO26-M-1043 | Recycled Crew-neck Pullover | 12 | 1584 | 13083.84 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71010343 | MDW | Morningdew Knit Ltd. | Men | KHO26-M-3029 | Acrylic Knitted Vest | 12 | 4692 | 27072.84 | 2026-12-07 | Pre-production | [5 empty] | 45 |  | 2026-12-07 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71010768 | OKH | Oakhaven Knitwear Ltd. | Men | KHO26-M-6172 | Acrylic Crew-neck Pullover | 12 | 4620 | 32986.8 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71010435 | BRW | Brightwool Knit Industries Ltd. | Men | KHO26-M-6695 | Acrylic Knitted Vest | 12 | 2400 | 13056 | 2026-12-05 | Pre-production | [5 empty] | 43 |  | 2026-12-05 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Mehedi Karim | ok
71008959 | BLF | Bluefinch Sweaters Ltd. | Women | KAW26-W-4047 | Acrylic Long Cardigan | 5 | 3216 | 25084.8 | 2026-10-17 | In production |  |  |  | 0 | 0 | 1 | 1 | 2026-10-17 | 0 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011289 | MDW | Morningdew Knit Ltd. | Men | KSS27-M-1013 | Linen-blend Crew-neck Pullover | 12 | 8424 | 92327.04 | 2026-12-27 | Pre-production | [5 empty] | 62 |  | 2026-12-27 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Mehedi Karim | ok
71011106 | BRW | Brightwool Knit Industries Ltd. | Men | KSS27-M-5187 | Organic Cotton Crew-neck Pullover | 12 | 2796 | 25751.16 | 2026-12-26 | Pre-production | [5 empty] | 61 |  | 2026-12-26 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71010350 | BRW | Brightwool Knit Industries Ltd. | Women | KAW26-W-2182 | Acrylic Crew-neck Pullover | 12 | 1968 | 13106.88 | 2026-11-11 | In production | Knitting | 109 | 37.2 | 9.49 | 10 | 23 | 13 | 2026-10-27 | -15 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71010849 | BRW | Brightwool Knit Industries Ltd. | Men | KSS27-M-8092 | Organic Cotton Knitted Vest | 12 | 3216 | 28043.52 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71011230 | OKH | Oakhaven Knitwear Ltd. | Kids | KSS27-K-6796 | Kids Cotton Crew-neck Jumper | 12 | 10920 | 51979.2 | 2026-12-29 | Pre-production | [5 empty] | 64 |  | 2026-12-29 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011168 | OKH | Oakhaven Knitwear Ltd. | Women | KSS27-W-4646 | Linen-blend Crew-neck Pullover | 14 | 7104 | 88018.56 | 2026-12-27 | Pre-production | [5 empty] | 62 |  | 2026-12-27 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Sadia Islam | ok
71011196 | BRW | Brightwool Knit Industries Ltd. | Men | KHO26-M-1051 | Cotton-blend Knitted Vest | 12 | 4200 | 25662 | 2026-12-20 | Pre-production | [5 empty] | 56 |  | 2026-12-20 | 0 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 91% | 0 | 0 |  | Farhana Rahman | ok
71010250 | BRW | Brightwool Knit Industries Ltd. | Kids | KHO26-K-6190 | Kids Acrylic Crew-neck Jumper | 12 | 4788 | 22359.96 | 2026-11-16 | In production | Trimming & Mending | 225.7 | 160.3 | 19.47 | 20 | 27 | 7 | 2026-11-08 | -8 | 0 | 0 | 450% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Farhana Rahman | ok
71011014 | MDW | Morningdew Knit Ltd. | Kids | KSS27-K-9549 | Kids Cotton Crew-neck Jumper | 12 | 5688 | 34241.76 | 2027-01-05 | Pre-production | [5 empty] | 70 |  | 2027-01-05 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71010004 | MDW | Morningdew Knit Ltd. | Women | KAW26-W-7820 | Lambswool V-neck Cardigan | 7 | 3636 | 62902.8 | 2026-10-27 | In production |  |  |  | 0 | 0 | 10 | 10 | 2026-10-27 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Mehedi Karim | ok
71009785 | BLF | Bluefinch Sweaters Ltd. | Men | KAW26-M-4998 | Lambswool Shawl-collar Cardigan | 3 | 8244 | 165786.84 | 2026-11-02 | In production | Linking | 496.7 | 19.1 | 2.5 | 3 | 15 | 12 | 2026-10-19 | -14 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71009689 | BLF | Bluefinch Sweaters Ltd. | Kids | KAW26-K-4385 | Kids Cotton-blend Cardigan | 7 | 4188 | 26049.36 | 2026-11-12 | In production | Knitting | 218 | 91.3 | 11.51 | 12 | 24 | 12 | 2026-10-29 | -14 | 0 | 0 | 510% | 0 | 0 | 5 | On track | 98% | 0 | 0 |  | Sadia Islam | ok
71011372 | MDW | Morningdew Knit Ltd. | Kids | KSS27-K-8993 | Kids Organic Cotton Crew-neck Jumper | 12 | 5460 | 32323.2 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 520% | 0 | 0 | 5 | On track | 90% | 0 | 0 |  | Nusrat Jahan | ok
71011461 | CLB | Cloudberry Knit Ltd. | Women | KSS27-W-9808 | Cotton-blend V-neck Cardigan | 12 | 1944 | 18720.72 | 2027-01-31 | Pre-production | [5 empty] | 92 |  | 2027-01-31 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71011456 | SND | Sundial Knitwear Ltd. | Kids | KSS27-K-8808 | Kids Cotton-blend Crew-neck Jumper | 12 | 4572 | 21488.4 | 2027-01-25 | Pre-production | [5 empty] | 87 |  | 2027-01-25 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71011327 | SND | Sundial Knitwear Ltd. | Women | KSS27-W-2633 | Organic Cotton V-neck Cardigan | 12 | 2520 | 27921.6 | 2027-01-25 | Pre-production | [5 empty] | 87 |  | 2027-01-25 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71011666 | KST | Kestrel Knitwear Ltd. | Men | KSS27-M-3834 | Organic Cotton V-neck Pullover | 12 | 4632 | 45717.84 | 2027-02-10 | Pre-production | [5 empty] | 101 |  | 2027-02-10 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | watch
71011645 | CLB | Cloudberry Knit Ltd. | Kids | KSS27-K-8762 | Kids Linen-blend Crew-neck Jumper | 12 | 3168 | 21067.2 | 2027-02-11 | Pre-production | [5 empty] | 102 |  | 2027-02-11 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71011442 | KST | Kestrel Knitwear Ltd. | Women | KSS27-W-5210 | Linen-blend Crew-neck Pullover | 14 | 7212 | 77817.48 | 2027-02-13 | Pre-production | [5 empty] | 103 |  | 2027-02-13 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71011675 | KST | Kestrel Knitwear Ltd. | Women | KSS27-W-2278 | Cotton Turtle-neck Pullover | 12 | 2808 | 28276.56 | 2027-02-16 | Pre-production | [5 empty] | 106 |  | 2027-02-16 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71011572 | SVP | Silverpine Knitwear Ltd. | Kids | KSS27-K-2474 | Kids Organic Cotton Crew-neck Jumper | 12 | 2616 | 15408.24 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71011686 | SND | Sundial Knitwear Ltd. | Kids | KSS27-K-2128 | Kids Cotton Crew-neck Jumper | 12 | 3384 | 21353.04 | 2027-02-18 | Pre-production | [5 empty] | 108 |  | 2027-02-18 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71010780 | CLB | Cloudberry Knit Ltd. | Women | KHO26-W-1418 | Cotton-blend Cropped Pullover | 7 | 2580 | 18782.4 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71010289 | KST | Kestrel Knitwear Ltd. | Kids | KHO26-K-1367 | Kids Merino Cardigan | 7 | 2412 | 27207.36 | 2026-12-06 | Pre-production | [5 empty] | 44 |  | 2026-12-06 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Sadia Islam | ok
71010019 | KST | Kestrel Knitwear Ltd. | Men | KHO26-M-2216 | Acrylic V-neck Pullover | 12 | 5808 | 40656 | 2026-11-24 | Pre-production | [5 empty] | 34 |  | 2026-11-24 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71010464 | SND | Sundial Knitwear Ltd. | Women | KHO26-W-8242 | Lambswool Turtle-neck Pullover | 7 | 5628 | 79354.8 | 2026-11-25 | Pre-production | [5 empty] | 35 |  | 2026-11-25 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | watch
71010377 | SVP | Silverpine Knitwear Ltd. | Women | KHO26-W-5584 | Wool-blend V-neck Cardigan | 12 | 6876 | 64840.68 | 2026-12-03 | Pre-production | [5 empty] | 42 |  | 2026-12-03 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010441 | CLB | Cloudberry Knit Ltd. | Women | KHO26-W-7570 | Acrylic Cropped Pullover | 7 | 4812 | 33058.44 | 2026-12-12 | Pre-production | [5 empty] | 49 |  | 2026-12-12 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | watch
71009505 | SVP | Silverpine Knitwear Ltd. | Women | KAW26-W-9951 | Cotton-blend Crew-neck Pullover | 12 | 3948 | 34071.24 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010907 | CLB | Cloudberry Knit Ltd. | Kids | KHO26-K-8677 | Kids Recycled Cardigan | 7 | 6180 | 28613.4 | 2026-12-07 | Pre-production | [5 empty] | 45 |  | 2026-12-07 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71010570 | KST | Kestrel Knitwear Ltd. | Men | KHO26-M-8302 | Wool-blend V-neck Pullover | 7 | 3636 | 30578.76 | 2026-11-22 | In production | Knitting | 234 | 117.3 | 17.54 | 18 | 32 | 14 | 2026-11-05 | -17 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010654 | KST | Kestrel Knitwear Ltd. | Men | KHO26-M-7805 | Acrylic V-neck Pullover | 12 | 6900 | 42573 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71010741 | CLB | Cloudberry Knit Ltd. | Men | KHO26-M-8032 | Recycled Crew-neck Pullover | 7 | 3600 | 28692 | 2026-11-23 | In production | Knitting | 172 | 112.4 | 22.43 | 23 | 33 | 10 | 2026-11-11 | -12 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71009802 | KST | Kestrel Knitwear Ltd. | Women | KHO26-W-9297 | Wool-blend Crew-neck Pullover | 7 | 3384 | 36750.24 | 2026-11-16 | In production | Washing | 182 | 123.2 | 18.59 | 19 | 27 | 8 | 2026-11-07 | -9 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Tanvir Hasan | ok
71010188 | SND | Sundial Knitwear Ltd. | Men | KHO26-M-8487 | Acrylic Half-zip Pullover | 7 | 3948 | 32649.96 | 2026-11-17 | In production | Linking | 210.7 | 127.1 | 17.49 | 18 | 28 | 10 | 2026-11-05 | -12 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Nusrat Jahan | ok
71009980 | CLB | Cloudberry Knit Ltd. | Men | KHO26-M-7986 | Lambswool Crew-neck Pullover | 7 | 5160 | 69969.6 | 2026-11-16 | In production | Trimming & Mending | 249.5 | 175.8 | 19.47 | 20 | 27 | 7 | 2026-11-08 | -8 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71010969 | SVP | Silverpine Knitwear Ltd. | Women | KSS27-W-9419 | Linen-blend V-neck Cardigan | 12 | 3156 | 41059.56 | 2026-12-23 | Pre-production | [5 empty] | 59 |  | 2026-12-23 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71011097 | SVP | Silverpine Knitwear Ltd. | Women | KSS27-W-3602 | Organic Cotton Turtle-neck Pullover | 12 | 4044 | 45737.64 | 2026-12-23 | Pre-production | [5 empty] | 59 |  | 2026-12-23 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Rumana Akter | ok
71011120 | SND | Sundial Knitwear Ltd. | Men | KHO26-M-3424 | Wool-blend Knitted Vest | 12 | 2688 | 21423.36 | 2026-12-16 | Pre-production | [5 empty] | 53 |  | 2026-12-16 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71010648 | SND | Sundial Knitwear Ltd. | Women | KHO26-W-9873 | Cotton-blend Crew-neck Pullover | 7 | 1884 | 17916.84 | 2026-12-17 | Pre-production | [5 empty] | 54 |  | 2026-12-17 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Tanvir Hasan | ok
71010657 | SVP | Silverpine Knitwear Ltd. | Kids | KHO26-K-1476 | Kids Wool-blend Crew-neck Jumper | 12 | 3936 | 21648 | 2026-12-17 | Pre-production | [5 empty] | 54 |  | 2026-12-17 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010863 | CLB | Cloudberry Knit Ltd. | Kids | KHO26-K-3192 | Kids Wool-blend Cardigan | 7 | 3240 | 20606.4 | 2026-12-17 | Pre-production | [5 empty] | 54 |  | 2026-12-17 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71010701 | SND | Sundial Knitwear Ltd. | Kids | KHO26-K-4087 | Kids Merino Jacquard Jumper | 7 | 2268 | 24607.8 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71011243 | CLB | Cloudberry Knit Ltd. | Men | KSS27-M-8010 | Cotton Knitted Vest | 12 | 4860 | 31687.2 | 2027-01-23 | Pre-production | [5 empty] | 85 |  | 2027-01-23 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71010513 | KST | Kestrel Knitwear Ltd. | Men | KHO26-M-2015 | Wool-blend Half-zip Pullover | 7 | 6096 | 55534.56 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-10 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71010630 | CLB | Cloudberry Knit Ltd. | Women | KHO26-W-3797 | Cotton-blend Turtle-neck Pullover | 12 | 5652 | 45894.24 | 2026-11-22 | In production | Knitting | 297 | 181.5 | 20.53 | 21 | 32 | 11 | 2026-11-09 | -13 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Rumana Akter | ok
71010524 | CLB | Cloudberry Knit Ltd. | Women | KHO26-W-2746 | Cotton-blend Crew-neck Pullover | 7 | 3144 | 28013.04 | 2026-11-18 | In production | Ironing | 158 | 104.8 | 19.4 | 20 | 29 | 9 | 2026-11-08 | -10 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Tanvir Hasan | ok
71009910 | SND | Sundial Knitwear Ltd. | Kids | KAW26-K-1226 | Kids Acrylic Cardigan | 7 | 2148 | 8742.36 | 2026-11-11 | In production | Linking | 106.9 | 59.6 | 13.48 | 14 | 23 | 9 | 2026-11-01 | -10 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Nusrat Jahan | ok
71009559 | SVP | Silverpine Knitwear Ltd. | Kids | KAW26-K-8328 | Kids Merino Crew-neck Jumper | 12 | 10188 | 90469.44 | 2026-11-09 | In production | Knitting | 470.2 | 274.2 | 13.5 | 14 | 21 | 7 | 2026-11-01 | -8 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Mehedi Karim | ok
71009273 | SVP | Silverpine Knitwear Ltd. | Kids | KAW26-K-7469 | Kids Recycled Crew-neck Jumper | 12 | 7632 | 31291.2 | 2026-10-21 | In production |  |  |  | 0 | 0 | 5 | 5 | 2026-10-21 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Mehedi Karim | ok
71010792 | CLB | Cloudberry Knit Ltd. | Kids | KSS27-K-5727 | Kids Cotton-blend Crew-neck Jumper | 12 | 5832 | 31784.4 | 2026-12-31 | Pre-production | [5 empty] | 66 |  | 2026-12-31 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | watch
71010229 | KST | Kestrel Knitwear Ltd. | Men | KAW26-M-1877 | Lambswool Crew-neck Pullover | 7 | 3492 | 54091.08 | 2026-11-12 | In production | Linking | 235.6 | 80.4 | 9.5 | 10 | 24 | 14 | 2026-10-27 | -16 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71010955 | SND | Sundial Knitwear Ltd. | Men | KSS27-M-3132 | Cotton-blend Crew-neck Pullover | 12 | 3360 | 27820.8 | 2026-12-21 | Pre-production | [5 empty] | 57 |  | 2026-12-21 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71010056 | KST | Kestrel Knitwear Ltd. | Women | KAW26-W-2160 | Recycled V-neck Cardigan | 7 | 9216 | 72161.28 | 2026-11-15 | In production | Packing | 801 | 323.7 | 10.51 | 11 | 26 | 15 | 2026-10-28 | -18 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71011208 | SND | Sundial Knitwear Ltd. | Kids | KSS27-K-1433 | Kids Cotton Crew-neck Jumper | 12 | 1776 | 10034.4 | 2026-12-29 | Pre-production | [5 empty] | 64 |  | 2026-12-29 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71011008 | CLB | Cloudberry Knit Ltd. | Men | KHO26-M-6356 | Acrylic Crew-neck Pullover | 12 | 6516 | 39421.8 | 2026-12-19 | Pre-production | [5 empty] | 55 |  | 2026-12-19 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71009358 | SND | Sundial Knitwear Ltd. | Kids | KAW26-K-9323 | Kids Merino Jacquard Jumper | 7 | 13248 | 139898.88 | 2026-10-31 | In production |  |  |  | 0 | 0 | 13 | 13 | 2026-10-31 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71011179 | SVP | Silverpine Knitwear Ltd. | Women | KSS27-W-3532 | Linen-blend Crew-neck Pullover | 14 | 2316 | 24943.32 | 2027-01-06 | Pre-production | [5 empty] | 71 |  | 2027-01-06 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Imran Hossain | ok
71010922 | KST | Kestrel Knitwear Ltd. | Men | KSS27-M-1165 | Organic Cotton Knitted Vest | 12 | 3048 | 26609.04 | 2026-12-29 | Pre-production | [5 empty] | 64 |  | 2026-12-29 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71011710 | KST | Kestrel Knitwear Ltd. | Kids | KSS27-K-6556 | Kids Cotton Crew-neck Jumper | 12 | 4152 | 21092.16 | 2027-02-24 | Pre-production | [5 empty] | 113 |  | 2027-02-24 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71011678 | KST | Kestrel Knitwear Ltd. | Men | KSS27-M-2559 | Organic Cotton Crew-neck Pullover | 12 | 14340 | 129060 | 2027-02-25 | Pre-production | [5 empty] | 114 |  | 2027-02-25 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Arif Chowdhury | ok
71011698 | SND | Sundial Knitwear Ltd. | Women | KSS27-W-3018 | Linen-blend Turtle-neck Pullover | 12 | 10188 | 128980.08 | 2027-02-28 | Pre-production | [5 empty] | 116 |  | 2027-02-28 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | watch
71011487 | SND | Sundial Knitwear Ltd. | Women | KSS27-W-2429 | Linen-blend V-neck Cardigan | 12 | 1536 | 19491.84 | 2027-02-08 | Pre-production | [5 empty] | 99 |  | 2027-02-08 | 0 | 0 | 0 | 370% | 0 | 0 | 4 | On track | 93% | 0 | 0 |  | Nusrat Jahan | ok
71009007 | CLB | Cloudberry Knit Ltd. | Men | KAW26-M-2841 | Merino Half-zip Pullover | 7 | 1224 | 24198.48 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 440% | 0 | 0 | 4 | On track | 91% | 0 | 0 |  | Rumana Akter | ok
71011382 | AMB | Amberline Knit Ltd. | Men | KSS27-M-1059 | Cotton V-neck Pullover | 12 | 3552 | 33175.68 | 2027-02-04 | Pre-production | [5 empty] | 96 |  | 2027-02-04 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011618 | AMB | Amberline Knit Ltd. | Men | KSS27-M-8882 | Organic Cotton V-neck Pullover | 12 | 4260 | 45539.4 | 2027-02-06 | Pre-production | [5 empty] | 97 |  | 2027-02-06 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011186 | AMB | Amberline Knit Ltd. | Men | KSS27-M-5653 | Cotton Knitted Vest | 12 | 2244 | 16897.32 | 2027-01-11 | Pre-production | [5 empty] | 75 |  | 2027-01-11 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | watch
71011335 | AMB | Amberline Knit Ltd. | Men | KSS27-M-1462 | Cotton-blend V-neck Pullover | 12 | 4140 | 33451.2 | 2027-01-04 | Pre-production | [5 empty] | 69 |  | 2027-01-04 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011553 | AMB | Amberline Knit Ltd. | Women | KSS27-W-7615 | Organic Cotton V-neck Cardigan | 12 | 3948 | 40032.72 | 2027-01-19 | Pre-production | [5 empty] | 82 |  | 2027-01-19 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010898 | AMB | Amberline Knit Ltd. | Women | KHO26-W-7872 | Merino Crew-neck Pullover | 12 | 5556 | 88729.32 | 2026-11-29 | Pre-production | [5 empty] | 38 |  | 2026-11-29 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010086 | AMB | Amberline Knit Ltd. | Women | KHO26-W-8379 | Wool-blend Turtle-neck Pullover | 7 | 3624 | 40190.16 | 2026-11-23 | In production | Knitting | 249 | 112.5 | 16.55 | 17 | 33 | 16 | 2026-11-04 | -19 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 98% | 0 | 0 |  | Arif Chowdhury | ok
71011657 | AMB | Amberline Knit Ltd. | Men | KSS27-M-1969 | Linen-blend V-neck Pullover | 12 | 4272 | 51605.76 | 2027-02-22 | Pre-production | [5 empty] | 111 |  | 2027-02-22 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011052 | AMB | Amberline Knit Ltd. | Women | KHO26-W-4859 | Wool-blend Turtle-neck Pullover | 12 | 2808 | 24401.52 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010842 | AMB | Amberline Knit Ltd. | Kids | KHO26-K-4470 | Kids Recycled Crew-neck Jumper | 12 | 2292 | 11001.6 | 2026-12-14 | Pre-production | [5 empty] | 51 |  | 2026-12-14 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010398 | AMB | Amberline Knit Ltd. | Women | KHO26-W-3067 | Wool-blend Cropped Pullover | 7 | 2004 | 16112.16 | 2026-12-10 | Pre-production | [5 empty] | 48 |  | 2026-12-10 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011239 | AMB | Amberline Knit Ltd. | Men | KSS27-M-4003 | Cotton-blend V-neck Pullover | 12 | 2376 | 20599.92 | 2027-01-20 | Pre-production | [5 empty] | 83 |  | 2027-01-20 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010883 | AMB | Amberline Knit Ltd. | Men | KSS27-M-3708 | Linen-blend V-neck Pullover | 12 | 5556 | 70394.52 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010892 | AMB | Amberline Knit Ltd. | Men | KSS27-M-2904 | Organic Cotton Knitted Vest | 12 | 8856 | 65534.4 | 2026-12-26 | Pre-production | [5 empty] | 61 |  | 2026-12-26 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71009148 | AMB | Amberline Knit Ltd. | Men | KAW26-M-4568 | Acrylic V-neck Pullover | 12 | 7740 | 61997.4 | 2026-10-19 | In production |  |  |  | 0 | 0 | 3 | 3 | 2026-10-19 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71010975 | AMB | Amberline Knit Ltd. | Women | KSS27-W-1264 | Cotton Turtle-neck Pullover | 12 | 5568 | 54510.72 | 2026-12-24 | Pre-production | [5 empty] | 60 |  | 2026-12-24 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71009222 | AMB | Amberline Knit Ltd. | Kids | KAW26-K-2917 | Kids Acrylic Crew-neck Jumper | 12 | 2244 | 9447.24 | 2026-10-15 | In production |  |  |  | 0 | 0 | 0 | 0 | 2026-10-15 | 0 | 0 | 0 | 260% | 0 | 0 | 3 | On track | 95% | 0 | 0 |  | Arif Chowdhury | ok
71011101 | FNS | Fernstitch Knitwear Ltd. | Women | KSS27-W-8346 | Cotton Crew-neck Pullover | 12 | 1224 | 9987.84 | 2027-01-06 | Pre-production | [5 empty] | 71 |  | 2027-01-06 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | watch
71011410 | CPL | Copperleaf Knit Ltd. | Kids | KSS27-K-6610 | Kids Linen-blend Crew-neck Jumper | 12 | 3108 | 20574.96 | 2027-01-16 | Pre-production | [5 empty] | 79 |  | 2027-01-16 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010870 | FNS | Fernstitch Knitwear Ltd. | Men | KSS27-M-3329 | Organic Cotton Knitted Vest | 12 | 4788 | 40985.28 | 2027-01-02 | Pre-production | [5 empty] | 67 |  | 2027-01-02 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Farhana Rahman | ok
71011356 | PBB | Pebblebrook Knit Ltd. | Men | KSS27-M-5373 | Organic Cotton Crew-neck Pullover | 12 | 6348 | 66780.96 | 2027-01-16 | Pre-production | [5 empty] | 79 |  | 2027-01-16 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok
71011018 | CPL | Copperleaf Knit Ltd. | Men | KSS27-M-7169 | Organic Cotton Knitted Vest | 12 | 3372 | 27279.48 | 2027-01-13 | Pre-production | [5 empty] | 77 |  | 2027-01-13 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011636 | PBB | Pebblebrook Knit Ltd. | Men | KSS27-M-8652 | Linen-blend Crew-neck Pullover | 12 | 2616 | 31548.96 | 2027-02-07 | Pre-production | [5 empty] | 98 |  | 2027-02-07 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok
71011161 | CPL | Copperleaf Knit Ltd. | Men | KSS27-M-8359 | Organic Cotton Crew-neck Pullover | 12 | 6204 | 69112.56 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Rumana Akter | ok
71009893 | FNS | Fernstitch Knitwear Ltd. | Women | KAW26-W-5814 | Acrylic Turtle-neck Pullover | 12 | 3480 | 26413.2 | 2026-10-18 | In production |  |  |  | 0 | 0 | 2 | 2 | 2026-10-18 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011691 | CPL | Copperleaf Knit Ltd. | Women | KSS27-W-9371 | Linen-blend Turtle-neck Pullover | 12 | 1968 | 26331.84 | 2027-02-18 | Pre-production | [5 empty] | 108 |  | 2027-02-18 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011663 | CPL | Copperleaf Knit Ltd. | Kids | KSS27-K-5929 | Kids Organic Cotton Crew-neck Jumper | 12 | 8076 | 46760.04 | 2027-02-11 | Pre-production | [5 empty] | 102 |  | 2027-02-11 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011394 | FNS | Fernstitch Knitwear Ltd. | Women | KSS27-W-8865 | Linen-blend Turtle-neck Pullover | 12 | 3216 | 42386.88 | 2027-01-18 | Pre-production | [5 empty] | 81 |  | 2027-01-18 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011171 | FNS | Fernstitch Knitwear Ltd. | Men | KSS27-M-4215 | Organic Cotton Knitted Vest | 12 | 9072 | 82645.92 | 2026-12-22 | Pre-production | [5 empty] | 58 |  | 2026-12-22 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | watch
71011202 | PBB | Pebblebrook Knit Ltd. | Men | KSS27-M-8249 | Linen-blend V-neck Pullover | 12 | 3372 | 40227.96 | 2026-12-26 | Pre-production | [5 empty] | 61 |  | 2026-12-26 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok
71009712 | CPL | Copperleaf Knit Ltd. | Men | KAW26-M-4999 | Wool-blend Knitted Vest | 12 | 6276 | 50459.04 | 2026-10-18 | In production |  |  |  | 0 | 0 | 2 | 2 | 2026-10-18 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011403 | CPL | Copperleaf Knit Ltd. | Men | KSS27-M-4931 | Cotton Crew-neck Pullover | 12 | 2616 | 25558.32 | 2027-01-10 | Pre-production | [5 empty] | 74 |  | 2027-01-10 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010503 | CPL | Copperleaf Knit Ltd. | Men | KHO26-M-2264 | Recycled Crew-neck Pullover | 12 | 3732 | 28213.92 | 2026-12-09 | Pre-production | [5 empty] | 47 |  | 2026-12-09 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011317 | CPL | Copperleaf Knit Ltd. | Men | KSS27-M-1224 | Linen-blend Crew-neck Pullover | 12 | 4764 | 54166.68 | 2027-01-23 | Pre-production | [5 empty] | 85 |  | 2027-01-23 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011530 | CPL | Copperleaf Knit Ltd. | Men | KSS27-M-1326 | Cotton-blend V-neck Pullover | 12 | 6324 | 60014.76 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011309 | CPL | Copperleaf Knit Ltd. | Women | KSS27-W-3745 | Linen-blend Turtle-neck Pullover | 12 | 3108 | 41958 | 2027-01-21 | Pre-production | [5 empty] | 84 |  | 2027-01-21 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010918 | CPL | Copperleaf Knit Ltd. | Kids | KHO26-K-3336 | Kids Wool-blend Crew-neck Jumper | 12 | 1788 | 10781.64 | 2026-12-16 | Pre-production | [5 empty] | 53 |  | 2026-12-16 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010946 | PBB | Pebblebrook Knit Ltd. | Men | KHO26-M-5032 | Merino V-neck Pullover | 12 | 3492 | 58735.44 | 2026-12-01 | Pre-production | [5 empty] | 40 |  | 2026-12-01 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok
71010573 | FNS | Fernstitch Knitwear Ltd. | Kids | KHO26-K-9232 | Kids Wool-blend Crew-neck Jumper | 12 | 4224 | 26822.4 | 2026-11-30 | Pre-production | [5 empty] | 39 |  | 2026-11-30 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Rumana Akter | ok
71010798 | FNS | Fernstitch Knitwear Ltd. | Kids | KHO26-K-6831 | Kids Wool-blend Crew-neck Jumper | 12 | 3648 | 21559.68 | 2026-11-30 | Pre-production | [5 empty] | 39 |  | 2026-11-30 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71010402 | FNS | Fernstitch Knitwear Ltd. | Kids | KHO26-K-1503 | Kids Recycled Crew-neck Jumper | 12 | 7728 | 37789.92 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Nusrat Jahan | ok
71010472 | PBB | Pebblebrook Knit Ltd. | Women | KHO26-W-3399 | Merino Turtle-neck Pullover | 12 | 3372 | 52771.8 | 2026-11-26 | Pre-production | [5 empty] | 36 |  | 2026-11-26 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok
71009828 | FNS | Fernstitch Knitwear Ltd. | Men | KAW26-M-9353 | Recycled V-neck Pullover | 12 | 3672 | 27576.72 | 2026-11-01 | In production | Linking | 183.1 | 58.6 | 5.5 | 6 | 14 | 8 | 2026-10-22 | -10 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 98% | 0 | 0 |  | Mehedi Karim | ok
71010455 | FNS | Fernstitch Knitwear Ltd. | Men | KHO26-M-1926 | Cotton-blend Crew-neck Pullover | 12 | 4392 | 40801.68 | 2026-11-17 | In production | Linking | 344.2 | 130 | 11.51 | 12 | 28 | 16 | 2026-10-29 | -19 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 98% | 0 | 0 |  | Mehedi Karim | ok
71011534 | FNS | Fernstitch Knitwear Ltd. | Women | KSS27-W-7527 | Cotton Crew-neck Pullover | 14 | 4440 | 38983.2 | 2027-02-25 | Pre-production | [5 empty] | 114 |  | 2027-02-25 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011276 | CPL | Copperleaf Knit Ltd. | Women | KSS27-W-5149 | Cotton Turtle-neck Pullover | 12 | 2256 | 23349.6 | 2027-01-26 | Pre-production | [5 empty] | 88 |  | 2027-01-26 | 0 | 0 | 0 | 220% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011418 | FNS | Fernstitch Knitwear Ltd. | Women | KSS27-W-2784 | Organic Cotton Crew-neck Pullover | 14 | 4236 | 48205.68 | 2027-01-31 | Pre-production | [5 empty] | 92 |  | 2027-01-31 | 0 | 0 | 0 | 180% | 0 | 0 | 2 | On track | 96% | 0 | 0 |  | Mehedi Karim | ok
71011323 | PBB | Pebblebrook Knit Ltd. | Men | KSS27-M-2201 | Cotton-blend Crew-neck Pullover | 12 | 2520 | 23914.8 | 2027-02-02 | Pre-production | [5 empty] | 94 |  | 2027-02-02 | 0 | 0 | 0 | 170% | 0 | 0 | 2 | On track | 97% | 0 | 0 |  | Sadia Islam | ok

## Factory Summary
Factory Code | Factory Name | Open POs | Open FOB USD | At risk + Critical + Late POs | Value at Risk USD | Share of Value at Risk | OTD 12m | AQL Pass 90d | Last Report | Reported Today
GRL | Greyloom Knitwear Ltd. | 52 | 2439005.16 | 18 | 774058.56 | 32.3% | 68.1% | 95% | 2026-10-14 | Yes
IRB | Ironbridge Sweaters Ltd. | 22 | 1408671.36 | 7 | 477578.04 | 19.9% | 69.6% | 67.2% | 2026-10-14 | Yes
SLM | Saltmarsh Knit Fashions Ltd. | 35 | 1390602.36 | 10 | 428400.24 | 17.8% | 71.7% | 90.4% | 2026-10-12 | No
KST | Kestrel Knitwear Ltd. | 21 | 988891.2 | 1 | 70884 | 3% | 92.5% | 100% | 2026-10-14 | Yes
BLF | Bluefinch Sweaters Ltd. | 13 | 694126.2 | 1 | 29491.2 | 1.2% | 89.7% | 100% | 2026-10-14 | Yes
CPL | Copperleaf Knit Ltd. | 17 | 627003.6 | 1 | 25496.64 | 1.1% | 95.7% | 89.3% | 2026-10-14 | Yes
TLG | Tallgrass Knitwear Ltd. | 30 | 1476689.4 | 0 | 0 | 0% | 87.2% | 98% | 2026-10-14 | Yes
RVS | Riverstone Sweaters Ltd. | 14 | 706837.44 | 1 | 44379.6 | 1.8% | 85.7% | 100% | 2026-10-14 | Yes
AMB | Amberline Knit Ltd. | 24 | 1144746.12 | 1 | 64202.4 | 2.7% | 94.9% | 92% | 2026-10-14 | Yes
SVP | Silverpine Knitwear Ltd. | 13 | 622425.24 | 0 | 0 | 0% | 92.5% | 96.6% | 2026-10-14 | Yes
LTF | Lanternfield Sweaters Ltd. | 12 | 413873.28 | 2 | 66793.68 | 2.8% | 87.5% | 96.2% | 2026-10-14 | Yes
MDW | Morningdew Knit Ltd. | 18 | 732578.76 | 0 | 0 | 0% | 89.7% | 100% | 2026-10-14 | Yes
OKH | Oakhaven Knitwear Ltd. | 18 | 850260.96 | 0 | 0 | 0% | 89.7% | 94.1% | 2026-10-11 | No
WTH | Wildthorn Sweaters Ltd. | 12 | 568460.88 | 2 | 106636.8 | 4.4% | 85.7% | 100% | 2026-10-14 | Yes
BRW | Brightwool Knit Industries Ltd. | 19 | 605466.84 | 0 | 0 | 0% | 90.9% | 100% | 2026-10-14 | Yes
FNS | Fernstitch Knitwear Ltd. | 16 | 688126.8 | 1 | 108780 | 4.5% | 96.4% | 100% | 2026-10-14 | Yes
HMR | Highmoor Sweaters Ltd. | 14 | 747139.08 | 2 | 138112.44 | 5.8% | 81.8% | 88.9% | 2026-10-13 | No
CLB | Cloudberry Knit Ltd. | 16 | 482472.36 | 0 | 0 | 0% | 91.2% | 100% | 2026-10-14 | Yes
SND | Sundial Knitwear Ltd. | 17 | 711374.28 | 0 | 0 | 0% | 92.6% | 100% | 2026-10-14 | Yes
RSG | Rosegate Sweaters Ltd. | 3 | 196678.44 | 0 | 0 | 0% | 81.8% | 92.9% | 2026-10-14 | Yes
PBB | Pebblebrook Knit Ltd. | 12 | 442644.36 | 0 | 0 | 0% | 96.6% | 90.5% | 2026-10-13 | No
WSM | Westmere Knitwear Ltd. | 14 | 663375.24 | 1 | 65192.64 | 2.7% | 88.2% | 100% | 2026-10-14 | Yes

## Weekly Outlook
Week | POs | Pcs | FOB USD | On track USD | Watch USD | At risk USD | Critical USD | Late USD
10 Oct - 16 Oct | 13 | 57072 | 503790 | 338379 | 21855.96 | 34702.56 | 0 | 108852.48
17 Oct - 23 Oct | 37 | 183096 | 1817168.64 | 1243347.84 | 56643.36 | 344495.88 | 172681.56 | 0
24 Oct - 30 Oct | 39 | 179772 | 2164270.8 | 1401548.76 | 325457.4 | 145734.72 | 291529.92 | 0
31 Oct - 06 Nov | 25 | 118068 | 1351519.08 | 1163602.68 | 32184.24 | 74115.24 | 81616.92 | 0
07 Nov - 13 Nov | 32 | 147288 | 1501511.76 | 1254302.16 | 27331.92 | 137734.8 | 82142.88 | 0
14 Nov - 20 Nov | 30 | 129144 | 1289988.12 | 1158841.68 | 0 | 88290.96 | 42855.48 | 0
21 Nov - 27 Nov | 31 | 148056 | 1289456.28 | 1255736.52 | 0 | 11174.4 | 22545.36 | 0
28 Nov - 04 Dec | 21 | 98640 | 931472.16 | 909836.28 | 0 | 21635.88 | 0 | 0

## Hero What-if
PO No | Option | Linking pcs/day | Required pcs/day | Available WD | Completion Day N | Projected Ex-factory | Slip Days | On time | Air freight avoided USD
71010305 | Current plan | 411.1 | 680 | 12 | 19 | 2026-11-07 | 9 | No | 0
71010305 | +6 linking M/C (13 -> 19) | 600.8 | 680 | 12 | 14 | 2026-11-01 | 3 | No | 0
71010305 | 2 Friday overtime days (16, 23 Oct) | 411.1 | 566.7 | 14 | 19 | 2026-11-04 | 6 | No | 0
71010305 | +6 linking M/C and 2 Friday overtime days | 600.8 | 566.7 | 14 | 14 | 2026-10-29 | 0 | Yes | 38016
71009573 | Donor today | 770.8 | 443.1 | 22 | 14 | 2026-11-01 | -9 | Yes
71009573 | Donor after giving 6 linking M/C (22 -> 16) | 560.6 | 443.1 | 22 | 18 | 2026-11-05 | -5 | Yes

## Parameters
Parameter | Value
Today | 15 Oct 2026
Latest expected report date | 14 Oct 2026
Weekend | Friday
Rate window | 7 working days, linear weights 1..n (latest heaviest)
Supply-limited stage | work-in-front <= 1.5 days of its own rate, or not started: finishes at upstream finish + lag
Stage lags (WD) | linking 1.0, mending 0.5, washing 0.5, ironing 0.5, packing 0.5
Yarn in-house to knitting start | 2 days
Air freight USD/kg | 6
Sea freight USD/kg | 0.5
Knitting machine minutes/day | 1020
Score: schedule (max 50) | slip>0: 35 + min(15, 1.5 x slip days); slack <=2 WD: 25; slack 3-5 WD: 12; else 0
Score: T&A (max 20) | yarn in-house late >=8 d: 12, 4-7 d: 8, 1-3 d: 4; PP sample approval late >=3 d: +8
Score: factory OTD (max 15) | min(15, (1 - OTD last 12 months) x 50)
Score: quality (max 10) | PO's latest inspection failed: 10; else factory AQL pass rate (90 d) < 85%: 5
Score: freshness (max 5) | in production only; working days without a report: 1 -> 3, 2+ -> 5
Bands | <25 On track, 25-49 Watch, 50-74 At risk, >=75 Critical; slip>0 -> at least At risk; slip>=7 -> Critical; planned ex-factory < today and not shipped -> Late
On-time probability | share of the factory's last-12-month shipments whose slip <= predicted slack (calendar days), clamped 2%-98%