## T&A Calendar
PO No | Factory Code | Seq | Milestone | Responsible | Planned Date | Revised Date | Actual Date | Status | Remarks
71004005 | MDW | 1 | Yarn booking | Factory | 2025-07-15 |  | 2025-07-17 | Done late
71004005 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-24 |  | 2025-07-23 | Done
71004005 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-30 | Done
71004005 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-08-19 |  | 2025-08-19 | Done
71004005 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004005 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-03 |  | 2025-09-03 | Done
71004005 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-09-06 |  | 2025-09-06 | Done
71004005 | MDW | 8 | Knitting start | Factory | 2025-09-08 |  | 2025-09-08 | Done
71004005 | MDW | 9 | Linking start | Factory | 2025-09-14 |  | 2025-09-13 | Done
71004005 | MDW | 10 | Final inspection | Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004005 | MDW | 11 | Ex-factory | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004013 | SLM | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-16 | Done
71004013 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-27 |  | 2025-07-27 | Done
71004013 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004013 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004013 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-09-01 | Done late
71004013 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-02 | Done
71004013 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-09-08 |  | 2025-09-10 | Done late
71004013 | SLM | 8 | Knitting start | Factory | 2025-09-10 |  | 2025-09-10 | Done
71004013 | SLM | 9 | Linking start | Factory | 2025-09-16 |  | 2025-09-15 | Done
71004013 | SLM | 10 | Final inspection | Karbar QA | 2025-10-19 |  | 2025-10-25 | Done late
71004013 | SLM | 11 | Ex-factory | Factory | 2025-10-20 |  | 2025-10-26 | Done late
71004017 | CLB | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-17 | Done
71004017 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-29 | Done late
71004017 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-04 | Done late
71004017 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004017 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-03 | Done late
71004017 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-06 |  | 2025-09-07 | Done late
71004017 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-09-09 |  | 2025-09-11 | Done late
71004017 | CLB | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-13 | Done late
71004017 | CLB | 9 | Linking start | Factory | 2025-09-17 |  | 2025-09-18 | Done late
71004017 | CLB | 10 | Final inspection | Karbar QA | 2025-10-20 |  | 2025-10-18 | Done
71004017 | CLB | 11 | Ex-factory | Factory | 2025-10-21 |  | 2025-10-19 | Done
71004021 | IRB | 1 | Yarn booking | Factory | 2025-07-13 |  | 2025-07-14 | Done late
71004021 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-23 |  | 2025-07-24 | Done late
71004021 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004021 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004021 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004021 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-01 |  | 2025-09-01 | Done
71004021 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-04 |  | 2025-09-04 | Done
71004021 | IRB | 8 | Knitting start | Factory | 2025-09-06 |  | 2025-09-06 | Done
71004021 | IRB | 9 | Linking start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004021 | IRB | 10 | Final inspection | Karbar QA | 2025-10-15 |  | 2025-10-27 | Done late
71004021 | IRB | 11 | Ex-factory | Factory | 2025-10-16 |  | 2025-10-28 | Done late
71004027 | IRB | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-21 | Done late
71004027 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-30 | Done
71004027 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-06 | Done late
71004027 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004027 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71004027 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-10 | Done late
71004027 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-11 | Done
71004027 | IRB | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004027 | IRB | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004027 | IRB | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-25 | Done late
71004027 | IRB | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-26 | Done late
71004031 | CPL | 1 | Yarn booking | Factory | 2025-07-22 |  | 2025-07-22 | Done
71004031 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-30 | Done
71004031 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-07 | Done late
71004031 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-24 | Done
71004031 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-06 | Done late
71004031 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-10 |  | 2025-09-11 | Done late
71004031 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-13 |  | 2025-09-13 | Done
71004031 | CPL | 8 | Knitting start | Factory | 2025-09-15 |  | 2025-09-15 | Done
71004031 | CPL | 9 | Linking start | Factory | 2025-09-21 |  | 2025-09-20 | Done
71004031 | CPL | 10 | Final inspection | Karbar QA | 2025-10-23 |  | 2025-10-23 | Done
71004031 | CPL | 11 | Ex-factory | Factory | 2025-10-25 |  | 2025-10-25 | Done
71004037 | RVS | 1 | Yarn booking | Factory | 2025-07-13 |  | 2025-07-14 | Done late
71004037 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-23 |  | 2025-07-22 | Done
71004037 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004037 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-16 | Done
71004037 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004037 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-01 |  | 2025-09-01 | Done
71004037 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-09-04 |  | 2025-09-02 | Done
71004037 | RVS | 8 | Knitting start | Factory | 2025-09-06 |  | 2025-09-07 | Done late
71004037 | RVS | 9 | Linking start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004037 | RVS | 10 | Final inspection | Karbar QA | 2025-10-15 |  | 2025-10-15 | Done
71004037 | RVS | 11 | Ex-factory | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004045 | BLF | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-20 | Done
71004045 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-28 | Done
71004045 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-06 | Done late
71004045 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004045 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71004045 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-09 | Done late
71004045 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-10 | Done
71004045 | BLF | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004045 | BLF | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004045 | BLF | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-25 | Done late
71004045 | BLF | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-26 | Done late
71004050 | GRL | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-16 | Done
71004050 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-27 |  | 2025-07-27 | Done
71004050 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-08-02 | Done late
71004050 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-20 | Done
71004050 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-30 | Done
71004050 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-04 | Done
71004050 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-08 |  | 2025-09-10 | Done late
71004050 | GRL | 8 | Knitting start | Factory | 2025-09-10 |  | 2025-09-11 | Done late
71004050 | GRL | 9 | Linking start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004050 | GRL | 10 | Final inspection | Karbar QA | 2025-10-19 |  | 2025-10-15 | Done
71004050 | GRL | 11 | Ex-factory | Factory | 2025-10-20 |  | 2025-10-16 | Done
71004057 | BLF | 1 | Yarn booking | Factory | 2025-07-19 |  | 2025-07-17 | Done
71004057 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-29 |  | 2025-07-27 | Done
71004057 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-05 | Done late
71004057 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-25 | Done late
71004057 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-03 | Done late
71004057 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-07 |  | 2025-09-07 | Done
71004057 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-10 |  | 2025-09-10 | Done
71004057 | BLF | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004057 | BLF | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-16 | Done
71004057 | BLF | 10 | Final inspection | Karbar QA | 2025-10-21 |  | 2025-10-21 | Done
71004057 | BLF | 11 | Ex-factory | Factory | 2025-10-22 |  | 2025-10-22 | Done
71004062 | BLF | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-19 | Done late
71004062 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-29 | Done late
71004062 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-02 |  | 2025-07-31 | Done
71004062 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-20 | Done
71004062 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004062 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-06 |  | 2025-09-04 | Done
71004062 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-09 |  | 2025-09-11 | Done late
71004062 | BLF | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004062 | BLF | 9 | Linking start | Factory | 2025-09-17 |  | 2025-09-16 | Done
71004062 | BLF | 10 | Final inspection | Karbar QA | 2025-10-20 |  | 2025-10-20 | Done
71004062 | BLF | 11 | Ex-factory | Factory | 2025-10-21 |  | 2025-10-21 | Done
71004069 | WSM | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-27 | Done
71004069 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004069 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-14 | Done late
71004069 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-03 | Done late
71004069 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004069 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-16 | Done
71004069 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-20 | Done
71004069 | WSM | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-23 | Done late
71004069 | WSM | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-28 | Done
71004069 | WSM | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71004069 | WSM | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-11-01 | Done
71004075 | BRW | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-24 | Done
71004075 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-05 | Done late
71004075 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-09 | Done
71004075 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-26 | Done
71004075 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-09 | Done late
71004075 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-13 |  | 2025-09-13 | Done
71004075 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-09-16 |  | 2025-09-16 | Done
71004075 | BRW | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-20 | Done late
71004075 | BRW | 9 | Linking start | Factory | 2025-09-24 |  | 2025-09-25 | Done late
71004075 | BRW | 10 | Final inspection | Karbar QA | 2025-10-27 |  | 2025-10-25 | Done
71004075 | BRW | 11 | Ex-factory | Factory | 2025-10-28 |  | 2025-10-26 | Done
71004080 | CPL | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-17 | Done
71004080 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-31 | Done late
71004080 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-02 | Done
71004080 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-21 | Done
71004080 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71004080 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-08 | Done
71004080 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-09 | Done
71004080 | CPL | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004080 | CPL | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004080 | CPL | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-22 | Done
71004080 | CPL | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004083 | BRW | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-24 | Done
71004083 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-03 | Done
71004083 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-06 | Done
71004083 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-27 | Done
71004083 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004083 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-11 | Done
71004083 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-09-15 |  | 2025-09-14 | Done
71004083 | BRW | 8 | Knitting start | Factory | 2025-09-17 |  | 2025-09-18 | Done late
71004083 | BRW | 9 | Linking start | Factory | 2025-09-23 |  | 2025-09-23 | Done
71004083 | BRW | 10 | Final inspection | Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004083 | BRW | 11 | Ex-factory | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004090 | AMB | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-24 | Done
71004090 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-04 | Done late
71004090 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-09 | Done late
71004090 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004090 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004090 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-13 | Done late
71004090 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-09-15 |  | 2025-09-15 | Done
71004090 | AMB | 8 | Knitting start | Factory | 2025-09-17 |  | 2025-09-17 | Done
71004090 | AMB | 9 | Linking start | Factory | 2025-09-23 |  | 2025-09-22 | Done
71004090 | AMB | 10 | Final inspection | Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004090 | AMB | 11 | Ex-factory | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004093 | IRB | 1 | Yarn booking | Factory | 2025-07-16 |  | 2025-07-16 | Done
71004093 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-26 |  | 2025-07-27 | Done late
71004093 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004093 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-20 | Done
71004093 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-09-01 | Done late
71004093 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-03 | Done
71004093 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-07 |  | 2025-09-06 | Done
71004093 | IRB | 8 | Knitting start | Factory | 2025-09-09 |  | 2025-09-09 | Done
71004093 | IRB | 9 | Linking start | Factory | 2025-09-15 |  | 2025-09-14 | Done
71004093 | IRB | 10 | Final inspection | Karbar QA | 2025-10-18 |  | 2025-10-20 | Done late
71004093 | IRB | 11 | Ex-factory | Factory | 2025-10-19 |  | 2025-10-21 | Done late
71004097 | SLM | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-15 | Done
71004097 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004097 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-03 | Done late
71004097 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004097 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004097 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-06 |  | 2025-09-06 | Done
71004097 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-09-09 |  | 2025-09-09 | Done
71004097 | SLM | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004097 | SLM | 9 | Linking start | Factory | 2025-09-17 |  | 2025-09-16 | Done
71004097 | SLM | 10 | Final inspection | Karbar QA | 2025-10-20 |  | 2025-10-20 | Done
71004097 | SLM | 11 | Ex-factory | Factory | 2025-10-21 |  | 2025-10-21 | Done
71004101 | KST | 1 | Yarn booking | Factory | 2025-07-26 |  | 2025-07-26 | Done
71004101 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-05 |  | 2025-08-07 | Done late
71004101 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-10 | Done
71004101 | KST | 4 | Size set approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-28 | Done
71004101 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-09 | Done
71004101 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-14 |  | 2025-09-16 | Done late
71004101 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-09-17 |  | 2025-09-17 | Done
71004101 | KST | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004101 | KST | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-23 | Done
71004101 | KST | 10 | Final inspection | Karbar QA | 2025-10-28 |  | 2025-10-28 | Done
71004101 | KST | 11 | Ex-factory | Factory | 2025-10-29 |  | 2025-10-29 | Done
71004110 | WSM | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-07-31 | Done
71004110 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-12 | Done late
71004110 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004110 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-02 | Done
71004110 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-14 | Done
71004110 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-20 | Done late
71004110 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-09-22 |  | 2025-09-22 | Done
71004110 | WSM | 8 | Knitting start | Factory | 2025-09-24 |  | 2025-09-24 | Done
71004110 | WSM | 9 | Linking start | Factory | 2025-09-30 |  | 2025-09-29 | Done
71004110 | WSM | 10 | Final inspection | Karbar QA | 2025-11-02 |  | 2025-11-01 | Done
71004110 | WSM | 11 | Ex-factory | Factory | 2025-11-03 |  | 2025-11-02 | Done
71004118 | CPL | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-29 | Done
71004118 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-09 | Done late
71004118 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-11 | Done
71004118 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-02 | Done
71004118 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004118 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-18 | Done late
71004118 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-22 | Done late
71004118 | CPL | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-22 | Done
71004118 | CPL | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-27 | Done
71004118 | CPL | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-29 | Done
71004118 | CPL | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-10-30 | Done
71004121 | IRB | 1 | Yarn booking | Factory | 2025-07-13 |  | 2025-07-15 | Done late
71004121 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-23 |  | 2025-07-22 | Done
71004121 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004121 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004121 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004121 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-01 |  | 2025-08-31 | Done
71004121 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-04 |  | 2025-09-04 | Done
71004121 | IRB | 8 | Knitting start | Factory | 2025-09-06 |  | 2025-09-06 | Done
71004121 | IRB | 9 | Linking start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004121 | IRB | 10 | Final inspection | Karbar QA | 2025-10-15 |  | 2025-10-15 | Done
71004121 | IRB | 11 | Ex-factory | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004130 | FNS | 1 | Yarn booking | Factory | 2025-07-13 |  | 2025-07-14 | Done late
71004130 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-23 |  | 2025-07-21 | Done
71004130 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-29 | Done late
71004130 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004130 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004130 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-01 |  | 2025-09-04 | Done late
71004130 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-09-04 |  | 2025-09-03 | Done
71004130 | FNS | 8 | Knitting start | Factory | 2025-09-06 |  | 2025-09-06 | Done
71004130 | FNS | 9 | Linking start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004130 | FNS | 10 | Final inspection | Karbar QA | 2025-10-15 |  | 2025-10-12 | Done
71004130 | FNS | 11 | Ex-factory | Factory | 2025-10-16 |  | 2025-10-13 | Done
71004134 | CPL | 1 | Yarn booking | Factory | 2025-07-15 |  | 2025-07-15 | Done
71004134 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-24 |  | 2025-07-22 | Done
71004134 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-30 | Done
71004134 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-08-19 |  | 2025-08-18 | Done
71004134 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004134 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-03 |  | 2025-09-03 | Done
71004134 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-06 |  | 2025-09-08 | Done late
71004134 | CPL | 8 | Knitting start | Factory | 2025-09-08 |  | 2025-09-08 | Done
71004134 | CPL | 9 | Linking start | Factory | 2025-09-14 |  | 2025-09-13 | Done
71004134 | CPL | 10 | Final inspection | Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004134 | CPL | 11 | Ex-factory | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004139 | OKH | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-17 | Done
71004139 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-30 | Done
71004139 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-02 | Done
71004139 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004139 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004139 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-06 | Done
71004139 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-11 | Done
71004139 | OKH | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004139 | OKH | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004139 | OKH | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-22 | Done
71004139 | OKH | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004145 | CLB | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-17 | Done
71004145 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-28 | Done
71004145 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-03 | Done
71004145 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004145 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004145 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-08 | Done
71004145 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-11 | Done
71004145 | CLB | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-13 | Done
71004145 | CLB | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004145 | CLB | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-26 | Done late
71004145 | CLB | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-27 | Done late
71004154 | PBB | 1 | Yarn booking | Factory | 2025-07-16 |  | 2025-07-16 | Done
71004154 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-26 |  | 2025-07-26 | Done
71004154 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-08-02 | Done late
71004154 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-18 | Done
71004154 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-28 | Done
71004154 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-06 | Done late
71004154 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-09-07 |  | 2025-09-07 | Done
71004154 | PBB | 8 | Knitting start | Factory | 2025-09-09 |  | 2025-09-10 | Done late
71004154 | PBB | 9 | Linking start | Factory | 2025-09-15 |  | 2025-09-15 | Done
71004154 | PBB | 10 | Final inspection | Karbar QA | 2025-10-18 |  | 2025-10-18 | Done
71004154 | PBB | 11 | Ex-factory | Factory | 2025-10-19 |  | 2025-10-19 | Done
71004157 | GRL | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-03 | Done
71004157 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-14 | Done late
71004157 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-18 | Done
71004157 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-08 | Done late
71004157 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004157 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-21 | Done
71004157 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-25 | Done
71004157 | GRL | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-27 | Done
71004157 | GRL | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004157 | GRL | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-17 | Done late
71004157 | GRL | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-18 | Done late
71004160 | SLM | 1 | Yarn booking | Factory | 2025-07-15 |  | 2025-07-14 | Done
71004160 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-24 |  | 2025-07-24 | Done
71004160 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-31 | Done late
71004160 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-08-19 |  | 2025-08-19 | Done
71004160 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004160 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-03 |  | 2025-09-03 | Done
71004160 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-09-06 |  | 2025-09-04 | Done
71004160 | SLM | 8 | Knitting start | Factory | 2025-09-08 |  | 2025-09-08 | Done
71004160 | SLM | 9 | Linking start | Factory | 2025-09-14 |  | 2025-09-13 | Done
71004160 | SLM | 10 | Final inspection | Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004160 | SLM | 11 | Ex-factory | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004164 | BRW | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-16 | Done
71004164 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004164 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-03 | Done late
71004164 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004164 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004164 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-06 |  | 2025-09-04 | Done
71004164 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-09-09 |  | 2025-09-07 | Done
71004164 | BRW | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-13 | Done late
71004164 | BRW | 9 | Linking start | Factory | 2025-09-17 |  | 2025-09-18 | Done late
71004164 | BRW | 10 | Final inspection | Karbar QA | 2025-10-20 |  | 2025-10-22 | Done late
71004164 | BRW | 11 | Ex-factory | Factory | 2025-10-21 |  | 2025-10-23 | Done late
71004173 | HMR | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-28 | Done
71004173 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004173 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-13 | Done
71004173 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-04 | Done late
71004173 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004173 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-17 | Done
71004173 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-20 | Done
71004173 | HMR | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-22 | Done
71004173 | HMR | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-27 | Done
71004173 | HMR | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71004173 | HMR | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-11-01 | Done
71004182 | SVP | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-07-31 | Done
71004182 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-12 | Done
71004182 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004182 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-04 | Done
71004182 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004182 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-22 | Done late
71004182 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-24 | Done
71004182 | SVP | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004182 | SVP | 9 | Linking start | Factory | 2025-10-02 |  | 2025-09-30 | Done
71004182 | SVP | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004182 | SVP | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004187 | IRB | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-17 | Done
71004187 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-31 | Done late
71004187 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-05 | Done late
71004187 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004187 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71004187 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-08 | Done
71004187 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-11 | Done
71004187 | IRB | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-13 | Done
71004187 | IRB | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004187 | IRB | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-22 | Done
71004187 | IRB | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004196 | GRL | 1 | Yarn booking | Factory | 2025-07-22 |  | 2025-07-21 | Done
71004196 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-29 | Done
71004196 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-06 | Done
71004196 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-25 | Done
71004196 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004196 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-10 |  | 2025-09-09 | Done
71004196 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-13 |  | 2025-09-15 | Done late
71004196 | GRL | 8 | Knitting start | Factory | 2025-09-15 |  | 2025-09-15 | Done
71004196 | GRL | 9 | Linking start | Factory | 2025-09-21 |  | 2025-09-20 | Done
71004196 | GRL | 10 | Final inspection | Karbar QA | 2025-10-23 |  | 2025-10-22 | Done
71004196 | GRL | 11 | Ex-factory | Factory | 2025-10-25 |  | 2025-10-23 | Done
71004205 | FNS | 1 | Yarn booking | Factory | 2025-07-23 |  | 2025-07-23 | Done
71004205 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-02 |  | 2025-07-31 | Done
71004205 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004205 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004205 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004205 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-11 | Done
71004205 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-09-14 |  | 2025-09-14 | Done
71004205 | FNS | 8 | Knitting start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004205 | FNS | 9 | Linking start | Factory | 2025-09-22 |  | 2025-09-21 | Done
71004205 | FNS | 10 | Final inspection | Karbar QA | 2025-10-25 |  | 2025-10-25 | Done
71004205 | FNS | 11 | Ex-factory | Factory | 2025-10-26 |  | 2025-10-26 | Done
71004212 | GRL | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-08-03 | Done late
71004212 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-13 | Done late
71004212 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-18 | Done late
71004212 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-07 | Done late
71004212 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004212 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-21 | Done
71004212 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-25 | Done late
71004212 | GRL | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-27 | Done late
71004212 | GRL | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004212 | GRL | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004212 | GRL | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004218 | IRB | 1 | Yarn booking | Factory | 2025-07-16 |  | 2025-07-15 | Done
71004218 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-26 |  | 2025-07-28 | Done late
71004218 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004218 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-18 | Done
71004218 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-30 | Done
71004218 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-02 | Done
71004218 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-07 |  | 2025-09-06 | Done
71004218 | IRB | 8 | Knitting start | Factory | 2025-09-09 |  | 2025-09-09 | Done
71004218 | IRB | 9 | Linking start | Factory | 2025-09-15 |  | 2025-09-14 | Done
71004218 | IRB | 10 | Final inspection | Karbar QA | 2025-10-18 |  | 2025-10-15 | Done
71004218 | IRB | 11 | Ex-factory | Factory | 2025-10-19 |  | 2025-10-16 | Done
71004222 | BLF | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-24 | Done
71004222 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-03 | Done
71004222 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004222 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004222 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004222 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-11 | Done
71004222 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-15 |  | 2025-09-13 | Done
71004222 | BLF | 8 | Knitting start | Factory | 2025-09-17 |  | 2025-09-17 | Done
71004222 | BLF | 9 | Linking start | Factory | 2025-09-23 |  | 2025-09-22 | Done
71004222 | BLF | 10 | Final inspection | Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004222 | BLF | 11 | Ex-factory | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004228 | LTF | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-23 | Done
71004228 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-04 | Done
71004228 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-11 | Done late
71004228 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004228 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004228 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-13 |  | 2025-09-14 | Done late
71004228 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-16 |  | 2025-09-15 | Done
71004228 | LTF | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004228 | LTF | 9 | Linking start | Factory | 2025-09-24 |  | 2025-09-23 | Done
71004228 | LTF | 10 | Final inspection | Karbar QA | 2025-10-27 |  | 2025-10-26 | Done
71004228 | LTF | 11 | Ex-factory | Factory | 2025-10-28 |  | 2025-10-27 | Done
71004235 | LTF | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-03 | Done
71004235 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-13 | Done
71004235 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-20 | Done late
71004235 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004235 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-18 | Done late
71004235 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-24 | Done late
71004235 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-24 | Done
71004235 | LTF | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71004235 | LTF | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004235 | LTF | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-05 | Done
71004235 | LTF | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004242 | LTF | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-02 | Done
71004242 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-12 | Done
71004242 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-20 | Done late
71004242 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-08 | Done late
71004242 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004242 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-22 | Done
71004242 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-25 | Done
71004242 | LTF | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-27 | Done
71004242 | LTF | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004242 | LTF | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-05 | Done
71004242 | LTF | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004247 | TLG | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-17 | Done
71004247 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-27 |  | 2025-07-24 | Done
71004247 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004247 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004247 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71004247 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-04 | Done
71004247 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-09-08 |  | 2025-09-08 | Done
71004247 | TLG | 8 | Knitting start | Factory | 2025-09-10 |  | 2025-09-11 | Done late
71004247 | TLG | 9 | Linking start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004247 | TLG | 10 | Final inspection | Karbar QA | 2025-10-19 |  | 2025-10-19 | Done
71004247 | TLG | 11 | Ex-factory | Factory | 2025-10-20 |  | 2025-10-20 | Done
71004256 | CPL | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-08-02 | Done late
71004256 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-13 | Done late
71004256 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-16 |  | 2025-08-14 | Done
71004256 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004256 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-16 | Done late
71004256 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-20 |  | 2025-09-22 | Done late
71004256 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-23 |  | 2025-09-21 | Done
71004256 | CPL | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004256 | CPL | 9 | Linking start | Factory | 2025-10-01 |  | 2025-09-30 | Done
71004256 | CPL | 10 | Final inspection | Karbar QA | 2025-11-03 |  | 2025-11-03 | Done
71004256 | CPL | 11 | Ex-factory | Factory | 2025-11-04 |  | 2025-11-04 | Done
71004260 | GRL | 1 | Yarn booking | Factory | 2025-08-12 |  | 2025-08-13 | Done late
71004260 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004260 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004260 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-14 | Done
71004260 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004260 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-01 |  | 2025-10-01 | Done
71004260 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-04 |  | 2025-10-02 | Done
71004260 | GRL | 8 | Knitting start | Factory | 2025-10-06 |  | 2025-10-06 | Done
71004260 | GRL | 9 | Linking start | Factory | 2025-10-12 |  | 2025-10-11 | Done
71004260 | GRL | 10 | Final inspection | Karbar QA | 2025-11-13 |  | 2025-11-13 | Done
71004260 | GRL | 11 | Ex-factory | Factory | 2025-11-15 |  | 2025-11-15 | Done
71004265 | MDW | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-14 | Done late
71004265 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004265 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004265 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004265 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-25 | Done
71004265 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71004265 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-05 | Done
71004265 | MDW | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-07 | Done
71004265 | MDW | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-12 | Done
71004265 | MDW | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-12 | Done
71004265 | MDW | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-13 | Done
71004272 | CLB | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-17 | Done
71004272 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-27 |  | 2025-07-24 | Done
71004272 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-08-02 | Done late
71004272 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004272 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-09-01 | Done late
71004272 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-04 | Done
71004272 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-09-08 |  | 2025-09-09 | Done late
71004272 | CLB | 8 | Knitting start | Factory | 2025-09-10 |  | 2025-09-10 | Done
71004272 | CLB | 9 | Linking start | Factory | 2025-09-16 |  | 2025-09-15 | Done
71004272 | CLB | 10 | Final inspection | Karbar QA | 2025-10-19 |  | 2025-10-19 | Done
71004272 | CLB | 11 | Ex-factory | Factory | 2025-10-20 |  | 2025-10-20 | Done
71004277 | FNS | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-30 | Done late
71004277 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004277 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-12 | Done
71004277 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-04 | Done late
71004277 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004277 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-18 | Done late
71004277 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-18 | Done
71004277 | FNS | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-22 | Done
71004277 | FNS | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-27 | Done
71004277 | FNS | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-29 | Done
71004277 | FNS | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-10-30 | Done
71004281 | HMR | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-06 | Done
71004281 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004281 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-20 | Done
71004281 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004281 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-22 | Done late
71004281 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-25 | Done
71004281 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-09-29 |  | 2025-09-29 | Done
71004281 | HMR | 8 | Knitting start | Factory | 2025-10-01 |  | 2025-10-01 | Done
71004281 | HMR | 9 | Linking start | Factory | 2025-10-07 |  | 2025-10-06 | Done
71004281 | HMR | 10 | Final inspection | Karbar QA | 2025-11-09 |  | 2025-11-09 | Done
71004281 | HMR | 11 | Ex-factory | Factory | 2025-11-10 |  | 2025-11-10 | Done
71004289 | AMB | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-09 | Done late
71004289 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-16 | Done
71004289 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004289 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004289 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-23 | Done late
71004289 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-28 | Done late
71004289 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-30 | Done
71004289 | AMB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-04 | Done late
71004289 | AMB | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-09 | Done late
71004289 | AMB | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-10 | Done
71004289 | AMB | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-11 | Done
71004296 | WTH | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-21 | Done late
71004296 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-29 | Done
71004296 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-02 | Done
71004296 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-23 | Done
71004296 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004296 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-09 | Done late
71004296 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-11 | Done
71004296 | WTH | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-13 | Done
71004296 | WTH | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004296 | WTH | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-22 | Done
71004296 | WTH | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004305 | LTF | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-29 | Done
71004305 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004305 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-13 | Done
71004305 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-02 | Done
71004305 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004305 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-20 | Done late
71004305 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-20 | Done
71004305 | LTF | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-22 | Done
71004305 | LTF | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-27 | Done
71004305 | LTF | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-11-02 | Done late
71004305 | LTF | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-11-03 | Done late
71004310 | GRL | 1 | Yarn booking | Factory | 2025-07-13 |  | 2025-07-12 | Done
71004310 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-23 |  | 2025-07-21 | Done
71004310 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-28 | Done
71004310 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-14 | Done
71004310 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004310 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-01 |  | 2025-09-01 | Done
71004310 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-04 |  | 2025-09-04 | Done
71004310 | GRL | 8 | Knitting start | Factory | 2025-09-06 |  | 2025-09-06 | Done
71004310 | GRL | 9 | Linking start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004310 | GRL | 10 | Final inspection | Karbar QA | 2025-10-15 |  | 2025-10-16 | Done late
71004310 | GRL | 11 | Ex-factory | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71004316 | IRB | 1 | Yarn booking | Factory | 2025-07-23 |  | 2025-07-23 | Done
71004316 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-02 | Done
71004316 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-06 | Done
71004316 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004316 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004316 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-09 | Done
71004316 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-14 |  | 2025-09-15 | Done late
71004316 | IRB | 8 | Knitting start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004316 | IRB | 9 | Linking start | Factory | 2025-09-22 |  | 2025-09-21 | Done
71004316 | IRB | 10 | Final inspection | Karbar QA | 2025-10-25 |  | 2025-10-23 | Done
71004316 | IRB | 11 | Ex-factory | Factory | 2025-10-26 |  | 2025-10-25 | Done
71004325 | FNS | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-24 | Done
71004325 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-02 | Done
71004325 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-06 | Done
71004325 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-27 | Done
71004325 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-08 | Done late
71004325 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-11 | Done
71004325 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-09-15 |  | 2025-09-15 | Done
71004325 | FNS | 8 | Knitting start | Factory | 2025-09-17 |  | 2025-09-17 | Done
71004325 | FNS | 9 | Linking start | Factory | 2025-09-23 |  | 2025-09-22 | Done
71004325 | FNS | 10 | Final inspection | Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004325 | FNS | 11 | Ex-factory | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004332 | BLF | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-07-31 | Done
71004332 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-13 | Done late
71004332 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004332 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-07 | Done late
71004332 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004332 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-21 | Done
71004332 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-25 | Done late
71004332 | BLF | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-27 | Done late
71004332 | BLF | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004332 | BLF | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-01 | Done
71004332 | BLF | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-02 | Done
71004337 | IRB | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-22 | Done late
71004337 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-31 | Done late
71004337 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-06 | Done late
71004337 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-21 | Done
71004337 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004337 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-08 | Done
71004337 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-09 | Done
71004337 | IRB | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004337 | IRB | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004337 | IRB | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-30 | Done late
71004337 | IRB | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-11-01 | Done late
71004344 | SVP | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-02 | Done
71004344 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-14 | Done late
71004344 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-16 | Done
71004344 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-06 | Done
71004344 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004344 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-25 | Done late
71004344 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-25 | Done
71004344 | SVP | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71004344 | SVP | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004344 | SVP | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-05 | Done
71004344 | SVP | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004347 | RVS | 1 | Yarn booking | Factory | 2025-08-05 |  | 2025-08-03 | Done
71004347 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-13 | Done
71004347 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-20 | Done
71004347 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-07 | Done
71004347 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71004347 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-24 |  | 2025-09-24 | Done
71004347 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-09-27 |  | 2025-09-25 | Done
71004347 | RVS | 8 | Knitting start | Factory | 2025-09-29 |  | 2025-09-30 | Done late
71004347 | RVS | 9 | Linking start | Factory | 2025-10-05 |  | 2025-10-05 | Done
71004347 | RVS | 10 | Final inspection | Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71004347 | RVS | 11 | Ex-factory | Factory | 2025-11-08 |  | 2025-11-08 | Done
71004351 | IRB | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-14 | Done
71004351 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71004351 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-30 | Done
71004351 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-22 | Done late
71004351 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-10-01 | Done late
71004351 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-02 | Done
71004351 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-09 | Done late
71004351 | IRB | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-11 | Done late
71004351 | IRB | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004351 | IRB | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-15 | Done
71004351 | IRB | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-16 | Done
71004354 | SLM | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-22 | Done
71004354 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-02 | Done
71004354 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-09 | Done late
71004354 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004354 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004354 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-09 | Done
71004354 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-09-15 |  | 2025-09-17 | Done late
71004354 | SLM | 8 | Knitting start | Factory | 2025-09-17 |  | 2025-09-18 | Done late
71004354 | SLM | 9 | Linking start | Factory | 2025-09-23 |  | 2025-09-23 | Done
71004354 | SLM | 10 | Final inspection | Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004354 | SLM | 11 | Ex-factory | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004360 | WTH | 1 | Yarn booking | Factory | 2025-07-27 |  | 2025-07-27 | Done
71004360 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-06 | Done
71004360 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-09 | Done
71004360 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-28 | Done
71004360 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-10 | Done
71004360 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-15 |  | 2025-09-16 | Done late
71004360 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-09-18 |  | 2025-09-16 | Done
71004360 | WTH | 8 | Knitting start | Factory | 2025-09-20 |  | 2025-09-20 | Done
71004360 | WTH | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004360 | WTH | 10 | Final inspection | Karbar QA | 2025-10-29 |  | 2025-10-29 | Done
71004360 | WTH | 11 | Ex-factory | Factory | 2025-10-30 |  | 2025-10-30 | Done
71004365 | SND | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-07-31 | Done
71004365 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-11 | Done
71004365 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004365 | SND | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-08 | Done late
71004365 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-15 | Done
71004365 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-23 | Done late
71004365 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-24 | Done
71004365 | SND | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-27 | Done late
71004365 | SND | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004365 | SND | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-03 | Done
71004365 | SND | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-04 | Done
71004371 | CLB | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-14 | Done
71004371 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71004371 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71004371 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-18 | Done
71004371 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71004371 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-05 | Done
71004371 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-07 | Done
71004371 | CLB | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004371 | CLB | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-14 | Done
71004371 | CLB | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-18 | Done
71004371 | CLB | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-19 | Done
71004378 | KST | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-20 | Done
71004378 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-30 | Done
71004378 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-04 | Done
71004378 | KST | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-25 | Done late
71004378 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71004378 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-11 | Done late
71004378 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-09 | Done
71004378 | KST | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004378 | KST | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004378 | KST | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-22 | Done
71004378 | KST | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004381 | GRL | 1 | Yarn booking | Factory | 2025-07-20 |  | 2025-07-19 | Done
71004381 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-30 |  | 2025-07-28 | Done
71004381 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-04 | Done
71004381 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-25 | Done late
71004381 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004381 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-08 |  | 2025-09-08 | Done
71004381 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-11 |  | 2025-09-09 | Done
71004381 | GRL | 8 | Knitting start | Factory | 2025-09-13 |  | 2025-09-14 | Done late
71004381 | GRL | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004381 | GRL | 10 | Final inspection | Karbar QA | 2025-10-22 |  | 2025-10-30 | Done late
71004381 | GRL | 11 | Ex-factory | Factory | 2025-10-23 |  | 2025-11-01 | Done late
71004384 | SVP | 1 | Yarn booking | Factory | 2025-07-26 |  | 2025-07-24 | Done
71004384 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-05 |  | 2025-08-06 | Done late
71004384 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-07 | Done
71004384 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-31 | Done late
71004384 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-10 | Done late
71004384 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-14 |  | 2025-09-14 | Done
71004384 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-09-17 |  | 2025-09-15 | Done
71004384 | SVP | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-20 | Done late
71004384 | SVP | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004384 | SVP | 10 | Final inspection | Karbar QA | 2025-10-28 |  | 2025-10-28 | Done
71004384 | SVP | 11 | Ex-factory | Factory | 2025-10-29 |  | 2025-10-29 | Done
71004389 | RVS | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004389 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-18 | Done
71004389 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004389 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004389 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-24 | Done late
71004389 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-27 | Done
71004389 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-29 | Done
71004389 | RVS | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-04 | Done late
71004389 | RVS | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-09 | Done late
71004389 | RVS | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-06 | Done
71004389 | RVS | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-08 | Done
71004395 | RVS | 1 | Yarn booking | Factory | 2025-08-10 |  | 2025-08-09 | Done
71004395 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-21 | Done late
71004395 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-25 |  | 2025-08-25 | Done
71004395 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-16 | Done late
71004395 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71004395 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-29 |  | 2025-10-01 | Done late
71004395 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-10-02 |  | 2025-10-02 | Done
71004395 | RVS | 8 | Knitting start | Factory | 2025-10-04 |  | 2025-10-05 | Done late
71004395 | RVS | 9 | Linking start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004395 | RVS | 10 | Final inspection | Karbar QA | 2025-11-12 |  | 2025-11-17 | Done late
71004395 | RVS | 11 | Ex-factory | Factory | 2025-11-13 |  | 2025-11-18 | Done late
71004399 | IRB | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-13 | Done
71004399 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004399 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004399 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004399 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-27 | Done
71004399 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71004399 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-05 | Done
71004399 | IRB | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-08 | Done late
71004399 | IRB | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-13 | Done
71004399 | IRB | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-15 | Done
71004399 | IRB | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-16 | Done
71004407 | FNS | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-16 | Done
71004407 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004407 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004407 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004407 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71004407 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-06 | Done
71004407 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-09 | Done
71004407 | FNS | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-11 | Done
71004407 | FNS | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004407 | FNS | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-11-16 | Done
71004407 | FNS | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-11-17 | Done
71004412 | LTF | 1 | Yarn booking | Factory | 2025-07-23 |  | 2025-07-22 | Done
71004412 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-04 | Done late
71004412 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004412 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-25 | Done
71004412 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004412 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-11 |  | 2025-09-11 | Done
71004412 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-14 |  | 2025-09-16 | Done late
71004412 | LTF | 8 | Knitting start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004412 | LTF | 9 | Linking start | Factory | 2025-09-22 |  | 2025-09-21 | Done
71004412 | LTF | 10 | Final inspection | Karbar QA | 2025-10-25 |  | 2025-10-22 | Done
71004412 | LTF | 11 | Ex-factory | Factory | 2025-10-26 |  | 2025-10-23 | Done
71004419 | AMB | 1 | Yarn booking | Factory | 2025-07-30 |  | 2025-07-28 | Done
71004419 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-11 | Done late
71004419 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004419 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71004419 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71004419 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-18 | Done
71004419 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-09-21 |  | 2025-09-21 | Done
71004419 | AMB | 8 | Knitting start | Factory | 2025-09-23 |  | 2025-09-24 | Done late
71004419 | AMB | 9 | Linking start | Factory | 2025-09-29 |  | 2025-09-29 | Done
71004419 | AMB | 10 | Final inspection | Karbar QA | 2025-11-01 |  | 2025-10-30 | Done
71004419 | AMB | 11 | Ex-factory | Factory | 2025-11-02 |  | 2025-11-01 | Done
71004422 | GRL | 1 | Yarn booking | Factory | 2025-08-10 |  | 2025-08-09 | Done
71004422 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-20 | Done
71004422 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-25 |  | 2025-08-27 | Done late
71004422 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-14 | Done
71004422 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71004422 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-29 |  | 2025-09-30 | Done late
71004422 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-02 |  | 2025-10-02 | Done
71004422 | GRL | 8 | Knitting start | Factory | 2025-10-04 |  | 2025-10-04 | Done
71004422 | GRL | 9 | Linking start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004422 | GRL | 10 | Final inspection | Karbar QA | 2025-11-12 |  | 2025-11-12 | Done
71004422 | GRL | 11 | Ex-factory | Factory | 2025-11-13 |  | 2025-11-13 | Done
71004431 | AMB | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004431 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71004431 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004431 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004431 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-05 | Done
71004431 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-09 |  | 2025-10-11 | Done late
71004431 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-10-13 |  | 2025-10-15 | Done late
71004431 | AMB | 8 | Knitting start | Factory | 2025-10-15 |  | 2025-10-16 | Done late
71004431 | AMB | 9 | Linking start | Factory | 2025-10-21 |  | 2025-10-21 | Done
71004431 | AMB | 10 | Final inspection | Karbar QA | 2025-11-23 |  | 2025-11-19 | Done
71004431 | AMB | 11 | Ex-factory | Factory | 2025-11-24 |  | 2025-11-20 | Done
71004437 | CLB | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004437 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71004437 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-02 | Done
71004437 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004437 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-04 | Done
71004437 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-09 |  | 2025-10-09 | Done
71004437 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-13 |  | 2025-10-12 | Done
71004437 | CLB | 8 | Knitting start | Factory | 2025-10-15 |  | 2025-10-15 | Done
71004437 | CLB | 9 | Linking start | Factory | 2025-10-21 |  | 2025-10-20 | Done
71004437 | CLB | 10 | Final inspection | Karbar QA | 2025-11-23 |  | 2025-11-23 | Done
71004437 | CLB | 11 | Ex-factory | Factory | 2025-11-24 |  | 2025-11-24 | Done
71004443 | IRB | 1 | Yarn booking | Factory | 2025-07-19 |  | 2025-07-19 | Done
71004443 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-29 |  | 2025-07-28 | Done
71004443 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-03 |  | 2025-08-02 | Done
71004443 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004443 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-02 |  | 2025-09-04 | Done late
71004443 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-07 |  | 2025-09-07 | Done
71004443 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-10 |  | 2025-09-08 | Done
71004443 | IRB | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-13 | Done late
71004443 | IRB | 9 | Linking start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004443 | IRB | 10 | Final inspection | Karbar QA | 2025-10-21 |  | 2025-10-21 | Done
71004443 | IRB | 11 | Ex-factory | Factory | 2025-10-22 |  | 2025-10-22 | Done
71004447 | LTF | 1 | Yarn booking | Factory | 2025-07-27 |  | 2025-07-27 | Done
71004447 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-07 | Done late
71004447 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-12 | Done late
71004447 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-08-31 |  | 2025-09-01 | Done late
71004447 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-11 | Done late
71004447 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-15 |  | 2025-09-15 | Done
71004447 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-18 |  | 2025-09-17 | Done
71004447 | LTF | 8 | Knitting start | Factory | 2025-09-20 |  | 2025-09-20 | Done
71004447 | LTF | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004447 | LTF | 10 | Final inspection | Karbar QA | 2025-10-29 |  | 2025-10-27 | Done
71004447 | LTF | 11 | Ex-factory | Factory | 2025-10-30 |  | 2025-10-28 | Done
71004450 | KST | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-07-31 | Done
71004450 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-12 | Done
71004450 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004450 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-08 | Done late
71004450 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004450 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-21 | Done
71004450 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-23 | Done
71004450 | KST | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-27 | Done late
71004450 | KST | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004450 | KST | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004450 | KST | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004454 | BRW | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-06 | Done
71004454 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004454 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-23 | Done late
71004454 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004454 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004454 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-25 | Done
71004454 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-09-29 |  | 2025-09-29 | Done
71004454 | BRW | 8 | Knitting start | Factory | 2025-10-01 |  | 2025-10-02 | Done late
71004454 | BRW | 9 | Linking start | Factory | 2025-10-07 |  | 2025-10-07 | Done
71004454 | BRW | 10 | Final inspection | Karbar QA | 2025-11-09 |  | 2025-11-05 | Done
71004454 | BRW | 11 | Ex-factory | Factory | 2025-11-10 |  | 2025-11-06 | Done
71004457 | AMB | 1 | Yarn booking | Factory | 2025-07-16 |  | 2025-07-16 | Done
71004457 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-26 |  | 2025-07-27 | Done late
71004457 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004457 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-18 | Done
71004457 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-09-01 | Done late
71004457 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-07 | Done late
71004457 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-09-07 |  | 2025-09-07 | Done
71004457 | AMB | 8 | Knitting start | Factory | 2025-09-09 |  | 2025-09-09 | Done
71004457 | AMB | 9 | Linking start | Factory | 2025-09-15 |  | 2025-09-14 | Done
71004457 | AMB | 10 | Final inspection | Karbar QA | 2025-10-18 |  | 2025-10-15 | Done
71004457 | AMB | 11 | Ex-factory | Factory | 2025-10-19 |  | 2025-10-16 | Done
71004462 | CPL | 1 | Yarn booking | Factory | 2025-08-10 |  | 2025-08-07 | Done
71004462 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-18 | Done
71004462 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-25 |  | 2025-08-23 | Done
71004462 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-16 | Done late
71004462 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71004462 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-29 |  | 2025-09-29 | Done
71004462 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-02 |  | 2025-10-01 | Done
71004462 | CPL | 8 | Knitting start | Factory | 2025-10-04 |  | 2025-10-05 | Done late
71004462 | CPL | 9 | Linking start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004462 | CPL | 10 | Final inspection | Karbar QA | 2025-11-12 |  | 2025-11-10 | Done
71004462 | CPL | 11 | Ex-factory | Factory | 2025-11-13 |  | 2025-11-11 | Done
71004469 | HMR | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-14 | Done
71004469 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-25 |  | 2025-08-27 | Done late
71004469 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-30 | Done
71004469 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71004469 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-29 | Done
71004469 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-04 |  | 2025-10-04 | Done
71004469 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-10-07 |  | 2025-10-06 | Done
71004469 | HMR | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004469 | HMR | 9 | Linking start | Factory | 2025-10-15 |  | 2025-10-14 | Done
71004469 | HMR | 10 | Final inspection | Karbar QA | 2025-11-17 |  | 2025-11-19 | Done late
71004469 | HMR | 11 | Ex-factory | Factory | 2025-11-18 |  | 2025-11-20 | Done late
71004478 | GRL | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-14 | Done
71004478 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004478 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004478 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-23 | Done late
71004478 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71004478 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-07 | Done late
71004478 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-09 | Done
71004478 | GRL | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-11 | Done
71004478 | GRL | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004478 | GRL | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-12-01 | Done late
71004478 | GRL | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-12-02 | Done late
71004487 | SVP | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004487 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-08-31 | Done
71004487 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-04 | Done
71004487 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004487 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71004487 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-12 | Done late
71004487 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-14 | Done
71004487 | SVP | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004487 | SVP | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-21 | Done
71004487 | SVP | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-24 | Done
71004487 | SVP | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-11-25 | Done
71004496 | SLM | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-17 | Done
71004496 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-28 |  | 2025-07-30 | Done late
71004496 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-02 |  | 2025-08-03 | Done late
71004496 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004496 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004496 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-06 |  | 2025-09-06 | Done
71004496 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-09-09 |  | 2025-09-09 | Done
71004496 | SLM | 8 | Knitting start | Factory | 2025-09-11 |  | 2025-09-11 | Done
71004496 | SLM | 9 | Linking start | Factory | 2025-09-17 |  | 2025-09-16 | Done
71004496 | SLM | 10 | Final inspection | Karbar QA | 2025-10-20 |  | 2025-10-20 | Done
71004496 | SLM | 11 | Ex-factory | Factory | 2025-10-21 |  | 2025-10-21 | Done
71004499 | CPL | 1 | Yarn booking | Factory | 2025-08-06 |  | 2025-08-07 | Done late
71004499 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-16 |  | 2025-08-14 | Done
71004499 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-23 | Done late
71004499 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-10 | Done
71004499 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71004499 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-25 | Done
71004499 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-28 |  | 2025-09-25 | Done
71004499 | CPL | 8 | Knitting start | Factory | 2025-09-30 |  | 2025-09-30 | Done
71004499 | CPL | 9 | Linking start | Factory | 2025-10-06 |  | 2025-10-05 | Done
71004499 | CPL | 10 | Final inspection | Karbar QA | 2025-11-08 |  | 2025-11-08 | Done
71004499 | CPL | 11 | Ex-factory | Factory | 2025-11-09 |  | 2025-11-09 | Done
71004507 | OKH | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004507 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-17 | Done
71004507 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-25 | Done late
71004507 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004507 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-21 | Done
71004507 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-27 | Done
71004507 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-30 | Done
71004507 | OKH | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004507 | OKH | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-07 | Done
71004507 | OKH | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-10 | Done
71004507 | OKH | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-11 | Done
71004511 | PBB | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004511 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-18 | Done
71004511 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004511 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004511 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-23 | Done late
71004511 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-27 | Done
71004511 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-10-02 | Done late
71004511 | PBB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-04 | Done late
71004511 | PBB | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-09 | Done late
71004511 | PBB | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-06 | Done
71004511 | PBB | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-08 | Done
71004520 | SVP | 1 | Yarn booking | Factory | 2025-07-17 |  | 2025-07-17 | Done
71004520 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-27 |  | 2025-07-28 | Done late
71004520 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004520 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-19 | Done
71004520 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71004520 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-04 |  | 2025-09-04 | Done
71004520 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-09-08 |  | 2025-09-07 | Done
71004520 | SVP | 8 | Knitting start | Factory | 2025-09-10 |  | 2025-09-11 | Done late
71004520 | SVP | 9 | Linking start | Factory | 2025-09-16 |  | 2025-09-16 | Done
71004520 | SVP | 10 | Final inspection | Karbar QA | 2025-10-19 |  | 2025-10-16 | Done
71004520 | SVP | 11 | Ex-factory | Factory | 2025-10-20 |  | 2025-10-18 | Done
71004529 | LTF | 1 | Yarn booking | Factory | 2025-07-22 |  | 2025-07-21 | Done
71004529 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-07-31 |  | 2025-07-31 | Done
71004529 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-05 | Done
71004529 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-28 | Done late
71004529 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004529 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-10 |  | 2025-09-10 | Done
71004529 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-13 |  | 2025-09-15 | Done late
71004529 | LTF | 8 | Knitting start | Factory | 2025-09-15 |  | 2025-09-15 | Done
71004529 | LTF | 9 | Linking start | Factory | 2025-09-21 |  | 2025-09-20 | Done
71004529 | LTF | 10 | Final inspection | Karbar QA | 2025-10-23 |  | 2025-10-23 | Done
71004529 | LTF | 11 | Ex-factory | Factory | 2025-10-25 |  | 2025-10-25 | Done
71004533 | GRL | 1 | Yarn booking | Factory | 2025-07-30 |  | 2025-07-30 | Done
71004533 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-09 | Done
71004533 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004533 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71004533 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-15 | Done late
71004533 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-18 | Done
71004533 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-21 |  | 2025-09-22 | Done late
71004533 | GRL | 8 | Knitting start | Factory | 2025-09-23 |  | 2025-09-24 | Done late
71004533 | GRL | 9 | Linking start | Factory | 2025-09-29 |  | 2025-09-29 | Done
71004533 | GRL | 10 | Final inspection | Karbar QA | 2025-11-01 |  | 2025-10-29 | Done
71004533 | GRL | 11 | Ex-factory | Factory | 2025-11-02 |  | 2025-10-30 | Done
71004536 | KST | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-03 | Done
71004536 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-14 | Done late
71004536 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-16 | Done
71004536 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-04 | Done
71004536 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-18 | Done late
71004536 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-20 | Done
71004536 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-25 | Done
71004536 | KST | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71004536 | KST | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004536 | KST | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-05 | Done
71004536 | KST | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004540 | TLG | 1 | Yarn booking | Factory | 2025-08-12 |  | 2025-08-12 | Done
71004540 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004540 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004540 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004540 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004540 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-01 |  | 2025-10-01 | Done
71004540 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-10-04 |  | 2025-10-04 | Done
71004540 | TLG | 8 | Knitting start | Factory | 2025-10-06 |  | 2025-10-06 | Done
71004540 | TLG | 9 | Linking start | Factory | 2025-10-12 |  | 2025-10-11 | Done
71004540 | TLG | 10 | Final inspection | Karbar QA | 2025-11-13 |  | 2025-11-13 | Done
71004540 | TLG | 11 | Ex-factory | Factory | 2025-11-15 |  | 2025-11-15 | Done
71004549 | GRL | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-18 | Done late
71004549 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-26 | Done
71004549 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-08-30 | Done
71004549 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004549 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71004549 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-06 | Done
71004549 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-11 | Done late
71004549 | GRL | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-11 | Done
71004549 | GRL | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004549 | GRL | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-11-22 | Done late
71004549 | GRL | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-11-23 | Done late
71004553 | BLF | 1 | Yarn booking | Factory | 2025-07-26 |  | 2025-07-26 | Done
71004553 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-05 |  | 2025-08-05 | Done
71004553 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-10 | Done
71004553 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-28 | Done
71004553 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-09 | Done
71004553 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-14 |  | 2025-09-14 | Done
71004553 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-17 |  | 2025-09-17 | Done
71004553 | BLF | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-20 | Done late
71004553 | BLF | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004553 | BLF | 10 | Final inspection | Karbar QA | 2025-10-28 |  | 2025-10-28 | Done
71004553 | BLF | 11 | Ex-factory | Factory | 2025-10-29 |  | 2025-10-29 | Done
71004559 | CPL | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-08-02 | Done
71004559 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-14 | Done late
71004559 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-18 | Done late
71004559 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004559 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004559 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-21 | Done
71004559 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-24 | Done
71004559 | CPL | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004559 | CPL | 9 | Linking start | Factory | 2025-10-02 |  | 2025-09-30 | Done
71004559 | CPL | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004559 | CPL | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004562 | CLB | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-09 | Done late
71004562 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-20 | Done late
71004562 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004562 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004562 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71004562 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-27 | Done
71004562 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-30 | Done
71004562 | CLB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004562 | CLB | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-07 | Done
71004562 | CLB | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-10 | Done
71004562 | CLB | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-11 | Done
71004570 | KST | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-16 | Done
71004570 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-26 | Done
71004570 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-08-31 | Done
71004570 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-23 | Done late
71004570 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71004570 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-05 | Done
71004570 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-11 | Done late
71004570 | KST | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-12 | Done late
71004570 | KST | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004570 | KST | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-11-18 | Done
71004570 | KST | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-11-19 | Done
71004579 | LTF | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-26 | Done late
71004579 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004579 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-06 | Done
71004579 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71004579 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71004579 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71004579 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004579 | LTF | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004579 | LTF | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004579 | LTF | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-25 | Done
71004579 | LTF | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-26 | Done
71004586 | TLG | 1 | Yarn booking | Factory | 2025-07-27 |  | 2025-07-27 | Done
71004586 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-05 | Done
71004586 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-11 | Done
71004586 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-30 | Done
71004586 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-11 | Done late
71004586 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-15 |  | 2025-09-17 | Done late
71004586 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-09-18 |  | 2025-09-18 | Done
71004586 | TLG | 8 | Knitting start | Factory | 2025-09-20 |  | 2025-09-20 | Done
71004586 | TLG | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004586 | TLG | 10 | Final inspection | Karbar QA | 2025-10-29 |  | 2025-10-29 | Done
71004586 | TLG | 11 | Ex-factory | Factory | 2025-10-30 |  | 2025-10-30 | Done
71004591 | TLG | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-28 | Done
71004591 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004591 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-13 | Done
71004591 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-08-31 | Done
71004591 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004591 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-20 | Done late
71004591 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-21 | Done late
71004591 | TLG | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-22 | Done
71004591 | TLG | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-27 | Done
71004591 | TLG | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71004591 | TLG | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-11-01 | Done
71004594 | WSM | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-13 | Done
71004594 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004594 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004594 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004594 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-27 | Done
71004594 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71004594 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-05 | Done
71004594 | WSM | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-07 | Done
71004594 | WSM | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-12 | Done
71004594 | WSM | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-15 | Done
71004594 | WSM | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-16 | Done
71004601 | SVP | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004601 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-31 |  | 2025-09-02 | Done late
71004601 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004601 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-23 | Done
71004601 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-05 | Done
71004601 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-09 |  | 2025-10-08 | Done
71004601 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-10-13 |  | 2025-10-15 | Done late
71004601 | SVP | 8 | Knitting start | Factory | 2025-10-15 |  | 2025-10-15 | Done
71004601 | SVP | 9 | Linking start | Factory | 2025-10-21 |  | 2025-10-20 | Done
71004601 | SVP | 10 | Final inspection | Karbar QA | 2025-11-23 |  | 2025-11-23 | Done
71004601 | SVP | 11 | Ex-factory | Factory | 2025-11-24 |  | 2025-11-24 | Done
71004604 | BLF | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-17 | Done late
71004604 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71004604 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-09-01 | Done late
71004604 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71004604 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-29 | Done
71004604 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-06 | Done late
71004604 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-09 | Done late
71004604 | BLF | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-11 | Done late
71004604 | BLF | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004604 | BLF | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-18 | Done
71004604 | BLF | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-19 | Done
71004608 | BRW | 1 | Yarn booking | Factory | 2025-08-26 |  | 2025-08-27 | Done late
71004608 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004608 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-08 | Done
71004608 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71004608 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-11 | Done late
71004608 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-15 |  | 2025-10-16 | Done late
71004608 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-10-18 |  | 2025-10-19 | Done late
71004608 | BRW | 8 | Knitting start | Factory | 2025-10-20 |  | 2025-10-20 | Done
71004608 | BRW | 9 | Linking start | Factory | 2025-10-26 |  | 2025-10-25 | Done
71004608 | BRW | 10 | Final inspection | Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71004608 | BRW | 11 | Ex-factory | Factory | 2025-11-29 |  | 2025-11-29 | Done
71004611 | GRL | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-28 | Done
71004611 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-06 | Done
71004611 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004611 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71004611 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71004611 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-16 |  | 2025-10-18 | Done late
71004611 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-20 |  | 2025-10-20 | Done
71004611 | GRL | 8 | Knitting start | Factory | 2025-10-22 |  | 2025-10-22 | Done
71004611 | GRL | 9 | Linking start | Factory | 2025-10-28 |  | 2025-10-27 | Done
71004611 | GRL | 10 | Final inspection | Karbar QA | 2025-11-30 |  | 2025-11-30 | Done
71004611 | GRL | 11 | Ex-factory | Factory | 2025-12-01 |  | 2025-12-01 | Done
71004615 | IRB | 1 | Yarn booking | Factory | 2025-07-24 |  | 2025-07-23 | Done
71004615 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-04 |  | 2025-08-04 | Done
71004615 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-09 | Done
71004615 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004615 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004615 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-13 |  | 2025-09-11 | Done
71004615 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-16 |  | 2025-09-18 | Done late
71004615 | IRB | 8 | Knitting start | Factory | 2025-09-18 |  | 2025-09-18 | Done
71004615 | IRB | 9 | Linking start | Factory | 2025-09-24 |  | 2025-09-23 | Done
71004615 | IRB | 10 | Final inspection | Karbar QA | 2025-10-27 |  | 2025-10-27 | Done
71004615 | IRB | 11 | Ex-factory | Factory | 2025-10-28 |  | 2025-10-28 | Done
71004623 | MDW | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-14 | Done
71004623 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004623 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004623 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71004623 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71004623 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-09-30 | Done
71004623 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-06 |  | 2025-10-05 | Done
71004623 | MDW | 8 | Knitting start | Factory | 2025-10-08 |  | 2025-10-08 | Done
71004623 | MDW | 9 | Linking start | Factory | 2025-10-14 |  | 2025-10-13 | Done
71004623 | MDW | 10 | Final inspection | Karbar QA | 2025-11-16 |  | 2025-11-16 | Done
71004623 | MDW | 11 | Ex-factory | Factory | 2025-11-17 |  | 2025-11-17 | Done
71004631 | SVP | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-16 | Done
71004631 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71004631 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-30 | Done
71004631 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-18 | Done
71004631 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71004631 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-06 | Done late
71004631 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-08 | Done
71004631 | SVP | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-11 | Done late
71004631 | SVP | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004631 | SVP | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-16 | Done
71004631 | SVP | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-17 | Done
71004637 | RVS | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-08-02 | Done late
71004637 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-07 | Done
71004637 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004637 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-02 | Done
71004637 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-14 | Done
71004637 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-20 | Done late
71004637 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-09-22 |  | 2025-09-22 | Done
71004637 | RVS | 8 | Knitting start | Factory | 2025-09-24 |  | 2025-09-24 | Done
71004637 | RVS | 9 | Linking start | Factory | 2025-09-30 |  | 2025-09-29 | Done
71004637 | RVS | 10 | Final inspection | Karbar QA | 2025-11-02 |  | 2025-10-30 | Done
71004637 | RVS | 11 | Ex-factory | Factory | 2025-11-03 |  | 2025-11-01 | Done
71004643 | HMR | 1 | Yarn booking | Factory | 2025-08-06 |  | 2025-08-07 | Done late
71004643 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-16 |  | 2025-08-14 | Done
71004643 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-20 | Done
71004643 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-11 | Done late
71004643 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-22 | Done late
71004643 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-25 | Done
71004643 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-09-28 |  | 2025-09-28 | Done
71004643 | HMR | 8 | Knitting start | Factory | 2025-09-30 |  | 2025-10-01 | Done late
71004643 | HMR | 9 | Linking start | Factory | 2025-10-06 |  | 2025-10-06 | Done
71004643 | HMR | 10 | Final inspection | Karbar QA | 2025-11-08 |  | 2025-11-12 | Done late
71004643 | HMR | 11 | Ex-factory | Factory | 2025-11-09 |  | 2025-11-13 | Done late
71004651 | RVS | 1 | Yarn booking | Factory | 2025-08-27 |  | 2025-08-28 | Done late
71004651 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004651 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-09 | Done
71004651 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-01 |  | 2025-09-30 | Done
71004651 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-11 | Done
71004651 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-16 |  | 2025-10-16 | Done
71004651 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-10-19 |  | 2025-10-21 | Done late
71004651 | RVS | 8 | Knitting start | Factory | 2025-10-21 |  | 2025-10-22 | Done late
71004651 | RVS | 9 | Linking start | Factory | 2025-10-27 |  | 2025-10-27 | Done
71004651 | RVS | 10 | Final inspection | Karbar QA | 2025-11-29 |  | 2025-12-01 | Done late
71004651 | RVS | 11 | Ex-factory | Factory | 2025-11-30 |  | 2025-12-02 | Done late
71004658 | CPL | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-08-02 | Done
71004658 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-11 | Done
71004658 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004658 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004658 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-18 | Done late
71004658 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-18 | Done
71004658 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-25 | Done late
71004658 | CPL | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004658 | CPL | 9 | Linking start | Factory | 2025-10-02 |  | 2025-09-30 | Done
71004658 | CPL | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004658 | CPL | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004667 | CPL | 1 | Yarn booking | Factory | 2025-08-03 |  | 2025-08-03 | Done
71004667 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-13 | Done
71004667 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-19 | Done late
71004667 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004667 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004667 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-22 |  | 2025-09-22 | Done
71004667 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-09-25 |  | 2025-09-25 | Done
71004667 | CPL | 8 | Knitting start | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71004667 | CPL | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004667 | CPL | 10 | Final inspection | Karbar QA | 2025-11-05 |  | 2025-11-05 | Done
71004667 | CPL | 11 | Ex-factory | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004676 | CLB | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-05 | Done
71004676 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004676 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71004676 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004676 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004676 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-24 | Done
71004676 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-09-29 |  | 2025-09-28 | Done
71004676 | CLB | 8 | Knitting start | Factory | 2025-10-01 |  | 2025-10-01 | Done
71004676 | CLB | 9 | Linking start | Factory | 2025-10-07 |  | 2025-10-06 | Done
71004676 | CLB | 10 | Final inspection | Karbar QA | 2025-11-09 |  | 2025-11-05 | Done
71004676 | CLB | 11 | Ex-factory | Factory | 2025-11-10 |  | 2025-11-06 | Done
71004682 | IRB | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004682 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-08-31 | Done
71004682 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004682 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-24 | Done
71004682 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71004682 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-11 | Done
71004682 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-15 | Done late
71004682 | IRB | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004682 | IRB | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-21 | Done
71004682 | IRB | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-24 | Done
71004682 | IRB | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-11-25 | Done
71004690 | PBB | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-14 | Done late
71004690 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-21 | Done
71004690 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-26 | Done
71004690 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-18 | Done late
71004690 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-28 | Done late
71004690 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71004690 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-05 | Done
71004690 | PBB | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-08 | Done late
71004690 | PBB | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-13 | Done
71004690 | PBB | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-19 | Done late
71004690 | PBB | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-20 | Done late
71004699 | MDW | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71004699 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004699 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-07 | Done
71004699 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71004699 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71004699 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-15 | Done late
71004699 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-15 | Done
71004699 | MDW | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71004699 | MDW | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004699 | MDW | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-23 | Done
71004699 | MDW | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-24 | Done
71004704 | SND | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-07-31 | Done
71004704 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-10 |  | 2025-08-10 | Done
71004704 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-16 | Done late
71004704 | SND | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004704 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-14 | Done
71004704 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-18 | Done
71004704 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-09-22 |  | 2025-09-22 | Done
71004704 | SND | 8 | Knitting start | Factory | 2025-09-24 |  | 2025-09-25 | Done late
71004704 | SND | 9 | Linking start | Factory | 2025-09-30 |  | 2025-09-30 | Done
71004704 | SND | 10 | Final inspection | Karbar QA | 2025-11-02 |  | 2025-10-30 | Done
71004704 | SND | 11 | Ex-factory | Factory | 2025-11-03 |  | 2025-11-01 | Done
71004712 | BLF | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004712 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-17 | Done
71004712 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-19 | Done
71004712 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-10 | Done
71004712 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004712 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-25 |  | 2025-09-25 | Done
71004712 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-29 |  | 2025-09-28 | Done
71004712 | BLF | 8 | Knitting start | Factory | 2025-10-01 |  | 2025-10-01 | Done
71004712 | BLF | 9 | Linking start | Factory | 2025-10-07 |  | 2025-10-06 | Done
71004712 | BLF | 10 | Final inspection | Karbar QA | 2025-11-09 |  | 2025-11-12 | Done late
71004712 | BLF | 11 | Ex-factory | Factory | 2025-11-10 |  | 2025-11-13 | Done late
71004717 | MDW | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71004717 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-02 | Done late
71004717 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-07 | Done late
71004717 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004717 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71004717 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-12 | Done late
71004717 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-14 | Done
71004717 | MDW | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004717 | MDW | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-21 | Done
71004717 | MDW | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-30 | Done late
71004717 | MDW | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-12-01 | Done late
71004725 | MDW | 1 | Yarn booking | Factory | 2025-09-03 |  | 2025-09-04 | Done late
71004725 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71004725 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71004725 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71004725 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-18 | Done
71004725 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-23 |  | 2025-10-23 | Done
71004725 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-26 |  | 2025-10-23 | Done
71004725 | MDW | 8 | Knitting start | Factory | 2025-10-28 |  | 2025-10-29 | Done late
71004725 | MDW | 9 | Linking start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71004725 | MDW | 10 | Final inspection | Karbar QA | 2025-12-06 |  | 2025-12-03 | Done
71004725 | MDW | 11 | Ex-factory | Factory | 2025-12-07 |  | 2025-12-04 | Done
71004734 | AMB | 1 | Yarn booking | Factory | 2025-07-27 |  | 2025-07-26 | Done
71004734 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-06 |  | 2025-08-06 | Done
71004734 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-11 | Done
71004734 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-28 | Done
71004734 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-11 | Done late
71004734 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-15 |  | 2025-09-14 | Done
71004734 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-09-18 |  | 2025-09-17 | Done
71004734 | AMB | 8 | Knitting start | Factory | 2025-09-20 |  | 2025-09-21 | Done late
71004734 | AMB | 9 | Linking start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004734 | AMB | 10 | Final inspection | Karbar QA | 2025-10-29 |  | 2025-10-26 | Done
71004734 | AMB | 11 | Ex-factory | Factory | 2025-10-30 |  | 2025-10-27 | Done
71004739 | HMR | 1 | Yarn booking | Factory | 2025-07-29 |  | 2025-07-31 | Done late
71004739 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-07 |  | 2025-08-07 | Done
71004739 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-08-13 |  | 2025-08-12 | Done
71004739 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-09-02 |  | 2025-08-31 | Done
71004739 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004739 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-17 |  | 2025-09-17 | Done
71004739 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-09-20 |  | 2025-09-20 | Done
71004739 | HMR | 8 | Knitting start | Factory | 2025-09-22 |  | 2025-09-23 | Done late
71004739 | HMR | 9 | Linking start | Factory | 2025-09-28 |  | 2025-09-28 | Done
71004739 | HMR | 10 | Final inspection | Karbar QA | 2025-10-30 |  | 2025-10-29 | Done
71004739 | HMR | 11 | Ex-factory | Factory | 2025-11-01 |  | 2025-10-30 | Done
71004748 | LTF | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-07-30 | Done
71004748 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-12 | Done late
71004748 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-16 |  | 2025-08-16 | Done
71004748 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004748 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-17 | Done late
71004748 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-20 |  | 2025-09-20 | Done
71004748 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-09-23 |  | 2025-09-22 | Done
71004748 | LTF | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004748 | LTF | 9 | Linking start | Factory | 2025-10-01 |  | 2025-09-30 | Done
71004748 | LTF | 10 | Final inspection | Karbar QA | 2025-11-03 |  | 2025-11-03 | Done
71004748 | LTF | 11 | Ex-factory | Factory | 2025-11-04 |  | 2025-11-04 | Done
71004756 | KST | 1 | Yarn booking | Factory | 2025-07-31 |  | 2025-07-29 | Done
71004756 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-11 |  | 2025-08-11 | Done
71004756 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-16 |  | 2025-08-14 | Done
71004756 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004756 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-15 | Done
71004756 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-20 |  | 2025-09-21 | Done late
71004756 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-09-23 |  | 2025-09-21 | Done
71004756 | KST | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-25 | Done
71004756 | KST | 9 | Linking start | Factory | 2025-10-01 |  | 2025-09-30 | Done
71004756 | KST | 10 | Final inspection | Karbar QA | 2025-11-03 |  | 2025-11-03 | Done
71004756 | KST | 11 | Ex-factory | Factory | 2025-11-04 |  | 2025-11-04 | Done
71004760 | GRL | 1 | Yarn booking | Factory | 2025-08-05 |  | 2025-08-05 | Done
71004760 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-16 | Done late
71004760 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-20 | Done
71004760 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-09 | Done
71004760 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004760 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-24 |  | 2025-09-24 | Done
71004760 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-27 |  | 2025-09-27 | Done
71004760 | GRL | 8 | Knitting start | Factory | 2025-09-29 |  | 2025-09-29 | Done
71004760 | GRL | 9 | Linking start | Factory | 2025-10-05 |  | 2025-10-04 | Done
71004760 | GRL | 10 | Final inspection | Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71004760 | GRL | 11 | Ex-factory | Factory | 2025-11-08 |  | 2025-11-08 | Done
71004765 | SLM | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-23 | Done
71004765 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-01 | Done
71004765 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004765 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71004765 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71004765 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71004765 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004765 | SLM | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004765 | SLM | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004765 | SLM | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-12-03 | Done late
71004765 | SLM | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-12-04 | Done late
71004772 | BLF | 1 | Yarn booking | Factory | 2025-08-05 |  | 2025-08-05 | Done
71004772 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004772 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-20 | Done
71004772 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-09 | Done
71004772 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71004772 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-24 |  | 2025-09-25 | Done late
71004772 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-09-27 |  | 2025-09-29 | Done late
71004772 | BLF | 8 | Knitting start | Factory | 2025-09-29 |  | 2025-09-29 | Done
71004772 | BLF | 9 | Linking start | Factory | 2025-10-05 |  | 2025-10-04 | Done
71004772 | BLF | 10 | Final inspection | Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71004772 | BLF | 11 | Ex-factory | Factory | 2025-11-08 |  | 2025-11-08 | Done
71004779 | MDW | 1 | Yarn booking | Factory | 2025-08-26 |  | 2025-08-28 | Done late
71004779 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-03 | Done
71004779 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-09 | Done
71004779 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-28 | Done
71004779 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71004779 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-15 |  | 2025-10-15 | Done
71004779 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-18 |  | 2025-10-18 | Done
71004779 | MDW | 8 | Knitting start | Factory | 2025-10-20 |  | 2025-10-20 | Done
71004779 | MDW | 9 | Linking start | Factory | 2025-10-26 |  | 2025-10-25 | Done
71004779 | MDW | 10 | Final inspection | Karbar QA | 2025-11-27 |  | 2025-11-30 | Done late
71004779 | MDW | 11 | Ex-factory | Factory | 2025-11-29 |  | 2025-12-01 | Done late
71004783 | GRL | 1 | Yarn booking | Factory | 2025-08-26 |  | 2025-08-24 | Done
71004783 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-02 | Done
71004783 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-10 | Done
71004783 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71004783 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71004783 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-15 |  | 2025-10-15 | Done
71004783 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-18 |  | 2025-10-18 | Done
71004783 | GRL | 8 | Knitting start | Factory | 2025-10-20 |  | 2025-10-21 | Done late
71004783 | GRL | 9 | Linking start | Factory | 2025-10-26 |  | 2025-10-26 | Done
71004783 | GRL | 10 | Final inspection | Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71004783 | GRL | 11 | Ex-factory | Factory | 2025-11-29 |  | 2025-11-29 | Done
71004786 | AMB | 1 | Yarn booking | Factory | 2025-09-03 |  | 2025-09-04 | Done late
71004786 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71004786 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004786 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71004786 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-20 | Done late
71004786 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-23 |  | 2025-10-26 | Done late
71004786 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71004786 | AMB | 8 | Knitting start | Factory | 2025-10-28 |  | 2025-10-29 | Done late
71004786 | AMB | 9 | Linking start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71004786 | AMB | 10 | Final inspection | Karbar QA | 2025-12-06 |  | 2025-12-06 | Done
71004786 | AMB | 11 | Ex-factory | Factory | 2025-12-07 |  | 2025-12-07 | Done
71004793 | GRL | 1 | Yarn booking | Factory | 2025-07-30 |  | 2025-07-31 | Done late
71004793 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-09 |  | 2025-08-09 | Done
71004793 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004793 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004793 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-14 | Done late
71004793 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-18 |  | 2025-09-18 | Done
71004793 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-09-21 |  | 2025-09-21 | Done
71004793 | GRL | 8 | Knitting start | Factory | 2025-09-23 |  | 2025-09-23 | Done
71004793 | GRL | 9 | Linking start | Factory | 2025-09-29 |  | 2025-09-28 | Done
71004793 | GRL | 10 | Final inspection | Karbar QA | 2025-11-01 |  | 2025-11-04 | Done late
71004793 | GRL | 11 | Ex-factory | Factory | 2025-11-02 |  | 2025-11-05 | Done late
71004797 | AMB | 1 | Yarn booking | Factory | 2025-08-23 |  | 2025-08-23 | Done
71004797 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-02 |  | 2025-08-31 | Done
71004797 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-08 | Done late
71004797 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-27 | Done
71004797 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-06 | Done
71004797 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-12 |  | 2025-10-11 | Done
71004797 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-10-15 |  | 2025-10-15 | Done
71004797 | AMB | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71004797 | AMB | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004797 | AMB | 10 | Final inspection | Karbar QA | 2025-11-25 |  | 2025-11-22 | Done
71004797 | AMB | 11 | Ex-factory | Factory | 2025-11-26 |  | 2025-11-23 | Done
71004804 | CPL | 1 | Yarn booking | Factory | 2025-09-04 |  | 2025-09-04 | Done
71004804 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-15 | Done
71004804 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71004804 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-08 | Done
71004804 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-19 | Done
71004804 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-25 |  | 2025-10-25 | Done
71004804 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-28 |  | 2025-10-28 | Done
71004804 | CPL | 8 | Knitting start | Factory | 2025-10-30 |  | 2025-11-01 | Done late
71004804 | CPL | 9 | Linking start | Factory | 2025-11-05 |  | 2025-11-06 | Done late
71004804 | CPL | 10 | Final inspection | Karbar QA | 2025-12-08 |  | 2025-12-08 | Done
71004804 | CPL | 11 | Ex-factory | Factory | 2025-12-09 |  | 2025-12-09 | Done
71004813 | RVS | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-06 | Done
71004813 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71004813 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71004813 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71004813 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71004813 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-27 | Done
71004813 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71004813 | RVS | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-01 | Done
71004813 | RVS | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71004813 | RVS | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-08 | Done
71004813 | RVS | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-09 | Done
71004818 | SVP | 1 | Yarn booking | Factory | 2025-08-02 |  | 2025-08-04 | Done late
71004818 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-12 |  | 2025-08-12 | Done
71004818 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-08-17 |  | 2025-08-19 | Done late
71004818 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71004818 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-15 | Done
71004818 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-21 |  | 2025-09-18 | Done
71004818 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-09-24 |  | 2025-09-25 | Done late
71004818 | SVP | 8 | Knitting start | Factory | 2025-09-25 |  | 2025-09-27 | Done late
71004818 | SVP | 9 | Linking start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004818 | SVP | 10 | Final inspection | Karbar QA | 2025-11-04 |  | 2025-11-04 | Done
71004818 | SVP | 11 | Ex-factory | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004823 | FNS | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004823 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-16 | Done
71004823 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-21 | Done
71004823 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71004823 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-24 | Done late
71004823 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-27 | Done
71004823 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-30 | Done
71004823 | FNS | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-04 | Done late
71004823 | FNS | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-09 | Done late
71004823 | FNS | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-06 | Done
71004823 | FNS | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-08 | Done
71004828 | TLG | 1 | Yarn booking | Factory | 2025-08-12 |  | 2025-08-14 | Done late
71004828 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-20 | Done
71004828 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-27 | Done
71004828 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71004828 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71004828 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-01 |  | 2025-10-01 | Done
71004828 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-10-04 |  | 2025-10-02 | Done
71004828 | TLG | 8 | Knitting start | Factory | 2025-10-06 |  | 2025-10-06 | Done
71004828 | TLG | 9 | Linking start | Factory | 2025-10-12 |  | 2025-10-11 | Done
71004828 | TLG | 10 | Final inspection | Karbar QA | 2025-11-13 |  | 2025-11-15 | Done late
71004828 | TLG | 11 | Ex-factory | Factory | 2025-11-15 |  | 2025-11-16 | Done late
71004833 | BLF | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-13 | Done
71004833 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-26 | Done late
71004833 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-26 | Done
71004833 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-17 | Done
71004833 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71004833 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71004833 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-10-06 |  | 2025-10-08 | Done late
71004833 | BLF | 8 | Knitting start | Factory | 2025-10-08 |  | 2025-10-08 | Done
71004833 | BLF | 9 | Linking start | Factory | 2025-10-14 |  | 2025-10-13 | Done
71004833 | BLF | 10 | Final inspection | Karbar QA | 2025-11-16 |  | 2025-11-13 | Done
71004833 | BLF | 11 | Ex-factory | Factory | 2025-11-17 |  | 2025-11-15 | Done
71004837 | WTH | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-21 | Done
71004837 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004837 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-06 | Done
71004837 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71004837 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71004837 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-16 | Done late
71004837 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004837 | WTH | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004837 | WTH | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004837 | WTH | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71004837 | WTH | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71004841 | RSG | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-26 | Done
71004841 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004841 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71004841 | RSG | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-04 | Done late
71004841 | RSG | 5 | PP sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71004841 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-18 |  | 2025-10-18 | Done
71004841 | RSG | 7 | PP meeting | Factory + Karbar QA | 2025-10-21 |  | 2025-10-20 | Done
71004841 | RSG | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-25 | Done late
71004841 | RSG | 9 | Linking start | Factory | 2025-10-29 |  | 2025-10-30 | Done late
71004841 | RSG | 10 | Final inspection | Karbar QA | 2025-12-01 |  | 2025-12-02 | Done late
71004841 | RSG | 11 | Ex-factory | Factory | 2025-12-02 |  | 2025-12-03 | Done late
71004847 | RVS | 1 | Yarn booking | Factory | 2025-08-20 |  | 2025-08-20 | Done
71004847 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-30 | Done
71004847 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-04 |  | 2025-09-04 | Done
71004847 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71004847 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-04 | Done
71004847 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-09 |  | 2025-10-08 | Done
71004847 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-10-12 |  | 2025-10-14 | Done late
71004847 | RVS | 8 | Knitting start | Factory | 2025-10-14 |  | 2025-10-15 | Done late
71004847 | RVS | 9 | Linking start | Factory | 2025-10-20 |  | 2025-10-20 | Done
71004847 | RVS | 10 | Final inspection | Karbar QA | 2025-11-22 |  | 2025-11-19 | Done
71004847 | RVS | 11 | Ex-factory | Factory | 2025-11-23 |  | 2025-11-20 | Done
71004856 | OKH | 1 | Yarn booking | Factory | 2025-09-04 |  | 2025-09-04 | Done
71004856 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-14 | Done
71004856 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-17 | Done
71004856 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71004856 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-18 | Done
71004856 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-23 |  | 2025-10-21 | Done
71004856 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-10-27 |  | 2025-10-27 | Done
71004856 | OKH | 8 | Knitting start | Factory | 2025-10-29 |  | 2025-10-30 | Done late
71004856 | OKH | 9 | Linking start | Factory | 2025-11-04 |  | 2025-11-04 | Done
71004856 | OKH | 10 | Final inspection | Karbar QA | 2025-12-07 |  | 2025-12-07 | Done
71004856 | OKH | 11 | Ex-factory | Factory | 2025-12-08 |  | 2025-12-08 | Done
71004860 | BLF | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-11 | Done late
71004860 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004860 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-25 | Done late
71004860 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71004860 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71004860 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-28 | Done
71004860 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-11-03 | Done late
71004860 | BLF | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71004860 | BLF | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-08 | Done
71004860 | BLF | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71004860 | BLF | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-13 | Done
71004865 | IRB | 1 | Yarn booking | Factory | 2025-08-09 |  | 2025-08-10 | Done late
71004865 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-19 |  | 2025-08-18 | Done
71004865 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004865 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-11 | Done
71004865 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-23 |  | 2025-09-25 | Done late
71004865 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-28 |  | 2025-09-30 | Done late
71004865 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-01 |  | 2025-09-30 | Done
71004865 | IRB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004865 | IRB | 9 | Linking start | Factory | 2025-10-09 |  | 2025-10-07 | Done
71004865 | IRB | 10 | Final inspection | Karbar QA | 2025-11-11 |  | 2025-11-11 | Done
71004865 | IRB | 11 | Ex-factory | Factory | 2025-11-12 |  | 2025-11-12 | Done
71004872 | CLB | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-14 | Done
71004872 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-25 |  | 2025-08-23 | Done
71004872 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-30 |  | 2025-08-31 | Done late
71004872 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-16 | Done
71004872 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-10-01 | Done late
71004872 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-04 |  | 2025-10-04 | Done
71004872 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-07 |  | 2025-10-07 | Done
71004872 | CLB | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004872 | CLB | 9 | Linking start | Factory | 2025-10-15 |  | 2025-10-14 | Done
71004872 | CLB | 10 | Final inspection | Karbar QA | 2025-11-17 |  | 2025-11-17 | Done
71004872 | CLB | 11 | Ex-factory | Factory | 2025-11-18 |  | 2025-11-18 | Done
71004879 | TLG | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-27 | Done
71004879 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004879 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71004879 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71004879 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71004879 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-18 |  | 2025-10-16 | Done
71004879 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-10-21 |  | 2025-10-20 | Done
71004879 | TLG | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-25 | Done late
71004879 | TLG | 9 | Linking start | Factory | 2025-10-29 |  | 2025-10-30 | Done late
71004879 | TLG | 10 | Final inspection | Karbar QA | 2025-12-01 |  | 2025-11-27 | Done
71004879 | TLG | 11 | Ex-factory | Factory | 2025-12-02 |  | 2025-11-29 | Done
71004882 | BRW | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-11 | Done late
71004882 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004882 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71004882 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-13 | Done
71004882 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71004882 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-29 | Done
71004882 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-10-30 | Done
71004882 | BRW | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-04 | Done late
71004882 | BRW | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-09 | Done
71004882 | BRW | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-10 | Done
71004882 | BRW | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-11 | Done
71004891 | RVS | 1 | Yarn booking | Factory | 2025-08-05 |  | 2025-08-03 | Done
71004891 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-14 |  | 2025-08-14 | Done
71004891 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-20 |  | 2025-08-18 | Done
71004891 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-10 | Done late
71004891 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004891 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-24 |  | 2025-09-24 | Done
71004891 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-09-27 |  | 2025-09-27 | Done
71004891 | RVS | 8 | Knitting start | Factory | 2025-09-29 |  | 2025-09-30 | Done late
71004891 | RVS | 9 | Linking start | Factory | 2025-10-05 |  | 2025-10-05 | Done
71004891 | RVS | 10 | Final inspection | Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71004891 | RVS | 11 | Ex-factory | Factory | 2025-11-08 |  | 2025-11-08 | Done
71004898 | WSM | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-17 | Done
71004898 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004898 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71004898 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004898 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71004898 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-08 | Done late
71004898 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-09 | Done
71004898 | WSM | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-11 | Done
71004898 | WSM | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004898 | WSM | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-11-16 | Done
71004898 | WSM | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-11-17 | Done
71004905 | PBB | 1 | Yarn booking | Factory | 2025-09-06 |  | 2025-09-04 | Done
71004905 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-14 | Done
71004905 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-21 | Done
71004905 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-09 | Done
71004905 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-22 | Done late
71004905 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-26 |  | 2025-10-26 | Done
71004905 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-10-29 |  | 2025-10-27 | Done
71004905 | PBB | 8 | Knitting start | Factory | 2025-10-30 |  | 2025-10-30 | Done
71004905 | PBB | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-04 | Done
71004905 | PBB | 10 | Final inspection | Karbar QA | 2025-12-09 |  | 2025-12-09 | Done
71004905 | PBB | 11 | Ex-factory | Factory | 2025-12-10 |  | 2025-12-10 | Done
71004912 | BRW | 1 | Yarn booking | Factory | 2025-08-19 |  | 2025-08-19 | Done
71004912 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004912 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-01 | Done
71004912 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-09-23 |  | 2025-09-24 | Done late
71004912 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71004912 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-08 |  | 2025-10-09 | Done late
71004912 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-10-11 |  | 2025-10-11 | Done
71004912 | BRW | 8 | Knitting start | Factory | 2025-10-13 |  | 2025-10-13 | Done
71004912 | BRW | 9 | Linking start | Factory | 2025-10-19 |  | 2025-10-18 | Done
71004912 | BRW | 10 | Final inspection | Karbar QA | 2025-11-20 |  | 2025-11-20 | Done
71004912 | BRW | 11 | Ex-factory | Factory | 2025-11-22 |  | 2025-11-22 | Done
71004919 | GRL | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-17 | Done late
71004919 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71004919 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-28 | Done
71004919 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71004919 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-29 | Done
71004919 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-07 | Done late
71004919 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-06 | Done
71004919 | GRL | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71004919 | GRL | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-14 | Done
71004919 | GRL | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-22 | Done late
71004919 | GRL | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-23 | Done late
71004928 | CLB | 1 | Yarn booking | Factory | 2025-08-17 |  | 2025-08-14 | Done
71004928 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71004928 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-02 | Done late
71004928 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-18 | Done
71004928 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71004928 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-06 |  | 2025-10-06 | Done
71004928 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-09 |  | 2025-10-09 | Done
71004928 | CLB | 8 | Knitting start | Factory | 2025-10-11 |  | 2025-10-11 | Done
71004928 | CLB | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71004928 | CLB | 10 | Final inspection | Karbar QA | 2025-11-19 |  | 2025-11-19 | Done
71004928 | CLB | 11 | Ex-factory | Factory | 2025-11-20 |  | 2025-11-20 | Done
71004934 | GRL | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-28 | Done
71004934 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004934 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-14 | Done late
71004934 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-09-30 | Done
71004934 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-15 | Done late
71004934 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-18 |  | 2025-10-18 | Done
71004934 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-10-21 |  | 2025-10-20 | Done
71004934 | GRL | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-25 | Done late
71004934 | GRL | 9 | Linking start | Factory | 2025-10-29 |  | 2025-10-30 | Done late
71004934 | GRL | 10 | Final inspection | Karbar QA | 2025-12-01 |  | 2025-12-10 | Done late
71004934 | GRL | 11 | Ex-factory | Factory | 2025-12-02 |  | 2025-12-11 | Done late
71004940 | CLB | 1 | Yarn booking | Factory | 2025-09-04 |  | 2025-09-04 | Done
71004940 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-17 | Done late
71004940 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-22 | Done late
71004940 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-07 | Done
71004940 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-21 | Done late
71004940 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-25 |  | 2025-10-28 | Done late
71004940 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-28 |  | 2025-10-28 | Done
71004940 | CLB | 8 | Knitting start | Factory | 2025-10-30 |  | 2025-10-30 | Done
71004940 | CLB | 9 | Linking start | Factory | 2025-11-05 |  | 2025-11-04 | Done
71004940 | CLB | 10 | Final inspection | Karbar QA | 2025-12-08 |  | 2025-12-08 | Done
71004940 | CLB | 11 | Ex-factory | Factory | 2025-12-09 |  | 2025-12-09 | Done
71004946 | SND | 1 | Yarn booking | Factory | 2025-09-11 |  | 2025-09-10 | Done
71004946 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-21 |  | 2025-09-20 | Done
71004946 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71004946 | SND | 4 | Size set approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-14 | Done
71004946 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-27 | Done late
71004946 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-30 |  | 2025-11-01 | Done late
71004946 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-03 |  | 2025-11-03 | Done
71004946 | SND | 8 | Knitting start | Factory | 2025-11-05 |  | 2025-11-05 | Done
71004946 | SND | 9 | Linking start | Factory | 2025-11-11 |  | 2025-11-10 | Done
71004946 | SND | 10 | Final inspection | Karbar QA | 2025-12-14 |  | 2025-12-10 | Done
71004946 | SND | 11 | Ex-factory | Factory | 2025-12-15 |  | 2025-12-11 | Done
71004954 | IRB | 1 | Yarn booking | Factory | 2025-08-09 |  | 2025-08-07 | Done
71004954 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-19 |  | 2025-08-19 | Done
71004954 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-21 | Done
71004954 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-14 | Done late
71004954 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-23 |  | 2025-09-24 | Done late
71004954 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-28 |  | 2025-09-28 | Done
71004954 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-01 |  | 2025-10-02 | Done late
71004954 | IRB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004954 | IRB | 9 | Linking start | Factory | 2025-10-09 |  | 2025-10-07 | Done
71004954 | IRB | 10 | Final inspection | Karbar QA | 2025-11-11 |  | 2025-11-19 | Done late
71004954 | IRB | 11 | Ex-factory | Factory | 2025-11-12 |  | 2025-11-20 | Done late
71004958 | TLG | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-14 | Done
71004958 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-24 | Done
71004958 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71004958 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-16 | Done
71004958 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71004958 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-05 | Done late
71004958 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-10-06 |  | 2025-10-07 | Done late
71004958 | TLG | 8 | Knitting start | Factory | 2025-10-08 |  | 2025-10-08 | Done
71004958 | TLG | 9 | Linking start | Factory | 2025-10-14 |  | 2025-10-13 | Done
71004958 | TLG | 10 | Final inspection | Karbar QA | 2025-11-16 |  | 2025-11-16 | Done
71004958 | TLG | 11 | Ex-factory | Factory | 2025-11-17 |  | 2025-11-17 | Done
71004964 | CPL | 1 | Yarn booking | Factory | 2025-08-31 |  | 2025-08-31 | Done
71004964 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-10 |  | 2025-09-11 | Done late
71004964 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-15 |  | 2025-09-15 | Done
71004964 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-05 | Done
71004964 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-15 | Done
71004964 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-20 |  | 2025-10-18 | Done
71004964 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-23 |  | 2025-10-23 | Done
71004964 | CPL | 8 | Knitting start | Factory | 2025-10-25 |  | 2025-10-26 | Done late
71004964 | CPL | 9 | Linking start | Factory | 2025-10-30 |  | 2025-10-30 | Done
71004964 | CPL | 10 | Final inspection | Karbar QA | 2025-12-03 |  | 2025-12-03 | Done
71004964 | CPL | 11 | Ex-factory | Factory | 2025-12-04 |  | 2025-12-04 | Done
71004973 | IRB | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-16 | Done late
71004973 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-25 | Done late
71004973 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-30 | Done late
71004973 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71004973 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-27 | Done
71004973 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-05 | Done late
71004973 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-06 |  | 2025-10-07 | Done late
71004973 | IRB | 8 | Knitting start | Factory | 2025-10-08 |  | 2025-10-08 | Done
71004973 | IRB | 9 | Linking start | Factory | 2025-10-14 |  | 2025-10-13 | Done
71004973 | IRB | 10 | Final inspection | Karbar QA | 2025-11-16 |  | 2025-11-16 | Done
71004973 | IRB | 11 | Ex-factory | Factory | 2025-11-17 |  | 2025-11-17 | Done
71004981 | KST | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-26 | Done late
71004981 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-03 | Done
71004981 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71004981 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71004981 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71004981 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71004981 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71004981 | KST | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71004981 | KST | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71004981 | KST | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71004981 | KST | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71004989 | LTF | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-26 | Done
71004989 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-07 | Done
71004989 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-09 | Done
71004989 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71004989 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-14 | Done late
71004989 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-16 |  | 2025-10-16 | Done
71004989 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-10-20 |  | 2025-10-20 | Done
71004989 | LTF | 8 | Knitting start | Factory | 2025-10-22 |  | 2025-10-22 | Done
71004989 | LTF | 9 | Linking start | Factory | 2025-10-28 |  | 2025-10-27 | Done
71004989 | LTF | 10 | Final inspection | Karbar QA | 2025-11-30 |  | 2025-11-30 | Done
71004989 | LTF | 11 | Ex-factory | Factory | 2025-12-01 |  | 2025-12-01 | Done
71004995 | IRB | 1 | Yarn booking | Factory | 2025-08-07 |  | 2025-08-07 | Done
71004995 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-18 |  | 2025-08-17 | Done
71004995 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71004995 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-10 | Done
71004995 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71004995 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-09-27 |  | 2025-09-28 | Done late
71004995 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-09-30 |  | 2025-09-30 | Done
71004995 | IRB | 8 | Knitting start | Factory | 2025-10-02 |  | 2025-10-02 | Done
71004995 | IRB | 9 | Linking start | Factory | 2025-10-08 |  | 2025-10-07 | Done
71004995 | IRB | 10 | Final inspection | Karbar QA | 2025-11-10 |  | 2025-11-06 | Done
71004995 | IRB | 11 | Ex-factory | Factory | 2025-11-11 |  | 2025-11-08 | Done
71005004 | BRW | 1 | Yarn booking | Factory | 2025-08-16 |  | 2025-08-16 | Done
71005004 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-26 |  | 2025-08-26 | Done
71005004 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-31 |  | 2025-08-31 | Done
71005004 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-21 | Done late
71005004 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-30 |  | 2025-10-01 | Done late
71005004 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-05 |  | 2025-10-07 | Done late
71005004 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-10-08 |  | 2025-10-07 | Done
71005004 | BRW | 8 | Knitting start | Factory | 2025-10-09 |  | 2025-10-09 | Done
71005004 | BRW | 9 | Linking start | Factory | 2025-10-16 |  | 2025-10-14 | Done
71005004 | BRW | 10 | Final inspection | Karbar QA | 2025-11-18 |  | 2025-11-18 | Done
71005004 | BRW | 11 | Ex-factory | Factory | 2025-11-19 |  | 2025-11-19 | Done
71005009 | PBB | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-28 | Done
71005009 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-07 |  | 2025-09-09 | Done late
71005009 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-09 | Done
71005009 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-01 | Done
71005009 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71005009 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-16 |  | 2025-10-16 | Done
71005009 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-10-20 |  | 2025-10-22 | Done late
71005009 | PBB | 8 | Knitting start | Factory | 2025-10-22 |  | 2025-10-23 | Done late
71005009 | PBB | 9 | Linking start | Factory | 2025-10-28 |  | 2025-10-28 | Done
71005009 | PBB | 10 | Final inspection | Karbar QA | 2025-11-30 |  | 2025-11-30 | Done
71005009 | PBB | 11 | Ex-factory | Factory | 2025-12-01 |  | 2025-12-01 | Done
71005018 | WSM | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-11 | Done late
71005018 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005018 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71005018 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71005018 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005018 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-29 | Done
71005018 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-11-01 | Done
71005018 | WSM | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71005018 | WSM | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-08 | Done
71005018 | WSM | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005018 | WSM | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005025 | SND | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-23 | Done late
71005025 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-01 | Done
71005025 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-04 | Done
71005025 | SND | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71005025 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-07 | Done late
71005025 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-11 | Done
71005025 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-12 | Done
71005025 | SND | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71005025 | SND | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-23 | Done late
71005025 | SND | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-23 | Done
71005025 | SND | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-11-24 | Done
71005031 | WSM | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-04 | Done
71005031 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-15 | Done
71005031 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-20 | Done
71005031 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-11 | Done
71005031 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005031 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-25 | Done
71005031 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71005031 | WSM | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-01 | Done
71005031 | WSM | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005031 | WSM | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-10 | Done
71005031 | WSM | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005040 | BRW | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-13 | Done
71005040 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-24 | Done late
71005040 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71005040 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71005040 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-28 | Done late
71005040 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71005040 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-06 | Done late
71005040 | BRW | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-08 | Done late
71005040 | BRW | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-13 | Done
71005040 | BRW | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-15 | Done
71005040 | BRW | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-16 | Done
71005048 | SLM | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-04 | Done
71005048 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-16 | Done
71005048 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71005048 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-13 | Done late
71005048 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005048 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-28 | Done late
71005048 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-11-01 | Done late
71005048 | SLM | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-02 | Done late
71005048 | SLM | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005048 | SLM | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-10 | Done
71005048 | SLM | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005052 | FNS | 1 | Yarn booking | Factory | 2025-08-12 |  | 2025-08-14 | Done late
71005052 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-21 |  | 2025-08-21 | Done
71005052 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-08-27 |  | 2025-08-28 | Done late
71005052 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-09-16 |  | 2025-09-16 | Done
71005052 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71005052 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-01 |  | 2025-10-01 | Done
71005052 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-10-04 |  | 2025-10-04 | Done
71005052 | FNS | 8 | Knitting start | Factory | 2025-10-06 |  | 2025-10-07 | Done late
71005052 | FNS | 9 | Linking start | Factory | 2025-10-12 |  | 2025-10-12 | Done
71005052 | FNS | 10 | Final inspection | Karbar QA | 2025-11-13 |  | 2025-11-13 | Done
71005052 | FNS | 11 | Ex-factory | Factory | 2025-11-15 |  | 2025-11-15 | Done
71005057 | KST | 1 | Yarn booking | Factory | 2025-08-14 |  | 2025-08-16 | Done late
71005057 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-24 |  | 2025-08-26 | Done late
71005057 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-27 | Done
71005057 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005057 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-27 | Done
71005057 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-10-02 | Done
71005057 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-10-06 |  | 2025-10-06 | Done
71005057 | KST | 8 | Knitting start | Factory | 2025-10-08 |  | 2025-10-08 | Done
71005057 | KST | 9 | Linking start | Factory | 2025-10-14 |  | 2025-10-13 | Done
71005057 | KST | 10 | Final inspection | Karbar QA | 2025-11-16 |  | 2025-11-22 | Done late
71005057 | KST | 11 | Ex-factory | Factory | 2025-11-17 |  | 2025-11-23 | Done late
71005066 | AMB | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005066 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71005066 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005066 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71005066 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005066 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-12 | Done
71005066 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-18 | Done late
71005066 | AMB | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71005066 | AMB | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005066 | AMB | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71005066 | AMB | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005073 | MDW | 1 | Yarn booking | Factory | 2025-09-02 |  | 2025-09-04 | Done late
71005073 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-13 | Done late
71005073 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-18 | Done late
71005073 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-05 | Done
71005073 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-16 | Done
71005073 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-22 |  | 2025-10-23 | Done late
71005073 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-10-25 |  | 2025-10-25 | Done
71005073 | MDW | 8 | Knitting start | Factory | 2025-10-27 |  | 2025-10-28 | Done late
71005073 | MDW | 9 | Linking start | Factory | 2025-11-02 |  | 2025-11-02 | Done
71005073 | MDW | 10 | Final inspection | Karbar QA | 2025-12-04 |  | 2025-12-04 | Done
71005073 | MDW | 11 | Ex-factory | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005080 | AMB | 1 | Yarn booking | Factory | 2025-09-16 |  | 2025-09-14 | Done
71005080 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71005080 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71005080 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-19 | Done
71005080 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005080 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-05 |  | 2025-11-06 | Done late
71005080 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-08 |  | 2025-11-10 | Done late
71005080 | AMB | 8 | Knitting start | Factory | 2025-11-10 |  | 2025-11-10 | Done
71005080 | AMB | 9 | Linking start | Factory | 2025-11-16 |  | 2025-11-15 | Done
71005080 | AMB | 10 | Final inspection | Karbar QA | 2025-12-18 |  | 2025-12-18 | Done
71005080 | AMB | 11 | Ex-factory | Factory | 2025-12-20 |  | 2025-12-20 | Done
71005088 | GRL | 1 | Yarn booking | Factory | 2025-09-20 |  | 2025-09-20 | Done
71005088 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71005088 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-05 | Done
71005088 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-25 | Done
71005088 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-03 | Done
71005088 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-09 |  | 2025-11-09 | Done
71005088 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-12 |  | 2025-11-12 | Done
71005088 | GRL | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-15 | Done late
71005088 | GRL | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005088 | GRL | 10 | Final inspection | Karbar QA | 2025-12-23 |  | 2025-12-23 | Done
71005088 | GRL | 11 | Ex-factory | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005096 | SLM | 1 | Yarn booking | Factory | 2025-08-13 |  | 2025-08-12 | Done
71005096 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-08-23 |  | 2025-08-23 | Done
71005096 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-08-28 |  | 2025-08-28 | Done
71005096 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71005096 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-27 | Done
71005096 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-02 |  | 2025-09-30 | Done
71005096 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-05 |  | 2025-10-05 | Done
71005096 | SLM | 8 | Knitting start | Factory | 2025-10-07 |  | 2025-10-08 | Done late
71005096 | SLM | 9 | Linking start | Factory | 2025-10-13 |  | 2025-10-13 | Done
71005096 | SLM | 10 | Final inspection | Karbar QA | 2025-11-15 |  | 2025-11-18 | Done late
71005096 | SLM | 11 | Ex-factory | Factory | 2025-11-16 |  | 2025-11-19 | Done late
71005103 | CPL | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-19 | Done
71005103 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-09-03 | Done late
71005103 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-07 | Done late
71005103 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71005103 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005103 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-14 | Done late
71005103 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-14 | Done
71005103 | CPL | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-16 | Done
71005103 | CPL | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-21 | Done
71005103 | CPL | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-24 | Done
71005103 | CPL | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-11-25 | Done
71005107 | IRB | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-16 | Done late
71005107 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-25 | Done late
71005107 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-29 | Done
71005107 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-16 | Done
71005107 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005107 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-03 | Done
71005107 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005107 | IRB | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-08 | Done
71005107 | IRB | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005107 | IRB | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-18 | Done late
71005107 | IRB | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-20 | Done late
71005116 | BRW | 1 | Yarn booking | Factory | 2025-09-16 |  | 2025-09-16 | Done
71005116 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-24 | Done
71005116 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005116 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-21 | Done
71005116 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005116 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-05 |  | 2025-11-05 | Done
71005116 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-11-08 |  | 2025-11-06 | Done
71005116 | BRW | 8 | Knitting start | Factory | 2025-11-10 |  | 2025-11-10 | Done
71005116 | BRW | 9 | Linking start | Factory | 2025-11-16 |  | 2025-11-15 | Done
71005116 | BRW | 10 | Final inspection | Karbar QA | 2025-12-18 |  | 2025-12-17 | Done
71005116 | BRW | 11 | Ex-factory | Factory | 2025-12-20 |  | 2025-12-18 | Done
71005123 | IRB | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005123 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-01 | Done
71005123 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005123 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-29 | Done late
71005123 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005123 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71005123 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71005123 | IRB | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71005123 | IRB | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005123 | IRB | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71005123 | IRB | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005128 | BLF | 1 | Yarn booking | Factory | 2025-08-30 |  | 2025-08-31 | Done late
71005128 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-10 | Done late
71005128 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-11 | Done
71005128 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-02 | Done
71005128 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71005128 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-19 |  | 2025-10-19 | Done
71005128 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-10-22 |  | 2025-10-20 | Done
71005128 | BLF | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005128 | BLF | 9 | Linking start | Factory | 2025-10-30 |  | 2025-10-28 | Done
71005128 | BLF | 10 | Final inspection | Karbar QA | 2025-12-02 |  | 2025-12-02 | Done
71005128 | BLF | 11 | Ex-factory | Factory | 2025-12-03 |  | 2025-12-03 | Done
71005132 | CPL | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005132 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71005132 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005132 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-29 | Done late
71005132 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005132 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71005132 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-18 | Done late
71005132 | CPL | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71005132 | CPL | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005132 | CPL | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-25 | Done
71005132 | CPL | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-26 | Done
71005138 | CPL | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-08 | Done late
71005138 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71005138 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-24 | Done late
71005138 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-14 | Done late
71005138 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005138 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-27 | Done
71005138 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-11-01 | Done late
71005138 | CPL | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-01 | Done
71005138 | CPL | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005138 | CPL | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-10 | Done
71005138 | CPL | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005145 | IRB | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005145 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71005145 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005145 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-28 | Done
71005145 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005145 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-12 | Done
71005145 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71005145 | IRB | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-18 | Done
71005145 | IRB | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005145 | IRB | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-24 | Done
71005145 | IRB | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-25 | Done
71005153 | KST | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005153 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71005153 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005153 | KST | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71005153 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005153 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71005153 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-18 | Done late
71005153 | KST | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71005153 | KST | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005153 | KST | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71005153 | KST | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005156 | RVS | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-27 | Done
71005156 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-10 | Done late
71005156 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-13 | Done
71005156 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-01 | Done
71005156 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005156 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-18 |  | 2025-10-18 | Done
71005156 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-10-21 |  | 2025-10-20 | Done
71005156 | RVS | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005156 | RVS | 9 | Linking start | Factory | 2025-10-29 |  | 2025-10-28 | Done
71005156 | RVS | 10 | Final inspection | Karbar QA | 2025-12-01 |  | 2025-11-27 | Done
71005156 | RVS | 11 | Ex-factory | Factory | 2025-12-02 |  | 2025-11-29 | Done
71005160 | CLB | 1 | Yarn booking | Factory | 2025-09-17 |  | 2025-09-17 | Done
71005160 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-25 | Done
71005160 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-01 | Done
71005160 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-20 | Done
71005160 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005160 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-06 |  | 2025-11-06 | Done
71005160 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-11-09 |  | 2025-11-09 | Done
71005160 | CLB | 8 | Knitting start | Factory | 2025-11-11 |  | 2025-11-11 | Done
71005160 | CLB | 9 | Linking start | Factory | 2025-11-17 |  | 2025-11-16 | Done
71005160 | CLB | 10 | Final inspection | Karbar QA | 2025-12-20 |  | 2025-12-20 | Done
71005160 | CLB | 11 | Ex-factory | Factory | 2025-12-21 |  | 2025-12-21 | Done
71005169 | WTH | 1 | Yarn booking | Factory | 2025-09-20 |  | 2025-09-20 | Done
71005169 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-30 |  | 2025-10-02 | Done late
71005169 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-07 | Done late
71005169 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-23 | Done
71005169 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-03 | Done
71005169 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-09 |  | 2025-11-10 | Done late
71005169 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-11-12 |  | 2025-11-13 | Done late
71005169 | WTH | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005169 | WTH | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-18 | Done
71005169 | WTH | 10 | Final inspection | Karbar QA | 2025-12-23 |  | 2025-12-22 | Done
71005169 | WTH | 11 | Ex-factory | Factory | 2025-12-24 |  | 2025-12-23 | Done
71005177 | SLM | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-21 | Done
71005177 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-02 | Done
71005177 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005177 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-27 | Done
71005177 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005177 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71005177 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71005177 | SLM | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71005177 | SLM | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005177 | SLM | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-12-04 | Done late
71005177 | SLM | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-12-06 | Done late
71005185 | BLF | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-07 | Done
71005185 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-17 | Done
71005185 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-20 | Done
71005185 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-14 | Done late
71005185 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005185 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-27 | Done
71005185 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71005185 | BLF | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-01 | Done
71005185 | BLF | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005185 | BLF | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-10 | Done
71005185 | BLF | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005189 | BLF | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-09 | Done
71005189 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005189 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71005189 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-15 | Done late
71005189 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005189 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-29 | Done
71005189 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-11-01 | Done
71005189 | BLF | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71005189 | BLF | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-08 | Done
71005189 | BLF | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-10 | Done
71005189 | BLF | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-11 | Done
71005197 | IRB | 1 | Yarn booking | Factory | 2025-09-21 |  | 2025-09-21 | Done
71005197 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005197 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-08 | Done late
71005197 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-25 | Done
71005197 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005197 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-10 |  | 2025-11-10 | Done
71005197 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-11-13 |  | 2025-11-13 | Done
71005197 | IRB | 8 | Knitting start | Factory | 2025-11-15 |  | 2025-11-15 | Done
71005197 | IRB | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005197 | IRB | 10 | Final inspection | Karbar QA | 2025-12-24 |  | 2025-12-31 | Done late
71005197 | IRB | 11 | Ex-factory | Factory | 2025-12-25 |  | 2026-01-01 | Done late
71005202 | BRW | 1 | Yarn booking | Factory | 2025-09-21 |  | 2025-09-23 | Done late
71005202 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005202 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005202 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-23 | Done
71005202 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005202 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-10 |  | 2025-11-10 | Done
71005202 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-11-13 |  | 2025-11-13 | Done
71005202 | BRW | 8 | Knitting start | Factory | 2025-11-15 |  | 2025-11-15 | Done
71005202 | BRW | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005202 | BRW | 10 | Final inspection | Karbar QA | 2025-12-24 |  | 2025-12-24 | Done
71005202 | BRW | 11 | Ex-factory | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005207 | AMB | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-14 | Done
71005207 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71005207 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-28 | Done
71005207 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005207 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-30 | Done late
71005207 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-04 | Done late
71005207 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005207 | AMB | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-08 | Done
71005207 | AMB | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005207 | AMB | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-17 | Done
71005207 | AMB | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005216 | IRB | 1 | Yarn booking | Factory | 2025-09-18 |  | 2025-09-20 | Done late
71005216 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-30 | Done late
71005216 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-02 |  | 2025-09-30 | Done
71005216 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-25 | Done late
71005216 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-04 | Done late
71005216 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-06 |  | 2025-11-06 | Done
71005216 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-11-10 |  | 2025-11-09 | Done
71005216 | IRB | 8 | Knitting start | Factory | 2025-11-12 |  | 2025-11-12 | Done
71005216 | IRB | 9 | Linking start | Factory | 2025-11-18 |  | 2025-11-17 | Done
71005216 | IRB | 10 | Final inspection | Karbar QA | 2025-12-21 |  | 2025-12-21 | Done
71005216 | IRB | 11 | Ex-factory | Factory | 2025-12-22 |  | 2025-12-22 | Done
71005222 | CLB | 1 | Yarn booking | Factory | 2025-08-21 |  | 2025-08-21 | Done
71005222 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-01 |  | 2025-08-30 | Done
71005222 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-07 | Done late
71005222 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71005222 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005222 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-11 |  | 2025-10-12 | Done late
71005222 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-14 |  | 2025-10-15 | Done late
71005222 | CLB | 8 | Knitting start | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71005222 | CLB | 9 | Linking start | Factory | 2025-10-22 |  | 2025-10-23 | Done late
71005222 | CLB | 10 | Final inspection | Karbar QA | 2025-11-24 |  | 2025-11-23 | Done
71005222 | CLB | 11 | Ex-factory | Factory | 2025-11-25 |  | 2025-11-24 | Done
71005230 | SLM | 1 | Yarn booking | Factory | 2025-08-24 |  | 2025-08-24 | Done
71005230 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-03 |  | 2025-09-04 | Done late
71005230 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-10 | Done late
71005230 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-09-28 |  | 2025-09-27 | Done
71005230 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005230 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-13 |  | 2025-10-13 | Done
71005230 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-16 |  | 2025-10-16 | Done
71005230 | SLM | 8 | Knitting start | Factory | 2025-10-18 |  | 2025-10-19 | Done late
71005230 | SLM | 9 | Linking start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005230 | SLM | 10 | Final inspection | Karbar QA | 2025-11-26 |  | 2025-11-26 | Done
71005230 | SLM | 11 | Ex-factory | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005237 | OKH | 1 | Yarn booking | Factory | 2025-08-28 |  | 2025-08-27 | Done
71005237 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-08 |  | 2025-09-08 | Done
71005237 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-14 | Done late
71005237 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-04 | Done late
71005237 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005237 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-18 |  | 2025-10-21 | Done late
71005237 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-10-21 |  | 2025-10-19 | Done
71005237 | OKH | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005237 | OKH | 9 | Linking start | Factory | 2025-10-29 |  | 2025-10-28 | Done
71005237 | OKH | 10 | Final inspection | Karbar QA | 2025-12-01 |  | 2025-11-30 | Done
71005237 | OKH | 11 | Ex-factory | Factory | 2025-12-02 |  | 2025-12-01 | Done
71005241 | LTF | 1 | Yarn booking | Factory | 2025-09-03 |  | 2025-09-03 | Done
71005241 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-11 | Done
71005241 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005241 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-07 | Done
71005241 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-18 | Done
71005241 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-23 |  | 2025-10-23 | Done
71005241 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-10-26 |  | 2025-10-26 | Done
71005241 | LTF | 8 | Knitting start | Factory | 2025-10-28 |  | 2025-10-28 | Done
71005241 | LTF | 9 | Linking start | Factory | 2025-11-03 |  | 2025-11-02 | Done
71005241 | LTF | 10 | Final inspection | Karbar QA | 2025-12-06 |  | 2025-12-04 | Done
71005241 | LTF | 11 | Ex-factory | Factory | 2025-12-07 |  | 2025-12-06 | Done
71005247 | FNS | 1 | Yarn booking | Factory | 2025-09-16 |  | 2025-09-16 | Done
71005247 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-23 | Done
71005247 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005247 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-22 | Done late
71005247 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-29 | Done
71005247 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-05 |  | 2025-11-05 | Done
71005247 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-11-08 |  | 2025-11-06 | Done
71005247 | FNS | 8 | Knitting start | Factory | 2025-11-10 |  | 2025-11-10 | Done
71005247 | FNS | 9 | Linking start | Factory | 2025-11-16 |  | 2025-11-15 | Done
71005247 | FNS | 10 | Final inspection | Karbar QA | 2025-12-18 |  | 2025-12-18 | Done
71005247 | FNS | 11 | Ex-factory | Factory | 2025-12-20 |  | 2025-12-20 | Done
71005254 | SVP | 1 | Yarn booking | Factory | 2025-09-18 |  | 2025-09-18 | Done
71005254 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-27 | Done
71005254 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-06 | Done late
71005254 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-21 | Done
71005254 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005254 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-08 |  | 2025-11-06 | Done
71005254 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-11-11 |  | 2025-11-13 | Done late
71005254 | SVP | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005254 | SVP | 9 | Linking start | Factory | 2025-11-19 |  | 2025-11-18 | Done
71005254 | SVP | 10 | Final inspection | Karbar QA | 2025-12-22 |  | 2025-12-20 | Done
71005254 | SVP | 11 | Ex-factory | Factory | 2025-12-23 |  | 2025-12-21 | Done
71005258 | RVS | 1 | Yarn booking | Factory | 2025-09-21 |  | 2025-09-21 | Done
71005258 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005258 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-08 | Done late
71005258 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-26 | Done
71005258 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005258 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-10 |  | 2025-11-10 | Done
71005258 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-11-13 |  | 2025-11-15 | Done late
71005258 | RVS | 8 | Knitting start | Factory | 2025-11-15 |  | 2025-11-16 | Done late
71005258 | RVS | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005258 | RVS | 10 | Final inspection | Karbar QA | 2025-12-24 |  | 2025-12-24 | Done
71005258 | RVS | 11 | Ex-factory | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005265 | SVP | 1 | Yarn booking | Factory | 2025-09-23 |  | 2025-09-23 | Done
71005265 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71005265 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005265 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-10-28 |  | 2025-10-28 | Done
71005265 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005265 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-12 |  | 2025-11-15 | Done late
71005265 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-11-15 |  | 2025-11-15 | Done
71005265 | SVP | 8 | Knitting start | Factory | 2025-11-17 |  | 2025-11-17 | Done
71005265 | SVP | 9 | Linking start | Factory | 2025-11-23 |  | 2025-11-22 | Done
71005265 | SVP | 10 | Final inspection | Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71005265 | SVP | 11 | Ex-factory | Factory | 2025-12-27 |  | 2025-12-27 | Done
71005274 | GRL | 1 | Yarn booking | Factory | 2025-09-27 |  | 2025-09-25 | Done
71005274 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-07 | Done
71005274 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71005274 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-01 |  | 2025-10-30 | Done
71005274 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-11 | Done
71005274 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-16 |  | 2025-11-16 | Done
71005274 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-19 |  | 2025-11-19 | Done
71005274 | GRL | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-22 | Done late
71005274 | GRL | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005274 | GRL | 10 | Final inspection | Karbar QA | 2025-12-30 |  | 2026-01-06 | Done late
71005274 | GRL | 11 | Ex-factory | Factory | 2025-12-31 |  | 2026-01-07 | Done late
71005281 | HMR | 1 | Yarn booking | Factory | 2025-09-02 |  | 2025-08-31 | Done
71005281 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71005281 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-16 | Done
71005281 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-07 | Done
71005281 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-16 | Done
71005281 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-22 |  | 2025-10-22 | Done
71005281 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-10-25 |  | 2025-10-23 | Done
71005281 | HMR | 8 | Knitting start | Factory | 2025-10-27 |  | 2025-10-27 | Done
71005281 | HMR | 9 | Linking start | Factory | 2025-11-02 |  | 2025-11-01 | Done
71005281 | HMR | 10 | Final inspection | Karbar QA | 2025-12-04 |  | 2025-12-04 | Done
71005281 | HMR | 11 | Ex-factory | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005285 | AMB | 1 | Yarn booking | Factory | 2025-09-20 |  | 2025-09-18 | Done
71005285 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-30 |  | 2025-10-01 | Done late
71005285 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-02 | Done
71005285 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-25 | Done
71005285 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-05 | Done late
71005285 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-09 |  | 2025-11-09 | Done
71005285 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-12 |  | 2025-11-13 | Done late
71005285 | AMB | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005285 | AMB | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-18 | Done
71005285 | AMB | 10 | Final inspection | Karbar QA | 2025-12-23 |  | 2025-12-23 | Done
71005285 | AMB | 11 | Ex-factory | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005289 | SLM | 1 | Yarn booking | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71005289 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-07 | Done
71005289 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-09 | Done
71005289 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005289 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-12 | Done late
71005289 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-16 |  | 2025-11-17 | Done late
71005289 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-11-19 |  | 2025-11-20 | Done late
71005289 | SLM | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005289 | SLM | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-25 | Done
71005289 | SLM | 10 | Final inspection | Karbar QA | 2025-12-30 |  | 2025-12-30 | Done
71005289 | SLM | 11 | Ex-factory | Factory | 2025-12-31 |  | 2025-12-31 | Done
71005296 | SLM | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-08 | Done late
71005296 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-15 | Done
71005296 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-24 | Done late
71005296 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-11 | Done
71005296 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005296 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-26 | Done
71005296 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71005296 | SLM | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-02 | Done late
71005296 | SLM | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005296 | SLM | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-18 | Done late
71005296 | SLM | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-20 | Done late
71005302 | CLB | 1 | Yarn booking | Factory | 2025-08-27 |  | 2025-08-25 | Done
71005302 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-06 |  | 2025-09-06 | Done
71005302 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-11 |  | 2025-09-11 | Done
71005302 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-01 | Done
71005302 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-11 | Done
71005302 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-16 |  | 2025-10-14 | Done
71005302 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-10-19 |  | 2025-10-19 | Done
71005302 | CLB | 8 | Knitting start | Factory | 2025-10-21 |  | 2025-10-21 | Done
71005302 | CLB | 9 | Linking start | Factory | 2025-10-27 |  | 2025-10-26 | Done
71005302 | CLB | 10 | Final inspection | Karbar QA | 2025-11-29 |  | 2025-11-27 | Done
71005302 | CLB | 11 | Ex-factory | Factory | 2025-11-30 |  | 2025-11-29 | Done
71005310 | CPL | 1 | Yarn booking | Factory | 2025-08-30 |  | 2025-08-30 | Done
71005310 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-09 |  | 2025-09-09 | Done
71005310 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-14 |  | 2025-09-11 | Done
71005310 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-06 | Done late
71005310 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71005310 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-19 |  | 2025-10-21 | Done late
71005310 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-10-22 |  | 2025-10-21 | Done
71005310 | CPL | 8 | Knitting start | Factory | 2025-10-23 |  | 2025-10-25 | Done late
71005310 | CPL | 9 | Linking start | Factory | 2025-10-30 |  | 2025-10-30 | Done
71005310 | CPL | 10 | Final inspection | Karbar QA | 2025-12-02 |  | 2025-12-02 | Done
71005310 | CPL | 11 | Ex-factory | Factory | 2025-12-03 |  | 2025-12-03 | Done
71005319 | SVP | 1 | Yarn booking | Factory | 2025-09-17 |  | 2025-09-18 | Done late
71005319 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-28 | Done late
71005319 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-10-02 |  | 2025-10-02 | Done
71005319 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005319 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005319 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-06 |  | 2025-11-06 | Done
71005319 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-11-09 |  | 2025-11-10 | Done late
71005319 | SVP | 8 | Knitting start | Factory | 2025-11-11 |  | 2025-11-11 | Done
71005319 | SVP | 9 | Linking start | Factory | 2025-11-17 |  | 2025-11-16 | Done
71005319 | SVP | 10 | Final inspection | Karbar QA | 2025-12-20 |  | 2025-12-20 | Done
71005319 | SVP | 11 | Ex-factory | Factory | 2025-12-21 |  | 2025-12-21 | Done
71005323 | CPL | 1 | Yarn booking | Factory | 2025-09-23 |  | 2025-09-23 | Done
71005323 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-02 |  | 2025-09-30 | Done
71005323 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005323 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-10-28 |  | 2025-10-30 | Done late
71005323 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005323 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-12 |  | 2025-11-11 | Done
71005323 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-11-15 |  | 2025-11-16 | Done late
71005323 | CPL | 8 | Knitting start | Factory | 2025-11-17 |  | 2025-11-18 | Done late
71005323 | CPL | 9 | Linking start | Factory | 2025-11-23 |  | 2025-11-23 | Done
71005323 | CPL | 10 | Final inspection | Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71005323 | CPL | 11 | Ex-factory | Factory | 2025-12-27 |  | 2025-12-27 | Done
71005332 | OKH | 1 | Yarn booking | Factory | 2025-09-03 |  | 2025-09-04 | Done late
71005332 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-13 |  | 2025-09-11 | Done
71005332 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-17 | Done
71005332 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005332 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-20 | Done late
71005332 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-23 |  | 2025-10-23 | Done
71005332 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-10-26 |  | 2025-10-23 | Done
71005332 | OKH | 8 | Knitting start | Factory | 2025-10-28 |  | 2025-10-28 | Done
71005332 | OKH | 9 | Linking start | Factory | 2025-11-03 |  | 2025-11-02 | Done
71005332 | OKH | 10 | Final inspection | Karbar QA | 2025-12-06 |  | 2025-12-03 | Done
71005332 | OKH | 11 | Ex-factory | Factory | 2025-12-07 |  | 2025-12-04 | Done
71005337 | GRL | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-14 | Done
71005337 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-25 | Done late
71005337 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-28 | Done
71005337 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005337 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005337 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-04 | Done late
71005337 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005337 | GRL | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-09 | Done late
71005337 | GRL | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005337 | GRL | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-17 | Done
71005337 | GRL | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005344 | AMB | 1 | Yarn booking | Factory | 2025-09-20 |  | 2025-09-22 | Done late
71005344 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-29 | Done
71005344 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-05 | Done
71005344 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-27 | Done late
71005344 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-06 | Done late
71005344 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-09 |  | 2025-11-09 | Done
71005344 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-12 |  | 2025-11-12 | Done
71005344 | AMB | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005344 | AMB | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-18 | Done
71005344 | AMB | 10 | Final inspection | Karbar QA | 2025-12-23 |  | 2025-12-23 | Done
71005344 | AMB | 11 | Ex-factory | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005351 | MDW | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-28 | Done
71005351 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005351 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-14 | Done late
71005351 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-04 | Done late
71005351 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005351 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-17 | Done
71005351 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-20 | Done
71005351 | MDW | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-22 | Done
71005351 | MDW | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005351 | MDW | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005351 | MDW | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005356 | OKH | 1 | Yarn booking | Factory | 2025-10-07 |  | 2025-10-07 | Done
71005356 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-18 | Done late
71005356 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005356 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-09 | Done
71005356 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005356 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-26 |  | 2025-11-27 | Done late
71005356 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-11-29 |  | 2025-11-29 | Done
71005356 | OKH | 8 | Knitting start | Factory | 2025-12-01 |  | 2025-12-01 | Done
71005356 | OKH | 9 | Linking start | Factory | 2025-12-07 |  | 2025-12-06 | Done
71005356 | OKH | 10 | Final inspection | Karbar QA | 2026-01-08 |  | 2026-01-07 | Done
71005356 | OKH | 11 | Ex-factory | Factory | 2026-01-10 |  | 2026-01-08 | Done
71005365 | TLG | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-09 | Done
71005365 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-20 | Done late
71005365 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-24 | Done
71005365 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-15 | Done late
71005365 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005365 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-29 | Done
71005365 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-11-03 | Done late
71005365 | TLG | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71005365 | TLG | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-08 | Done
71005365 | TLG | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005365 | TLG | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005369 | GRL | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-09 | Done
71005369 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005369 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-25 | Done late
71005369 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71005369 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005369 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-11-01 | Done late
71005369 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-10-30 | Done
71005369 | GRL | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-03 | Done
71005369 | GRL | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-08 | Done
71005369 | GRL | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005369 | GRL | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005373 | AMB | 1 | Yarn booking | Factory | 2025-09-10 |  | 2025-09-10 | Done
71005373 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71005373 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71005373 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-13 | Done
71005373 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-26 | Done late
71005373 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-30 |  | 2025-11-01 | Done late
71005373 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-02 |  | 2025-11-02 | Done
71005373 | AMB | 8 | Knitting start | Factory | 2025-11-04 |  | 2025-11-04 | Done
71005373 | AMB | 9 | Linking start | Factory | 2025-11-10 |  | 2025-11-09 | Done
71005373 | AMB | 10 | Final inspection | Karbar QA | 2025-12-13 |  | 2025-12-13 | Done
71005373 | AMB | 11 | Ex-factory | Factory | 2025-12-14 |  | 2025-12-14 | Done
71005379 | BRW | 1 | Yarn booking | Factory | 2025-09-24 |  | 2025-09-24 | Done
71005379 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-06 | Done late
71005379 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71005379 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-27 | Done
71005379 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71005379 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-13 |  | 2025-11-13 | Done
71005379 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-11-16 |  | 2025-11-16 | Done
71005379 | BRW | 8 | Knitting start | Factory | 2025-11-18 |  | 2025-11-19 | Done late
71005379 | BRW | 9 | Linking start | Factory | 2025-11-24 |  | 2025-11-24 | Done
71005379 | BRW | 10 | Final inspection | Karbar QA | 2025-12-27 |  | 2025-12-27 | Done
71005379 | BRW | 11 | Ex-factory | Factory | 2025-12-28 |  | 2025-12-28 | Done
71005387 | CLB | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-11 | Done
71005387 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71005387 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-29 | Done
71005387 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005387 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005387 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-03 | Done
71005387 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005387 | CLB | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-08 | Done
71005387 | CLB | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005387 | CLB | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-17 | Done
71005387 | CLB | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005394 | IRB | 1 | Yarn booking | Factory | 2025-09-16 |  | 2025-09-16 | Done
71005394 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-23 | Done
71005394 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-01 |  | 2025-09-30 | Done
71005394 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-19 | Done
71005394 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005394 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-05 |  | 2025-11-06 | Done late
71005394 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-11-08 |  | 2025-11-08 | Done
71005394 | IRB | 8 | Knitting start | Factory | 2025-11-10 |  | 2025-11-11 | Done late
71005394 | IRB | 9 | Linking start | Factory | 2025-11-16 |  | 2025-11-16 | Done
71005394 | IRB | 10 | Final inspection | Karbar QA | 2025-12-18 |  | 2025-12-17 | Done
71005394 | IRB | 11 | Ex-factory | Factory | 2025-12-20 |  | 2025-12-18 | Done
71005403 | FNS | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-28 | Done
71005403 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005403 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-14 | Done late
71005403 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-10-30 | Done
71005403 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005403 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-18 | Done late
71005403 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-20 | Done
71005403 | FNS | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-23 | Done late
71005403 | FNS | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005403 | FNS | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005403 | FNS | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005412 | GRL | 1 | Yarn booking | Factory | 2025-10-02 |  | 2025-10-01 | Done
71005412 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-12 | Done
71005412 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-16 | Done
71005412 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-05 | Done
71005412 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-17 | Done
71005412 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-22 |  | 2025-11-23 | Done late
71005412 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-25 |  | 2025-11-26 | Done late
71005412 | GRL | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005412 | GRL | 9 | Linking start | Factory | 2025-12-03 |  | 2025-12-02 | Done
71005412 | GRL | 10 | Final inspection | Karbar QA | 2026-01-05 |  | 2026-01-01 | Done
71005412 | GRL | 11 | Ex-factory | Factory | 2026-01-06 |  | 2026-01-03 | Done
71005421 | LTF | 1 | Yarn booking | Factory | 2025-09-10 |  | 2025-09-11 | Done late
71005421 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-22 | Done late
71005421 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-25 | Done
71005421 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-15 | Done
71005421 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-25 | Done
71005421 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-30 |  | 2025-10-30 | Done
71005421 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-11-02 |  | 2025-11-02 | Done
71005421 | LTF | 8 | Knitting start | Factory | 2025-11-04 |  | 2025-11-04 | Done
71005421 | LTF | 9 | Linking start | Factory | 2025-11-10 |  | 2025-11-09 | Done
71005421 | LTF | 10 | Final inspection | Karbar QA | 2025-12-13 |  | 2025-12-13 | Done
71005421 | LTF | 11 | Ex-factory | Factory | 2025-12-14 |  | 2025-12-14 | Done
71005427 | WSM | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-13 | Done
71005427 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-25 | Done late
71005427 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-28 | Done
71005427 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005427 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005427 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-03 | Done
71005427 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-05 | Done
71005427 | WSM | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-08 | Done
71005427 | WSM | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005427 | WSM | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-17 | Done
71005427 | WSM | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005430 | WSM | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-25 | Done
71005430 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005430 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005430 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71005430 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005430 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-17 | Done
71005430 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-22 | Done late
71005430 | WSM | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-22 | Done
71005430 | WSM | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005430 | WSM | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005430 | WSM | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005438 | GRL | 1 | Yarn booking | Factory | 2025-10-04 |  | 2025-10-05 | Done late
71005438 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-12 | Done
71005438 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005438 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-09 | Done late
71005438 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-19 | Done late
71005438 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-23 |  | 2025-11-25 | Done late
71005438 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-26 |  | 2025-11-27 | Done late
71005438 | GRL | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005438 | GRL | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-02 | Done
71005438 | GRL | 10 | Final inspection | Karbar QA | 2026-01-06 |  | 2026-01-06 | Done
71005438 | GRL | 11 | Ex-factory | Factory | 2026-01-07 |  | 2026-01-07 | Done
71005446 | RVS | 1 | Yarn booking | Factory | 2025-09-09 |  | 2025-09-11 | Done late
71005446 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-18 |  | 2025-09-18 | Done
71005446 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-22 | Done
71005446 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-14 | Done
71005446 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005446 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-29 |  | 2025-10-27 | Done
71005446 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-11-01 |  | 2025-11-02 | Done late
71005446 | RVS | 8 | Knitting start | Factory | 2025-11-03 |  | 2025-11-04 | Done late
71005446 | RVS | 9 | Linking start | Factory | 2025-11-09 |  | 2025-11-09 | Done
71005446 | RVS | 10 | Final inspection | Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005446 | RVS | 11 | Ex-factory | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005454 | WTH | 1 | Yarn booking | Factory | 2025-09-18 |  | 2025-09-18 | Done
71005454 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-29 | Done
71005454 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-04 | Done
71005454 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005454 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-05 | Done late
71005454 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-08 |  | 2025-11-10 | Done late
71005454 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-11-11 |  | 2025-11-13 | Done late
71005454 | WTH | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005454 | WTH | 9 | Linking start | Factory | 2025-11-19 |  | 2025-11-18 | Done
71005454 | WTH | 10 | Final inspection | Karbar QA | 2025-12-22 |  | 2025-12-24 | Done late
71005454 | WTH | 11 | Ex-factory | Factory | 2025-12-23 |  | 2025-12-25 | Done late
71005461 | GRL | 1 | Yarn booking | Factory | 2025-09-30 |  | 2025-09-30 | Done
71005461 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-11 | Done late
71005461 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-16 | Done late
71005461 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-04 | Done
71005461 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-12 | Done
71005461 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-19 |  | 2025-11-22 | Done late
71005461 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-22 |  | 2025-11-22 | Done
71005461 | GRL | 8 | Knitting start | Factory | 2025-11-24 |  | 2025-11-24 | Done
71005461 | GRL | 9 | Linking start | Factory | 2025-11-30 |  | 2025-11-29 | Done
71005461 | GRL | 10 | Final inspection | Karbar QA | 2026-01-01 |  | 2025-12-31 | Done
71005461 | GRL | 11 | Ex-factory | Factory | 2026-01-03 |  | 2026-01-01 | Done
71005470 | RVS | 1 | Yarn booking | Factory | 2025-10-02 |  | 2025-10-01 | Done
71005470 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71005470 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-14 | Done
71005470 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005470 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-15 | Done
71005470 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-20 |  | 2025-11-20 | Done
71005470 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-11-24 |  | 2025-11-24 | Done
71005470 | RVS | 8 | Knitting start | Factory | 2025-11-26 |  | 2025-11-26 | Done
71005470 | RVS | 9 | Linking start | Factory | 2025-12-02 |  | 2025-12-01 | Done
71005470 | RVS | 10 | Final inspection | Karbar QA | 2026-01-04 |  | 2025-12-31 | Done
71005470 | RVS | 11 | Ex-factory | Factory | 2026-01-05 |  | 2026-01-01 | Done
71005479 | SLM | 1 | Yarn booking | Factory | 2025-09-07 |  | 2025-09-09 | Done late
71005479 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-17 |  | 2025-09-18 | Done late
71005479 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71005479 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-09 | Done
71005479 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005479 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-27 |  | 2025-10-29 | Done late
71005479 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-10-30 |  | 2025-10-30 | Done
71005479 | SLM | 8 | Knitting start | Factory | 2025-11-01 |  | 2025-11-02 | Done late
71005479 | SLM | 9 | Linking start | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005479 | SLM | 10 | Final inspection | Karbar QA | 2025-12-10 |  | 2025-12-22 | Done late
71005479 | SLM | 11 | Ex-factory | Factory | 2025-12-11 |  | 2025-12-23 | Done late
71005487 | OKH | 1 | Yarn booking | Factory | 2025-09-10 |  | 2025-09-10 | Done
71005487 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-20 |  | 2025-09-20 | Done
71005487 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-09-25 |  | 2025-09-27 | Done late
71005487 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-15 | Done
71005487 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-27 | Done late
71005487 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-10-30 |  | 2025-10-30 | Done
71005487 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-11-02 |  | 2025-11-02 | Done
71005487 | OKH | 8 | Knitting start | Factory | 2025-11-04 |  | 2025-11-05 | Done late
71005487 | OKH | 9 | Linking start | Factory | 2025-11-10 |  | 2025-11-10 | Done
71005487 | OKH | 10 | Final inspection | Karbar QA | 2025-12-13 |  | 2025-12-13 | Done
71005487 | OKH | 11 | Ex-factory | Factory | 2025-12-14 |  | 2025-12-14 | Done
71005493 | SND | 1 | Yarn booking | Factory | 2025-10-05 |  | 2025-10-04 | Done
71005493 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-14 | Done
71005493 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-20 | Done
71005493 | SND | 4 | Size set approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-10 | Done late
71005493 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005493 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-24 |  | 2025-11-25 | Done late
71005493 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71005493 | SND | 8 | Knitting start | Factory | 2025-11-29 |  | 2025-11-30 | Done late
71005493 | SND | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005493 | SND | 10 | Final inspection | Karbar QA | 2026-01-07 |  | 2026-01-06 | Done
71005493 | SND | 11 | Ex-factory | Factory | 2026-01-08 |  | 2026-01-07 | Done
71005501 | GRL | 1 | Yarn booking | Factory | 2025-10-07 |  | 2025-10-09 | Done late
71005501 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-18 | Done late
71005501 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005501 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-11 | Done
71005501 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005501 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-26 |  | 2025-11-24 | Done
71005501 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-29 |  | 2025-11-27 | Done
71005501 | GRL | 8 | Knitting start | Factory | 2025-12-01 |  | 2025-12-01 | Done
71005501 | GRL | 9 | Linking start | Factory | 2025-12-07 |  | 2025-12-06 | Done
71005501 | GRL | 10 | Final inspection | Karbar QA | 2026-01-08 |  | 2026-01-08 | Done
71005501 | GRL | 11 | Ex-factory | Factory | 2026-01-10 |  | 2026-01-10 | Done
71005504 | WSM | 1 | Yarn booking | Factory | 2025-09-11 |  | 2025-09-13 | Done late
71005504 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-22 |  | 2025-09-22 | Done
71005504 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-09-27 |  | 2025-09-27 | Done
71005504 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-16 | Done
71005504 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-27 | Done
71005504 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-01 |  | 2025-11-03 | Done late
71005504 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-04 |  | 2025-11-06 | Done late
71005504 | WSM | 8 | Knitting start | Factory | 2025-11-06 |  | 2025-11-08 | Done late
71005504 | WSM | 9 | Linking start | Factory | 2025-11-12 |  | 2025-11-13 | Done late
71005504 | WSM | 10 | Final inspection | Karbar QA | 2025-12-15 |  | 2025-12-11 | Done
71005504 | WSM | 11 | Ex-factory | Factory | 2025-12-16 |  | 2025-12-13 | Done
71005511 | WTH | 1 | Yarn booking | Factory | 2025-09-25 |  | 2025-09-25 | Done
71005511 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-07 | Done late
71005511 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-13 | Done late
71005511 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005511 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-12 | Done late
71005511 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-15 |  | 2025-11-15 | Done
71005511 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-11-18 |  | 2025-11-20 | Done late
71005511 | WTH | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-22 | Done late
71005511 | WTH | 9 | Linking start | Factory | 2025-11-26 |  | 2025-11-27 | Done late
71005511 | WTH | 10 | Final inspection | Karbar QA | 2025-12-29 |  | 2025-12-31 | Done late
71005511 | WTH | 11 | Ex-factory | Factory | 2025-12-30 |  | 2026-01-01 | Done late
71005520 | AMB | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-29 | Done late
71005520 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005520 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-14 | Done late
71005520 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-10-30 | Done
71005520 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71005520 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-15 | Done
71005520 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-18 | Done
71005520 | AMB | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-22 | Done
71005520 | AMB | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005520 | AMB | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-29 | Done
71005520 | AMB | 11 | Ex-factory | Factory | 2026-01-01 |  | 2025-12-30 | Done
71005524 | LTF | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-28 | Done
71005524 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005524 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005524 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71005524 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71005524 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-18 | Done late
71005524 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-19 | Done
71005524 | LTF | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-23 | Done late
71005524 | LTF | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005524 | LTF | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2026-01-03 | Done late
71005524 | LTF | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-04 | Done late
71005531 | MDW | 1 | Yarn booking | Factory | 2025-10-02 |  | 2025-10-02 | Done
71005531 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-11 | Done
71005531 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-16 | Done
71005531 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-05 | Done
71005531 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-17 | Done
71005531 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-22 |  | 2025-11-20 | Done
71005531 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-11-25 |  | 2025-11-25 | Done
71005531 | MDW | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-29 | Done late
71005531 | MDW | 9 | Linking start | Factory | 2025-12-03 |  | 2025-12-04 | Done late
71005531 | MDW | 10 | Final inspection | Karbar QA | 2026-01-05 |  | 2026-01-05 | Done
71005531 | MDW | 11 | Ex-factory | Factory | 2026-01-06 |  | 2026-01-06 | Done
71005539 | SVP | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-16 | Done late
71005539 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71005539 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-10-01 | Done late
71005539 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005539 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-30 | Done late
71005539 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-01 | Done
71005539 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005539 | SVP | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-09 | Done late
71005539 | SVP | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005539 | SVP | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-17 | Done
71005539 | SVP | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005547 | RVS | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-14 | Done
71005547 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71005547 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-29 | Done
71005547 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005547 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-30 | Done late
71005547 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-01 | Done
71005547 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-04 | Done
71005547 | RVS | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-09 | Done late
71005547 | RVS | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005547 | RVS | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-14 | Done
71005547 | RVS | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-15 | Done
71005552 | RSG | 1 | Yarn booking | Factory | 2025-09-18 |  | 2025-09-18 | Done
71005552 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-29 |  | 2025-10-01 | Done late
71005552 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-04 |  | 2025-10-04 | Done
71005552 | RSG | 4 | Size set approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005552 | RSG | 5 | PP sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-02 | Done
71005552 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-08 |  | 2025-11-08 | Done
71005552 | RSG | 7 | PP meeting | Factory + Karbar QA | 2025-11-11 |  | 2025-11-09 | Done
71005552 | RSG | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-15 | Done late
71005552 | RSG | 9 | Linking start | Factory | 2025-11-19 |  | 2025-11-20 | Done late
71005552 | RSG | 10 | Final inspection | Karbar QA | 2025-12-22 |  | 2025-12-22 | Done
71005552 | RSG | 11 | Ex-factory | Factory | 2025-12-23 |  | 2025-12-23 | Done
71005557 | SLM | 1 | Yarn booking | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71005557 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-07 | Done
71005557 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-14 | Done late
71005557 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-01 |  | 2025-10-30 | Done
71005557 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-12 | Done late
71005557 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-16 |  | 2025-11-17 | Done late
71005557 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-11-19 |  | 2025-11-19 | Done
71005557 | SLM | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005557 | SLM | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-25 | Done
71005557 | SLM | 10 | Final inspection | Karbar QA | 2025-12-30 |  | 2025-12-30 | Done
71005557 | SLM | 11 | Ex-factory | Factory | 2025-12-31 |  | 2025-12-31 | Done
71005565 | SLM | 1 | Yarn booking | Factory | 2025-10-09 |  | 2025-10-11 | Done late
71005565 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-20 | Done late
71005565 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-21 | Done
71005565 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-13 | Done
71005565 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005565 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-27 |  | 2025-11-27 | Done
71005565 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-12-01 |  | 2025-12-01 | Done
71005565 | SLM | 8 | Knitting start | Factory | 2025-12-03 |  | 2025-12-04 | Done late
71005565 | SLM | 9 | Linking start | Factory | 2025-12-09 |  | 2025-12-09 | Done
71005565 | SLM | 10 | Final inspection | Karbar QA | 2026-01-11 |  | 2026-01-07 | Done
71005565 | SLM | 11 | Ex-factory | Factory | 2026-01-12 |  | 2026-01-08 | Done
71005568 | SLM | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-16 | Done
71005568 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-23 | Done
71005568 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005568 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005568 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71005568 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-04 |  | 2025-12-04 | Done
71005568 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-12-08 |  | 2025-12-07 | Done
71005568 | SLM | 8 | Knitting start | Factory | 2025-12-10 |  | 2025-12-10 | Done
71005568 | SLM | 9 | Linking start | Factory | 2025-12-16 |  | 2025-12-15 | Done
71005568 | SLM | 10 | Final inspection | Karbar QA | 2026-01-18 |  | 2026-01-18 | Done
71005568 | SLM | 11 | Ex-factory | Factory | 2026-01-19 |  | 2026-01-19 | Done
71005575 | SVP | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-27 | Done
71005575 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-09 | Done late
71005575 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005575 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71005575 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-11 | Done
71005575 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-17 | Done
71005575 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-20 | Done
71005575 | SVP | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-23 | Done late
71005575 | SVP | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005575 | SVP | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005575 | SVP | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005580 | LTF | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71005580 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-28 | Done late
71005580 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-10-30 | Done
71005580 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-22 | Done late
71005580 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71005580 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-06 |  | 2025-12-06 | Done
71005580 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-09 |  | 2025-12-09 | Done
71005580 | LTF | 8 | Knitting start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005580 | LTF | 9 | Linking start | Factory | 2025-12-17 |  | 2025-12-16 | Done
71005580 | LTF | 10 | Final inspection | Karbar QA | 2026-01-19 |  | 2026-01-19 | Done
71005580 | LTF | 11 | Ex-factory | Factory | 2026-01-20 |  | 2026-01-20 | Done
71005588 | CPL | 1 | Yarn booking | Factory | 2025-10-05 |  | 2025-10-06 | Done late
71005588 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-16 | Done late
71005588 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-20 | Done
71005588 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-09 | Done
71005588 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005588 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-24 |  | 2025-11-24 | Done
71005588 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71005588 | CPL | 8 | Knitting start | Factory | 2025-11-29 |  | 2025-11-29 | Done
71005588 | CPL | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005588 | CPL | 10 | Final inspection | Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71005588 | CPL | 11 | Ex-factory | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005595 | GRL | 1 | Yarn booking | Factory | 2025-10-09 |  | 2025-10-09 | Done
71005595 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-22 | Done late
71005595 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-26 | Done late
71005595 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-15 | Done late
71005595 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71005595 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-29 |  | 2025-11-27 | Done
71005595 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-02 |  | 2025-12-02 | Done
71005595 | GRL | 8 | Knitting start | Factory | 2025-12-04 |  | 2025-12-06 | Done late
71005595 | GRL | 9 | Linking start | Factory | 2025-12-10 |  | 2025-12-11 | Done late
71005595 | GRL | 10 | Final inspection | Karbar QA | 2026-01-12 |  | 2026-01-12 | Done
71005595 | GRL | 11 | Ex-factory | Factory | 2026-01-13 |  | 2026-01-13 | Done
71005601 | SLM | 1 | Yarn booking | Factory | 2025-09-27 |  | 2025-09-28 | Done late
71005601 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-07 |  | 2025-10-09 | Done late
71005601 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-12 |  | 2025-10-12 | Done
71005601 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-01 |  | 2025-10-30 | Done
71005601 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-11 |  | 2025-11-11 | Done
71005601 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-16 |  | 2025-11-13 | Done
71005601 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-11-19 |  | 2025-11-18 | Done
71005601 | SLM | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005601 | SLM | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-25 | Done
71005601 | SLM | 10 | Final inspection | Karbar QA | 2025-12-30 |  | 2025-12-31 | Done late
71005601 | SLM | 11 | Ex-factory | Factory | 2025-12-31 |  | 2026-01-01 | Done late
71005605 | HMR | 1 | Yarn booking | Factory | 2025-10-04 |  | 2025-10-02 | Done
71005605 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-16 | Done late
71005605 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005605 | HMR | 4 | Size set approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71005605 | HMR | 5 | PP sample approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-19 | Done late
71005605 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-23 |  | 2025-11-24 | Done late
71005605 | HMR | 7 | PP meeting | Factory + Karbar QA | 2025-11-26 |  | 2025-11-27 | Done late
71005605 | HMR | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005605 | HMR | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-02 | Done
71005605 | HMR | 10 | Final inspection | Karbar QA | 2026-01-06 |  | 2026-01-06 | Done
71005605 | HMR | 11 | Ex-factory | Factory | 2026-01-07 |  | 2026-01-07 | Done
71005609 | KST | 1 | Yarn booking | Factory | 2025-10-22 |  | 2025-10-23 | Done late
71005609 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005609 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-04 | Done
71005609 | KST | 4 | Size set approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-27 | Done late
71005609 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-06 | Done
71005609 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-11 |  | 2025-12-11 | Done
71005609 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-12-14 |  | 2025-12-11 | Done
71005609 | KST | 8 | Knitting start | Factory | 2025-12-16 |  | 2025-12-16 | Done
71005609 | KST | 9 | Linking start | Factory | 2025-12-22 |  | 2025-12-21 | Done
71005609 | KST | 10 | Final inspection | Karbar QA | 2026-01-24 |  | 2026-01-24 | Done
71005609 | KST | 11 | Ex-factory | Factory | 2026-01-25 |  | 2026-01-25 | Done
71005613 | SND | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-28 | Done
71005613 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-08 | Done
71005613 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005613 | SND | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71005613 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005613 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-18 | Done late
71005613 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-22 | Done late
71005613 | SND | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-22 | Done
71005613 | SND | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005613 | SND | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005613 | SND | 11 | Ex-factory | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005618 | OKH | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-16 | Done
71005618 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-30 | Done late
71005618 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005618 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005618 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-02 | Done
71005618 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-07 | Done
71005618 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005618 | OKH | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-14 | Done late
71005618 | OKH | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005618 | OKH | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-22 | Done late
71005618 | OKH | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-24 | Done late
71005627 | SND | 1 | Yarn booking | Factory | 2025-09-14 |  | 2025-09-15 | Done late
71005627 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-24 |  | 2025-09-23 | Done
71005627 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-09-29 |  | 2025-09-27 | Done
71005627 | SND | 4 | Size set approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-19 | Done
71005627 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005627 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-03 |  | 2025-11-03 | Done
71005627 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-06 |  | 2025-11-06 | Done
71005627 | SND | 8 | Knitting start | Factory | 2025-11-08 |  | 2025-11-09 | Done late
71005627 | SND | 9 | Linking start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005627 | SND | 10 | Final inspection | Karbar QA | 2025-12-17 |  | 2025-12-15 | Done
71005627 | SND | 11 | Ex-factory | Factory | 2025-12-18 |  | 2025-12-16 | Done
71005633 | WTH | 1 | Yarn booking | Factory | 2025-09-25 |  | 2025-09-25 | Done
71005633 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-04 | Done
71005633 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71005633 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-10-30 |  | 2025-11-01 | Done late
71005633 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-09 | Done
71005633 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-13 |  | 2025-11-13 | Done
71005633 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-11-17 |  | 2025-11-17 | Done
71005633 | WTH | 8 | Knitting start | Factory | 2025-11-19 |  | 2025-11-19 | Done
71005633 | WTH | 9 | Linking start | Factory | 2025-11-25 |  | 2025-11-24 | Done
71005633 | WTH | 10 | Final inspection | Karbar QA | 2025-12-28 |  | 2025-12-28 | Done
71005633 | WTH | 11 | Ex-factory | Factory | 2025-12-29 |  | 2025-12-29 | Done
71005638 | RSG | 1 | Yarn booking | Factory | 2025-09-25 |  | 2025-09-24 | Done
71005638 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005638 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-11 | Done
71005638 | RSG | 4 | Size set approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005638 | RSG | 5 | PP sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-10 | Done
71005638 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-15 |  | 2025-11-15 | Done
71005638 | RSG | 7 | PP meeting | Factory + Karbar QA | 2025-11-18 |  | 2025-11-18 | Done
71005638 | RSG | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005638 | RSG | 9 | Linking start | Factory | 2025-11-26 |  | 2025-11-25 | Done
71005638 | RSG | 10 | Final inspection | Karbar QA | 2025-12-29 |  | 2026-01-01 | Done late
71005638 | RSG | 11 | Ex-factory | Factory | 2025-12-30 |  | 2026-01-03 | Done late
71005646 | SND | 1 | Yarn booking | Factory | 2025-09-30 |  | 2025-09-30 | Done
71005646 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-09 | Done
71005646 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-13 | Done
71005646 | SND | 4 | Size set approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-04 | Done
71005646 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-12 | Done
71005646 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-19 |  | 2025-11-19 | Done
71005646 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-22 |  | 2025-11-22 | Done
71005646 | SND | 8 | Knitting start | Factory | 2025-11-24 |  | 2025-11-24 | Done
71005646 | SND | 9 | Linking start | Factory | 2025-11-30 |  | 2025-11-29 | Done
71005646 | SND | 10 | Final inspection | Karbar QA | 2026-01-01 |  | 2026-01-01 | Done
71005646 | SND | 11 | Ex-factory | Factory | 2026-01-03 |  | 2026-01-03 | Done
71005654 | TLG | 1 | Yarn booking | Factory | 2025-10-08 |  | 2025-10-06 | Done
71005654 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-20 | Done late
71005654 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005654 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005654 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-11-22 |  | 2025-11-22 | Done
71005654 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-27 |  | 2025-11-27 | Done
71005654 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-11-30 |  | 2025-11-30 | Done
71005654 | TLG | 8 | Knitting start | Factory | 2025-12-02 |  | 2025-12-02 | Done
71005654 | TLG | 9 | Linking start | Factory | 2025-12-08 |  | 2025-12-07 | Done
71005654 | TLG | 10 | Final inspection | Karbar QA | 2026-01-10 |  | 2026-01-10 | Done
71005654 | TLG | 11 | Ex-factory | Factory | 2026-01-11 |  | 2026-01-11 | Done
71005658 | GRL | 1 | Yarn booking | Factory | 2025-09-21 |  | 2025-09-21 | Done
71005658 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71005658 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005658 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-26 | Done
71005658 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005658 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-10 |  | 2025-11-10 | Done
71005658 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-13 |  | 2025-11-15 | Done late
71005658 | GRL | 8 | Knitting start | Factory | 2025-11-15 |  | 2025-11-16 | Done late
71005658 | GRL | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005658 | GRL | 10 | Final inspection | Karbar QA | 2025-12-24 |  | 2025-12-24 | Done
71005658 | GRL | 11 | Ex-factory | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005665 | IRB | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-20 | Done late
71005665 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005665 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005665 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005665 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005665 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-11 | Done late
71005665 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005665 | IRB | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005665 | IRB | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005665 | IRB | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-25 | Done late
71005665 | IRB | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-26 | Done late
71005673 | LTF | 1 | Yarn booking | Factory | 2025-10-21 |  | 2025-10-23 | Done late
71005673 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-30 |  | 2025-11-01 | Done late
71005673 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005673 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-26 | Done late
71005673 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-03 | Done
71005673 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-10 |  | 2025-12-08 | Done
71005673 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-13 |  | 2025-12-11 | Done
71005673 | LTF | 8 | Knitting start | Factory | 2025-12-15 |  | 2025-12-15 | Done
71005673 | LTF | 9 | Linking start | Factory | 2025-12-21 |  | 2025-12-20 | Done
71005673 | LTF | 10 | Final inspection | Karbar QA | 2026-01-22 |  | 2026-01-22 | Done
71005673 | LTF | 11 | Ex-factory | Factory | 2026-01-24 |  | 2026-01-24 | Done
71005678 | TLG | 1 | Yarn booking | Factory | 2025-09-28 |  | 2025-09-27 | Done
71005678 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-08 |  | 2025-10-07 | Done
71005678 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-11 | Done
71005678 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71005678 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005678 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-17 |  | 2025-11-16 | Done
71005678 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-11-20 |  | 2025-11-20 | Done
71005678 | TLG | 8 | Knitting start | Factory | 2025-11-22 |  | 2025-11-23 | Done late
71005678 | TLG | 9 | Linking start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005678 | TLG | 10 | Final inspection | Karbar QA | 2025-12-31 |  | 2025-12-29 | Done
71005678 | TLG | 11 | Ex-factory | Factory | 2026-01-01 |  | 2025-12-30 | Done
71005686 | PBB | 1 | Yarn booking | Factory | 2025-09-30 |  | 2025-09-28 | Done
71005686 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-11 | Done late
71005686 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-15 | Done
71005686 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-02 | Done
71005686 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-15 | Done late
71005686 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-19 |  | 2025-11-19 | Done
71005686 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-11-22 |  | 2025-11-20 | Done
71005686 | PBB | 8 | Knitting start | Factory | 2025-11-24 |  | 2025-11-24 | Done
71005686 | PBB | 9 | Linking start | Factory | 2025-11-30 |  | 2025-11-29 | Done
71005686 | PBB | 10 | Final inspection | Karbar QA | 2026-01-01 |  | 2026-01-01 | Done
71005686 | PBB | 11 | Ex-factory | Factory | 2026-01-03 |  | 2026-01-03 | Done
71005693 | WSM | 1 | Yarn booking | Factory | 2025-09-21 |  | 2025-09-21 | Done
71005693 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-01 |  | 2025-10-02 | Done late
71005693 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005693 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-26 | Done
71005693 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-06 | Done late
71005693 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-10 |  | 2025-11-11 | Done late
71005693 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-13 |  | 2025-11-15 | Done late
71005693 | WSM | 8 | Knitting start | Factory | 2025-11-15 |  | 2025-11-15 | Done
71005693 | WSM | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005693 | WSM | 10 | Final inspection | Karbar QA | 2025-12-24 |  | 2025-12-24 | Done
71005693 | WSM | 11 | Ex-factory | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005698 | GRL | 1 | Yarn booking | Factory | 2025-10-22 |  | 2025-10-22 | Done
71005698 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005698 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005698 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-25 | Done
71005698 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-07 | Done late
71005698 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-11 |  | 2025-12-10 | Done
71005698 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-14 |  | 2025-12-15 | Done late
71005698 | GRL | 8 | Knitting start | Factory | 2025-12-16 |  | 2025-12-17 | Done late
71005698 | GRL | 9 | Linking start | Factory | 2025-12-22 |  | 2025-12-22 | Done
71005698 | GRL | 10 | Final inspection | Karbar QA | 2026-01-24 |  | 2026-01-24 | Done
71005698 | GRL | 11 | Ex-factory | Factory | 2026-01-25 |  | 2026-01-25 | Done
71005703 | RSG | 1 | Yarn booking | Factory | 2025-09-20 |  | 2025-09-22 | Done late
71005703 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-09-30 |  | 2025-09-30 | Done
71005703 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-04 | Done
71005703 | RSG | 4 | Size set approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-27 | Done late
71005703 | RSG | 5 | PP sample approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-04 | Done
71005703 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-09 |  | 2025-11-09 | Done
71005703 | RSG | 7 | PP meeting | Factory + Karbar QA | 2025-11-12 |  | 2025-11-12 | Done
71005703 | RSG | 8 | Knitting start | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005703 | RSG | 9 | Linking start | Factory | 2025-11-20 |  | 2025-11-18 | Done
71005703 | RSG | 10 | Final inspection | Karbar QA | 2025-12-23 |  | 2025-12-23 | Done
71005703 | RSG | 11 | Ex-factory | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005709 | KST | 1 | Yarn booking | Factory | 2025-10-02 |  | 2025-10-02 | Done
71005709 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-13 |  | 2025-10-13 | Done
71005709 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-16 | Done
71005709 | KST | 4 | Size set approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005709 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-17 | Done
71005709 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-22 |  | 2025-11-22 | Done
71005709 | KST | 7 | PP meeting | Factory + Karbar QA | 2025-11-25 |  | 2025-11-23 | Done
71005709 | KST | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005709 | KST | 9 | Linking start | Factory | 2025-12-03 |  | 2025-12-02 | Done
71005709 | KST | 10 | Final inspection | Karbar QA | 2026-01-05 |  | 2026-01-06 | Done late
71005709 | KST | 11 | Ex-factory | Factory | 2026-01-06 |  | 2026-01-07 | Done late
71005717 | MDW | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-20 | Done late
71005717 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005717 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-01 | Done
71005717 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005717 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71005717 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-10 | Done late
71005717 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005717 | MDW | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-14 | Done late
71005717 | MDW | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005717 | MDW | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005717 | MDW | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005723 | IRB | 1 | Yarn booking | Factory | 2025-09-25 |  | 2025-09-24 | Done
71005723 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-06 |  | 2025-10-06 | Done
71005723 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-11 | Done
71005723 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005723 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-10 | Done
71005723 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-15 |  | 2025-11-15 | Done
71005723 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-11-18 |  | 2025-11-17 | Done
71005723 | IRB | 8 | Knitting start | Factory | 2025-11-20 |  | 2025-11-20 | Done
71005723 | IRB | 9 | Linking start | Factory | 2025-11-26 |  | 2025-11-25 | Done
71005723 | IRB | 10 | Final inspection | Karbar QA | 2025-12-29 |  | 2026-01-04 | Done late
71005723 | IRB | 11 | Ex-factory | Factory | 2025-12-30 |  | 2026-01-05 | Done late
71005727 | GRL | 1 | Yarn booking | Factory | 2025-10-01 |  | 2025-10-01 | Done
71005727 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-11 |  | 2025-10-09 | Done
71005727 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-16 |  | 2025-10-16 | Done
71005727 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-06 | Done late
71005727 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-16 | Done late
71005727 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-20 |  | 2025-11-20 | Done
71005727 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-11-23 |  | 2025-11-20 | Done
71005727 | GRL | 8 | Knitting start | Factory | 2025-11-25 |  | 2025-11-26 | Done late
71005727 | GRL | 9 | Linking start | Factory | 2025-12-01 |  | 2025-12-01 | Done
71005727 | GRL | 10 | Final inspection | Karbar QA | 2026-01-03 |  | 2026-01-10 | Done late
71005727 | GRL | 11 | Ex-factory | Factory | 2026-01-04 |  | 2026-01-11 | Done late
71005731 | SLM | 1 | Yarn booking | Factory | 2025-10-05 |  | 2025-10-05 | Done
71005731 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-13 | Done
71005731 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-19 | Done
71005731 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-08 | Done
71005731 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-19 | Done
71005731 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-24 |  | 2025-11-25 | Done late
71005731 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71005731 | SLM | 8 | Knitting start | Factory | 2025-11-29 |  | 2025-11-29 | Done
71005731 | SLM | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005731 | SLM | 10 | Final inspection | Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71005731 | SLM | 11 | Ex-factory | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005737 | BRW | 1 | Yarn booking | Factory | 2025-10-12 |  | 2025-10-12 | Done
71005737 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-20 | Done
71005737 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-25 | Done
71005737 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-16 | Done
71005737 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71005737 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-01 |  | 2025-12-02 | Done late
71005737 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-12-04 |  | 2025-12-04 | Done
71005737 | BRW | 8 | Knitting start | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005737 | BRW | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005737 | BRW | 10 | Final inspection | Karbar QA | 2026-01-14 |  | 2026-01-14 | Done
71005737 | BRW | 11 | Ex-factory | Factory | 2026-01-15 |  | 2026-01-15 | Done
71005743 | OKH | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-16 | Done
71005743 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-26 | Done
71005743 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-11-01 | Done late
71005743 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005743 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-12-02 | Done late
71005743 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-04 |  | 2025-12-04 | Done
71005743 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-12-08 |  | 2025-12-10 | Done late
71005743 | OKH | 8 | Knitting start | Factory | 2025-12-10 |  | 2025-12-11 | Done late
71005743 | OKH | 9 | Linking start | Factory | 2025-12-16 |  | 2025-12-16 | Done
71005743 | OKH | 10 | Final inspection | Karbar QA | 2026-01-18 |  | 2026-01-18 | Done
71005743 | OKH | 11 | Ex-factory | Factory | 2026-01-19 |  | 2026-01-19 | Done
71005747 | LTF | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-14 | Done
71005747 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-28 | Done late
71005747 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005747 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005747 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-11-30 | Done
71005747 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-06 |  | 2025-12-04 | Done
71005747 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-09 |  | 2025-12-11 | Done late
71005747 | LTF | 8 | Knitting start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005747 | LTF | 9 | Linking start | Factory | 2025-12-17 |  | 2025-12-16 | Done
71005747 | LTF | 10 | Final inspection | Karbar QA | 2026-01-19 |  | 2026-01-19 | Done
71005747 | LTF | 11 | Ex-factory | Factory | 2026-01-20 |  | 2026-01-20 | Done
71005752 | CPL | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-16 | Done
71005752 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-25 | Done
71005752 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-10-30 | Done
71005752 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005752 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71005752 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-06 |  | 2025-12-07 | Done late
71005752 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-12-09 |  | 2025-12-08 | Done
71005752 | CPL | 8 | Knitting start | Factory | 2025-12-11 |  | 2025-12-13 | Done late
71005752 | CPL | 9 | Linking start | Factory | 2025-12-17 |  | 2025-12-18 | Done late
71005752 | CPL | 10 | Final inspection | Karbar QA | 2026-01-19 |  | 2026-01-19 | Done
71005752 | CPL | 11 | Ex-factory | Factory | 2026-01-20 |  | 2026-01-20 | Done
71005758 | TLG | 1 | Yarn booking | Factory | 2025-10-25 |  | 2025-10-26 | Done late
71005758 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-04 |  | 2025-11-05 | Done late
71005758 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-06 | Done
71005758 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-11-29 |  | 2025-11-30 | Done late
71005758 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-12-09 |  | 2025-12-09 | Done
71005758 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-14 |  | 2025-12-15 | Done late
71005758 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-12-17 |  | 2025-12-16 | Done
71005758 | TLG | 8 | Knitting start | Factory | 2025-12-18 |  | 2025-12-20 | Done late
71005758 | TLG | 9 | Linking start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005758 | TLG | 10 | Final inspection | Karbar QA | 2026-01-27 |  | 2026-02-01 | Done late
71005758 | TLG | 11 | Ex-factory | Factory | 2026-01-28 |  | 2026-02-02 | Done late
71005763 | WSM | 1 | Yarn booking | Factory | 2025-09-25 |  | 2025-09-24 | Done
71005763 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-05 |  | 2025-10-06 | Done late
71005763 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-09 |  | 2025-10-08 | Done
71005763 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-29 | Done
71005763 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-11 | Done late
71005763 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-13 |  | 2025-11-13 | Done
71005763 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-11-17 |  | 2025-11-19 | Done late
71005763 | WSM | 8 | Knitting start | Factory | 2025-11-19 |  | 2025-11-19 | Done
71005763 | WSM | 9 | Linking start | Factory | 2025-11-25 |  | 2025-11-24 | Done
71005763 | WSM | 10 | Final inspection | Karbar QA | 2025-12-28 |  | 2025-12-28 | Done
71005763 | WSM | 11 | Ex-factory | Factory | 2025-12-29 |  | 2025-12-29 | Done
71005771 | WSM | 1 | Yarn booking | Factory | 2025-10-30 |  | 2025-10-30 | Done
71005771 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-10 | Done
71005771 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-16 | Done late
71005771 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-03 | Done
71005771 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-15 |  | 2025-12-14 | Done
71005771 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-20 |  | 2025-12-20 | Done
71005771 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-12-23 |  | 2025-12-23 | Done
71005771 | WSM | 8 | Knitting start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005771 | WSM | 9 | Linking start | Factory | 2025-12-31 |  | 2025-12-30 | Done
71005771 | WSM | 10 | Final inspection | Karbar QA | 2026-02-02 |  | 2026-02-04 | Done late
71005771 | WSM | 11 | Ex-factory | Factory | 2026-02-03 |  | 2026-02-05 | Done late
71005780 | CLB | 1 | Yarn booking | Factory | 2025-10-22 |  | 2025-10-20 | Done
71005780 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-01 | Done
71005780 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005780 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71005780 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-04 | Done
71005780 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-11 |  | 2025-12-14 | Done late
71005780 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-12-14 |  | 2025-12-14 | Done
71005780 | CLB | 8 | Knitting start | Factory | 2025-12-16 |  | 2025-12-17 | Done late
71005780 | CLB | 9 | Linking start | Factory | 2025-12-22 |  | 2025-12-22 | Done
71005780 | CLB | 10 | Final inspection | Karbar QA | 2026-01-24 |  | 2026-01-26 | Done late
71005780 | CLB | 11 | Ex-factory | Factory | 2026-01-25 |  | 2026-01-27 | Done late
71005785 | WSM | 1 | Yarn booking | Factory | 2025-10-11 |  | 2025-10-09 | Done
71005785 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-21 | Done
71005785 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-23 | Done
71005785 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-15 | Done
71005785 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-25 | Done
71005785 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-30 |  | 2025-12-01 | Done late
71005785 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-12-03 |  | 2025-12-03 | Done
71005785 | WSM | 8 | Knitting start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005785 | WSM | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-09 | Done
71005785 | WSM | 10 | Final inspection | Karbar QA | 2026-01-13 |  | 2026-01-12 | Done
71005785 | WSM | 11 | Ex-factory | Factory | 2026-01-14 |  | 2026-01-13 | Done
71005789 | AMB | 1 | Yarn booking | Factory | 2025-10-05 |  | 2025-10-06 | Done late
71005789 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-16 | Done late
71005789 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-19 | Done
71005789 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-09 | Done
71005789 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-19 | Done
71005789 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-24 |  | 2025-11-25 | Done late
71005789 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-11-27 |  | 2025-11-29 | Done late
71005789 | AMB | 8 | Knitting start | Factory | 2025-11-29 |  | 2025-11-30 | Done late
71005789 | AMB | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005789 | AMB | 10 | Final inspection | Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71005789 | AMB | 11 | Ex-factory | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005794 | SND | 1 | Yarn booking | Factory | 2025-10-04 |  | 2025-10-04 | Done
71005794 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-14 |  | 2025-10-16 | Done late
71005794 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-10-19 |  | 2025-10-16 | Done
71005794 | SND | 4 | Size set approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71005794 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-19 | Done late
71005794 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-23 |  | 2025-11-24 | Done late
71005794 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-11-26 |  | 2025-11-24 | Done
71005794 | SND | 8 | Knitting start | Factory | 2025-11-27 |  | 2025-11-27 | Done
71005794 | SND | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-02 | Done
71005794 | SND | 10 | Final inspection | Karbar QA | 2026-01-06 |  | 2026-01-04 | Done
71005794 | SND | 11 | Ex-factory | Factory | 2026-01-07 |  | 2026-01-05 | Done
71005803 | RVS | 1 | Yarn booking | Factory | 2025-11-08 |  | 2025-11-08 | Done
71005803 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-19 | Done late
71005803 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-22 | Done
71005803 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71005803 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-23 | Done
71005803 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-28 |  | 2025-12-28 | Done
71005803 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005803 | RVS | 8 | Knitting start | Factory | 2026-01-01 |  | 2026-01-03 | Done late
71005803 | RVS | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005803 | RVS | 10 | Final inspection | Karbar QA | 2026-02-10 |  | 2026-02-10 | Done
71005803 | RVS | 11 | Ex-factory | Factory | 2026-02-11 |  | 2026-02-11 | Done
71005810 | RVS | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-16 | Done
71005810 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005810 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-02 | Done
71005810 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-25 | Done late
71005810 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71005810 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-07 | Done
71005810 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-10 | Done
71005810 | RVS | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-14 | Done late
71005810 | RVS | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005810 | RVS | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005810 | RVS | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005814 | IRB | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-19 | Done
71005814 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005814 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005814 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-22 | Done
71005814 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005814 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-08 | Done
71005814 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-13 | Done late
71005814 | IRB | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005814 | IRB | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005814 | IRB | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005814 | IRB | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005817 | BRW | 1 | Yarn booking | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005817 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-16 | Done
71005817 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-19 | Done
71005817 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71005817 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-23 | Done late
71005817 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-24 | Done
71005817 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-12-29 |  | 2025-12-28 | Done
71005817 | BRW | 8 | Knitting start | Factory | 2025-12-31 |  | 2026-01-01 | Done late
71005817 | BRW | 9 | Linking start | Factory | 2026-01-06 |  | 2026-01-06 | Done
71005817 | BRW | 10 | Final inspection | Karbar QA | 2026-02-08 |  | 2026-02-07 | Done
71005817 | BRW | 11 | Ex-factory | Factory | 2026-02-09 |  | 2026-02-08 | Done
71005825 | SLM | 1 | Yarn booking | Factory | 2025-11-08 |  | 2025-11-09 | Done late
71005825 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-19 | Done late
71005825 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005825 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71005825 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-23 | Done
71005825 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-28 |  | 2025-12-30 | Done late
71005825 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-12-31 |  | 2025-12-31 | Done
71005825 | SLM | 8 | Knitting start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005825 | SLM | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-06 | Done
71005825 | SLM | 10 | Final inspection | Karbar QA | 2026-02-10 |  | 2026-02-11 | Done late
71005825 | SLM | 11 | Ex-factory | Factory | 2026-02-11 |  | 2026-02-12 | Done late
71005831 | BRW | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-18 | Done late
71005831 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-29 | Done late
71005831 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-02 | Done late
71005831 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005831 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71005831 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-06 |  | 2025-12-04 | Done
71005831 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-12-09 |  | 2025-12-10 | Done late
71005831 | BRW | 8 | Knitting start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005831 | BRW | 9 | Linking start | Factory | 2025-12-17 |  | 2025-12-16 | Done
71005831 | BRW | 10 | Final inspection | Karbar QA | 2026-01-19 |  | 2026-01-17 | Done
71005831 | BRW | 11 | Ex-factory | Factory | 2026-01-20 |  | 2026-01-18 | Done
71005837 | RVS | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-19 | Done
71005837 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005837 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-01 | Done
71005837 | RVS | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005837 | RVS | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-02 | Done
71005837 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-10 | Done late
71005837 | RVS | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-09 | Done
71005837 | RVS | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005837 | RVS | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005837 | RVS | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005837 | RVS | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005842 | SLM | 1 | Yarn booking | Factory | 2025-11-02 |  | 2025-11-02 | Done
71005842 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-11 | Done
71005842 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-18 | Done late
71005842 | SLM | 4 | Size set approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-06 | Done
71005842 | SLM | 5 | PP sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-17 | Done
71005842 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-22 |  | 2025-12-20 | Done
71005842 | SLM | 7 | PP meeting | Factory + Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71005842 | SLM | 8 | Knitting start | Factory | 2025-12-27 |  | 2025-12-28 | Done late
71005842 | SLM | 9 | Linking start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005842 | SLM | 10 | Final inspection | Karbar QA | 2026-02-04 |  | 2026-02-02 | Done
71005842 | SLM | 11 | Ex-factory | Factory | 2026-02-05 |  | 2026-02-03 | Done
71005847 | OKH | 1 | Yarn booking | Factory | 2025-10-16 |  | 2025-10-16 | Done
71005847 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-27 | Done
71005847 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-01 |  | 2025-11-02 | Done late
71005847 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005847 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71005847 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-06 |  | 2025-12-06 | Done
71005847 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-12-09 |  | 2025-12-11 | Done late
71005847 | OKH | 8 | Knitting start | Factory | 2025-12-11 |  | 2025-12-13 | Done late
71005847 | OKH | 9 | Linking start | Factory | 2025-12-17 |  | 2025-12-18 | Done late
71005847 | OKH | 10 | Final inspection | Karbar QA | 2026-01-19 |  | 2026-01-19 | Done
71005847 | OKH | 11 | Ex-factory | Factory | 2026-01-20 |  | 2026-01-20 | Done
71005856 | SVP | 1 | Yarn booking | Factory | 2025-10-28 |  | 2025-10-26 | Done
71005856 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71005856 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-10 | Done
71005856 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-12-02 |  | 2025-12-01 | Done
71005856 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71005856 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-17 |  | 2025-12-18 | Done late
71005856 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-12-20 |  | 2025-12-22 | Done late
71005856 | SVP | 8 | Knitting start | Factory | 2025-12-22 |  | 2025-12-22 | Done
71005856 | SVP | 9 | Linking start | Factory | 2025-12-28 |  | 2025-12-27 | Done
71005856 | SVP | 10 | Final inspection | Karbar QA | 2026-01-29 |  | 2026-01-29 | Done
71005856 | SVP | 11 | Ex-factory | Factory | 2026-01-31 |  | 2026-01-31 | Done
71005859 | CLB | 1 | Yarn booking | Factory | 2025-10-29 |  | 2025-10-30 | Done late
71005859 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-10 | Done late
71005859 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-13 | Done
71005859 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-02 | Done
71005859 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71005859 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-20 | Done late
71005859 | CLB | 7 | PP meeting | Factory + Karbar QA | 2025-12-21 |  | 2025-12-21 | Done
71005859 | CLB | 8 | Knitting start | Factory | 2025-12-23 |  | 2025-12-24 | Done late
71005859 | CLB | 9 | Linking start | Factory | 2025-12-29 |  | 2025-12-29 | Done
71005859 | CLB | 10 | Final inspection | Karbar QA | 2026-01-31 |  | 2026-01-28 | Done
71005859 | CLB | 11 | Ex-factory | Factory | 2026-02-01 |  | 2026-01-29 | Done
71005867 | MDW | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-19 | Done
71005867 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-29 | Done
71005867 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-04 | Done late
71005867 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-25 | Done late
71005867 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005867 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-08 | Done
71005867 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005867 | MDW | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-14 | Done late
71005867 | MDW | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005867 | MDW | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005867 | MDW | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005872 | TLG | 1 | Yarn booking | Factory | 2025-10-05 |  | 2025-10-07 | Done late
71005872 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-15 |  | 2025-10-13 | Done
71005872 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-10-20 |  | 2025-10-20 | Done
71005872 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-10 | Done late
71005872 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005872 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-24 |  | 2025-11-24 | Done
71005872 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-11-27 |  | 2025-11-27 | Done
71005872 | TLG | 8 | Knitting start | Factory | 2025-11-29 |  | 2025-11-30 | Done late
71005872 | TLG | 9 | Linking start | Factory | 2025-12-04 |  | 2025-12-04 | Done
71005872 | TLG | 10 | Final inspection | Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71005872 | TLG | 11 | Ex-factory | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005877 | FNS | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-18 | Done
71005877 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-30 | Done late
71005877 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005877 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71005877 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005877 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-06 | Done
71005877 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71005877 | FNS | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005877 | FNS | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005877 | FNS | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-21 | Done
71005877 | FNS | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-22 | Done
71005881 | IRB | 1 | Yarn booking | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005881 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-17 | Done late
71005881 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005881 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71005881 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-21 | Done
71005881 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-27 | Done late
71005881 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-12-29 |  | 2025-12-29 | Done
71005881 | IRB | 8 | Knitting start | Factory | 2025-12-31 |  | 2026-01-01 | Done late
71005881 | IRB | 9 | Linking start | Factory | 2026-01-06 |  | 2026-01-06 | Done
71005881 | IRB | 10 | Final inspection | Karbar QA | 2026-02-08 |  | 2026-02-08 | Done
71005881 | IRB | 11 | Ex-factory | Factory | 2026-02-09 |  | 2026-02-09 | Done
71005887 | CPL | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-19 | Done
71005887 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-28 | Done
71005887 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005887 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-20 | Done
71005887 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005887 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-09 | Done late
71005887 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-10 | Done
71005887 | CPL | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71005887 | CPL | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005887 | CPL | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-18 | Done
71005887 | CPL | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-19 | Done
71005895 | PBB | 1 | Yarn booking | Factory | 2025-10-08 |  | 2025-10-08 | Done
71005895 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-18 |  | 2025-10-20 | Done late
71005895 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-23 |  | 2025-10-23 | Done
71005895 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005895 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-11-22 |  | 2025-11-22 | Done
71005895 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-27 |  | 2025-11-27 | Done
71005895 | PBB | 7 | PP meeting | Factory + Karbar QA | 2025-11-30 |  | 2025-11-30 | Done
71005895 | PBB | 8 | Knitting start | Factory | 2025-12-02 |  | 2025-12-03 | Done late
71005895 | PBB | 9 | Linking start | Factory | 2025-12-08 |  | 2025-12-08 | Done
71005895 | PBB | 10 | Final inspection | Karbar QA | 2026-01-10 |  | 2026-01-10 | Done
71005895 | PBB | 11 | Ex-factory | Factory | 2026-01-11 |  | 2026-01-11 | Done
71005898 | LTF | 1 | Yarn booking | Factory | 2025-10-12 |  | 2025-10-14 | Done late
71005898 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005898 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-25 | Done
71005898 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-18 | Done late
71005898 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71005898 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-01 |  | 2025-12-01 | Done
71005898 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-04 |  | 2025-12-06 | Done late
71005898 | LTF | 8 | Knitting start | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005898 | LTF | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005898 | LTF | 10 | Final inspection | Karbar QA | 2026-01-14 |  | 2026-01-14 | Done
71005898 | LTF | 11 | Ex-factory | Factory | 2026-01-15 |  | 2026-01-15 | Done
71005905 | LTF | 1 | Yarn booking | Factory | 2025-10-23 |  | 2025-10-23 | Done
71005905 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71005905 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71005905 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71005905 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-07 | Done
71005905 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-13 |  | 2025-12-13 | Done
71005905 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-16 |  | 2025-12-17 | Done late
71005905 | LTF | 8 | Knitting start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71005905 | LTF | 9 | Linking start | Factory | 2025-12-24 |  | 2025-12-23 | Done
71005905 | LTF | 10 | Final inspection | Karbar QA | 2026-01-26 |  | 2026-01-25 | Done
71005905 | LTF | 11 | Ex-factory | Factory | 2026-01-27 |  | 2026-01-26 | Done
71005909 | SVP | 1 | Yarn booking | Factory | 2025-10-30 |  | 2025-10-30 | Done
71005909 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-10 | Done late
71005909 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-13 | Done
71005909 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-03 | Done
71005909 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71005909 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-18 | Done
71005909 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-12-22 |  | 2025-12-21 | Done
71005909 | SVP | 8 | Knitting start | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005909 | SVP | 9 | Linking start | Factory | 2025-12-30 |  | 2025-12-29 | Done
71005909 | SVP | 10 | Final inspection | Karbar QA | 2026-02-01 |  | 2026-02-01 | Done
71005909 | SVP | 11 | Ex-factory | Factory | 2026-02-02 |  | 2026-02-02 | Done
71005915 | GRL | 1 | Yarn booking | Factory | 2025-10-12 |  | 2025-10-11 | Done
71005915 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-23 | Done late
71005915 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-27 | Done
71005915 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-17 | Done late
71005915 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-27 | Done late
71005915 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-01 |  | 2025-11-29 | Done
71005915 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-04 |  | 2025-12-04 | Done
71005915 | GRL | 8 | Knitting start | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005915 | GRL | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005915 | GRL | 10 | Final inspection | Karbar QA | 2026-01-14 |  | 2026-01-14 | Done
71005915 | GRL | 11 | Ex-factory | Factory | 2026-01-15 |  | 2026-01-15 | Done
71005922 | WTH | 1 | Yarn booking | Factory | 2025-10-30 |  | 2025-10-30 | Done
71005922 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-09 |  | 2025-11-09 | Done
71005922 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-13 | Done
71005922 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-04 | Done
71005922 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71005922 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-20 | Done late
71005922 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-12-22 |  | 2025-12-24 | Done late
71005922 | WTH | 8 | Knitting start | Factory | 2025-12-24 |  | 2025-12-24 | Done
71005922 | WTH | 9 | Linking start | Factory | 2025-12-30 |  | 2025-12-29 | Done
71005922 | WTH | 10 | Final inspection | Karbar QA | 2026-02-01 |  | 2026-01-31 | Done
71005922 | WTH | 11 | Ex-factory | Factory | 2026-02-02 |  | 2026-02-01 | Done
71005927 | FNS | 1 | Yarn booking | Factory | 2025-10-12 |  | 2025-10-12 | Done
71005927 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005927 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-25 | Done
71005927 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-16 | Done
71005927 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-27 | Done late
71005927 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-01 |  | 2025-12-01 | Done
71005927 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-12-04 |  | 2025-12-06 | Done late
71005927 | FNS | 8 | Knitting start | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005927 | FNS | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005927 | FNS | 10 | Final inspection | Karbar QA | 2026-01-14 |  | 2026-01-14 | Done
71005927 | FNS | 11 | Ex-factory | Factory | 2026-01-15 |  | 2026-01-15 | Done
71005935 | OKH | 1 | Yarn booking | Factory | 2025-11-02 |  | 2025-11-02 | Done
71005935 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71005935 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-15 | Done
71005935 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71005935 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-17 | Done
71005935 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-22 |  | 2025-12-22 | Done
71005935 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71005935 | OKH | 8 | Knitting start | Factory | 2025-12-27 |  | 2025-12-28 | Done late
71005935 | OKH | 9 | Linking start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005935 | OKH | 10 | Final inspection | Karbar QA | 2026-02-04 |  | 2026-02-04 | Done
71005935 | OKH | 11 | Ex-factory | Factory | 2026-02-05 |  | 2026-02-05 | Done
71005938 | GRL | 1 | Yarn booking | Factory | 2025-11-06 |  | 2025-11-06 | Done
71005938 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-18 | Done late
71005938 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71005938 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71005938 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-20 | Done
71005938 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-25 | Done
71005938 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-29 |  | 2025-12-28 | Done
71005938 | GRL | 8 | Knitting start | Factory | 2025-12-31 |  | 2026-01-01 | Done late
71005938 | GRL | 9 | Linking start | Factory | 2026-01-06 |  | 2026-01-06 | Done
71005938 | GRL | 10 | Final inspection | Karbar QA | 2026-02-08 |  | 2026-02-05 | Done
71005938 | GRL | 11 | Ex-factory | Factory | 2026-02-09 |  | 2026-02-07 | Done
71005941 | BLF | 1 | Yarn booking | Factory | 2025-10-12 |  | 2025-10-12 | Done
71005941 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-22 |  | 2025-10-22 | Done
71005941 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-10-27 |  | 2025-10-27 | Done
71005941 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-15 | Done
71005941 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-25 | Done
71005941 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-01 |  | 2025-12-01 | Done
71005941 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-12-04 |  | 2025-12-04 | Done
71005941 | BLF | 8 | Knitting start | Factory | 2025-12-06 |  | 2025-12-06 | Done
71005941 | BLF | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005941 | BLF | 10 | Final inspection | Karbar QA | 2026-01-14 |  | 2026-01-14 | Done
71005941 | BLF | 11 | Ex-factory | Factory | 2026-01-15 |  | 2026-01-15 | Done
71005946 | AMB | 1 | Yarn booking | Factory | 2025-10-15 |  | 2025-10-16 | Done late
71005946 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-23 | Done
71005946 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-30 | Done
71005946 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005946 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-11-29 |  | 2025-12-01 | Done late
71005946 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-04 |  | 2025-12-07 | Done late
71005946 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-12-07 |  | 2025-12-07 | Done
71005946 | AMB | 8 | Knitting start | Factory | 2025-12-09 |  | 2025-12-09 | Done
71005946 | AMB | 9 | Linking start | Factory | 2025-12-15 |  | 2025-12-14 | Done
71005946 | AMB | 10 | Final inspection | Karbar QA | 2026-01-17 |  | 2026-01-17 | Done
71005946 | AMB | 11 | Ex-factory | Factory | 2026-01-18 |  | 2026-01-18 | Done
71005950 | LTF | 1 | Yarn booking | Factory | 2025-10-11 |  | 2025-10-09 | Done
71005950 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-21 |  | 2025-10-23 | Done late
71005950 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-10-26 |  | 2025-10-26 | Done
71005950 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-15 | Done
71005950 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-25 | Done
71005950 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-11-30 |  | 2025-11-30 | Done
71005950 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-03 |  | 2025-12-01 | Done
71005950 | LTF | 8 | Knitting start | Factory | 2025-12-04 |  | 2025-12-06 | Done late
71005950 | LTF | 9 | Linking start | Factory | 2025-12-11 |  | 2025-12-11 | Done
71005950 | LTF | 10 | Final inspection | Karbar QA | 2026-01-13 |  | 2026-01-13 | Done
71005950 | LTF | 11 | Ex-factory | Factory | 2026-01-14 |  | 2026-01-14 | Done
71005957 | BRW | 1 | Yarn booking | Factory | 2025-10-29 |  | 2025-10-29 | Done
71005957 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71005957 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-13 | Done
71005957 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71005957 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71005957 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-21 | Done late
71005957 | BRW | 7 | PP meeting | Factory + Karbar QA | 2025-12-21 |  | 2025-12-20 | Done
71005957 | BRW | 8 | Knitting start | Factory | 2025-12-23 |  | 2025-12-23 | Done
71005957 | BRW | 9 | Linking start | Factory | 2025-12-29 |  | 2025-12-28 | Done
71005957 | BRW | 10 | Final inspection | Karbar QA | 2026-01-31 |  | 2026-01-28 | Done
71005957 | BRW | 11 | Ex-factory | Factory | 2026-02-01 |  | 2026-01-29 | Done
71005962 | PBB | 1 | Yarn booking | Factory | 2025-11-09 |  | 2025-11-10 | Done late
71005962 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005962 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71005962 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-11 | Done
71005962 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71005962 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-29 |  | 2026-01-01 | Done late
71005962 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-01-01 |  | 2025-12-30 | Done
71005962 | PBB | 8 | Knitting start | Factory | 2026-01-03 |  | 2026-01-03 | Done
71005962 | PBB | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005962 | PBB | 10 | Final inspection | Karbar QA | 2026-02-11 |  | 2026-02-11 | Done
71005962 | PBB | 11 | Ex-factory | Factory | 2026-02-12 |  | 2026-02-12 | Done
71005971 | WSM | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-13 | Done
71005971 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71005971 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-29 |  | 2025-11-29 | Done
71005971 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71005971 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-29 | Done
71005971 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-03 |  | 2026-01-05 | Done late
71005971 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-01-06 |  | 2026-01-06 | Done
71005971 | WSM | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005971 | WSM | 9 | Linking start | Factory | 2026-01-14 |  | 2026-01-13 | Done
71005971 | WSM | 10 | Final inspection | Karbar QA | 2026-02-16 |  | 2026-02-16 | Done
71005971 | WSM | 11 | Ex-factory | Factory | 2026-02-17 |  | 2026-02-17 | Done
71005978 | WTH | 1 | Yarn booking | Factory | 2025-10-15 |  | 2025-10-13 | Done
71005978 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-25 |  | 2025-10-27 | Done late
71005978 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-10-30 |  | 2025-10-29 | Done
71005978 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-20 | Done late
71005978 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-11-29 |  | 2025-11-27 | Done
71005978 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-04 |  | 2025-12-02 | Done
71005978 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-12-07 |  | 2025-12-07 | Done
71005978 | WTH | 8 | Knitting start | Factory | 2025-12-09 |  | 2025-12-09 | Done
71005978 | WTH | 9 | Linking start | Factory | 2025-12-15 |  | 2025-12-14 | Done
71005978 | WTH | 10 | Final inspection | Karbar QA | 2026-01-17 |  | 2026-01-19 | Done late
71005978 | WTH | 11 | Ex-factory | Factory | 2026-01-18 |  | 2026-01-20 | Done late
71005983 | WTH | 1 | Yarn booking | Factory | 2025-11-02 |  | 2025-11-02 | Done
71005983 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-13 | Done late
71005983 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-18 | Done late
71005983 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71005983 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-16 | Done
71005983 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-22 |  | 2025-12-24 | Done late
71005983 | WTH | 7 | PP meeting | Factory + Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71005983 | WTH | 8 | Knitting start | Factory | 2025-12-27 |  | 2025-12-27 | Done
71005983 | WTH | 9 | Linking start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71005983 | WTH | 10 | Final inspection | Karbar QA | 2026-02-04 |  | 2026-02-03 | Done
71005983 | WTH | 11 | Ex-factory | Factory | 2026-02-05 |  | 2026-02-04 | Done
71005992 | PBB | 1 | Yarn booking | Factory | 2025-11-09 |  | 2025-11-10 | Done late
71005992 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-19 | Done
71005992 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-26 | Done late
71005992 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71005992 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-25 | Done late
71005992 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-29 |  | 2025-12-30 | Done late
71005992 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-01-01 |  | 2026-01-03 | Done late
71005992 | PBB | 8 | Knitting start | Factory | 2026-01-03 |  | 2026-01-04 | Done late
71005992 | PBB | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71005992 | PBB | 10 | Final inspection | Karbar QA | 2026-02-11 |  | 2026-02-11 | Done
71005992 | PBB | 11 | Ex-factory | Factory | 2026-02-12 |  | 2026-02-12 | Done
71005995 | BLF | 1 | Yarn booking | Factory | 2025-10-26 |  | 2025-10-25 | Done
71005995 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71005995 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-09 | Done
71005995 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71005995 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71005995 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-15 |  | 2025-12-13 | Done
71005995 | BLF | 7 | PP meeting | Factory + Karbar QA | 2025-12-18 |  | 2025-12-18 | Done
71005995 | BLF | 8 | Knitting start | Factory | 2025-12-20 |  | 2025-12-20 | Done
71005995 | BLF | 9 | Linking start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71005995 | BLF | 10 | Final inspection | Karbar QA | 2026-01-28 |  | 2026-01-25 | Done
71005995 | BLF | 11 | Ex-factory | Factory | 2026-01-29 |  | 2026-01-26 | Done
71006002 | IRB | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-12 | Done
71006002 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-22 | Done
71006002 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-29 | Done late
71006002 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006002 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006002 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2025-12-31 | Done
71006002 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-01-05 |  | 2026-01-05 | Done
71006002 | IRB | 8 | Knitting start | Factory | 2026-01-07 |  | 2026-01-07 | Done
71006002 | IRB | 9 | Linking start | Factory | 2026-01-13 |  | 2026-01-12 | Done
71006002 | IRB | 10 | Final inspection | Karbar QA | 2026-02-15 |  | 2026-02-15 | Done
71006002 | IRB | 11 | Ex-factory | Factory | 2026-02-16 |  | 2026-02-16 | Done
71006011 | BLF | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-16 | Done
71006011 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71006011 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-11-30 | Done
71006011 | BLF | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-23 | Done late
71006011 | BLF | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2026-01-01 | Done late
71006011 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-08 | Done late
71006011 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-08 | Done
71006011 | BLF | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-10 | Done
71006011 | BLF | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006011 | BLF | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-15 | Done
71006011 | BLF | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-16 | Done
71006017 | AMB | 1 | Yarn booking | Factory | 2025-11-09 |  | 2025-11-09 | Done
71006017 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-19 | Done
71006017 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-22 | Done
71006017 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-16 | Done late
71006017 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71006017 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-29 |  | 2025-12-30 | Done late
71006017 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-01-01 |  | 2025-12-30 | Done
71006017 | AMB | 8 | Knitting start | Factory | 2026-01-03 |  | 2026-01-04 | Done late
71006017 | AMB | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006017 | AMB | 10 | Final inspection | Karbar QA | 2026-02-11 |  | 2026-02-11 | Done
71006017 | AMB | 11 | Ex-factory | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006023 | GRL | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-24 | Done late
71006023 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71006023 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-08 | Done
71006023 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-29 | Done late
71006023 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-08 | Done late
71006023 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-12 | Done
71006023 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-15 | Done
71006023 | GRL | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-17 | Done
71006023 | GRL | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006023 | GRL | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-25 | Done
71006023 | GRL | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006031 | IRB | 1 | Yarn booking | Factory | 2025-11-05 |  | 2025-11-06 | Done late
71006031 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-16 | Done late
71006031 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-19 | Done
71006031 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006031 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-21 | Done late
71006031 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-23 | Done
71006031 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-12-28 |  | 2025-12-28 | Done
71006031 | IRB | 8 | Knitting start | Factory | 2025-12-30 |  | 2025-12-30 | Done
71006031 | IRB | 9 | Linking start | Factory | 2026-01-05 |  | 2026-01-04 | Done
71006031 | IRB | 10 | Final inspection | Karbar QA | 2026-02-07 |  | 2026-02-07 | Done
71006031 | IRB | 11 | Ex-factory | Factory | 2026-02-08 |  | 2026-02-08 | Done
71006038 | CPL | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-16 | Done
71006038 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71006038 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71006038 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-21 | Done
71006038 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006038 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-05 | Done
71006038 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-08 | Done
71006038 | CPL | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-10 | Done
71006038 | CPL | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006038 | CPL | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-16 | Done
71006038 | CPL | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-17 | Done
71006043 | RSG | 1 | Yarn booking | Factory | 2025-11-12 |  | 2025-11-12 | Done
71006043 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-22 |  | 2025-11-20 | Done
71006043 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71006043 | RSG | 4 | Size set approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-18 | Done late
71006043 | RSG | 5 | PP sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-28 | Done late
71006043 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-04 | Done late
71006043 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-01-04 |  | 2026-01-05 | Done late
71006043 | RSG | 8 | Knitting start | Factory | 2026-01-06 |  | 2026-01-06 | Done
71006043 | RSG | 9 | Linking start | Factory | 2026-01-12 |  | 2026-01-11 | Done
71006043 | RSG | 10 | Final inspection | Karbar QA | 2026-02-14 |  | 2026-02-14 | Done
71006043 | RSG | 11 | Ex-factory | Factory | 2026-02-15 |  | 2026-02-15 | Done
71006046 | GRL | 1 | Yarn booking | Factory | 2025-10-19 |  | 2025-10-19 | Done
71006046 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-10-29 |  | 2025-10-28 | Done
71006046 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-03 |  | 2025-11-03 | Done
71006046 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-22 | Done
71006046 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71006046 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-08 |  | 2025-12-08 | Done
71006046 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-11 |  | 2025-12-11 | Done
71006046 | GRL | 8 | Knitting start | Factory | 2025-12-13 |  | 2025-12-13 | Done
71006046 | GRL | 9 | Linking start | Factory | 2025-12-18 |  | 2025-12-18 | Done
71006046 | GRL | 10 | Final inspection | Karbar QA | 2026-01-21 |  | 2026-01-24 | Done late
71006046 | GRL | 11 | Ex-factory | Factory | 2026-01-22 |  | 2026-01-25 | Done late
71006055 | BRW | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-13 | Done
71006055 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71006055 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-29 |  | 2025-11-29 | Done
71006055 | BRW | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006055 | BRW | 5 | PP sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-29 | Done
71006055 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-03 |  | 2026-01-04 | Done late
71006055 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-01-06 |  | 2026-01-05 | Done
71006055 | BRW | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006055 | BRW | 9 | Linking start | Factory | 2026-01-14 |  | 2026-01-13 | Done
71006055 | BRW | 10 | Final inspection | Karbar QA | 2026-02-16 |  | 2026-02-21 | Done late
71006055 | BRW | 11 | Ex-factory | Factory | 2026-02-17 |  | 2026-02-22 | Done late
71006064 | CPL | 1 | Yarn booking | Factory | 2025-10-26 |  | 2025-10-26 | Done
71006064 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-04 | Done
71006064 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-10 | Done
71006064 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-29 | Done
71006064 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006064 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-15 |  | 2025-12-15 | Done
71006064 | CPL | 7 | PP meeting | Factory + Karbar QA | 2025-12-18 |  | 2025-12-17 | Done
71006064 | CPL | 8 | Knitting start | Factory | 2025-12-20 |  | 2025-12-20 | Done
71006064 | CPL | 9 | Linking start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71006064 | CPL | 10 | Final inspection | Karbar QA | 2026-01-28 |  | 2026-01-28 | Done
71006064 | CPL | 11 | Ex-factory | Factory | 2026-01-29 |  | 2026-01-29 | Done
71006068 | KST | 1 | Yarn booking | Factory | 2025-11-09 |  | 2025-11-11 | Done late
71006068 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-17 | Done
71006068 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71006068 | KST | 4 | Size set approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-15 | Done late
71006068 | KST | 5 | PP sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71006068 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-29 |  | 2026-01-01 | Done late
71006068 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-01 |  | 2026-01-01 | Done
71006068 | KST | 8 | Knitting start | Factory | 2026-01-03 |  | 2026-01-03 | Done
71006068 | KST | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006068 | KST | 10 | Final inspection | Karbar QA | 2026-02-11 |  | 2026-02-10 | Done
71006068 | KST | 11 | Ex-factory | Factory | 2026-02-12 |  | 2026-02-11 | Done
71006077 | SND | 1 | Yarn booking | Factory | 2025-10-23 |  | 2025-10-23 | Done
71006077 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71006077 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71006077 | SND | 4 | Size set approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71006077 | SND | 5 | PP sample approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71006077 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-11 |  | 2025-12-11 | Done
71006077 | SND | 7 | PP meeting | Factory + Karbar QA | 2025-12-15 |  | 2025-12-14 | Done
71006077 | SND | 8 | Knitting start | Factory | 2025-12-17 |  | 2025-12-17 | Done
71006077 | SND | 9 | Linking start | Factory | 2025-12-23 |  | 2025-12-22 | Done
71006077 | SND | 10 | Final inspection | Karbar QA | 2026-01-25 |  | 2026-01-24 | Done
71006077 | SND | 11 | Ex-factory | Factory | 2026-01-26 |  | 2026-01-25 | Done
71006086 | TLG | 1 | Yarn booking | Factory | 2025-10-23 |  | 2025-10-22 | Done
71006086 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-02 |  | 2025-11-02 | Done
71006086 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71006086 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71006086 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71006086 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-11 |  | 2025-12-10 | Done
71006086 | TLG | 7 | PP meeting | Factory + Karbar QA | 2025-12-15 |  | 2025-12-15 | Done
71006086 | TLG | 8 | Knitting start | Factory | 2025-12-17 |  | 2025-12-17 | Done
71006086 | TLG | 9 | Linking start | Factory | 2025-12-23 |  | 2025-12-22 | Done
71006086 | TLG | 10 | Final inspection | Karbar QA | 2026-01-25 |  | 2026-01-21 | Done
71006086 | TLG | 11 | Ex-factory | Factory | 2026-01-26 |  | 2026-01-22 | Done
71006089 | SVP | 1 | Yarn booking | Factory | 2025-10-26 |  | 2025-10-25 | Done
71006089 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71006089 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-10 | Done
71006089 | SVP | 4 | Size set approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71006089 | SVP | 5 | PP sample approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-09 | Done
71006089 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-15 |  | 2025-12-15 | Done
71006089 | SVP | 7 | PP meeting | Factory + Karbar QA | 2025-12-18 |  | 2025-12-18 | Done
71006089 | SVP | 8 | Knitting start | Factory | 2025-12-20 |  | 2025-12-20 | Done
71006089 | SVP | 9 | Linking start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71006089 | SVP | 10 | Final inspection | Karbar QA | 2026-01-28 |  | 2026-01-27 | Done
71006089 | SVP | 11 | Ex-factory | Factory | 2026-01-29 |  | 2026-01-28 | Done
71006093 | WTH | 1 | Yarn booking | Factory | 2025-11-12 |  | 2025-11-12 | Done
71006093 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-22 |  | 2025-11-22 | Done
71006093 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-29 | Done late
71006093 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-15 | Done
71006093 | WTH | 5 | PP sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-27 | Done
71006093 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-01 | Done
71006093 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-01-04 |  | 2026-01-05 | Done late
71006093 | WTH | 8 | Knitting start | Factory | 2026-01-06 |  | 2026-01-07 | Done late
71006093 | WTH | 9 | Linking start | Factory | 2026-01-12 |  | 2026-01-12 | Done
71006093 | WTH | 10 | Final inspection | Karbar QA | 2026-02-14 |  | 2026-02-14 | Done
71006093 | WTH | 11 | Ex-factory | Factory | 2026-02-15 |  | 2026-02-15 | Done
71006097 | WSM | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-16 | Done
71006097 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-27 | Done late
71006097 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-02 | Done late
71006097 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-22 | Done late
71006097 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006097 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-07 | Done late
71006097 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-06 | Done
71006097 | WSM | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-10 | Done
71006097 | WSM | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006097 | WSM | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-18 | Done
71006097 | WSM | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006106 | LTF | 1 | Yarn booking | Factory | 2025-10-26 |  | 2025-10-26 | Done
71006106 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-05 |  | 2025-11-05 | Done
71006106 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-10 |  | 2025-11-09 | Done
71006106 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71006106 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-11 | Done late
71006106 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-15 |  | 2025-12-18 | Done late
71006106 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-18 |  | 2025-12-18 | Done
71006106 | LTF | 8 | Knitting start | Factory | 2025-12-20 |  | 2025-12-20 | Done
71006106 | LTF | 9 | Linking start | Factory | 2025-12-25 |  | 2025-12-25 | Done
71006106 | LTF | 10 | Final inspection | Karbar QA | 2026-01-28 |  | 2026-01-26 | Done
71006106 | LTF | 11 | Ex-factory | Factory | 2026-01-29 |  | 2026-01-27 | Done
71006114 | WTH | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-25 | Done late
71006114 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71006114 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-08 | Done
71006114 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-30 | Done late
71006114 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006114 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-10 | Done
71006114 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-15 | Done
71006114 | WTH | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-17 | Done
71006114 | WTH | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006114 | WTH | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-22 | Done
71006114 | WTH | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-23 | Done
71006119 | GRL | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-23 | Done
71006119 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71006119 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-07 | Done
71006119 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006119 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006119 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-14 | Done late
71006119 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-15 | Done
71006119 | GRL | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-18 | Done late
71006119 | GRL | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006119 | GRL | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-22 | Done
71006119 | GRL | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-23 | Done
71006123 | KST | 1 | Yarn booking | Factory | 2025-12-04 |  | 2025-12-04 | Done
71006123 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71006123 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006123 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-08 | Done
71006123 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006123 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-22 |  | 2026-01-25 | Done late
71006123 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-26 |  | 2026-01-26 | Done
71006123 | KST | 8 | Knitting start | Factory | 2026-01-28 |  | 2026-01-29 | Done late
71006123 | KST | 9 | Linking start | Factory | 2026-02-03 |  | 2026-02-03 | Done
71006123 | KST | 10 | Final inspection | Karbar QA | 2026-03-08 |  | 2026-03-08 | Done
71006123 | KST | 11 | Ex-factory | Factory | 2026-03-09 |  | 2026-03-09 | Done
71006131 | OKH | 1 | Yarn booking | Factory | 2025-10-29 |  | 2025-10-27 | Done
71006131 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-08 | Done
71006131 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-12 | Done
71006131 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71006131 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-11 | Done
71006131 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-18 | Done
71006131 | OKH | 7 | PP meeting | Factory + Karbar QA | 2025-12-21 |  | 2025-12-21 | Done
71006131 | OKH | 8 | Knitting start | Factory | 2025-12-23 |  | 2025-12-23 | Done
71006131 | OKH | 9 | Linking start | Factory | 2025-12-29 |  | 2025-12-28 | Done
71006131 | OKH | 10 | Final inspection | Karbar QA | 2026-01-31 |  | 2026-02-05 | Done late
71006131 | OKH | 11 | Ex-factory | Factory | 2026-02-01 |  | 2026-02-07 | Done late
71006139 | LTF | 1 | Yarn booking | Factory | 2025-11-05 |  | 2025-11-06 | Done late
71006139 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-15 | Done
71006139 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71006139 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006139 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-18 | Done
71006139 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-25 | Done
71006139 | LTF | 7 | PP meeting | Factory + Karbar QA | 2025-12-28 |  | 2025-12-29 | Done late
71006139 | LTF | 8 | Knitting start | Factory | 2025-12-30 |  | 2025-12-30 | Done
71006139 | LTF | 9 | Linking start | Factory | 2026-01-05 |  | 2026-01-04 | Done
71006139 | LTF | 10 | Final inspection | Karbar QA | 2026-02-07 |  | 2026-02-09 | Done late
71006139 | LTF | 11 | Ex-factory | Factory | 2026-02-08 |  | 2026-02-10 | Done late
71006142 | GRL | 1 | Yarn booking | Factory | 2025-10-28 |  | 2025-10-28 | Done
71006142 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-06 |  | 2025-11-06 | Done
71006142 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71006142 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-02 |  | 2025-12-02 | Done
71006142 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71006142 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-17 |  | 2025-12-17 | Done
71006142 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-20 |  | 2025-12-22 | Done late
71006142 | GRL | 8 | Knitting start | Factory | 2025-12-22 |  | 2025-12-23 | Done late
71006142 | GRL | 9 | Linking start | Factory | 2025-12-28 |  | 2025-12-28 | Done
71006142 | GRL | 10 | Final inspection | Karbar QA | 2026-01-29 |  | 2026-01-28 | Done
71006142 | GRL | 11 | Ex-factory | Factory | 2026-01-31 |  | 2026-01-29 | Done
71006145 | CLB | 1 | Yarn booking | Factory | 2025-11-15 |  | 2025-11-13 | Done
71006145 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-24 | Done
71006145 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-12-01 | Done late
71006145 | CLB | 4 | Size set approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-20 | Done
71006145 | CLB | 5 | PP sample approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-31 | Done late
71006145 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-04 |  | 2026-01-05 | Done late
71006145 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71006145 | CLB | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006145 | CLB | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-13 | Done
71006145 | CLB | 10 | Final inspection | Karbar QA | 2026-02-17 |  | 2026-02-17 | Done
71006145 | CLB | 11 | Ex-factory | Factory | 2026-02-18 |  | 2026-02-18 | Done
71006152 | WSM | 1 | Yarn booking | Factory | 2025-10-29 |  | 2025-10-29 | Done
71006152 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-08 |  | 2025-11-06 | Done
71006152 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-13 |  | 2025-11-12 | Done
71006152 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71006152 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71006152 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-18 |  | 2025-12-18 | Done
71006152 | WSM | 7 | PP meeting | Factory + Karbar QA | 2025-12-21 |  | 2025-12-20 | Done
71006152 | WSM | 8 | Knitting start | Factory | 2025-12-23 |  | 2025-12-23 | Done
71006152 | WSM | 9 | Linking start | Factory | 2025-12-29 |  | 2025-12-28 | Done
71006152 | WSM | 10 | Final inspection | Karbar QA | 2026-01-31 |  | 2026-01-31 | Done
71006152 | WSM | 11 | Ex-factory | Factory | 2026-02-01 |  | 2026-02-01 | Done
71006155 | OKH | 1 | Yarn booking | Factory | 2025-11-15 |  | 2025-11-16 | Done late
71006155 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-24 | Done
71006155 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-12-02 | Done late
71006155 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-20 | Done
71006155 | OKH | 5 | PP sample approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-30 | Done
71006155 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-04 |  | 2026-01-05 | Done late
71006155 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-01-07 |  | 2026-01-05 | Done
71006155 | OKH | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006155 | OKH | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-13 | Done
71006155 | OKH | 10 | Final inspection | Karbar QA | 2026-02-17 |  | 2026-02-17 | Done
71006155 | OKH | 11 | Ex-factory | Factory | 2026-02-18 |  | 2026-02-18 | Done
71006159 | GRL | 1 | Yarn booking | Factory | 2025-11-02 |  | 2025-11-03 | Done late
71006159 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71006159 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-19 | Done late
71006159 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71006159 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-16 | Done
71006159 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-22 |  | 2025-12-22 | Done
71006159 | GRL | 7 | PP meeting | Factory + Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71006159 | GRL | 8 | Knitting start | Factory | 2025-12-27 |  | 2025-12-27 | Done
71006159 | GRL | 9 | Linking start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71006159 | GRL | 10 | Final inspection | Karbar QA | 2026-02-04 |  | 2026-02-04 | Done
71006159 | GRL | 11 | Ex-factory | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006164 | IRB | 1 | Yarn booking | Factory | 2025-11-05 |  | 2025-11-04 | Done
71006164 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-15 |  | 2025-11-15 | Done
71006164 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71006164 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-11 | Done late
71006164 | IRB | 5 | PP sample approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-22 | Done late
71006164 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-25 | Done
71006164 | IRB | 7 | PP meeting | Factory + Karbar QA | 2025-12-28 |  | 2025-12-29 | Done late
71006164 | IRB | 8 | Knitting start | Factory | 2025-12-30 |  | 2025-12-31 | Done late
71006164 | IRB | 9 | Linking start | Factory | 2026-01-05 |  | 2026-01-05 | Done
71006164 | IRB | 10 | Final inspection | Karbar QA | 2026-02-07 |  | 2026-02-09 | Done late
71006164 | IRB | 11 | Ex-factory | Factory | 2026-02-08 |  | 2026-02-10 | Done late
71006167 | RSG | 1 | Yarn booking | Factory | 2025-12-07 |  | 2025-12-06 | Done
71006167 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-17 | Done
71006167 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2025-12-22 |  | 2025-12-22 | Done
71006167 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-01-11 |  | 2026-01-08 | Done
71006167 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-20 | Done
71006167 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-26 |  | 2026-01-25 | Done
71006167 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-01-29 |  | 2026-01-29 | Done
71006167 | RSG | 8 | Knitting start | Factory | 2026-01-31 |  | 2026-02-01 | Done late
71006167 | RSG | 9 | Linking start | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006167 | RSG | 10 | Final inspection | Karbar QA | 2026-03-11 |  | 2026-03-11 | Done
71006167 | RSG | 11 | Ex-factory | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006176 | MDW | 1 | Yarn booking | Factory | 2025-11-02 |  | 2025-11-01 | Done
71006176 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-12 |  | 2025-11-12 | Done
71006176 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-17 |  | 2025-11-19 | Done late
71006176 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71006176 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-17 | Done
71006176 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-22 |  | 2025-12-24 | Done late
71006176 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-12-25 |  | 2025-12-25 | Done
71006176 | MDW | 8 | Knitting start | Factory | 2025-12-27 |  | 2025-12-28 | Done late
71006176 | MDW | 9 | Linking start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71006176 | MDW | 10 | Final inspection | Karbar QA | 2026-02-04 |  | 2026-02-04 | Done
71006176 | MDW | 11 | Ex-factory | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006184 | TLG | 1 | Yarn booking | Factory | 2025-11-15 |  | 2025-11-15 | Done
71006184 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-23 | Done
71006184 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-12-02 | Done late
71006184 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-18 | Done
71006184 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-29 | Done
71006184 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-04 |  | 2026-01-06 | Done late
71006184 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-01-07 |  | 2026-01-07 | Done
71006184 | TLG | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-10 | Done late
71006184 | TLG | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006184 | TLG | 10 | Final inspection | Karbar QA | 2026-02-17 |  | 2026-02-18 | Done late
71006184 | TLG | 11 | Ex-factory | Factory | 2026-02-18 |  | 2026-02-19 | Done late
71006189 | TLG | 1 | Yarn booking | Factory | 2025-11-29 |  | 2025-11-29 | Done
71006189 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-09 |  | 2025-12-07 | Done
71006189 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-13 | Done
71006189 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-01 | Done
71006189 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-01-13 |  | 2026-01-15 | Done late
71006189 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-18 |  | 2026-01-18 | Done
71006189 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-01-21 |  | 2026-01-19 | Done
71006189 | TLG | 8 | Knitting start | Factory | 2026-01-22 |  | 2026-01-24 | Done late
71006189 | TLG | 9 | Linking start | Factory | 2026-01-29 |  | 2026-01-29 | Done
71006189 | TLG | 10 | Final inspection | Karbar QA | 2026-03-03 |  | 2026-03-03 | Done
71006189 | TLG | 11 | Ex-factory | Factory | 2026-03-04 |  | 2026-03-04 | Done
71006196 | AMB | 1 | Yarn booking | Factory | 2025-11-08 |  | 2025-11-08 | Done
71006196 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-18 | Done
71006196 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-24 | Done late
71006196 | AMB | 4 | Size set approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-14 | Done late
71006196 | AMB | 5 | PP sample approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-22 | Done
71006196 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-28 |  | 2025-12-28 | Done
71006196 | AMB | 7 | PP meeting | Factory + Karbar QA | 2025-12-31 |  | 2026-01-01 | Done late
71006196 | AMB | 8 | Knitting start | Factory | 2026-01-01 |  | 2026-01-03 | Done late
71006196 | AMB | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006196 | AMB | 10 | Final inspection | Karbar QA | 2026-02-10 |  | 2026-02-10 | Done
71006196 | AMB | 11 | Ex-factory | Factory | 2026-02-11 |  | 2026-02-11 | Done
71006205 | MDW | 1 | Yarn booking | Factory | 2025-11-06 |  | 2025-11-06 | Done
71006205 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-16 |  | 2025-11-15 | Done
71006205 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-11-20 |  | 2025-11-20 | Done
71006205 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-09 | Done
71006205 | MDW | 5 | PP sample approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-23 | Done late
71006205 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-25 |  | 2025-12-25 | Done
71006205 | MDW | 7 | PP meeting | Factory + Karbar QA | 2025-12-29 |  | 2025-12-28 | Done
71006205 | MDW | 8 | Knitting start | Factory | 2025-12-31 |  | 2026-01-01 | Done late
71006205 | MDW | 9 | Linking start | Factory | 2026-01-06 |  | 2026-01-06 | Done
71006205 | MDW | 10 | Final inspection | Karbar QA | 2026-02-08 |  | 2026-02-07 | Done
71006205 | MDW | 11 | Ex-factory | Factory | 2026-02-09 |  | 2026-02-08 | Done
71006210 | LTF | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-13 | Done
71006210 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-25 | Done late
71006210 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71006210 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-20 | Done late
71006210 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-30 | Done late
71006210 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-04 | Done late
71006210 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-01-05 |  | 2026-01-05 | Done
71006210 | LTF | 8 | Knitting start | Factory | 2026-01-07 |  | 2026-01-08 | Done late
71006210 | LTF | 9 | Linking start | Factory | 2026-01-13 |  | 2026-01-13 | Done
71006210 | LTF | 10 | Final inspection | Karbar QA | 2026-02-15 |  | 2026-02-15 | Done
71006210 | LTF | 11 | Ex-factory | Factory | 2026-02-16 |  | 2026-02-16 | Done
71006215 | TLG | 1 | Yarn booking | Factory | 2025-11-09 |  | 2025-11-09 | Done
71006215 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-19 |  | 2025-11-19 | Done
71006215 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-11-24 |  | 2025-11-24 | Done
71006215 | TLG | 4 | Size set approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71006215 | TLG | 5 | PP sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71006215 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-29 |  | 2025-12-31 | Done late
71006215 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-01-01 |  | 2026-01-01 | Done
71006215 | TLG | 8 | Knitting start | Factory | 2026-01-03 |  | 2026-01-04 | Done late
71006215 | TLG | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006215 | TLG | 10 | Final inspection | Karbar QA | 2026-02-11 |  | 2026-02-08 | Done
71006215 | TLG | 11 | Ex-factory | Factory | 2026-02-12 |  | 2026-02-09 | Done
71006222 | CPL | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-11 | Done
71006222 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-20 | Done
71006222 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-25 | Done
71006222 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006222 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006222 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-04 | Done late
71006222 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-01-05 |  | 2026-01-05 | Done
71006222 | CPL | 8 | Knitting start | Factory | 2026-01-07 |  | 2026-01-08 | Done late
71006222 | CPL | 9 | Linking start | Factory | 2026-01-13 |  | 2026-01-13 | Done
71006222 | CPL | 10 | Final inspection | Karbar QA | 2026-02-15 |  | 2026-02-15 | Done
71006222 | CPL | 11 | Ex-factory | Factory | 2026-02-16 |  | 2026-02-16 | Done
71006227 | PBB | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-13 | Done
71006227 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-26 | Done
71006227 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71006227 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-23 | Done late
71006227 | PBB | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2026-01-01 | Done late
71006227 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-05 | Done
71006227 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-08 | Done
71006227 | PBB | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-10 | Done
71006227 | PBB | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006227 | PBB | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-17 | Done
71006227 | PBB | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-18 | Done
71006234 | WTH | 1 | Yarn booking | Factory | 2025-11-18 |  | 2025-11-18 | Done
71006234 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-29 | Done late
71006234 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71006234 | WTH | 4 | Size set approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-25 | Done late
71006234 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-01-01 |  | 2026-01-01 | Done
71006234 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-07 |  | 2026-01-08 | Done late
71006234 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-01-10 |  | 2026-01-10 | Done
71006234 | WTH | 8 | Knitting start | Factory | 2026-01-12 |  | 2026-01-12 | Done
71006234 | WTH | 9 | Linking start | Factory | 2026-01-18 |  | 2026-01-17 | Done
71006234 | WTH | 10 | Final inspection | Karbar QA | 2026-02-19 |  | 2026-02-17 | Done
71006234 | WTH | 11 | Ex-factory | Factory | 2026-02-21 |  | 2026-02-18 | Done
71006243 | GRL | 1 | Yarn booking | Factory | 2025-11-20 |  | 2025-11-20 | Done
71006243 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71006243 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-04 | Done
71006243 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-25 |  | 2025-12-25 | Done
71006243 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-06 | Done late
71006243 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-08 |  | 2026-01-08 | Done
71006243 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-12 |  | 2026-01-12 | Done
71006243 | GRL | 8 | Knitting start | Factory | 2026-01-14 |  | 2026-01-15 | Done late
71006243 | GRL | 9 | Linking start | Factory | 2026-01-20 |  | 2026-01-20 | Done
71006243 | GRL | 10 | Final inspection | Karbar QA | 2026-02-22 |  | 2026-02-21 | Done
71006243 | GRL | 11 | Ex-factory | Factory | 2026-02-23 |  | 2026-02-22 | Done
71006248 | BRW | 1 | Yarn booking | Factory | 2025-11-27 |  | 2025-11-25 | Done
71006248 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-09 | Done late
71006248 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-14 | Done late
71006248 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-01-01 |  | 2026-01-03 | Done late
71006248 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-01-12 |  | 2026-01-11 | Done
71006248 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-17 |  | 2026-01-18 | Done late
71006248 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-01-20 |  | 2026-01-18 | Done
71006248 | BRW | 8 | Knitting start | Factory | 2026-01-22 |  | 2026-01-24 | Done late
71006248 | BRW | 9 | Linking start | Factory | 2026-01-28 |  | 2026-01-29 | Done late
71006248 | BRW | 10 | Final inspection | Karbar QA | 2026-03-02 |  | 2026-02-28 | Done
71006248 | BRW | 11 | Ex-factory | Factory | 2026-03-03 |  | 2026-03-01 | Done
71006255 | FNS | 1 | Yarn booking | Factory | 2025-11-08 |  | 2025-11-10 | Done late
71006255 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-18 |  | 2025-11-17 | Done
71006255 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-25 | Done late
71006255 | FNS | 4 | Size set approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-14 | Done late
71006255 | FNS | 5 | PP sample approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-24 | Done late
71006255 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2025-12-28 |  | 2025-12-30 | Done late
71006255 | FNS | 7 | PP meeting | Factory + Karbar QA | 2025-12-31 |  | 2025-12-30 | Done
71006255 | FNS | 8 | Knitting start | Factory | 2026-01-01 |  | 2026-01-01 | Done
71006255 | FNS | 9 | Linking start | Factory | 2026-01-08 |  | 2026-01-06 | Done
71006255 | FNS | 10 | Final inspection | Karbar QA | 2026-02-10 |  | 2026-02-07 | Done
71006255 | FNS | 11 | Ex-factory | Factory | 2026-02-11 |  | 2026-02-08 | Done
71006260 | LTF | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-18 | Done late
71006260 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-27 | Done late
71006260 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-01 | Done
71006260 | LTF | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-22 | Done late
71006260 | LTF | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006260 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-05 | Done
71006260 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-07 | Done
71006260 | LTF | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-11 | Done late
71006260 | LTF | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006260 | LTF | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-19 | Done late
71006260 | LTF | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-21 | Done late
71006265 | CPL | 1 | Yarn booking | Factory | 2025-11-16 |  | 2025-11-15 | Done
71006265 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-26 |  | 2025-11-24 | Done
71006265 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-01 |  | 2025-11-29 | Done
71006265 | CPL | 4 | Size set approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-23 | Done late
71006265 | CPL | 5 | PP sample approval | Karbar Merchandising | 2025-12-31 |  | 2026-01-01 | Done late
71006265 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-05 |  | 2026-01-05 | Done
71006265 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-01-08 |  | 2026-01-10 | Done late
71006265 | CPL | 8 | Knitting start | Factory | 2026-01-10 |  | 2026-01-10 | Done
71006265 | CPL | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006265 | CPL | 10 | Final inspection | Karbar QA | 2026-02-18 |  | 2026-02-16 | Done
71006265 | CPL | 11 | Ex-factory | Factory | 2026-02-19 |  | 2026-02-17 | Done
71006274 | BRW | 1 | Yarn booking | Factory | 2025-12-13 |  | 2025-12-11 | Done
71006274 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-23 | Done
71006274 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006274 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-18 | Done late
71006274 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-01-27 |  | 2026-01-29 | Done late
71006274 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-01 |  | 2026-01-31 | Done
71006274 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-02-04 |  | 2026-02-04 | Done
71006274 | BRW | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-07 | Done late
71006274 | BRW | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006274 | BRW | 10 | Final inspection | Karbar QA | 2026-03-17 |  | 2026-03-17 | Done
71006274 | BRW | 11 | Ex-factory | Factory | 2026-03-18 |  | 2026-03-18 | Done
71006283 | WSM | 1 | Yarn booking | Factory | 2025-11-12 |  | 2025-11-12 | Done
71006283 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-22 |  | 2025-11-22 | Done
71006283 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-25 | Done
71006283 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-16 | Done
71006283 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-29 | Done late
71006283 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-01 | Done
71006283 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-01-04 |  | 2026-01-04 | Done
71006283 | WSM | 8 | Knitting start | Factory | 2026-01-06 |  | 2026-01-07 | Done late
71006283 | WSM | 9 | Linking start | Factory | 2026-01-12 |  | 2026-01-12 | Done
71006283 | WSM | 10 | Final inspection | Karbar QA | 2026-02-14 |  | 2026-02-14 | Done
71006283 | WSM | 11 | Ex-factory | Factory | 2026-02-15 |  | 2026-02-15 | Done
71006286 | BRW | 1 | Yarn booking | Factory | 2025-12-16 |  | 2025-12-16 | Done
71006286 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-25 |  | 2025-12-25 | Done
71006286 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2025-12-31 |  | 2026-01-01 | Done late
71006286 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-01-20 |  | 2026-01-20 | Done
71006286 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-29 | Done
71006286 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-04 |  | 2026-02-05 | Done late
71006286 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-02-07 |  | 2026-02-07 | Done
71006286 | BRW | 8 | Knitting start | Factory | 2026-02-09 |  | 2026-02-10 | Done late
71006286 | BRW | 9 | Linking start | Factory | 2026-02-15 |  | 2026-02-15 | Done
71006286 | BRW | 10 | Final inspection | Karbar QA | 2026-03-19 |  | 2026-03-19 | Done
71006286 | BRW | 11 | Ex-factory | Factory | 2026-03-21 |  | 2026-03-21 | Done
71006289 | GRL | 1 | Yarn booking | Factory | 2025-11-13 |  | 2025-11-13 | Done
71006289 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-23 |  | 2025-11-23 | Done
71006289 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-27 | Done
71006289 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-20 | Done late
71006289 | GRL | 5 | PP sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006289 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-01 |  | 2026-01-01 | Done
71006289 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-05 |  | 2026-01-05 | Done
71006289 | GRL | 8 | Knitting start | Factory | 2026-01-07 |  | 2026-01-08 | Done late
71006289 | GRL | 9 | Linking start | Factory | 2026-01-13 |  | 2026-01-13 | Done
71006289 | GRL | 10 | Final inspection | Karbar QA | 2026-02-15 |  | 2026-02-17 | Done late
71006289 | GRL | 11 | Ex-factory | Factory | 2026-02-16 |  | 2026-02-18 | Done late
71006297 | WSM | 1 | Yarn booking | Factory | 2025-11-15 |  | 2025-11-16 | Done late
71006297 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-25 |  | 2025-11-24 | Done
71006297 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-11-30 |  | 2025-11-30 | Done
71006297 | WSM | 4 | Size set approval | Karbar Merchandising | 2025-12-20 |  | 2025-12-18 | Done
71006297 | WSM | 5 | PP sample approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-29 | Done
71006297 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-04 |  | 2026-01-03 | Done
71006297 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-01-07 |  | 2026-01-06 | Done
71006297 | WSM | 8 | Knitting start | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006297 | WSM | 9 | Linking start | Factory | 2026-01-15 |  | 2026-01-13 | Done
71006297 | WSM | 10 | Final inspection | Karbar QA | 2026-02-17 |  | 2026-02-19 | Done late
71006297 | WSM | 11 | Ex-factory | Factory | 2026-02-18 |  | 2026-02-21 | Done late
71006301 | KST | 1 | Yarn booking | Factory | 2025-11-27 |  | 2025-11-27 | Done
71006301 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-07 |  | 2025-12-07 | Done
71006301 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71006301 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-01 |  | 2026-01-01 | Done
71006301 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-11 |  | 2026-01-13 | Done late
71006301 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-15 |  | 2026-01-15 | Done
71006301 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-19 |  | 2026-01-20 | Done late
71006301 | KST | 8 | Knitting start | Factory | 2026-01-21 |  | 2026-01-21 | Done
71006301 | KST | 9 | Linking start | Factory | 2026-01-27 |  | 2026-01-26 | Done
71006301 | KST | 10 | Final inspection | Karbar QA | 2026-03-01 |  | 2026-03-01 | Done
71006301 | KST | 11 | Ex-factory | Factory | 2026-03-02 |  | 2026-03-02 | Done
71006306 | GRL | 1 | Yarn booking | Factory | 2025-11-26 |  | 2025-11-26 | Done
71006306 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-07 | Done late
71006306 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71006306 | GRL | 4 | Size set approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006306 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-10 |  | 2026-01-11 | Done late
71006306 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-15 |  | 2026-01-17 | Done late
71006306 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-18 |  | 2026-01-18 | Done
71006306 | GRL | 8 | Knitting start | Factory | 2026-01-20 |  | 2026-01-20 | Done
71006306 | GRL | 9 | Linking start | Factory | 2026-01-26 |  | 2026-01-25 | Done
71006306 | GRL | 10 | Final inspection | Karbar QA | 2026-02-28 |  | 2026-02-28 | Done
71006306 | GRL | 11 | Ex-factory | Factory | 2026-03-01 |  | 2026-03-01 | Done
71006310 | OKH | 1 | Yarn booking | Factory | 2025-11-18 |  | 2025-11-19 | Done late
71006310 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-27 |  | 2025-11-25 | Done
71006310 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71006310 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-23 | Done
71006310 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-01-01 |  | 2025-12-31 | Done
71006310 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-07 |  | 2026-01-08 | Done late
71006310 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-01-10 |  | 2026-01-10 | Done
71006310 | OKH | 8 | Knitting start | Factory | 2026-01-12 |  | 2026-01-12 | Done
71006310 | OKH | 9 | Linking start | Factory | 2026-01-18 |  | 2026-01-17 | Done
71006310 | OKH | 10 | Final inspection | Karbar QA | 2026-02-19 |  | 2026-02-19 | Done
71006310 | OKH | 11 | Ex-factory | Factory | 2026-02-21 |  | 2026-02-21 | Done
71006314 | OKH | 1 | Yarn booking | Factory | 2025-11-20 |  | 2025-11-18 | Done
71006314 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-01 |  | 2025-12-02 | Done late
71006314 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-06 | Done
71006314 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-25 |  | 2025-12-24 | Done
71006314 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-01-05 |  | 2026-01-05 | Done
71006314 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-10 |  | 2026-01-10 | Done
71006314 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-01-13 |  | 2026-01-15 | Done late
71006314 | OKH | 8 | Knitting start | Factory | 2026-01-15 |  | 2026-01-17 | Done late
71006314 | OKH | 9 | Linking start | Factory | 2026-01-21 |  | 2026-01-22 | Done late
71006314 | OKH | 10 | Final inspection | Karbar QA | 2026-02-23 |  | 2026-02-25 | Done late
71006314 | OKH | 11 | Ex-factory | Factory | 2026-02-24 |  | 2026-02-26 | Done late
71006317 | WSM | 1 | Yarn booking | Factory | 2025-12-11 |  | 2025-12-13 | Done late
71006317 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-22 |  | 2025-12-24 | Done late
71006317 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-28 | Done late
71006317 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006317 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-27 | Done late
71006317 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-31 |  | 2026-01-31 | Done
71006317 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-02-03 |  | 2026-02-03 | Done
71006317 | WSM | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006317 | WSM | 9 | Linking start | Factory | 2026-02-11 |  | 2026-02-10 | Done
71006317 | WSM | 10 | Final inspection | Karbar QA | 2026-03-16 |  | 2026-03-16 | Done
71006317 | WSM | 11 | Ex-factory | Factory | 2026-03-17 |  | 2026-03-17 | Done
71006321 | IRB | 1 | Yarn booking | Factory | 2025-11-26 |  | 2025-11-26 | Done
71006321 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-06 |  | 2025-12-07 | Done late
71006321 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71006321 | IRB | 4 | Size set approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006321 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-01-10 |  | 2026-01-11 | Done late
71006321 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-15 |  | 2026-01-18 | Done late
71006321 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-01-18 |  | 2026-01-15 | Done
71006321 | IRB | 8 | Knitting start | Factory | 2026-01-20 |  | 2026-01-20 | Done
71006321 | IRB | 9 | Linking start | Factory | 2026-01-26 |  | 2026-01-25 | Done
71006321 | IRB | 10 | Final inspection | Karbar QA | 2026-02-28 |  | 2026-03-11 | Done late
71006321 | IRB | 11 | Ex-factory | Factory | 2026-03-01 |  | 2026-03-12 | Done late
71006325 | PBB | 1 | Yarn booking | Factory | 2025-12-20 |  | 2025-12-20 | Done
71006325 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-30 | Done
71006325 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-04 | Done
71006325 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-01-24 |  | 2026-01-24 | Done
71006325 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-02-03 |  | 2026-02-03 | Done
71006325 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-08 |  | 2026-02-08 | Done
71006325 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-02-11 |  | 2026-02-11 | Done
71006325 | PBB | 8 | Knitting start | Factory | 2026-02-12 |  | 2026-02-14 | Done late
71006325 | PBB | 9 | Linking start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006325 | PBB | 10 | Final inspection | Karbar QA | 2026-03-24 |  | 2026-03-24 | Done
71006325 | PBB | 11 | Ex-factory | Factory | 2026-03-25 |  | 2026-03-25 | Done
71006334 | SND | 1 | Yarn booking | Factory | 2025-11-19 |  | 2025-11-19 | Done
71006334 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2025-11-29 |  | 2025-12-01 | Done late
71006334 | SND | 3 | Fit sample approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-04 | Done
71006334 | SND | 4 | Size set approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-22 | Done
71006334 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-03 | Done
71006334 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-08 |  | 2026-01-06 | Done
71006334 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-01-11 |  | 2026-01-11 | Done
71006334 | SND | 8 | Knitting start | Factory | 2026-01-13 |  | 2026-01-13 | Done
71006334 | SND | 9 | Linking start | Factory | 2026-01-19 |  | 2026-01-18 | Done
71006334 | SND | 10 | Final inspection | Karbar QA | 2026-02-21 |  | 2026-02-21 | Done
71006334 | SND | 11 | Ex-factory | Factory | 2026-02-22 |  | 2026-02-22 | Done
71006337 | TLG | 1 | Yarn booking | Factory | 2025-12-02 |  | 2025-12-02 | Done
71006337 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-11 |  | 2025-12-11 | Done
71006337 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2025-12-17 |  | 2025-12-17 | Done
71006337 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-01-06 |  | 2026-01-06 | Done
71006337 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006337 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-21 |  | 2026-01-21 | Done
71006337 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-01-24 |  | 2026-01-24 | Done
71006337 | TLG | 8 | Knitting start | Factory | 2026-01-26 |  | 2026-01-26 | Done
71006337 | TLG | 9 | Linking start | Factory | 2026-02-01 |  | 2026-01-31 | Done
71006337 | TLG | 10 | Final inspection | Karbar QA | 2026-03-05 |  | 2026-03-05 | Done
71006337 | TLG | 11 | Ex-factory | Factory | 2026-03-07 |  | 2026-03-07 | Done
71006343 | KST | 1 | Yarn booking | Factory | 2025-12-04 |  | 2025-12-04 | Done
71006343 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-14 |  | 2025-12-14 | Done
71006343 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-20 | Done late
71006343 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-07 | Done
71006343 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-20 | Done late
71006343 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-22 |  | 2026-01-22 | Done
71006343 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-26 |  | 2026-01-27 | Done late
71006343 | KST | 8 | Knitting start | Factory | 2026-01-28 |  | 2026-01-28 | Done
71006343 | KST | 9 | Linking start | Factory | 2026-02-03 |  | 2026-02-02 | Done
71006343 | KST | 10 | Final inspection | Karbar QA | 2026-03-08 |  | 2026-03-05 | Done
71006343 | KST | 11 | Ex-factory | Factory | 2026-03-09 |  | 2026-03-07 | Done
71006352 | LTF | 1 | Yarn booking | Factory | 2025-12-13 |  | 2025-12-11 | Done
71006352 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-23 |  | 2025-12-25 | Done late
71006352 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-29 | Done late
71006352 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-18 | Done late
71006352 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-01-27 |  | 2026-01-27 | Done
71006352 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-01 |  | 2026-02-02 | Done late
71006352 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-02-04 |  | 2026-02-02 | Done
71006352 | LTF | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-07 | Done late
71006352 | LTF | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006352 | LTF | 10 | Final inspection | Karbar QA | 2026-03-17 |  | 2026-03-15 | Done
71006352 | LTF | 11 | Ex-factory | Factory | 2026-03-18 |  | 2026-03-16 | Done
71006355 | KST | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-25 | Done late
71006355 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-01 | Done
71006355 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-10 | Done late
71006355 | KST | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006355 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006355 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-12 | Done
71006355 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-15 | Done
71006355 | KST | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-17 | Done
71006355 | KST | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006355 | KST | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-25 | Done
71006355 | KST | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006358 | SVP | 1 | Yarn booking | Factory | 2025-12-11 |  | 2025-12-11 | Done
71006358 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-21 |  | 2025-12-21 | Done
71006358 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-12-25 |  | 2025-12-23 | Done
71006358 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006358 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-26 | Done late
71006358 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-29 |  | 2026-01-29 | Done
71006358 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-02-02 |  | 2026-02-03 | Done late
71006358 | SVP | 8 | Knitting start | Factory | 2026-02-04 |  | 2026-02-04 | Done
71006358 | SVP | 9 | Linking start | Factory | 2026-02-10 |  | 2026-02-09 | Done
71006358 | SVP | 10 | Final inspection | Karbar QA | 2026-03-15 |  | 2026-03-15 | Done
71006358 | SVP | 11 | Ex-factory | Factory | 2026-03-16 |  | 2026-03-16 | Done
71006365 | PBB | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-20 | Done
71006365 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-02 | Done
71006365 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-07 | Done
71006365 | PBB | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006365 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006365 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-12 | Done
71006365 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-14 | Done
71006365 | PBB | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-17 | Done
71006365 | PBB | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006365 | PBB | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-25 | Done
71006365 | PBB | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006370 | IRB | 1 | Yarn booking | Factory | 2025-12-03 |  | 2025-12-03 | Done
71006370 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-13 |  | 2025-12-13 | Done
71006370 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006370 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-08 | Done late
71006370 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-15 | Done
71006370 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-22 |  | 2026-01-24 | Done late
71006370 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-01-25 |  | 2026-01-25 | Done
71006370 | IRB | 8 | Knitting start | Factory | 2026-01-27 |  | 2026-01-28 | Done late
71006370 | IRB | 9 | Linking start | Factory | 2026-02-02 |  | 2026-02-02 | Done
71006370 | IRB | 10 | Final inspection | Karbar QA | 2026-03-07 |  | 2026-03-05 | Done
71006370 | IRB | 11 | Ex-factory | Factory | 2026-03-08 |  | 2026-03-07 | Done
71006376 | SVP | 1 | Yarn booking | Factory | 2025-12-25 |  | 2025-12-27 | Done late
71006376 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-05 |  | 2026-01-05 | Done
71006376 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-01-10 |  | 2026-01-12 | Done late
71006376 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-29 | Done
71006376 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-02-09 |  | 2026-02-08 | Done
71006376 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-14 |  | 2026-02-14 | Done
71006376 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-02-17 |  | 2026-02-17 | Done
71006376 | SVP | 8 | Knitting start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006376 | SVP | 9 | Linking start | Factory | 2026-02-25 |  | 2026-02-24 | Done
71006376 | SVP | 10 | Final inspection | Karbar QA | 2026-03-30 |  | 2026-03-29 | Done
71006376 | SVP | 11 | Ex-factory | Factory | 2026-03-31 |  | 2026-03-30 | Done
71006381 | GRL | 1 | Yarn booking | Factory | 2025-11-30 |  | 2025-12-02 | Done late
71006381 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006381 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-15 |  | 2025-12-14 | Done
71006381 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-04 | Done
71006381 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-14 |  | 2026-01-14 | Done
71006381 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-19 |  | 2026-01-18 | Done
71006381 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-01-22 |  | 2026-01-22 | Done
71006381 | GRL | 8 | Knitting start | Factory | 2026-01-24 |  | 2026-01-24 | Done
71006381 | GRL | 9 | Linking start | Factory | 2026-01-29 |  | 2026-01-29 | Done
71006381 | GRL | 10 | Final inspection | Karbar QA | 2026-03-04 |  | 2026-03-04 | Done
71006381 | GRL | 11 | Ex-factory | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006384 | CLB | 1 | Yarn booking | Factory | 2025-12-14 |  | 2025-12-15 | Done late
71006384 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71006384 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-30 | Done late
71006384 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006384 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-29 | Done late
71006384 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-02 |  | 2026-02-03 | Done late
71006384 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-02-05 |  | 2026-02-03 | Done
71006384 | CLB | 8 | Knitting start | Factory | 2026-02-07 |  | 2026-02-07 | Done
71006384 | CLB | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006384 | CLB | 10 | Final inspection | Karbar QA | 2026-03-18 |  | 2026-03-18 | Done
71006384 | CLB | 11 | Ex-factory | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006390 | OKH | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-23 | Done
71006390 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-03 | Done
71006390 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-08 | Done
71006390 | OKH | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-25 | Done
71006390 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-06 | Done
71006390 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-10 | Done
71006390 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-13 | Done
71006390 | OKH | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-17 | Done
71006390 | OKH | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006390 | OKH | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-25 | Done
71006390 | OKH | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006398 | SLM | 1 | Yarn booking | Factory | 2025-12-17 |  | 2025-12-18 | Done late
71006398 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-29 | Done late
71006398 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-01-01 |  | 2026-01-01 | Done
71006398 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-21 | Done
71006398 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-01-31 |  | 2026-01-31 | Done
71006398 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-05 |  | 2026-02-05 | Done
71006398 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-02-08 |  | 2026-02-08 | Done
71006398 | SLM | 8 | Knitting start | Factory | 2026-02-10 |  | 2026-02-10 | Done
71006398 | SLM | 9 | Linking start | Factory | 2026-02-16 |  | 2026-02-15 | Done
71006398 | SLM | 10 | Final inspection | Karbar QA | 2026-03-21 |  | 2026-03-21 | Done
71006398 | SLM | 11 | Ex-factory | Factory | 2026-03-22 |  | 2026-03-22 | Done
71006401 | IRB | 1 | Yarn booking | Factory | 2025-12-21 |  | 2025-12-21 | Done
71006401 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006401 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-05 |  | 2026-01-03 | Done
71006401 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-26 | Done late
71006401 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-02-04 |  | 2026-02-05 | Done late
71006401 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-09 |  | 2026-02-09 | Done
71006401 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-02-12 |  | 2026-02-14 | Done late
71006401 | IRB | 8 | Knitting start | Factory | 2026-02-14 |  | 2026-02-15 | Done late
71006401 | IRB | 9 | Linking start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006401 | IRB | 10 | Final inspection | Karbar QA | 2026-03-25 |  | 2026-03-25 | Done
71006401 | IRB | 11 | Ex-factory | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006404 | KST | 1 | Yarn booking | Factory | 2025-11-23 |  | 2025-11-23 | Done
71006404 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-03 |  | 2025-12-04 | Done late
71006404 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-08 |  | 2025-12-10 | Done late
71006404 | KST | 4 | Size set approval | Karbar Merchandising | 2025-12-28 |  | 2025-12-28 | Done
71006404 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006404 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-12 |  | 2026-01-13 | Done late
71006404 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-15 |  | 2026-01-14 | Done
71006404 | KST | 8 | Knitting start | Factory | 2026-01-17 |  | 2026-01-18 | Done late
71006404 | KST | 9 | Linking start | Factory | 2026-01-22 |  | 2026-01-22 | Done
71006404 | KST | 10 | Final inspection | Karbar QA | 2026-02-25 |  | 2026-02-23 | Done
71006404 | KST | 11 | Ex-factory | Factory | 2026-02-26 |  | 2026-02-24 | Done
71006409 | MDW | 1 | Yarn booking | Factory | 2025-11-25 |  | 2025-11-25 | Done
71006409 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-04 |  | 2025-12-04 | Done
71006409 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006409 | MDW | 4 | Size set approval | Karbar Merchandising | 2025-12-30 |  | 2025-12-30 | Done
71006409 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-07 | Done
71006409 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-14 |  | 2026-01-14 | Done
71006409 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-01-17 |  | 2026-01-17 | Done
71006409 | MDW | 8 | Knitting start | Factory | 2026-01-19 |  | 2026-01-19 | Done
71006409 | MDW | 9 | Linking start | Factory | 2026-01-25 |  | 2026-01-24 | Done
71006409 | MDW | 10 | Final inspection | Karbar QA | 2026-02-26 |  | 2026-02-26 | Done
71006409 | MDW | 11 | Ex-factory | Factory | 2026-02-28 |  | 2026-02-28 | Done
71006414 | GRL | 1 | Yarn booking | Factory | 2025-12-17 |  | 2025-12-15 | Done
71006414 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-27 | Done
71006414 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-01-01 |  | 2025-12-30 | Done
71006414 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-19 | Done
71006414 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-31 |  | 2026-01-29 | Done
71006414 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-05 |  | 2026-02-08 | Done late
71006414 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-02-08 |  | 2026-02-10 | Done late
71006414 | GRL | 8 | Knitting start | Factory | 2026-02-10 |  | 2026-02-11 | Done late
71006414 | GRL | 9 | Linking start | Factory | 2026-02-16 |  | 2026-02-16 | Done
71006414 | GRL | 10 | Final inspection | Karbar QA | 2026-03-21 |  | 2026-03-21 | Done
71006414 | GRL | 11 | Ex-factory | Factory | 2026-03-22 |  | 2026-03-22 | Done
71006421 | GRL | 1 | Yarn booking | Factory | 2025-12-24 |  | 2025-12-24 | Done
71006421 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-01 | Done
71006421 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-08 | Done
71006421 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-29 | Done late
71006421 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-02-07 |  | 2026-02-07 | Done
71006421 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-12 |  | 2026-02-12 | Done
71006421 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-02-15 |  | 2026-02-17 | Done late
71006421 | GRL | 8 | Knitting start | Factory | 2026-02-17 |  | 2026-02-17 | Done
71006421 | GRL | 9 | Linking start | Factory | 2026-02-23 |  | 2026-02-22 | Done
71006421 | GRL | 10 | Final inspection | Karbar QA | 2026-03-28 |  | 2026-03-28 | Done
71006421 | GRL | 11 | Ex-factory | Factory | 2026-03-29 |  | 2026-03-29 | Done
71006426 | KST | 1 | Yarn booking | Factory | 2025-11-30 |  | 2025-11-27 | Done
71006426 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-10 |  | 2025-12-10 | Done
71006426 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-15 |  | 2025-12-15 | Done
71006426 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-04 | Done
71006426 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-14 |  | 2026-01-15 | Done late
71006426 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-19 |  | 2026-01-19 | Done
71006426 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-01-22 |  | 2026-01-22 | Done
71006426 | KST | 8 | Knitting start | Factory | 2026-01-24 |  | 2026-01-24 | Done
71006426 | KST | 9 | Linking start | Factory | 2026-01-29 |  | 2026-01-29 | Done
71006426 | KST | 10 | Final inspection | Karbar QA | 2026-03-04 |  | 2026-03-01 | Done
71006426 | KST | 11 | Ex-factory | Factory | 2026-03-05 |  | 2026-03-02 | Done
71006433 | GRL | 1 | Yarn booking | Factory | 2025-12-27 |  | 2025-12-28 | Done late
71006433 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-06 |  | 2026-01-04 | Done
71006433 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-01-11 |  | 2026-01-12 | Done late
71006433 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-01-31 |  | 2026-01-29 | Done
71006433 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-02-10 |  | 2026-02-10 | Done
71006433 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-15 |  | 2026-02-16 | Done late
71006433 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-02-18 |  | 2026-02-18 | Done
71006433 | GRL | 8 | Knitting start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006433 | GRL | 9 | Linking start | Factory | 2026-02-26 |  | 2026-02-24 | Done
71006433 | GRL | 10 | Final inspection | Karbar QA | 2026-03-31 |  | 2026-03-31 | Done
71006433 | GRL | 11 | Ex-factory | Factory | 2026-04-01 |  | 2026-04-01 | Done
71006438 | KST | 1 | Yarn booking | Factory | 2025-12-18 |  | 2025-12-17 | Done
71006438 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-29 | Done
71006438 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-04 | Done late
71006438 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006438 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-02-02 |  | 2026-02-03 | Done late
71006438 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-07 |  | 2026-02-09 | Done late
71006438 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-02-10 |  | 2026-02-12 | Done late
71006438 | KST | 8 | Knitting start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006438 | KST | 9 | Linking start | Factory | 2026-02-18 |  | 2026-02-17 | Done
71006438 | KST | 10 | Final inspection | Karbar QA | 2026-03-23 |  | 2026-03-21 | Done
71006438 | KST | 11 | Ex-factory | Factory | 2026-03-24 |  | 2026-03-22 | Done
71006445 | MDW | 1 | Yarn booking | Factory | 2025-12-28 |  | 2025-12-29 | Done late
71006445 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-08 | Done late
71006445 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-12 |  | 2026-01-13 | Done late
71006445 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-02-01 |  | 2026-01-29 | Done
71006445 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-10 | Done
71006445 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-16 |  | 2026-02-19 | Done late
71006445 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-02-19 |  | 2026-02-17 | Done
71006445 | MDW | 8 | Knitting start | Factory | 2026-02-21 |  | 2026-02-21 | Done
71006445 | MDW | 9 | Linking start | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006445 | MDW | 10 | Final inspection | Karbar QA | 2026-04-01 |  | 2026-04-01 | Done
71006445 | MDW | 11 | Ex-factory | Factory | 2026-04-02 |  | 2026-04-02 | Done
71006448 | SLM | 1 | Yarn booking | Factory | 2026-01-03 |  | 2026-01-05 | Done late
71006448 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-13 |  | 2026-01-13 | Done
71006448 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006448 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-02-07 |  | 2026-02-07 | Done
71006448 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-02-17 |  | 2026-02-19 | Done late
71006448 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-22 |  | 2026-02-19 | Done
71006448 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-02-25 |  | 2026-02-23 | Done
71006448 | SLM | 8 | Knitting start | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006448 | SLM | 9 | Linking start | Factory | 2026-03-05 |  | 2026-03-03 | Done
71006448 | SLM | 10 | Final inspection | Karbar QA | 2026-04-07 |  | 2026-04-07 | Done
71006448 | SLM | 11 | Ex-factory | Factory | 2026-04-08 |  | 2026-04-08 | Done
71006456 | SLM | 1 | Yarn booking | Factory | 2025-12-25 |  | 2025-12-24 | Done
71006456 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-04 | Done
71006456 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-08 | Done
71006456 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-28 | Done
71006456 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-09 | Done late
71006456 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-12 |  | 2026-02-12 | Done
71006456 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-02-16 |  | 2026-02-16 | Done
71006456 | SLM | 8 | Knitting start | Factory | 2026-02-18 |  | 2026-02-19 | Done late
71006456 | SLM | 9 | Linking start | Factory | 2026-02-24 |  | 2026-02-24 | Done
71006456 | SLM | 10 | Final inspection | Karbar QA | 2026-03-29 |  | 2026-03-29 | Done
71006456 | SLM | 11 | Ex-factory | Factory | 2026-03-30 |  | 2026-03-30 | Done
71006460 | FNS | 1 | Yarn booking | Factory | 2026-01-04 |  | 2026-01-06 | Done late
71006460 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-14 |  | 2026-01-15 | Done late
71006460 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-19 |  | 2026-01-19 | Done
71006460 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-08 | Done
71006460 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-02-18 |  | 2026-02-18 | Done
71006460 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-23 |  | 2026-02-23 | Done
71006460 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-02-26 |  | 2026-02-26 | Done
71006460 | FNS | 8 | Knitting start | Factory | 2026-02-28 |  | 2026-03-01 | Done late
71006460 | FNS | 9 | Linking start | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006460 | FNS | 10 | Final inspection | Karbar QA | 2026-04-08 |  | 2026-04-08 | Done
71006460 | FNS | 11 | Ex-factory | Factory | 2026-04-09 |  | 2026-04-09 | Done
71006468 | SLM | 1 | Yarn booking | Factory | 2025-12-14 |  | 2025-12-13 | Done
71006468 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-22 | Done
71006468 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-29 | Done
71006468 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-17 | Done
71006468 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-27 | Done
71006468 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-02 |  | 2026-02-04 | Done late
71006468 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-02-05 |  | 2026-02-05 | Done
71006468 | SLM | 8 | Knitting start | Factory | 2026-02-07 |  | 2026-02-07 | Done
71006468 | SLM | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006468 | SLM | 10 | Final inspection | Karbar QA | 2026-03-18 |  | 2026-03-18 | Done
71006468 | SLM | 11 | Ex-factory | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006473 | BLF | 1 | Yarn booking | Factory | 2025-12-11 |  | 2025-12-11 | Done
71006473 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-22 |  | 2025-12-22 | Done
71006473 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-25 | Done
71006473 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-13 | Done
71006473 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-25 | Done
71006473 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-31 |  | 2026-02-01 | Done late
71006473 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-02-03 |  | 2026-02-01 | Done
71006473 | BLF | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-07 | Done late
71006473 | BLF | 9 | Linking start | Factory | 2026-02-11 |  | 2026-02-12 | Done late
71006473 | BLF | 10 | Final inspection | Karbar QA | 2026-03-16 |  | 2026-03-16 | Done
71006473 | BLF | 11 | Ex-factory | Factory | 2026-03-17 |  | 2026-03-17 | Done
71006479 | RVS | 1 | Yarn booking | Factory | 2026-01-06 |  | 2026-01-07 | Done late
71006479 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006479 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-21 | Done
71006479 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-02-10 |  | 2026-02-08 | Done
71006479 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-18 | Done
71006479 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-25 |  | 2026-02-23 | Done
71006479 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-02-28 |  | 2026-03-01 | Done late
71006479 | RVS | 8 | Knitting start | Factory | 2026-03-02 |  | 2026-03-03 | Done late
71006479 | RVS | 9 | Linking start | Factory | 2026-03-08 |  | 2026-03-08 | Done
71006479 | RVS | 10 | Final inspection | Karbar QA | 2026-04-09 |  | 2026-04-13 | Done late
71006479 | RVS | 11 | Ex-factory | Factory | 2026-04-11 |  | 2026-04-14 | Done late
71006487 | CLB | 1 | Yarn booking | Factory | 2026-01-08 |  | 2026-01-06 | Done
71006487 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-19 |  | 2026-01-20 | Done late
71006487 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-24 |  | 2026-01-22 | Done
71006487 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-02-12 |  | 2026-02-12 | Done
71006487 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-02-23 |  | 2026-02-23 | Done
71006487 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-28 |  | 2026-02-28 | Done
71006487 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-03-03 |  | 2026-03-03 | Done
71006487 | CLB | 8 | Knitting start | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006487 | CLB | 9 | Linking start | Factory | 2026-03-11 |  | 2026-03-10 | Done
71006487 | CLB | 10 | Final inspection | Karbar QA | 2026-04-13 |  | 2026-04-13 | Done
71006487 | CLB | 11 | Ex-factory | Factory | 2026-04-14 |  | 2026-04-14 | Done
71006492 | SLM | 1 | Yarn booking | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006492 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006492 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006492 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-02-12 |  | 2026-02-12 | Done
71006492 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-23 | Done late
71006492 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-26 |  | 2026-02-26 | Done
71006492 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-03-02 |  | 2026-03-02 | Done
71006492 | SLM | 8 | Knitting start | Factory | 2026-03-04 |  | 2026-03-04 | Done
71006492 | SLM | 9 | Linking start | Factory | 2026-03-10 |  | 2026-03-09 | Done
71006492 | SLM | 10 | Final inspection | Karbar QA | 2026-04-12 |  | 2026-04-21 | Done late
71006492 | SLM | 11 | Ex-factory | Factory | 2026-04-13 |  | 2026-04-22 | Done late
71006497 | GRL | 1 | Yarn booking | Factory | 2025-12-11 |  | 2025-12-10 | Done
71006497 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-22 |  | 2025-12-20 | Done
71006497 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-27 | Done
71006497 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006497 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-28 | Done late
71006497 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-31 |  | 2026-01-31 | Done
71006497 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-02-03 |  | 2026-02-01 | Done
71006497 | GRL | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-07 | Done late
71006497 | GRL | 9 | Linking start | Factory | 2026-02-11 |  | 2026-02-12 | Done late
71006497 | GRL | 10 | Final inspection | Karbar QA | 2026-03-16 |  | 2026-03-16 | Done
71006497 | GRL | 11 | Ex-factory | Factory | 2026-03-17 |  | 2026-03-17 | Done
71006503 | PBB | 1 | Yarn booking | Factory | 2025-12-11 |  | 2025-12-11 | Done
71006503 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-22 |  | 2025-12-22 | Done
71006503 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2025-12-27 |  | 2025-12-25 | Done
71006503 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-15 | Done
71006503 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-28 | Done late
71006503 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-31 |  | 2026-01-29 | Done
71006503 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-02-03 |  | 2026-02-05 | Done late
71006503 | PBB | 8 | Knitting start | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006503 | PBB | 9 | Linking start | Factory | 2026-02-11 |  | 2026-02-10 | Done
71006503 | PBB | 10 | Final inspection | Karbar QA | 2026-03-16 |  | 2026-03-16 | Done
71006503 | PBB | 11 | Ex-factory | Factory | 2026-03-17 |  | 2026-03-17 | Done
71006510 | SLM | 1 | Yarn booking | Factory | 2025-12-09 |  | 2025-12-11 | Done late
71006510 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-18 |  | 2025-12-18 | Done
71006510 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-22 | Done
71006510 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-01-13 |  | 2026-01-11 | Done
71006510 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006510 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-01-28 |  | 2026-01-28 | Done
71006510 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-01-31 |  | 2026-01-29 | Done
71006510 | SLM | 8 | Knitting start | Factory | 2026-02-02 |  | 2026-02-02 | Done
71006510 | SLM | 9 | Linking start | Factory | 2026-02-08 |  | 2026-02-07 | Done
71006510 | SLM | 10 | Final inspection | Karbar QA | 2026-03-12 |  | 2026-03-12 | Done
71006510 | SLM | 11 | Ex-factory | Factory | 2026-03-14 |  | 2026-03-14 | Done
71006513 | IRB | 1 | Yarn booking | Factory | 2025-12-21 |  | 2025-12-21 | Done
71006513 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-30 | Done
71006513 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-05 |  | 2026-01-05 | Done
71006513 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-25 | Done
71006513 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-02-04 |  | 2026-02-05 | Done late
71006513 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-09 |  | 2026-02-09 | Done
71006513 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-02-12 |  | 2026-02-12 | Done
71006513 | IRB | 8 | Knitting start | Factory | 2026-02-14 |  | 2026-02-14 | Done
71006513 | IRB | 9 | Linking start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006513 | IRB | 10 | Final inspection | Karbar QA | 2026-03-25 |  | 2026-03-25 | Done
71006513 | IRB | 11 | Ex-factory | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006522 | RVS | 1 | Yarn booking | Factory | 2025-12-24 |  | 2025-12-25 | Done late
71006522 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-03 | Done
71006522 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-08 | Done
71006522 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-27 | Done
71006522 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-02-07 |  | 2026-02-07 | Done
71006522 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-12 |  | 2026-02-12 | Done
71006522 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-02-15 |  | 2026-02-12 | Done
71006522 | RVS | 8 | Knitting start | Factory | 2026-02-17 |  | 2026-02-17 | Done
71006522 | RVS | 9 | Linking start | Factory | 2026-02-23 |  | 2026-02-22 | Done
71006522 | RVS | 10 | Final inspection | Karbar QA | 2026-03-28 |  | 2026-03-28 | Done
71006522 | RVS | 11 | Ex-factory | Factory | 2026-03-29 |  | 2026-03-29 | Done
71006530 | LTF | 1 | Yarn booking | Factory | 2026-01-07 |  | 2026-01-06 | Done
71006530 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-19 | Done late
71006530 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006530 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-12 | Done late
71006530 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-21 | Done
71006530 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-26 |  | 2026-02-26 | Done
71006530 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-03-01 |  | 2026-02-28 | Done
71006530 | LTF | 8 | Knitting start | Factory | 2026-03-03 |  | 2026-03-03 | Done
71006530 | LTF | 9 | Linking start | Factory | 2026-03-09 |  | 2026-03-08 | Done
71006530 | LTF | 10 | Final inspection | Karbar QA | 2026-04-11 |  | 2026-04-11 | Done
71006530 | LTF | 11 | Ex-factory | Factory | 2026-04-12 |  | 2026-04-12 | Done
71006535 | KST | 1 | Yarn booking | Factory | 2025-12-14 |  | 2025-12-14 | Done
71006535 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-25 | Done late
71006535 | KST | 3 | Fit sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-30 | Done late
71006535 | KST | 4 | Size set approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006535 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-28 | Done
71006535 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-02 |  | 2026-02-02 | Done
71006535 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-02-05 |  | 2026-02-05 | Done
71006535 | KST | 8 | Knitting start | Factory | 2026-02-07 |  | 2026-02-07 | Done
71006535 | KST | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006535 | KST | 10 | Final inspection | Karbar QA | 2026-03-18 |  | 2026-03-18 | Done
71006535 | KST | 11 | Ex-factory | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006544 | SVP | 1 | Yarn booking | Factory | 2025-12-14 |  | 2025-12-15 | Done late
71006544 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-22 | Done
71006544 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-28 | Done
71006544 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-15 | Done
71006544 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-29 | Done late
71006544 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-02 |  | 2026-02-04 | Done late
71006544 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-02-05 |  | 2026-02-05 | Done
71006544 | SVP | 8 | Knitting start | Factory | 2026-02-07 |  | 2026-02-07 | Done
71006544 | SVP | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006544 | SVP | 10 | Final inspection | Karbar QA | 2026-03-18 |  | 2026-03-18 | Done
71006544 | SVP | 11 | Ex-factory | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006549 | SND | 1 | Yarn booking | Factory | 2025-12-25 |  | 2025-12-24 | Done
71006549 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-04 |  | 2026-01-06 | Done late
71006549 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-01-08 |  | 2026-01-08 | Done
71006549 | SND | 4 | Size set approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-29 | Done
71006549 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-08 | Done
71006549 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-12 |  | 2026-02-12 | Done
71006549 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-02-16 |  | 2026-02-17 | Done late
71006549 | SND | 8 | Knitting start | Factory | 2026-02-18 |  | 2026-02-18 | Done
71006549 | SND | 9 | Linking start | Factory | 2026-02-24 |  | 2026-02-23 | Done
71006549 | SND | 10 | Final inspection | Karbar QA | 2026-03-29 |  | 2026-03-29 | Done
71006549 | SND | 11 | Ex-factory | Factory | 2026-03-30 |  | 2026-03-30 | Done
71006558 | BRW | 1 | Yarn booking | Factory | 2026-01-08 |  | 2026-01-08 | Done
71006558 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-18 | Done
71006558 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006558 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-02-12 |  | 2026-02-12 | Done
71006558 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-22 | Done
71006558 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-26 |  | 2026-02-26 | Done
71006558 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-03-02 |  | 2026-03-02 | Done
71006558 | BRW | 8 | Knitting start | Factory | 2026-03-04 |  | 2026-03-05 | Done late
71006558 | BRW | 9 | Linking start | Factory | 2026-03-10 |  | 2026-03-10 | Done
71006558 | BRW | 10 | Final inspection | Karbar QA | 2026-04-12 |  | 2026-04-12 | Done
71006558 | BRW | 11 | Ex-factory | Factory | 2026-04-13 |  | 2026-04-13 | Done
71006562 | TLG | 1 | Yarn booking | Factory | 2026-01-11 |  | 2026-01-13 | Done late
71006562 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-21 | Done
71006562 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-26 | Done
71006562 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-17 | Done late
71006562 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-02-25 |  | 2026-02-25 | Done
71006562 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-02 |  | 2026-03-02 | Done
71006562 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-03-05 |  | 2026-03-05 | Done
71006562 | TLG | 8 | Knitting start | Factory | 2026-03-07 |  | 2026-03-07 | Done
71006562 | TLG | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006562 | TLG | 10 | Final inspection | Karbar QA | 2026-04-15 |  | 2026-04-15 | Done
71006562 | TLG | 11 | Ex-factory | Factory | 2026-04-16 |  | 2026-04-16 | Done
71006569 | SVP | 1 | Yarn booking | Factory | 2025-12-14 |  | 2025-12-14 | Done
71006569 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-24 |  | 2025-12-24 | Done
71006569 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-31 | Done late
71006569 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-17 | Done
71006569 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-28 | Done
71006569 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-02 |  | 2026-01-31 | Done
71006569 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-02-05 |  | 2026-02-05 | Done
71006569 | SVP | 8 | Knitting start | Factory | 2026-02-07 |  | 2026-02-07 | Done
71006569 | SVP | 9 | Linking start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006569 | SVP | 10 | Final inspection | Karbar QA | 2026-03-18 |  | 2026-03-18 | Done
71006569 | SVP | 11 | Ex-factory | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006574 | SLM | 1 | Yarn booking | Factory | 2026-01-18 |  | 2026-01-20 | Done late
71006574 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-28 | Done
71006574 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-02-02 |  | 2026-02-03 | Done late
71006574 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-22 | Done
71006574 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-03-04 |  | 2026-03-04 | Done
71006574 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-09 |  | 2026-03-09 | Done
71006574 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-03-12 |  | 2026-03-11 | Done
71006574 | SLM | 8 | Knitting start | Factory | 2026-03-14 |  | 2026-03-15 | Done late
71006574 | SLM | 9 | Linking start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006574 | SLM | 10 | Final inspection | Karbar QA | 2026-04-22 |  | 2026-04-22 | Done
71006574 | SLM | 11 | Ex-factory | Factory | 2026-04-23 |  | 2026-04-23 | Done
71006582 | FNS | 1 | Yarn booking | Factory | 2025-12-16 |  | 2025-12-16 | Done
71006582 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-25 |  | 2025-12-25 | Done
71006582 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006582 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-01-20 |  | 2026-01-19 | Done
71006582 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-29 | Done
71006582 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-04 |  | 2026-02-02 | Done
71006582 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-02-07 |  | 2026-02-09 | Done late
71006582 | FNS | 8 | Knitting start | Factory | 2026-02-09 |  | 2026-02-09 | Done
71006582 | FNS | 9 | Linking start | Factory | 2026-02-15 |  | 2026-02-14 | Done
71006582 | FNS | 10 | Final inspection | Karbar QA | 2026-03-19 |  | 2026-03-19 | Done
71006582 | FNS | 11 | Ex-factory | Factory | 2026-03-21 |  | 2026-03-21 | Done
71006586 | GRL | 1 | Yarn booking | Factory | 2025-12-28 |  | 2025-12-30 | Done late
71006586 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-07 |  | 2026-01-07 | Done
71006586 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-01-12 |  | 2026-01-12 | Done
71006586 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-02-01 |  | 2026-02-02 | Done late
71006586 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-11 | Done
71006586 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-16 |  | 2026-02-14 | Done
71006586 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-02-19 |  | 2026-02-17 | Done
71006586 | GRL | 8 | Knitting start | Factory | 2026-02-21 |  | 2026-02-21 | Done
71006586 | GRL | 9 | Linking start | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006586 | GRL | 10 | Final inspection | Karbar QA | 2026-04-01 |  | 2026-04-01 | Done
71006586 | GRL | 11 | Ex-factory | Factory | 2026-04-02 |  | 2026-04-02 | Done
71006595 | FNS | 1 | Yarn booking | Factory | 2026-01-11 |  | 2026-01-08 | Done
71006595 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-22 | Done late
71006595 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-28 | Done late
71006595 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-17 | Done late
71006595 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-02-25 |  | 2026-02-25 | Done
71006595 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-02 |  | 2026-03-02 | Done
71006595 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-03-05 |  | 2026-03-05 | Done
71006595 | FNS | 8 | Knitting start | Factory | 2026-03-07 |  | 2026-03-07 | Done
71006595 | FNS | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006595 | FNS | 10 | Final inspection | Karbar QA | 2026-04-15 |  | 2026-04-15 | Done
71006595 | FNS | 11 | Ex-factory | Factory | 2026-04-16 |  | 2026-04-16 | Done
71006598 | FNS | 1 | Yarn booking | Factory | 2025-12-21 |  | 2025-12-21 | Done
71006598 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-31 |  | 2025-12-31 | Done
71006598 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-05 |  | 2026-01-07 | Done late
71006598 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-26 | Done late
71006598 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-02-04 |  | 2026-02-05 | Done late
71006598 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-09 |  | 2026-02-09 | Done
71006598 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-02-12 |  | 2026-02-11 | Done
71006598 | FNS | 8 | Knitting start | Factory | 2026-02-14 |  | 2026-02-14 | Done
71006598 | FNS | 9 | Linking start | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006598 | FNS | 10 | Final inspection | Karbar QA | 2026-03-25 |  | 2026-03-25 | Done
71006598 | FNS | 11 | Ex-factory | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006606 | KST | 1 | Yarn booking | Factory | 2026-01-17 |  | 2026-01-18 | Done late
71006606 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-27 |  | 2026-01-28 | Done late
71006606 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-02-01 |  | 2026-02-02 | Done late
71006606 | KST | 4 | Size set approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-21 | Done
71006606 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-03-03 |  | 2026-03-05 | Done late
71006606 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-08 |  | 2026-03-08 | Done
71006606 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-03-11 |  | 2026-03-11 | Done
71006606 | KST | 8 | Knitting start | Factory | 2026-03-12 |  | 2026-03-14 | Done late
71006606 | KST | 9 | Linking start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006606 | KST | 10 | Final inspection | Karbar QA | 2026-04-21 |  | 2026-04-21 | Done
71006606 | KST | 11 | Ex-factory | Factory | 2026-04-22 |  | 2026-04-22 | Done
71006612 | WSM | 1 | Yarn booking | Factory | 2026-01-18 |  | 2026-01-20 | Done late
71006612 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-28 |  | 2026-01-28 | Done
71006612 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-02-02 |  | 2026-02-01 | Done
71006612 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-22 | Done
71006612 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-03-04 |  | 2026-03-05 | Done late
71006612 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-09 |  | 2026-03-11 | Done late
71006612 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-03-12 |  | 2026-03-12 | Done
71006612 | WSM | 8 | Knitting start | Factory | 2026-03-14 |  | 2026-03-15 | Done late
71006612 | WSM | 9 | Linking start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006612 | WSM | 10 | Final inspection | Karbar QA | 2026-04-22 |  | 2026-04-19 | Done
71006612 | WSM | 11 | Ex-factory | Factory | 2026-04-23 |  | 2026-04-20 | Done
71006617 | MDW | 1 | Yarn booking | Factory | 2025-12-18 |  | 2025-12-18 | Done
71006617 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2025-12-29 |  | 2025-12-29 | Done
71006617 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-03 |  | 2026-01-05 | Done late
71006617 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-22 | Done
71006617 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-02-02 |  | 2026-02-02 | Done
71006617 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-07 |  | 2026-02-08 | Done late
71006617 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-02-10 |  | 2026-02-12 | Done late
71006617 | MDW | 8 | Knitting start | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006617 | MDW | 9 | Linking start | Factory | 2026-02-18 |  | 2026-02-17 | Done
71006617 | MDW | 10 | Final inspection | Karbar QA | 2026-03-23 |  | 2026-03-22 | Done
71006617 | MDW | 11 | Ex-factory | Factory | 2026-03-24 |  | 2026-03-23 | Done
71006625 | BLF | 1 | Yarn booking | Factory | 2026-01-03 |  | 2026-01-03 | Done
71006625 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-13 |  | 2026-01-15 | Done late
71006625 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-01-18 |  | 2026-01-20 | Done late
71006625 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-02-07 |  | 2026-02-09 | Done late
71006625 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-02-17 |  | 2026-02-17 | Done
71006625 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-22 |  | 2026-02-24 | Done late
71006625 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-02-25 |  | 2026-02-26 | Done late
71006625 | BLF | 8 | Knitting start | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006625 | BLF | 9 | Linking start | Factory | 2026-03-05 |  | 2026-03-03 | Done
71006625 | BLF | 10 | Final inspection | Karbar QA | 2026-04-07 |  | 2026-04-04 | Done
71006625 | BLF | 11 | Ex-factory | Factory | 2026-04-08 |  | 2026-04-05 | Done
71006633 | IRB | 1 | Yarn booking | Factory | 2026-01-06 |  | 2026-01-06 | Done
71006633 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-15 |  | 2026-01-14 | Done
71006633 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-19 | Done
71006633 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-02-10 |  | 2026-02-10 | Done
71006633 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-18 | Done
71006633 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-25 |  | 2026-02-28 | Done late
71006633 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-02-28 |  | 2026-02-28 | Done
71006633 | IRB | 8 | Knitting start | Factory | 2026-03-02 |  | 2026-03-02 | Done
71006633 | IRB | 9 | Linking start | Factory | 2026-03-08 |  | 2026-03-07 | Done
71006633 | IRB | 10 | Final inspection | Karbar QA | 2026-04-09 |  | 2026-04-09 | Done
71006633 | IRB | 11 | Ex-factory | Factory | 2026-04-11 |  | 2026-04-11 | Done
71006639 | KST | 1 | Yarn booking | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006639 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-28 | Done late
71006639 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-01-31 |  | 2026-02-02 | Done late
71006639 | KST | 4 | Size set approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-21 | Done late
71006639 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-03-02 |  | 2026-03-02 | Done
71006639 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-07 |  | 2026-03-07 | Done
71006639 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-03-10 |  | 2026-03-12 | Done late
71006639 | KST | 8 | Knitting start | Factory | 2026-03-12 |  | 2026-03-14 | Done late
71006639 | KST | 9 | Linking start | Factory | 2026-03-18 |  | 2026-03-19 | Done late
71006639 | KST | 10 | Final inspection | Karbar QA | 2026-04-20 |  | 2026-04-20 | Done
71006639 | KST | 11 | Ex-factory | Factory | 2026-04-21 |  | 2026-04-21 | Done
71006642 | LTF | 1 | Yarn booking | Factory | 2026-01-15 |  | 2026-01-15 | Done
71006642 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-24 | Done
71006642 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-01-31 |  | 2026-01-31 | Done
71006642 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-19 | Done
71006642 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-03-02 |  | 2026-03-03 | Done late
71006642 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-07 |  | 2026-03-07 | Done
71006642 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-03-10 |  | 2026-03-10 | Done
71006642 | LTF | 8 | Knitting start | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006642 | LTF | 9 | Linking start | Factory | 2026-03-18 |  | 2026-03-17 | Done
71006642 | LTF | 10 | Final inspection | Karbar QA | 2026-04-20 |  | 2026-04-20 | Done
71006642 | LTF | 11 | Ex-factory | Factory | 2026-04-21 |  | 2026-04-21 | Done
71006647 | PBB | 1 | Yarn booking | Factory | 2026-01-08 |  | 2026-01-10 | Done late
71006647 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-19 |  | 2026-01-21 | Done late
71006647 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-24 |  | 2026-01-25 | Done late
71006647 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-02-12 |  | 2026-02-12 | Done
71006647 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-02-23 |  | 2026-02-23 | Done
71006647 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-28 |  | 2026-03-01 | Done late
71006647 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-03-03 |  | 2026-03-04 | Done late
71006647 | PBB | 8 | Knitting start | Factory | 2026-03-05 |  | 2026-03-07 | Done late
71006647 | PBB | 9 | Linking start | Factory | 2026-03-11 |  | 2026-03-12 | Done late
71006647 | PBB | 10 | Final inspection | Karbar QA | 2026-04-13 |  | 2026-04-13 | Done
71006647 | PBB | 11 | Ex-factory | Factory | 2026-04-14 |  | 2026-04-14 | Done
71006650 | AMB | 1 | Yarn booking | Factory | 2026-01-10 |  | 2026-01-12 | Done late
71006650 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-20 |  | 2026-01-20 | Done
71006650 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-22 | Done
71006650 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-02-14 |  | 2026-02-14 | Done
71006650 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-02-24 |  | 2026-02-26 | Done late
71006650 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-01 |  | 2026-02-26 | Done
71006650 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-03-04 |  | 2026-03-02 | Done
71006650 | AMB | 8 | Knitting start | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006650 | AMB | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-10 | Done
71006650 | AMB | 10 | Final inspection | Karbar QA | 2026-04-14 |  | 2026-04-14 | Done
71006650 | AMB | 11 | Ex-factory | Factory | 2026-04-15 |  | 2026-04-15 | Done
71006658 | GRL | 1 | Yarn booking | Factory | 2026-02-01 |  | 2026-02-03 | Done late
71006658 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-12 | Done late
71006658 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-02-16 |  | 2026-02-16 | Done
71006658 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-03-08 |  | 2026-03-08 | Done
71006658 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-19 | Done late
71006658 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-23 |  | 2026-03-26 | Done late
71006658 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-03-26 |  | 2026-03-25 | Done
71006658 | GRL | 8 | Knitting start | Factory | 2026-03-28 |  | 2026-03-29 | Done late
71006658 | GRL | 9 | Linking start | Factory | 2026-04-02 |  | 2026-04-02 | Done
71006658 | GRL | 10 | Final inspection | Karbar QA | 2026-05-06 |  | 2026-05-06 | Done
71006658 | GRL | 11 | Ex-factory | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006667 | IRB | 1 | Yarn booking | Factory | 2026-01-07 |  | 2026-01-08 | Done late
71006667 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-17 | Done
71006667 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-01-22 |  | 2026-01-24 | Done late
71006667 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-10 | Done
71006667 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-23 | Done late
71006667 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-26 |  | 2026-02-26 | Done
71006667 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-03-01 |  | 2026-02-26 | Done
71006667 | IRB | 8 | Knitting start | Factory | 2026-03-03 |  | 2026-03-03 | Done
71006667 | IRB | 9 | Linking start | Factory | 2026-03-09 |  | 2026-03-08 | Done
71006667 | IRB | 10 | Final inspection | Karbar QA | 2026-04-11 |  | 2026-04-11 | Done
71006667 | IRB | 11 | Ex-factory | Factory | 2026-04-12 |  | 2026-04-12 | Done
71006673 | BRW | 1 | Yarn booking | Factory | 2026-01-01 |  | 2026-01-01 | Done
71006673 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-12 |  | 2026-01-12 | Done
71006673 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-17 |  | 2026-01-15 | Done
71006673 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-02-05 |  | 2026-02-04 | Done
71006673 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-02-16 |  | 2026-02-18 | Done late
71006673 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-02-21 |  | 2026-02-23 | Done late
71006673 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-02-24 |  | 2026-02-22 | Done
71006673 | BRW | 8 | Knitting start | Factory | 2026-02-26 |  | 2026-02-26 | Done
71006673 | BRW | 9 | Linking start | Factory | 2026-03-04 |  | 2026-03-03 | Done
71006673 | BRW | 10 | Final inspection | Karbar QA | 2026-04-06 |  | 2026-04-06 | Done
71006673 | BRW | 11 | Ex-factory | Factory | 2026-04-07 |  | 2026-04-07 | Done
71006679 | LTF | 1 | Yarn booking | Factory | 2026-02-04 |  | 2026-02-05 | Done late
71006679 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-14 |  | 2026-02-14 | Done
71006679 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-17 | Done
71006679 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-03-11 |  | 2026-03-10 | Done
71006679 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-19 | Done
71006679 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-26 |  | 2026-03-28 | Done late
71006679 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-03-29 |  | 2026-03-29 | Done
71006679 | LTF | 8 | Knitting start | Factory | 2026-03-31 |  | 2026-03-31 | Done
71006679 | LTF | 9 | Linking start | Factory | 2026-04-06 |  | 2026-04-05 | Done
71006679 | LTF | 10 | Final inspection | Karbar QA | 2026-05-09 |  | 2026-05-06 | Done
71006679 | LTF | 11 | Ex-factory | Factory | 2026-05-10 |  | 2026-05-07 | Done
71006688 | AMB | 1 | Yarn booking | Factory | 2026-01-24 |  | 2026-01-25 | Done late
71006688 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-03 |  | 2026-02-03 | Done
71006688 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-08 | Done
71006688 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-02-28 |  | 2026-02-26 | Done
71006688 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-09 | Done
71006688 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-15 |  | 2026-03-12 | Done
71006688 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-03-18 |  | 2026-03-19 | Done late
71006688 | AMB | 8 | Knitting start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006688 | AMB | 9 | Linking start | Factory | 2026-03-26 |  | 2026-03-24 | Done
71006688 | AMB | 10 | Final inspection | Karbar QA | 2026-04-28 |  | 2026-04-28 | Done
71006688 | AMB | 11 | Ex-factory | Factory | 2026-04-29 |  | 2026-04-29 | Done
71006695 | WTH | 1 | Yarn booking | Factory | 2026-02-01 |  | 2026-01-31 | Done
71006695 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-11 |  | 2026-02-09 | Done
71006695 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-02-16 |  | 2026-02-15 | Done
71006695 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-03-08 |  | 2026-03-07 | Done
71006695 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-18 | Done
71006695 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-23 |  | 2026-03-26 | Done late
71006695 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-03-26 |  | 2026-03-26 | Done
71006695 | WTH | 8 | Knitting start | Factory | 2026-03-28 |  | 2026-03-29 | Done late
71006695 | WTH | 9 | Linking start | Factory | 2026-04-02 |  | 2026-04-02 | Done
71006695 | WTH | 10 | Final inspection | Karbar QA | 2026-05-06 |  | 2026-05-06 | Done
71006695 | WTH | 11 | Ex-factory | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006700 | BRW | 1 | Yarn booking | Factory | 2026-01-11 |  | 2026-01-08 | Done
71006700 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-19 | Done
71006700 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-26 | Done
71006700 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-14 | Done
71006700 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-02-25 |  | 2026-02-25 | Done
71006700 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-02 |  | 2026-03-03 | Done late
71006700 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-03-05 |  | 2026-03-05 | Done
71006700 | BRW | 8 | Knitting start | Factory | 2026-03-07 |  | 2026-03-07 | Done
71006700 | BRW | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006700 | BRW | 10 | Final inspection | Karbar QA | 2026-04-15 |  | 2026-04-16 | Done late
71006700 | BRW | 11 | Ex-factory | Factory | 2026-04-16 |  | 2026-04-18 | Done late
71006707 | MDW | 1 | Yarn booking | Factory | 2026-01-10 |  | 2026-01-08 | Done
71006707 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-20 |  | 2026-01-22 | Done late
71006707 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-01-25 |  | 2026-01-26 | Done late
71006707 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-02-14 |  | 2026-02-14 | Done
71006707 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-02-24 |  | 2026-02-24 | Done
71006707 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-01 |  | 2026-03-02 | Done late
71006707 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-03-04 |  | 2026-03-02 | Done
71006707 | MDW | 8 | Knitting start | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006707 | MDW | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-10 | Done
71006707 | MDW | 10 | Final inspection | Karbar QA | 2026-04-14 |  | 2026-04-14 | Done
71006707 | MDW | 11 | Ex-factory | Factory | 2026-04-15 |  | 2026-04-15 | Done
71006715 | GRL | 1 | Yarn booking | Factory | 2026-01-11 |  | 2026-01-12 | Done late
71006715 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-21 |  | 2026-01-20 | Done
71006715 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-01-26 |  | 2026-01-26 | Done
71006715 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-16 | Done late
71006715 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-02-25 |  | 2026-02-26 | Done late
71006715 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-02 |  | 2026-03-02 | Done
71006715 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-03-05 |  | 2026-03-03 | Done
71006715 | GRL | 8 | Knitting start | Factory | 2026-03-07 |  | 2026-03-07 | Done
71006715 | GRL | 9 | Linking start | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006715 | GRL | 10 | Final inspection | Karbar QA | 2026-04-15 |  | 2026-04-15 | Done
71006715 | GRL | 11 | Ex-factory | Factory | 2026-04-16 |  | 2026-04-16 | Done
71006724 | RVS | 1 | Yarn booking | Factory | 2026-02-07 |  | 2026-02-08 | Done late
71006724 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-17 |  | 2026-02-17 | Done
71006724 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-22 | Done
71006724 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-03-14 |  | 2026-03-16 | Done late
71006724 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-03-24 |  | 2026-03-25 | Done late
71006724 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-29 |  | 2026-03-26 | Done
71006724 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-04-01 |  | 2026-04-01 | Done
71006724 | RVS | 8 | Knitting start | Factory | 2026-04-02 |  | 2026-04-04 | Done late
71006724 | RVS | 9 | Linking start | Factory | 2026-04-09 |  | 2026-04-09 | Done
71006724 | RVS | 10 | Final inspection | Karbar QA | 2026-05-12 |  | 2026-05-12 | Done
71006724 | RVS | 11 | Ex-factory | Factory | 2026-05-13 |  | 2026-05-13 | Done
71006730 | BRW | 1 | Yarn booking | Factory | 2026-01-25 |  | 2026-01-25 | Done
71006730 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-04 |  | 2026-02-04 | Done
71006730 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-02-09 |  | 2026-02-09 | Done
71006730 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-03-01 |  | 2026-02-26 | Done
71006730 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-03-11 |  | 2026-03-12 | Done late
71006730 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-16 |  | 2026-03-14 | Done
71006730 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-03-19 |  | 2026-03-19 | Done
71006730 | BRW | 8 | Knitting start | Factory | 2026-03-21 |  | 2026-03-21 | Done
71006730 | BRW | 9 | Linking start | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006730 | BRW | 10 | Final inspection | Karbar QA | 2026-04-29 |  | 2026-04-29 | Done
71006730 | BRW | 11 | Ex-factory | Factory | 2026-04-30 |  | 2026-04-30 | Done
71006734 | IRB | 1 | Yarn booking | Factory | 2026-02-15 |  | 2026-02-16 | Done late
71006734 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-25 |  | 2026-02-25 | Done
71006734 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-03-02 |  | 2026-03-02 | Done
71006734 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-03-22 |  | 2026-03-24 | Done late
71006734 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-04-01 |  | 2026-04-02 | Done late
71006734 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-06 |  | 2026-04-07 | Done late
71006734 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-04-09 |  | 2026-04-09 | Done
71006734 | IRB | 8 | Knitting start | Factory | 2026-04-11 |  | 2026-04-12 | Done late
71006734 | IRB | 9 | Linking start | Factory | 2026-04-16 |  | 2026-04-16 | Done
71006734 | IRB | 10 | Final inspection | Karbar QA | 2026-05-20 |  | 2026-05-20 | Done
71006734 | IRB | 11 | Ex-factory | Factory | 2026-05-21 |  | 2026-05-21 | Done
71006738 | FNS | 1 | Yarn booking | Factory | 2026-01-31 |  | 2026-01-31 | Done
71006738 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-10 |  | 2026-02-10 | Done
71006738 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-17 | Done late
71006738 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-03-07 |  | 2026-03-07 | Done
71006738 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-03-17 |  | 2026-03-19 | Done late
71006738 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-22 |  | 2026-03-24 | Done late
71006738 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-03-25 |  | 2026-03-25 | Done
71006738 | FNS | 8 | Knitting start | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006738 | FNS | 9 | Linking start | Factory | 2026-04-02 |  | 2026-03-31 | Done
71006738 | FNS | 10 | Final inspection | Karbar QA | 2026-05-05 |  | 2026-05-06 | Done late
71006738 | FNS | 11 | Ex-factory | Factory | 2026-05-06 |  | 2026-05-07 | Done late
71006747 | RVS | 1 | Yarn booking | Factory | 2026-01-14 |  | 2026-01-13 | Done
71006747 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-01-24 |  | 2026-01-24 | Done
71006747 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-01-29 |  | 2026-01-29 | Done
71006747 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-02-18 |  | 2026-02-18 | Done
71006747 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-02-28 |  | 2026-02-28 | Done
71006747 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-05 |  | 2026-03-04 | Done
71006747 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-03-08 |  | 2026-03-08 | Done
71006747 | RVS | 8 | Knitting start | Factory | 2026-03-10 |  | 2026-03-10 | Done
71006747 | RVS | 9 | Linking start | Factory | 2026-03-16 |  | 2026-03-15 | Done
71006747 | RVS | 10 | Final inspection | Karbar QA | 2026-04-18 |  | 2026-04-18 | Done
71006747 | RVS | 11 | Ex-factory | Factory | 2026-04-19 |  | 2026-04-19 | Done
71006756 | TLG | 1 | Yarn booking | Factory | 2026-02-17 |  | 2026-02-15 | Done
71006756 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-26 |  | 2026-02-26 | Done
71006756 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-03-04 |  | 2026-03-04 | Done
71006756 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-03-24 |  | 2026-03-24 | Done
71006756 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-01 | Done
71006756 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-08 |  | 2026-04-08 | Done
71006756 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-04-11 |  | 2026-04-12 | Done late
71006756 | TLG | 8 | Knitting start | Factory | 2026-04-13 |  | 2026-04-14 | Done late
71006756 | TLG | 9 | Linking start | Factory | 2026-04-19 |  | 2026-04-19 | Done
71006756 | TLG | 10 | Final inspection | Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71006756 | TLG | 11 | Ex-factory | Factory | 2026-05-23 |  | 2026-05-23 | Done
71006759 | BLF | 1 | Yarn booking | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006759 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-16 |  | 2026-02-15 | Done
71006759 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-23 | Done late
71006759 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-03-12 |  | 2026-03-12 | Done
71006759 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-22 | Done
71006759 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-28 |  | 2026-03-31 | Done late
71006759 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-03-31 |  | 2026-03-31 | Done
71006759 | BLF | 8 | Knitting start | Factory | 2026-04-02 |  | 2026-04-04 | Done late
71006759 | BLF | 9 | Linking start | Factory | 2026-04-08 |  | 2026-04-09 | Done late
71006759 | BLF | 10 | Final inspection | Karbar QA | 2026-05-11 |  | 2026-05-11 | Done
71006759 | BLF | 11 | Ex-factory | Factory | 2026-05-12 |  | 2026-05-12 | Done
71006764 | RVS | 1 | Yarn booking | Factory | 2026-01-24 |  | 2026-01-25 | Done late
71006764 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-03 |  | 2026-02-01 | Done
71006764 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-05 | Done
71006764 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-02-28 |  | 2026-02-28 | Done
71006764 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-09 | Done
71006764 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-15 |  | 2026-03-17 | Done late
71006764 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-03-18 |  | 2026-03-17 | Done
71006764 | RVS | 8 | Knitting start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006764 | RVS | 9 | Linking start | Factory | 2026-03-26 |  | 2026-03-24 | Done
71006764 | RVS | 10 | Final inspection | Karbar QA | 2026-04-28 |  | 2026-04-25 | Done
71006764 | RVS | 11 | Ex-factory | Factory | 2026-04-29 |  | 2026-04-26 | Done
71006773 | SLM | 1 | Yarn booking | Factory | 2026-02-03 |  | 2026-02-04 | Done late
71006773 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-12 |  | 2026-02-11 | Done
71006773 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-02-18 |  | 2026-02-19 | Done late
71006773 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-09 | Done
71006773 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006773 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-25 |  | 2026-03-26 | Done late
71006773 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-03-28 |  | 2026-03-26 | Done
71006773 | SLM | 8 | Knitting start | Factory | 2026-03-30 |  | 2026-03-31 | Done late
71006773 | SLM | 9 | Linking start | Factory | 2026-04-05 |  | 2026-04-05 | Done
71006773 | SLM | 10 | Final inspection | Karbar QA | 2026-05-07 |  | 2026-05-06 | Done
71006773 | SLM | 11 | Ex-factory | Factory | 2026-05-09 |  | 2026-05-07 | Done
71006779 | WTH | 1 | Yarn booking | Factory | 2026-02-14 |  | 2026-02-16 | Done late
71006779 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-24 |  | 2026-02-22 | Done
71006779 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-03-01 |  | 2026-03-01 | Done
71006779 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-19 | Done
71006779 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-03-31 |  | 2026-03-30 | Done
71006779 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-05 |  | 2026-04-05 | Done
71006779 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-04-08 |  | 2026-04-09 | Done late
71006779 | WTH | 8 | Knitting start | Factory | 2026-04-09 |  | 2026-04-09 | Done
71006779 | WTH | 9 | Linking start | Factory | 2026-04-16 |  | 2026-04-14 | Done
71006779 | WTH | 10 | Final inspection | Karbar QA | 2026-05-19 |  | 2026-05-19 | Done
71006779 | WTH | 11 | Ex-factory | Factory | 2026-05-20 |  | 2026-05-20 | Done
71006785 | MDW | 1 | Yarn booking | Factory | 2026-01-31 |  | 2026-01-31 | Done
71006785 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-10 |  | 2026-02-09 | Done
71006785 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-17 | Done late
71006785 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-03-07 |  | 2026-03-07 | Done
71006785 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-03-17 |  | 2026-03-17 | Done
71006785 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-22 |  | 2026-03-24 | Done late
71006785 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-03-25 |  | 2026-03-25 | Done
71006785 | MDW | 8 | Knitting start | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006785 | MDW | 9 | Linking start | Factory | 2026-04-02 |  | 2026-03-31 | Done
71006785 | MDW | 10 | Final inspection | Karbar QA | 2026-05-05 |  | 2026-05-05 | Done
71006785 | MDW | 11 | Ex-factory | Factory | 2026-05-06 |  | 2026-05-06 | Done
71006791 | SLM | 1 | Yarn booking | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006791 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-23 |  | 2026-02-22 | Done
71006791 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-02-28 |  | 2026-03-02 | Done late
71006791 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006791 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-03-30 |  | 2026-03-30 | Done
71006791 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-04 |  | 2026-04-06 | Done late
71006791 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-04-07 |  | 2026-04-05 | Done
71006791 | SLM | 8 | Knitting start | Factory | 2026-04-09 |  | 2026-04-11 | Done late
71006791 | SLM | 9 | Linking start | Factory | 2026-04-15 |  | 2026-04-16 | Done late
71006791 | SLM | 10 | Final inspection | Karbar QA | 2026-05-18 |  | 2026-05-18 | Done
71006791 | SLM | 11 | Ex-factory | Factory | 2026-05-19 |  | 2026-05-19 | Done
71006794 | HMR | 1 | Yarn booking | Factory | 2026-02-12 |  | 2026-02-12 | Done
71006794 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-23 |  | 2026-02-21 | Done
71006794 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-02-28 |  | 2026-02-28 | Done
71006794 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-21 | Done late
71006794 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-03-30 |  | 2026-03-30 | Done
71006794 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-04 |  | 2026-04-04 | Done
71006794 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-04-07 |  | 2026-04-07 | Done
71006794 | HMR | 8 | Knitting start | Factory | 2026-04-09 |  | 2026-04-11 | Done late
71006794 | HMR | 9 | Linking start | Factory | 2026-04-15 |  | 2026-04-16 | Done late
71006794 | HMR | 10 | Final inspection | Karbar QA | 2026-05-18 |  | 2026-05-18 | Done
71006794 | HMR | 11 | Ex-factory | Factory | 2026-05-19 |  | 2026-05-19 | Done
71006802 | WTH | 1 | Yarn booking | Factory | 2026-03-01 |  | 2026-03-03 | Done late
71006802 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-11 |  | 2026-03-10 | Done
71006802 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-03-16 |  | 2026-03-17 | Done late
71006802 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-04-05 |  | 2026-04-05 | Done
71006802 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-14 | Done
71006802 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-20 |  | 2026-04-22 | Done late
71006802 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-04-23 |  | 2026-04-23 | Done
71006802 | WTH | 8 | Knitting start | Factory | 2026-04-25 |  | 2026-04-26 | Done late
71006802 | WTH | 9 | Linking start | Factory | 2026-04-30 |  | 2026-04-30 | Done
71006802 | WTH | 10 | Final inspection | Karbar QA | 2026-06-03 |  | 2026-06-02 | Done
71006802 | WTH | 11 | Ex-factory | Factory | 2026-06-04 |  | 2026-06-03 | Done
71006808 | RVS | 1 | Yarn booking | Factory | 2026-02-17 |  | 2026-02-17 | Done
71006808 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-26 |  | 2026-02-26 | Done
71006808 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-03-04 |  | 2026-03-03 | Done
71006808 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-03-24 |  | 2026-03-24 | Done
71006808 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-02 | Done
71006808 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-08 |  | 2026-04-09 | Done late
71006808 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-04-11 |  | 2026-04-11 | Done
71006808 | RVS | 8 | Knitting start | Factory | 2026-04-13 |  | 2026-04-13 | Done
71006808 | RVS | 9 | Linking start | Factory | 2026-04-19 |  | 2026-04-18 | Done
71006808 | RVS | 10 | Final inspection | Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71006808 | RVS | 11 | Ex-factory | Factory | 2026-05-23 |  | 2026-05-23 | Done
71006811 | IRB | 1 | Yarn booking | Factory | 2026-01-24 |  | 2026-01-26 | Done late
71006811 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-03 |  | 2026-02-05 | Done late
71006811 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-02-08 |  | 2026-02-09 | Done late
71006811 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-02-28 |  | 2026-03-01 | Done late
71006811 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-11 | Done late
71006811 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-15 |  | 2026-03-17 | Done late
71006811 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-03-18 |  | 2026-03-17 | Done
71006811 | IRB | 8 | Knitting start | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006811 | IRB | 9 | Linking start | Factory | 2026-03-26 |  | 2026-03-24 | Done
71006811 | IRB | 10 | Final inspection | Karbar QA | 2026-04-28 |  | 2026-05-04 | Done late
71006811 | IRB | 11 | Ex-factory | Factory | 2026-04-29 |  | 2026-05-05 | Done late
71006814 | BRW | 1 | Yarn booking | Factory | 2026-02-04 |  | 2026-02-02 | Done
71006814 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-14 |  | 2026-02-16 | Done late
71006814 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-18 | Done
71006814 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-03-11 |  | 2026-03-12 | Done late
71006814 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-22 | Done late
71006814 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-26 |  | 2026-03-26 | Done
71006814 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-03-29 |  | 2026-03-28 | Done
71006814 | BRW | 8 | Knitting start | Factory | 2026-03-31 |  | 2026-04-01 | Done late
71006814 | BRW | 9 | Linking start | Factory | 2026-04-06 |  | 2026-04-06 | Done
71006814 | BRW | 10 | Final inspection | Karbar QA | 2026-05-09 |  | 2026-05-06 | Done
71006814 | BRW | 11 | Ex-factory | Factory | 2026-05-10 |  | 2026-05-07 | Done
71006818 | SVP | 1 | Yarn booking | Factory | 2026-02-12 |  | 2026-02-11 | Done
71006818 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-22 |  | 2026-02-22 | Done
71006818 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-02-26 |  | 2026-02-26 | Done
71006818 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006818 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-03-29 |  | 2026-03-28 | Done
71006818 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-02 |  | 2026-04-05 | Done late
71006818 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-04-06 |  | 2026-04-06 | Done
71006818 | SVP | 8 | Knitting start | Factory | 2026-04-08 |  | 2026-04-09 | Done late
71006818 | SVP | 9 | Linking start | Factory | 2026-04-14 |  | 2026-04-14 | Done
71006818 | SVP | 10 | Final inspection | Karbar QA | 2026-05-17 |  | 2026-05-17 | Done
71006818 | SVP | 11 | Ex-factory | Factory | 2026-05-18 |  | 2026-05-18 | Done
71006822 | BLF | 1 | Yarn booking | Factory | 2026-03-05 |  | 2026-03-05 | Done
71006822 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-16 |  | 2026-03-15 | Done
71006822 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-23 | Done late
71006822 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71006822 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-22 | Done late
71006822 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-25 |  | 2026-04-26 | Done late
71006822 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-04-28 |  | 2026-04-28 | Done
71006822 | BLF | 8 | Knitting start | Factory | 2026-04-30 |  | 2026-05-02 | Done late
71006822 | BLF | 9 | Linking start | Factory | 2026-05-06 |  | 2026-05-07 | Done late
71006822 | BLF | 10 | Final inspection | Karbar QA | 2026-06-08 |  | 2026-06-08 | Done
71006822 | BLF | 11 | Ex-factory | Factory | 2026-06-09 |  | 2026-06-09 | Done
71006827 | RVS | 1 | Yarn booking | Factory | 2026-02-19 |  | 2026-02-19 | Done
71006827 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-02 |  | 2026-03-02 | Done
71006827 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-03-07 |  | 2026-03-05 | Done
71006827 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-03-26 |  | 2026-03-26 | Done
71006827 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-04-06 |  | 2026-04-06 | Done
71006827 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-11 |  | 2026-04-13 | Done late
71006827 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-04-14 |  | 2026-04-14 | Done
71006827 | RVS | 8 | Knitting start | Factory | 2026-04-16 |  | 2026-04-18 | Done late
71006827 | RVS | 9 | Linking start | Factory | 2026-04-22 |  | 2026-04-23 | Done late
71006827 | RVS | 10 | Final inspection | Karbar QA | 2026-05-25 |  | 2026-05-25 | Done
71006827 | RVS | 11 | Ex-factory | Factory | 2026-05-26 |  | 2026-05-26 | Done
71006836 | TLG | 1 | Yarn booking | Factory | 2026-02-22 |  | 2026-02-22 | Done
71006836 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-04 |  | 2026-03-05 | Done late
71006836 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-03-09 |  | 2026-03-07 | Done
71006836 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-03-29 |  | 2026-03-30 | Done late
71006836 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-08 | Done
71006836 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-13 |  | 2026-04-12 | Done
71006836 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-04-16 |  | 2026-04-16 | Done
71006836 | TLG | 8 | Knitting start | Factory | 2026-04-18 |  | 2026-04-18 | Done
71006836 | TLG | 9 | Linking start | Factory | 2026-04-23 |  | 2026-04-23 | Done
71006836 | TLG | 10 | Final inspection | Karbar QA | 2026-05-27 |  | 2026-05-27 | Done
71006836 | TLG | 11 | Ex-factory | Factory | 2026-05-28 |  | 2026-05-28 | Done
71006843 | AMB | 1 | Yarn booking | Factory | 2026-02-05 |  | 2026-02-05 | Done
71006843 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-15 |  | 2026-02-16 | Done late
71006843 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-02-19 |  | 2026-02-18 | Done
71006843 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-03-12 |  | 2026-03-10 | Done
71006843 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-03-22 |  | 2026-03-22 | Done
71006843 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-03-26 |  | 2026-03-28 | Done late
71006843 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-03-30 |  | 2026-03-28 | Done
71006843 | AMB | 8 | Knitting start | Factory | 2026-04-01 |  | 2026-04-01 | Done
71006843 | AMB | 9 | Linking start | Factory | 2026-04-07 |  | 2026-04-06 | Done
71006843 | AMB | 10 | Final inspection | Karbar QA | 2026-05-10 |  | 2026-05-10 | Done
71006843 | AMB | 11 | Ex-factory | Factory | 2026-05-11 |  | 2026-05-11 | Done
71006849 | KST | 1 | Yarn booking | Factory | 2026-02-11 |  | 2026-02-11 | Done
71006849 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-19 | Done
71006849 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-02-26 |  | 2026-02-26 | Done
71006849 | KST | 4 | Size set approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-18 | Done
71006849 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-29 | Done late
71006849 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-02 |  | 2026-03-31 | Done
71006849 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-04-05 |  | 2026-04-06 | Done late
71006849 | KST | 8 | Knitting start | Factory | 2026-04-07 |  | 2026-04-08 | Done late
71006849 | KST | 9 | Linking start | Factory | 2026-04-13 |  | 2026-04-13 | Done
71006849 | KST | 10 | Final inspection | Karbar QA | 2026-05-16 |  | 2026-05-16 | Done
71006849 | KST | 11 | Ex-factory | Factory | 2026-05-17 |  | 2026-05-17 | Done
71006855 | MDW | 1 | Yarn booking | Factory | 2026-03-10 |  | 2026-03-10 | Done
71006855 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006855 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-03-25 |  | 2026-03-26 | Done late
71006855 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-16 | Done late
71006855 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71006855 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-29 |  | 2026-04-30 | Done late
71006855 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-05-02 |  | 2026-05-02 | Done
71006855 | MDW | 8 | Knitting start | Factory | 2026-05-04 |  | 2026-05-04 | Done
71006855 | MDW | 9 | Linking start | Factory | 2026-05-10 |  | 2026-05-09 | Done
71006855 | MDW | 10 | Final inspection | Karbar QA | 2026-06-11 |  | 2026-06-11 | Done
71006855 | MDW | 11 | Ex-factory | Factory | 2026-06-13 |  | 2026-06-13 | Done
71006864 | GRL | 1 | Yarn booking | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006864 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-23 | Done
71006864 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-26 | Done
71006864 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-15 | Done
71006864 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-28 | Done late
71006864 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-02 |  | 2026-05-02 | Done
71006864 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-05 |  | 2026-05-06 | Done late
71006864 | GRL | 8 | Knitting start | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006864 | GRL | 9 | Linking start | Factory | 2026-05-13 |  | 2026-05-12 | Done
71006864 | GRL | 10 | Final inspection | Karbar QA | 2026-06-15 |  | 2026-06-15 | Done
71006864 | GRL | 11 | Ex-factory | Factory | 2026-06-16 |  | 2026-06-16 | Done
71006868 | FNS | 1 | Yarn booking | Factory | 2026-03-05 |  | 2026-03-07 | Done late
71006868 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-15 |  | 2026-03-15 | Done
71006868 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006868 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71006868 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-04-19 |  | 2026-04-18 | Done
71006868 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-23 |  | 2026-04-23 | Done
71006868 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-04-27 |  | 2026-04-27 | Done
71006868 | FNS | 8 | Knitting start | Factory | 2026-04-29 |  | 2026-04-29 | Done
71006868 | FNS | 9 | Linking start | Factory | 2026-05-05 |  | 2026-05-04 | Done
71006868 | FNS | 10 | Final inspection | Karbar QA | 2026-06-07 |  | 2026-06-07 | Done
71006868 | FNS | 11 | Ex-factory | Factory | 2026-06-08 |  | 2026-06-08 | Done
71006874 | WSM | 1 | Yarn booking | Factory | 2026-03-08 |  | 2026-03-09 | Done late
71006874 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-18 | Done
71006874 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-22 | Done
71006874 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-14 | Done late
71006874 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-22 | Done
71006874 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-27 |  | 2026-04-27 | Done
71006874 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-04-30 |  | 2026-04-29 | Done
71006874 | WSM | 8 | Knitting start | Factory | 2026-05-02 |  | 2026-05-03 | Done late
71006874 | WSM | 9 | Linking start | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006874 | WSM | 10 | Final inspection | Karbar QA | 2026-06-10 |  | 2026-06-09 | Done
71006874 | WSM | 11 | Ex-factory | Factory | 2026-06-11 |  | 2026-06-10 | Done
71006882 | BRW | 1 | Yarn booking | Factory | 2026-02-25 |  | 2026-02-25 | Done
71006882 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-07 |  | 2026-03-05 | Done
71006882 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-03-12 |  | 2026-03-14 | Done late
71006882 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-04-01 |  | 2026-04-01 | Done
71006882 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71006882 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-16 |  | 2026-04-14 | Done
71006882 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-04-19 |  | 2026-04-16 | Done
71006882 | BRW | 8 | Knitting start | Factory | 2026-04-21 |  | 2026-04-21 | Done
71006882 | BRW | 9 | Linking start | Factory | 2026-04-27 |  | 2026-04-26 | Done
71006882 | BRW | 10 | Final inspection | Karbar QA | 2026-05-30 |  | 2026-05-30 | Done
71006882 | BRW | 11 | Ex-factory | Factory | 2026-05-31 |  | 2026-05-31 | Done
71006888 | IRB | 1 | Yarn booking | Factory | 2026-03-11 |  | 2026-03-10 | Done
71006888 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-21 | Done
71006888 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-03-26 |  | 2026-03-28 | Done late
71006888 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71006888 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-04-25 |  | 2026-04-23 | Done
71006888 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-30 |  | 2026-04-30 | Done
71006888 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-03 |  | 2026-04-30 | Done
71006888 | IRB | 8 | Knitting start | Factory | 2026-05-05 |  | 2026-05-05 | Done
71006888 | IRB | 9 | Linking start | Factory | 2026-05-11 |  | 2026-05-10 | Done
71006888 | IRB | 10 | Final inspection | Karbar QA | 2026-06-13 |  | 2026-06-13 | Done
71006888 | IRB | 11 | Ex-factory | Factory | 2026-06-14 |  | 2026-06-14 | Done
71006892 | RVS | 1 | Yarn booking | Factory | 2026-02-28 |  | 2026-03-01 | Done late
71006892 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-11 | Done late
71006892 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-03-15 |  | 2026-03-14 | Done
71006892 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-04 | Done
71006892 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-15 | Done late
71006892 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-19 |  | 2026-04-16 | Done
71006892 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-04-22 |  | 2026-04-23 | Done late
71006892 | RVS | 8 | Knitting start | Factory | 2026-04-23 |  | 2026-04-25 | Done late
71006892 | RVS | 9 | Linking start | Factory | 2026-04-30 |  | 2026-04-30 | Done
71006892 | RVS | 10 | Final inspection | Karbar QA | 2026-06-02 |  | 2026-06-03 | Done late
71006892 | RVS | 11 | Ex-factory | Factory | 2026-06-03 |  | 2026-06-04 | Done late
71006901 | KST | 1 | Yarn booking | Factory | 2026-03-04 |  | 2026-03-03 | Done
71006901 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-14 |  | 2026-03-12 | Done
71006901 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006901 | KST | 4 | Size set approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-08 | Done
71006901 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-18 | Done
71006901 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-23 |  | 2026-04-21 | Done
71006901 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-04-26 |  | 2026-04-28 | Done late
71006901 | KST | 8 | Knitting start | Factory | 2026-04-28 |  | 2026-04-28 | Done
71006901 | KST | 9 | Linking start | Factory | 2026-05-04 |  | 2026-05-03 | Done
71006901 | KST | 10 | Final inspection | Karbar QA | 2026-06-06 |  | 2026-06-06 | Done
71006901 | KST | 11 | Ex-factory | Factory | 2026-06-07 |  | 2026-06-07 | Done
71006904 | RVS | 1 | Yarn booking | Factory | 2026-03-15 |  | 2026-03-15 | Done
71006904 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-25 |  | 2026-03-25 | Done
71006904 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-03-30 |  | 2026-04-01 | Done late
71006904 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-04-19 |  | 2026-04-19 | Done
71006904 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-29 | Done
71006904 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-04 |  | 2026-05-05 | Done late
71006904 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-05-07 |  | 2026-05-05 | Done
71006904 | RVS | 8 | Knitting start | Factory | 2026-05-09 |  | 2026-05-09 | Done
71006904 | RVS | 9 | Linking start | Factory | 2026-05-14 |  | 2026-05-14 | Done
71006904 | RVS | 10 | Final inspection | Karbar QA | 2026-06-17 |  | 2026-06-17 | Done
71006904 | RVS | 11 | Ex-factory | Factory | 2026-06-18 |  | 2026-06-18 | Done
71006908 | RSG | 1 | Yarn booking | Factory | 2026-02-11 |  | 2026-02-11 | Done
71006908 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-21 |  | 2026-02-21 | Done
71006908 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-02-26 |  | 2026-02-26 | Done
71006908 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-19 | Done late
71006908 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-26 | Done
71006908 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-02 |  | 2026-04-02 | Done
71006908 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-04-05 |  | 2026-04-05 | Done
71006908 | RSG | 8 | Knitting start | Factory | 2026-04-07 |  | 2026-04-07 | Done
71006908 | RSG | 9 | Linking start | Factory | 2026-04-13 |  | 2026-04-12 | Done
71006908 | RSG | 10 | Final inspection | Karbar QA | 2026-05-16 |  | 2026-05-16 | Done
71006908 | RSG | 11 | Ex-factory | Factory | 2026-05-17 |  | 2026-05-17 | Done
71006913 | GRL | 1 | Yarn booking | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006913 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-22 |  | 2026-03-21 | Done
71006913 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-03-26 |  | 2026-03-24 | Done
71006913 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-14 | Done
71006913 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-27 | Done late
71006913 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-30 |  | 2026-04-30 | Done
71006913 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-04 |  | 2026-05-04 | Done
71006913 | GRL | 8 | Knitting start | Factory | 2026-05-06 |  | 2026-05-06 | Done
71006913 | GRL | 9 | Linking start | Factory | 2026-05-12 |  | 2026-05-11 | Done
71006913 | GRL | 10 | Final inspection | Karbar QA | 2026-06-14 |  | 2026-06-14 | Done
71006913 | GRL | 11 | Ex-factory | Factory | 2026-06-15 |  | 2026-06-15 | Done
71006918 | MDW | 1 | Yarn booking | Factory | 2026-02-18 |  | 2026-02-16 | Done
71006918 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-02-28 |  | 2026-02-28 | Done
71006918 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-03-05 |  | 2026-03-07 | Done late
71006918 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-03-25 |  | 2026-03-26 | Done late
71006918 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-04 | Done
71006918 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-09 |  | 2026-04-11 | Done late
71006918 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-04-12 |  | 2026-04-12 | Done
71006918 | MDW | 8 | Knitting start | Factory | 2026-04-14 |  | 2026-04-14 | Done
71006918 | MDW | 9 | Linking start | Factory | 2026-04-20 |  | 2026-04-19 | Done
71006918 | MDW | 10 | Final inspection | Karbar QA | 2026-05-23 |  | 2026-05-23 | Done
71006918 | MDW | 11 | Ex-factory | Factory | 2026-05-24 |  | 2026-05-24 | Done
71006925 | AMB | 1 | Yarn booking | Factory | 2026-02-28 |  | 2026-03-02 | Done late
71006925 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-10 |  | 2026-03-10 | Done
71006925 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-03-15 |  | 2026-03-16 | Done late
71006925 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-02 | Done
71006925 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-14 | Done
71006925 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-19 |  | 2026-04-18 | Done
71006925 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-04-22 |  | 2026-04-21 | Done
71006925 | AMB | 8 | Knitting start | Factory | 2026-04-23 |  | 2026-04-23 | Done
71006925 | AMB | 9 | Linking start | Factory | 2026-04-30 |  | 2026-04-28 | Done
71006925 | AMB | 10 | Final inspection | Karbar QA | 2026-06-02 |  | 2026-06-02 | Done
71006925 | AMB | 11 | Ex-factory | Factory | 2026-06-03 |  | 2026-06-03 | Done
71006934 | RVS | 1 | Yarn booking | Factory | 2026-03-22 |  | 2026-03-22 | Done
71006934 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-01 |  | 2026-04-01 | Done
71006934 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-06 |  | 2026-04-04 | Done
71006934 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-26 | Done
71006934 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71006934 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-11 |  | 2026-05-12 | Done late
71006934 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-05-14 |  | 2026-05-14 | Done
71006934 | RVS | 8 | Knitting start | Factory | 2026-05-16 |  | 2026-05-16 | Done
71006934 | RVS | 9 | Linking start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71006934 | RVS | 10 | Final inspection | Karbar QA | 2026-06-24 |  | 2026-06-29 | Done late
71006934 | RVS | 11 | Ex-factory | Factory | 2026-06-25 |  | 2026-06-30 | Done late
71006940 | BRW | 1 | Yarn booking | Factory | 2026-03-08 |  | 2026-03-08 | Done
71006940 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-18 |  | 2026-03-18 | Done
71006940 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-21 | Done
71006940 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71006940 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-23 | Done late
71006940 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-27 |  | 2026-04-27 | Done
71006940 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-04-30 |  | 2026-04-30 | Done
71006940 | BRW | 8 | Knitting start | Factory | 2026-05-02 |  | 2026-05-02 | Done
71006940 | BRW | 9 | Linking start | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006940 | BRW | 10 | Final inspection | Karbar QA | 2026-06-10 |  | 2026-06-10 | Done
71006940 | BRW | 11 | Ex-factory | Factory | 2026-06-11 |  | 2026-06-11 | Done
71006944 | IRB | 1 | Yarn booking | Factory | 2026-03-12 |  | 2026-03-14 | Done late
71006944 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-23 | Done
71006944 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-26 | Done
71006944 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71006944 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-28 | Done late
71006944 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-02 |  | 2026-05-04 | Done late
71006944 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-05 |  | 2026-05-05 | Done
71006944 | IRB | 8 | Knitting start | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006944 | IRB | 9 | Linking start | Factory | 2026-05-13 |  | 2026-05-12 | Done
71006944 | IRB | 10 | Final inspection | Karbar QA | 2026-06-15 |  | 2026-06-11 | Done
71006944 | IRB | 11 | Ex-factory | Factory | 2026-06-16 |  | 2026-06-13 | Done
71006949 | MDW | 1 | Yarn booking | Factory | 2026-03-18 |  | 2026-03-18 | Done
71006949 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-26 | Done
71006949 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-02 | Done
71006949 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-22 | Done
71006949 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-04 | Done late
71006949 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-07 |  | 2026-05-06 | Done
71006949 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-05-10 |  | 2026-05-11 | Done late
71006949 | MDW | 8 | Knitting start | Factory | 2026-05-12 |  | 2026-05-13 | Done late
71006949 | MDW | 9 | Linking start | Factory | 2026-05-18 |  | 2026-05-18 | Done
71006949 | MDW | 10 | Final inspection | Karbar QA | 2026-06-20 |  | 2026-06-18 | Done
71006949 | MDW | 11 | Ex-factory | Factory | 2026-06-21 |  | 2026-06-20 | Done
71006952 | SVP | 1 | Yarn booking | Factory | 2026-03-10 |  | 2026-03-10 | Done
71006952 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006952 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-03-25 |  | 2026-03-24 | Done
71006952 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-14 | Done
71006952 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71006952 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-29 |  | 2026-05-02 | Done late
71006952 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-05-02 |  | 2026-04-30 | Done
71006952 | SVP | 8 | Knitting start | Factory | 2026-05-04 |  | 2026-05-04 | Done
71006952 | SVP | 9 | Linking start | Factory | 2026-05-10 |  | 2026-05-09 | Done
71006952 | SVP | 10 | Final inspection | Karbar QA | 2026-06-11 |  | 2026-06-17 | Done late
71006952 | SVP | 11 | Ex-factory | Factory | 2026-06-13 |  | 2026-06-18 | Done late
71006961 | IRB | 1 | Yarn booking | Factory | 2026-03-19 |  | 2026-03-19 | Done
71006961 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-29 |  | 2026-03-28 | Done
71006961 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-02 | Done
71006961 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-25 | Done late
71006961 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71006961 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-07 |  | 2026-05-07 | Done
71006961 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-11 |  | 2026-05-10 | Done
71006961 | IRB | 8 | Knitting start | Factory | 2026-05-13 |  | 2026-05-14 | Done late
71006961 | IRB | 9 | Linking start | Factory | 2026-05-19 |  | 2026-05-19 | Done
71006961 | IRB | 10 | Final inspection | Karbar QA | 2026-06-21 |  | 2026-06-21 | Done
71006961 | IRB | 11 | Ex-factory | Factory | 2026-06-22 |  | 2026-06-22 | Done
71006969 | BLF | 1 | Yarn booking | Factory | 2026-03-26 |  | 2026-03-26 | Done
71006969 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-05 |  | 2026-04-04 | Done
71006969 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71006969 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-04-30 |  | 2026-04-30 | Done
71006969 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-10 | Done
71006969 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-14 |  | 2026-05-12 | Done
71006969 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-05-18 |  | 2026-05-20 | Done late
71006969 | BLF | 8 | Knitting start | Factory | 2026-05-20 |  | 2026-05-20 | Done
71006969 | BLF | 9 | Linking start | Factory | 2026-05-26 |  | 2026-05-25 | Done
71006969 | BLF | 10 | Final inspection | Karbar QA | 2026-06-28 |  | 2026-06-28 | Done
71006969 | BLF | 11 | Ex-factory | Factory | 2026-06-29 |  | 2026-06-29 | Done
71006972 | PBB | 1 | Yarn booking | Factory | 2026-02-19 |  | 2026-02-18 | Done
71006972 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-01 |  | 2026-02-28 | Done
71006972 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-03-05 |  | 2026-03-07 | Done late
71006972 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-03-26 |  | 2026-03-24 | Done
71006972 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-04-05 |  | 2026-04-07 | Done late
71006972 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-09 |  | 2026-04-11 | Done late
71006972 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-04-13 |  | 2026-04-12 | Done
71006972 | PBB | 8 | Knitting start | Factory | 2026-04-15 |  | 2026-04-15 | Done
71006972 | PBB | 9 | Linking start | Factory | 2026-04-21 |  | 2026-04-20 | Done
71006972 | PBB | 10 | Final inspection | Karbar QA | 2026-05-24 |  | 2026-05-24 | Done
71006972 | PBB | 11 | Ex-factory | Factory | 2026-05-25 |  | 2026-05-25 | Done
71006978 | KST | 1 | Yarn booking | Factory | 2026-03-12 |  | 2026-03-12 | Done
71006978 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-23 |  | 2026-03-25 | Done late
71006978 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-28 | Done
71006978 | KST | 4 | Size set approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71006978 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-29 | Done late
71006978 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-02 |  | 2026-05-03 | Done late
71006978 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-05-05 |  | 2026-05-05 | Done
71006978 | KST | 8 | Knitting start | Factory | 2026-05-07 |  | 2026-05-07 | Done
71006978 | KST | 9 | Linking start | Factory | 2026-05-13 |  | 2026-05-12 | Done
71006978 | KST | 10 | Final inspection | Karbar QA | 2026-06-15 |  | 2026-06-15 | Done
71006978 | KST | 11 | Ex-factory | Factory | 2026-06-16 |  | 2026-06-16 | Done
71006981 | PBB | 1 | Yarn booking | Factory | 2026-03-18 |  | 2026-03-18 | Done
71006981 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-28 | Done
71006981 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-03-31 | Done
71006981 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-21 | Done
71006981 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-03 | Done late
71006981 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-07 |  | 2026-05-07 | Done
71006981 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-05-10 |  | 2026-05-07 | Done
71006981 | PBB | 8 | Knitting start | Factory | 2026-05-12 |  | 2026-05-12 | Done
71006981 | PBB | 9 | Linking start | Factory | 2026-05-18 |  | 2026-05-17 | Done
71006981 | PBB | 10 | Final inspection | Karbar QA | 2026-06-20 |  | 2026-06-20 | Done
71006981 | PBB | 11 | Ex-factory | Factory | 2026-06-21 |  | 2026-06-21 | Done
71006984 | RVS | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-26 | Done
71006984 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-06 | Done
71006984 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71006984 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-02 | Done
71006984 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-14 | Done late
71006984 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-14 | Done
71006984 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-20 | Done
71006984 | RVS | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71006984 | RVS | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71006984 | RVS | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-07-04 | Done late
71006984 | RVS | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-07-05 | Done late
71006989 | GRL | 1 | Yarn booking | Factory | 2026-03-10 |  | 2026-03-11 | Done late
71006989 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-19 |  | 2026-03-19 | Done
71006989 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-03-25 |  | 2026-03-26 | Done late
71006989 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-14 | Done
71006989 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-25 | Done late
71006989 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-29 |  | 2026-04-29 | Done
71006989 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-02 |  | 2026-05-02 | Done
71006989 | GRL | 8 | Knitting start | Factory | 2026-05-04 |  | 2026-05-04 | Done
71006989 | GRL | 9 | Linking start | Factory | 2026-05-10 |  | 2026-05-09 | Done
71006989 | GRL | 10 | Final inspection | Karbar QA | 2026-06-11 |  | 2026-06-09 | Done
71006989 | GRL | 11 | Ex-factory | Factory | 2026-06-13 |  | 2026-06-10 | Done
71006996 | GRL | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-30 | Done late
71006996 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-06 | Done
71006996 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71006996 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71006996 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-14 | Done late
71006996 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-17 | Done
71006996 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71006996 | GRL | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-24 | Done late
71006996 | GRL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71006996 | GRL | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71006996 | GRL | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007003 | SND | 1 | Yarn booking | Factory | 2026-04-02 |  | 2026-04-02 | Done
71007003 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-09 | Done
71007003 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-14 | Done
71007003 | SND | 4 | Size set approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-07 | Done
71007003 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-18 | Done late
71007003 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-21 | Done
71007003 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-05-25 |  | 2026-05-25 | Done
71007003 | SND | 8 | Knitting start | Factory | 2026-05-27 |  | 2026-05-27 | Done
71007003 | SND | 9 | Linking start | Factory | 2026-06-02 |  | 2026-06-01 | Done
71007003 | SND | 10 | Final inspection | Karbar QA | 2026-07-05 |  | 2026-07-02 | Done
71007003 | SND | 11 | Ex-factory | Factory | 2026-07-06 |  | 2026-07-04 | Done
71007010 | IRB | 1 | Yarn booking | Factory | 2026-03-18 |  | 2026-03-18 | Done
71007010 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-28 |  | 2026-03-26 | Done
71007010 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-02 | Done
71007010 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-23 | Done late
71007010 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-04 | Done late
71007010 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-07 |  | 2026-05-06 | Done
71007010 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-10 |  | 2026-05-10 | Done
71007010 | IRB | 8 | Knitting start | Factory | 2026-05-12 |  | 2026-05-12 | Done
71007010 | IRB | 9 | Linking start | Factory | 2026-05-18 |  | 2026-05-17 | Done
71007010 | IRB | 10 | Final inspection | Karbar QA | 2026-06-20 |  | 2026-06-20 | Done
71007010 | IRB | 11 | Ex-factory | Factory | 2026-06-21 |  | 2026-06-21 | Done
71007013 | SVP | 1 | Yarn booking | Factory | 2026-03-19 |  | 2026-03-18 | Done
71007013 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-30 |  | 2026-03-30 | Done
71007013 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-06 | Done late
71007013 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-25 | Done late
71007013 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-04 | Done
71007013 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-09 |  | 2026-05-09 | Done
71007013 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-05-12 |  | 2026-05-12 | Done
71007013 | SVP | 8 | Knitting start | Factory | 2026-05-14 |  | 2026-05-16 | Done late
71007013 | SVP | 9 | Linking start | Factory | 2026-05-20 |  | 2026-05-21 | Done late
71007013 | SVP | 10 | Final inspection | Karbar QA | 2026-06-22 |  | 2026-06-22 | Done
71007013 | SVP | 11 | Ex-factory | Factory | 2026-06-23 |  | 2026-06-23 | Done
71007017 | AMB | 1 | Yarn booking | Factory | 2026-03-24 |  | 2026-03-24 | Done
71007017 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-02 |  | 2026-03-31 | Done
71007017 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-07 | Done
71007017 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-04-28 |  | 2026-04-26 | Done
71007017 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-07 | Done
71007017 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-13 |  | 2026-05-13 | Done
71007017 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-05-16 |  | 2026-05-14 | Done
71007017 | AMB | 8 | Knitting start | Factory | 2026-05-18 |  | 2026-05-19 | Done late
71007017 | AMB | 9 | Linking start | Factory | 2026-05-24 |  | 2026-05-24 | Done
71007017 | AMB | 10 | Final inspection | Karbar QA | 2026-06-25 |  | 2026-06-25 | Done
71007017 | AMB | 11 | Ex-factory | Factory | 2026-06-27 |  | 2026-06-27 | Done
71007026 | OKH | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-30 | Done late
71007026 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-07 | Done
71007026 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71007026 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-04-30 | Done
71007026 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007026 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-17 | Done
71007026 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-21 | Done late
71007026 | OKH | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007026 | OKH | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71007026 | OKH | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-06-30 | Done
71007026 | OKH | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007034 | FNS | 1 | Yarn booking | Factory | 2026-03-31 |  | 2026-03-31 | Done
71007034 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007034 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007034 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-06 | Done late
71007034 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-13 | Done
71007034 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-20 |  | 2026-05-20 | Done
71007034 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-05-23 |  | 2026-05-21 | Done
71007034 | FNS | 8 | Knitting start | Factory | 2026-05-25 |  | 2026-05-25 | Done
71007034 | FNS | 9 | Linking start | Factory | 2026-05-31 |  | 2026-05-30 | Done
71007034 | FNS | 10 | Final inspection | Karbar QA | 2026-07-02 |  | 2026-06-30 | Done
71007034 | FNS | 11 | Ex-factory | Factory | 2026-07-04 |  | 2026-07-01 | Done
71007040 | WTH | 1 | Yarn booking | Factory | 2026-03-05 |  | 2026-03-05 | Done
71007040 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-16 |  | 2026-03-16 | Done
71007040 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-21 | Done
71007040 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007040 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-22 | Done late
71007040 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-25 |  | 2026-04-25 | Done
71007040 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-04-28 |  | 2026-04-26 | Done
71007040 | WTH | 8 | Knitting start | Factory | 2026-04-30 |  | 2026-04-30 | Done
71007040 | WTH | 9 | Linking start | Factory | 2026-05-06 |  | 2026-05-05 | Done
71007040 | WTH | 10 | Final inspection | Karbar QA | 2026-06-08 |  | 2026-06-08 | Done
71007040 | WTH | 11 | Ex-factory | Factory | 2026-06-09 |  | 2026-06-09 | Done
71007045 | KST | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-03-30 | Done
71007045 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71007045 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007045 | KST | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007045 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007045 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-19 | Done
71007045 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-26 | Done late
71007045 | KST | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-26 | Done
71007045 | KST | 9 | Linking start | Factory | 2026-06-01 |  | 2026-05-31 | Done
71007045 | KST | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-02 | Done
71007045 | KST | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007048 | LTF | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-03-31 | Done
71007048 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71007048 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007048 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-05 | Done
71007048 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-17 | Done late
71007048 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-20 | Done
71007048 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-21 | Done
71007048 | LTF | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-27 | Done late
71007048 | LTF | 9 | Linking start | Factory | 2026-06-01 |  | 2026-06-01 | Done
71007048 | LTF | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-02 | Done
71007048 | LTF | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007052 | BLF | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007052 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-08 | Done
71007052 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-11 | Done
71007052 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71007052 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-14 | Done late
71007052 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-20 | Done late
71007052 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-23 | Done late
71007052 | BLF | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-24 | Done late
71007052 | BLF | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007052 | BLF | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-06-29 | Done
71007052 | BLF | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-06-30 | Done
71007056 | WTH | 1 | Yarn booking | Factory | 2026-03-31 |  | 2026-03-30 | Done
71007056 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007056 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71007056 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-05 | Done
71007056 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007056 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-20 |  | 2026-05-21 | Done late
71007056 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-05-23 |  | 2026-05-25 | Done late
71007056 | WTH | 8 | Knitting start | Factory | 2026-05-25 |  | 2026-05-25 | Done
71007056 | WTH | 9 | Linking start | Factory | 2026-05-31 |  | 2026-05-30 | Done
71007056 | WTH | 10 | Final inspection | Karbar QA | 2026-07-02 |  | 2026-07-02 | Done
71007056 | WTH | 11 | Ex-factory | Factory | 2026-07-04 |  | 2026-07-04 | Done
71007062 | GRL | 1 | Yarn booking | Factory | 2026-04-07 |  | 2026-04-05 | Done
71007062 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007062 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-23 | Done late
71007062 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007062 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007062 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-27 |  | 2026-05-28 | Done late
71007062 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-30 |  | 2026-05-28 | Done
71007062 | GRL | 8 | Knitting start | Factory | 2026-06-01 |  | 2026-06-01 | Done
71007062 | GRL | 9 | Linking start | Factory | 2026-06-07 |  | 2026-06-06 | Done
71007062 | GRL | 10 | Final inspection | Karbar QA | 2026-07-09 |  | 2026-07-12 | Done late
71007062 | GRL | 11 | Ex-factory | Factory | 2026-07-11 |  | 2026-07-13 | Done late
71007069 | CLB | 1 | Yarn booking | Factory | 2026-03-21 |  | 2026-03-21 | Done
71007069 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-31 |  | 2026-03-31 | Done
71007069 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-05 |  | 2026-04-05 | Done
71007069 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-04-25 |  | 2026-04-25 | Done
71007069 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-05 | Done
71007069 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-10 |  | 2026-05-11 | Done late
71007069 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-05-13 |  | 2026-05-12 | Done
71007069 | CLB | 8 | Knitting start | Factory | 2026-05-14 |  | 2026-05-14 | Done
71007069 | CLB | 9 | Linking start | Factory | 2026-05-21 |  | 2026-05-19 | Done
71007069 | CLB | 10 | Final inspection | Karbar QA | 2026-06-23 |  | 2026-06-21 | Done
71007069 | CLB | 11 | Ex-factory | Factory | 2026-06-24 |  | 2026-06-22 | Done
71007078 | OKH | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-30 | Done late
71007078 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-09 | Done late
71007078 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007078 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-02 | Done
71007078 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007078 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-16 | Done
71007078 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-19 | Done
71007078 | OKH | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-23 | Done
71007078 | OKH | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007078 | OKH | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007078 | OKH | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007083 | WTH | 1 | Yarn booking | Factory | 2026-04-02 |  | 2026-04-02 | Done
71007083 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007083 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-16 | Done
71007083 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-09 | Done late
71007083 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-18 | Done
71007083 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-23 |  | 2026-05-24 | Done late
71007083 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-05-26 |  | 2026-05-26 | Done
71007083 | WTH | 8 | Knitting start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007083 | WTH | 9 | Linking start | Factory | 2026-06-03 |  | 2026-06-02 | Done
71007083 | WTH | 10 | Final inspection | Karbar QA | 2026-07-06 |  | 2026-07-06 | Done
71007083 | WTH | 11 | Ex-factory | Factory | 2026-07-07 |  | 2026-07-07 | Done
71007089 | RVS | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-05 | Done
71007089 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71007089 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-21 | Done late
71007089 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-09 | Done
71007089 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-19 | Done
71007089 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-26 | Done late
71007089 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-26 | Done
71007089 | RVS | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71007089 | RVS | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007089 | RVS | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-07 | Done
71007089 | RVS | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-08 | Done
71007098 | RVS | 1 | Yarn booking | Factory | 2026-04-09 |  | 2026-04-09 | Done
71007098 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-20 | Done
71007098 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-25 |  | 2026-04-26 | Done late
71007098 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007098 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-24 | Done
71007098 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-30 |  | 2026-05-30 | Done
71007098 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-06-02 |  | 2026-06-03 | Done late
71007098 | RVS | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007098 | RVS | 9 | Linking start | Factory | 2026-06-10 |  | 2026-06-09 | Done
71007098 | RVS | 10 | Final inspection | Karbar QA | 2026-07-13 |  | 2026-07-13 | Done
71007098 | RVS | 11 | Ex-factory | Factory | 2026-07-14 |  | 2026-07-14 | Done
71007106 | IRB | 1 | Yarn booking | Factory | 2026-03-31 |  | 2026-03-29 | Done
71007106 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007106 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007106 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-03 | Done
71007106 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-13 | Done
71007106 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-20 |  | 2026-05-20 | Done
71007106 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-23 |  | 2026-05-21 | Done
71007106 | IRB | 8 | Knitting start | Factory | 2026-05-25 |  | 2026-05-25 | Done
71007106 | IRB | 9 | Linking start | Factory | 2026-05-31 |  | 2026-05-30 | Done
71007106 | IRB | 10 | Final inspection | Karbar QA | 2026-07-02 |  | 2026-07-01 | Done
71007106 | IRB | 11 | Ex-factory | Factory | 2026-07-04 |  | 2026-07-02 | Done
71007112 | GRL | 1 | Yarn booking | Factory | 2026-03-22 |  | 2026-03-22 | Done
71007112 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-01 |  | 2026-04-01 | Done
71007112 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-06 |  | 2026-04-06 | Done
71007112 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-23 | Done
71007112 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007112 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-11 |  | 2026-05-11 | Done
71007112 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-14 |  | 2026-05-12 | Done
71007112 | GRL | 8 | Knitting start | Factory | 2026-05-16 |  | 2026-05-16 | Done
71007112 | GRL | 9 | Linking start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007112 | GRL | 10 | Final inspection | Karbar QA | 2026-06-24 |  | 2026-06-24 | Done
71007112 | GRL | 11 | Ex-factory | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007115 | OKH | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007115 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-06 | Done
71007115 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007115 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-04-30 | Done
71007115 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007115 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-18 | Done
71007115 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71007115 | OKH | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-24 | Done late
71007115 | OKH | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007115 | OKH | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007115 | OKH | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007121 | BRW | 1 | Yarn booking | Factory | 2026-03-26 |  | 2026-03-25 | Done
71007121 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-05 |  | 2026-04-05 | Done
71007121 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007121 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-04-30 |  | 2026-04-29 | Done
71007121 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-11 | Done late
71007121 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-14 |  | 2026-05-14 | Done
71007121 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-05-18 |  | 2026-05-19 | Done late
71007121 | BRW | 8 | Knitting start | Factory | 2026-05-20 |  | 2026-05-20 | Done
71007121 | BRW | 9 | Linking start | Factory | 2026-05-26 |  | 2026-05-25 | Done
71007121 | BRW | 10 | Final inspection | Karbar QA | 2026-06-28 |  | 2026-07-01 | Done late
71007121 | BRW | 11 | Ex-factory | Factory | 2026-06-29 |  | 2026-07-02 | Done late
71007126 | HMR | 1 | Yarn booking | Factory | 2026-03-05 |  | 2026-03-05 | Done
71007126 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-16 |  | 2026-03-17 | Done late
71007126 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-03-21 |  | 2026-03-22 | Done late
71007126 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-08 | Done
71007126 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-20 | Done
71007126 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-04-25 |  | 2026-04-25 | Done
71007126 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-04-28 |  | 2026-04-30 | Done late
71007126 | HMR | 8 | Knitting start | Factory | 2026-04-30 |  | 2026-05-02 | Done late
71007126 | HMR | 9 | Linking start | Factory | 2026-05-06 |  | 2026-05-07 | Done late
71007126 | HMR | 10 | Final inspection | Karbar QA | 2026-06-08 |  | 2026-06-08 | Done
71007126 | HMR | 11 | Ex-factory | Factory | 2026-06-09 |  | 2026-06-09 | Done
71007131 | RVS | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-30 | Done late
71007131 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-06 | Done
71007131 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71007131 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-03 | Done late
71007131 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007131 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-19 | Done late
71007131 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-21 | Done late
71007131 | RVS | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007131 | RVS | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71007131 | RVS | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-06-28 | Done
71007131 | RVS | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-06-29 | Done
71007139 | BRW | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007139 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-08 | Done
71007139 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-12 | Done
71007139 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-02 | Done
71007139 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007139 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-19 | Done late
71007139 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-19 | Done
71007139 | BRW | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-23 | Done
71007139 | BRW | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007139 | BRW | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007139 | BRW | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007144 | GRL | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-04-01 | Done
71007144 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71007144 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007144 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007144 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007144 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-20 | Done
71007144 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-21 | Done
71007144 | GRL | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-26 | Done
71007144 | GRL | 9 | Linking start | Factory | 2026-06-01 |  | 2026-05-31 | Done
71007144 | GRL | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-04 | Done
71007144 | GRL | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-05 | Done
71007150 | SND | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-03-30 | Done
71007150 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-12 | Done late
71007150 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007150 | SND | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007150 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-14 | Done
71007150 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-24 | Done late
71007150 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-21 | Done
71007150 | SND | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-27 | Done late
71007150 | SND | 9 | Linking start | Factory | 2026-06-01 |  | 2026-06-01 | Done
71007150 | SND | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-04 | Done
71007150 | SND | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-05 | Done
71007157 | AMB | 1 | Yarn booking | Factory | 2026-04-09 |  | 2026-04-09 | Done
71007157 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-21 | Done late
71007157 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-25 |  | 2026-04-26 | Done late
71007157 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-13 | Done
71007157 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-24 | Done
71007157 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-30 |  | 2026-05-31 | Done late
71007157 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-06-02 |  | 2026-06-02 | Done
71007157 | AMB | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007157 | AMB | 9 | Linking start | Factory | 2026-06-10 |  | 2026-06-09 | Done
71007157 | AMB | 10 | Final inspection | Karbar QA | 2026-07-13 |  | 2026-07-11 | Done
71007157 | AMB | 11 | Ex-factory | Factory | 2026-07-14 |  | 2026-07-12 | Done
71007161 | GRL | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-12 | Done
71007161 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-22 | Done
71007161 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007161 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-19 | Done late
71007161 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007161 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-06-01 | Done
71007161 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-03 | Done
71007161 | GRL | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-07 | Done late
71007161 | GRL | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007161 | GRL | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007161 | GRL | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007165 | WSM | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-11 | Done
71007165 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-23 | Done late
71007165 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007165 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007165 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007165 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-05-30 | Done
71007165 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-06 | Done late
71007165 | WSM | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-06 | Done
71007165 | WSM | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007165 | WSM | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007165 | WSM | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007174 | SLM | 1 | Yarn booking | Factory | 2026-03-19 |  | 2026-03-18 | Done
71007174 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-30 |  | 2026-03-30 | Done
71007174 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-02 | Done
71007174 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71007174 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-04 | Done
71007174 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-09 |  | 2026-05-09 | Done
71007174 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-05-12 |  | 2026-05-12 | Done
71007174 | SLM | 8 | Knitting start | Factory | 2026-05-14 |  | 2026-05-14 | Done
71007174 | SLM | 9 | Linking start | Factory | 2026-05-20 |  | 2026-05-19 | Done
71007174 | SLM | 10 | Final inspection | Karbar QA | 2026-06-22 |  | 2026-06-20 | Done
71007174 | SLM | 11 | Ex-factory | Factory | 2026-06-23 |  | 2026-06-21 | Done
71007182 | GRL | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-26 | Done
71007182 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-06 | Done
71007182 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-09 | Done
71007182 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-03 | Done late
71007182 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007182 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-19 | Done late
71007182 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-21 | Done late
71007182 | GRL | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007182 | GRL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71007182 | GRL | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-07-01 | Done late
71007182 | GRL | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-07-02 | Done late
71007189 | AMB | 1 | Yarn booking | Factory | 2026-03-31 |  | 2026-04-01 | Done late
71007189 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007189 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007189 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-06 | Done late
71007189 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-13 | Done
71007189 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-20 |  | 2026-05-20 | Done
71007189 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-05-23 |  | 2026-05-23 | Done
71007189 | AMB | 8 | Knitting start | Factory | 2026-05-25 |  | 2026-05-26 | Done late
71007189 | AMB | 9 | Linking start | Factory | 2026-05-31 |  | 2026-05-31 | Done
71007189 | AMB | 10 | Final inspection | Karbar QA | 2026-07-02 |  | 2026-07-02 | Done
71007189 | AMB | 11 | Ex-factory | Factory | 2026-07-04 |  | 2026-07-04 | Done
71007192 | BRW | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-15 | Done
71007192 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-26 | Done
71007192 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-04-30 | Done
71007192 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007192 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-03 | Done late
71007192 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-06 |  | 2026-06-08 | Done late
71007192 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-06-09 |  | 2026-06-08 | Done
71007192 | BRW | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-13 | Done late
71007192 | BRW | 9 | Linking start | Factory | 2026-06-17 |  | 2026-06-18 | Done late
71007192 | BRW | 10 | Final inspection | Karbar QA | 2026-07-20 |  | 2026-07-20 | Done
71007192 | BRW | 11 | Ex-factory | Factory | 2026-07-21 |  | 2026-07-21 | Done
71007200 | BLF | 1 | Yarn booking | Factory | 2026-04-18 |  | 2026-04-20 | Done late
71007200 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-28 |  | 2026-04-28 | Done
71007200 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71007200 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-25 | Done late
71007200 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-04 | Done late
71007200 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-07 |  | 2026-06-09 | Done late
71007200 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-06-10 |  | 2026-06-11 | Done late
71007200 | BLF | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-13 | Done late
71007200 | BLF | 9 | Linking start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007200 | BLF | 10 | Final inspection | Karbar QA | 2026-07-21 |  | 2026-07-21 | Done
71007200 | BLF | 11 | Ex-factory | Factory | 2026-07-22 |  | 2026-07-22 | Done
71007207 | GRL | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-05 | Done
71007207 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007207 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-19 | Done
71007207 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-10 | Done
71007207 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007207 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-23 | Done
71007207 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-28 | Done
71007207 | GRL | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71007207 | GRL | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007207 | GRL | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007207 | GRL | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007210 | WTH | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-30 | Done late
71007210 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-06 | Done
71007210 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71007210 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-04-30 | Done
71007210 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007210 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-19 | Done late
71007210 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-18 | Done
71007210 | WTH | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007210 | WTH | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71007210 | WTH | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-06-30 | Done
71007210 | WTH | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007213 | CPL | 1 | Yarn booking | Factory | 2026-03-28 |  | 2026-03-30 | Done late
71007213 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-07 |  | 2026-04-06 | Done
71007213 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-12 |  | 2026-04-12 | Done
71007213 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-02 | Done
71007213 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-14 | Done late
71007213 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-17 |  | 2026-05-19 | Done late
71007213 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-05-20 |  | 2026-05-19 | Done
71007213 | CPL | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007213 | CPL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-26 | Done
71007213 | CPL | 10 | Final inspection | Karbar QA | 2026-06-30 |  | 2026-06-30 | Done
71007213 | CPL | 11 | Ex-factory | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007220 | IRB | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-06 | Done late
71007220 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71007220 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-20 | Done
71007220 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-07 | Done
71007220 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007220 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-25 | Done
71007220 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-30 | Done late
71007220 | IRB | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71007220 | IRB | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007220 | IRB | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007220 | IRB | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007229 | GRL | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007229 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-08 | Done
71007229 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007229 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-04-30 | Done
71007229 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-14 | Done late
71007229 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-17 | Done
71007229 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71007229 | GRL | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-24 | Done late
71007229 | GRL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007229 | GRL | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007229 | GRL | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007238 | SLM | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-03-31 | Done
71007238 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71007238 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007238 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007238 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007238 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-19 | Done
71007238 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-23 | Done
71007238 | SLM | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-27 | Done late
71007238 | SLM | 9 | Linking start | Factory | 2026-06-01 |  | 2026-06-01 | Done
71007238 | SLM | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-01 | Done
71007238 | SLM | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-02 | Done
71007244 | SLM | 1 | Yarn booking | Factory | 2026-04-08 |  | 2026-04-08 | Done
71007244 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-19 | Done late
71007244 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-22 | Done
71007244 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007244 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-24 | Done late
71007244 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-28 | Done
71007244 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-05-31 |  | 2026-05-31 | Done
71007244 | SLM | 8 | Knitting start | Factory | 2026-06-02 |  | 2026-06-03 | Done late
71007244 | SLM | 9 | Linking start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007244 | SLM | 10 | Final inspection | Karbar QA | 2026-07-11 |  | 2026-07-11 | Done
71007244 | SLM | 11 | Ex-factory | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007253 | GRL | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-14 | Done late
71007253 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-20 | Done
71007253 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-29 | Done late
71007253 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-17 | Done
71007253 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71007253 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-06-01 | Done
71007253 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-04 | Done
71007253 | GRL | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-07 | Done late
71007253 | GRL | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007253 | GRL | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007253 | GRL | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007259 | GRL | 1 | Yarn booking | Factory | 2026-04-01 |  | 2026-03-31 | Done
71007259 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-13 | Done late
71007259 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-16 | Done
71007259 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007259 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007259 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-21 |  | 2026-05-21 | Done
71007259 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-24 |  | 2026-05-26 | Done late
71007259 | GRL | 8 | Knitting start | Factory | 2026-05-26 |  | 2026-05-26 | Done
71007259 | GRL | 9 | Linking start | Factory | 2026-06-01 |  | 2026-05-31 | Done
71007259 | GRL | 10 | Final inspection | Karbar QA | 2026-07-04 |  | 2026-07-01 | Done
71007259 | GRL | 11 | Ex-factory | Factory | 2026-07-05 |  | 2026-07-02 | Done
71007264 | WSM | 1 | Yarn booking | Factory | 2026-04-04 |  | 2026-04-02 | Done
71007264 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-12 | Done
71007264 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-19 |  | 2026-04-16 | Done
71007264 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-09 | Done
71007264 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-20 | Done late
71007264 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-24 |  | 2026-05-24 | Done
71007264 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-05-27 |  | 2026-05-25 | Done
71007264 | WSM | 8 | Knitting start | Factory | 2026-05-28 |  | 2026-05-30 | Done late
71007264 | WSM | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007264 | WSM | 10 | Final inspection | Karbar QA | 2026-07-07 |  | 2026-07-07 | Done
71007264 | WSM | 11 | Ex-factory | Factory | 2026-07-08 |  | 2026-07-08 | Done
71007271 | CPL | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007271 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-07 | Done
71007271 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007271 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-04-30 | Done
71007271 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007271 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-18 | Done
71007271 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-21 | Done
71007271 | CPL | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-23 | Done
71007271 | CPL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007271 | CPL | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-07 | Done late
71007271 | CPL | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-08 | Done late
71007277 | BRW | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-06 | Done late
71007277 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007277 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-19 | Done
71007277 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-12 | Done late
71007277 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-21 | Done late
71007277 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-25 | Done
71007277 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-28 | Done
71007277 | BRW | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71007277 | BRW | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007277 | BRW | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007277 | BRW | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007284 | KST | 1 | Yarn booking | Factory | 2026-03-22 |  | 2026-03-24 | Done late
71007284 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-01 |  | 2026-04-01 | Done
71007284 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-04-06 |  | 2026-04-06 | Done
71007284 | KST | 4 | Size set approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-23 | Done
71007284 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007284 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-11 |  | 2026-05-10 | Done
71007284 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-05-14 |  | 2026-05-14 | Done
71007284 | KST | 8 | Knitting start | Factory | 2026-05-16 |  | 2026-05-17 | Done late
71007284 | KST | 9 | Linking start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007284 | KST | 10 | Final inspection | Karbar QA | 2026-06-24 |  | 2026-06-30 | Done late
71007284 | KST | 11 | Ex-factory | Factory | 2026-06-25 |  | 2026-07-01 | Done late
71007289 | FNS | 1 | Yarn booking | Factory | 2026-04-02 |  | 2026-04-02 | Done
71007289 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-12 | Done
71007289 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-18 | Done
71007289 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-07 | Done
71007289 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-20 | Done late
71007289 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-23 |  | 2026-05-23 | Done
71007289 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-05-26 |  | 2026-05-26 | Done
71007289 | FNS | 8 | Knitting start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007289 | FNS | 9 | Linking start | Factory | 2026-06-03 |  | 2026-06-02 | Done
71007289 | FNS | 10 | Final inspection | Karbar QA | 2026-07-06 |  | 2026-07-06 | Done
71007289 | FNS | 11 | Ex-factory | Factory | 2026-07-07 |  | 2026-07-07 | Done
71007292 | OKH | 1 | Yarn booking | Factory | 2026-03-19 |  | 2026-03-19 | Done
71007292 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-29 |  | 2026-03-29 | Done
71007292 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-04-02 |  | 2026-04-02 | Done
71007292 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-25 | Done late
71007292 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71007292 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-07 |  | 2026-05-07 | Done
71007292 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-05-11 |  | 2026-05-13 | Done late
71007292 | OKH | 8 | Knitting start | Factory | 2026-05-13 |  | 2026-05-14 | Done late
71007292 | OKH | 9 | Linking start | Factory | 2026-05-19 |  | 2026-05-19 | Done
71007292 | OKH | 10 | Final inspection | Karbar QA | 2026-06-21 |  | 2026-06-21 | Done
71007292 | OKH | 11 | Ex-factory | Factory | 2026-06-22 |  | 2026-06-22 | Done
71007300 | RSG | 1 | Yarn booking | Factory | 2026-04-08 |  | 2026-04-08 | Done
71007300 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-16 | Done
71007300 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-25 | Done late
71007300 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007300 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-21 | Done
71007300 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-28 | Done
71007300 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-05-31 |  | 2026-05-31 | Done
71007300 | RSG | 8 | Knitting start | Factory | 2026-06-02 |  | 2026-06-03 | Done late
71007300 | RSG | 9 | Linking start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007300 | RSG | 10 | Final inspection | Karbar QA | 2026-07-11 |  | 2026-07-11 | Done
71007300 | RSG | 11 | Ex-factory | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007303 | TLG | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-16 | Done
71007303 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007303 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-03 | Done late
71007303 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007303 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-02 | Done late
71007303 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-06 |  | 2026-06-06 | Done
71007303 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-06-09 |  | 2026-06-07 | Done
71007303 | TLG | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007303 | TLG | 9 | Linking start | Factory | 2026-06-17 |  | 2026-06-16 | Done
71007303 | TLG | 10 | Final inspection | Karbar QA | 2026-07-20 |  | 2026-07-20 | Done
71007303 | TLG | 11 | Ex-factory | Factory | 2026-07-21 |  | 2026-07-21 | Done
71007312 | SLM | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-06 | Done late
71007312 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007312 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-21 | Done late
71007312 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-10 | Done
71007312 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007312 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-28 | Done late
71007312 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-27 | Done
71007312 | SLM | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-30 | Done
71007312 | SLM | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007312 | SLM | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007312 | SLM | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007317 | PBB | 1 | Yarn booking | Factory | 2026-04-09 |  | 2026-04-09 | Done
71007317 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-19 |  | 2026-04-19 | Done
71007317 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71007317 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007317 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007317 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-28 | Done
71007317 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-06-01 |  | 2026-06-03 | Done late
71007317 | PBB | 8 | Knitting start | Factory | 2026-06-03 |  | 2026-06-03 | Done
71007317 | PBB | 9 | Linking start | Factory | 2026-06-09 |  | 2026-06-08 | Done
71007317 | PBB | 10 | Final inspection | Karbar QA | 2026-07-12 |  | 2026-07-09 | Done
71007317 | PBB | 11 | Ex-factory | Factory | 2026-07-13 |  | 2026-07-11 | Done
71007325 | RVS | 1 | Yarn booking | Factory | 2026-04-23 |  | 2026-04-22 | Done
71007325 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-03 | Done
71007325 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-10 | Done late
71007325 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007325 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-08 | Done
71007325 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-13 |  | 2026-06-13 | Done
71007325 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-06-16 |  | 2026-06-18 | Done late
71007325 | RVS | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007325 | RVS | 9 | Linking start | Factory | 2026-06-24 |  | 2026-06-23 | Done
71007325 | RVS | 10 | Final inspection | Karbar QA | 2026-07-27 |  | 2026-07-27 | Done
71007325 | RVS | 11 | Ex-factory | Factory | 2026-07-28 |  | 2026-07-28 | Done
71007329 | IRB | 1 | Yarn booking | Factory | 2026-03-19 |  | 2026-03-17 | Done
71007329 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-03-30 |  | 2026-04-01 | Done late
71007329 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-04 |  | 2026-04-04 | Done
71007329 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-21 | Done
71007329 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-04 | Done
71007329 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-09 |  | 2026-05-11 | Done late
71007329 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-12 |  | 2026-05-12 | Done
71007329 | IRB | 8 | Knitting start | Factory | 2026-05-14 |  | 2026-05-16 | Done late
71007329 | IRB | 9 | Linking start | Factory | 2026-05-20 |  | 2026-05-21 | Done late
71007329 | IRB | 10 | Final inspection | Karbar QA | 2026-06-22 |  | 2026-06-29 | Done late
71007329 | IRB | 11 | Ex-factory | Factory | 2026-06-23 |  | 2026-06-30 | Done late
71007333 | KST | 1 | Yarn booking | Factory | 2026-04-04 |  | 2026-04-04 | Done
71007333 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-14 |  | 2026-04-12 | Done
71007333 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-04-19 |  | 2026-04-19 | Done
71007333 | KST | 4 | Size set approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-11 | Done late
71007333 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-21 | Done late
71007333 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-24 |  | 2026-05-24 | Done
71007333 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-05-27 |  | 2026-05-27 | Done
71007333 | KST | 8 | Knitting start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007333 | KST | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-02 | Done
71007333 | KST | 10 | Final inspection | Karbar QA | 2026-07-07 |  | 2026-07-07 | Done
71007333 | KST | 11 | Ex-factory | Factory | 2026-07-08 |  | 2026-07-08 | Done
71007342 | WSM | 1 | Yarn booking | Factory | 2026-04-08 |  | 2026-04-09 | Done late
71007342 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-20 | Done late
71007342 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71007342 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007342 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-23 | Done
71007342 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-31 | Done late
71007342 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-05-31 |  | 2026-05-31 | Done
71007342 | WSM | 8 | Knitting start | Factory | 2026-06-02 |  | 2026-06-03 | Done late
71007342 | WSM | 9 | Linking start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007342 | WSM | 10 | Final inspection | Karbar QA | 2026-07-11 |  | 2026-07-12 | Done late
71007342 | WSM | 11 | Ex-factory | Factory | 2026-07-12 |  | 2026-07-13 | Done late
71007346 | SLM | 1 | Yarn booking | Factory | 2026-03-31 |  | 2026-03-29 | Done
71007346 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-09 |  | 2026-04-09 | Done
71007346 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007346 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-05 | Done
71007346 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-16 | Done late
71007346 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-20 |  | 2026-05-21 | Done late
71007346 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-05-23 |  | 2026-05-25 | Done late
71007346 | SLM | 8 | Knitting start | Factory | 2026-05-25 |  | 2026-05-26 | Done late
71007346 | SLM | 9 | Linking start | Factory | 2026-05-31 |  | 2026-05-31 | Done
71007346 | SLM | 10 | Final inspection | Karbar QA | 2026-07-02 |  | 2026-06-30 | Done
71007346 | SLM | 11 | Ex-factory | Factory | 2026-07-04 |  | 2026-07-01 | Done
71007351 | HMR | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-12 | Done
71007351 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-22 | Done
71007351 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007351 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007351 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71007351 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-06-01 | Done
71007351 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-02 | Done
71007351 | HMR | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-06 | Done
71007351 | HMR | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007351 | HMR | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-16 | Done late
71007351 | HMR | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71007355 | GRL | 1 | Yarn booking | Factory | 2026-04-18 |  | 2026-04-18 | Done
71007355 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-28 |  | 2026-04-28 | Done
71007355 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71007355 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-24 | Done late
71007355 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-02 | Done
71007355 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-07 |  | 2026-06-04 | Done
71007355 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-10 |  | 2026-06-10 | Done
71007355 | GRL | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-13 | Done late
71007355 | GRL | 9 | Linking start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007355 | GRL | 10 | Final inspection | Karbar QA | 2026-07-21 |  | 2026-07-21 | Done
71007355 | GRL | 11 | Ex-factory | Factory | 2026-07-22 |  | 2026-07-22 | Done
71007358 | IRB | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-27 | Done late
71007358 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007358 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-11 | Done
71007358 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-31 | Done
71007358 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007358 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-13 | Done
71007358 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-18 | Done
71007358 | IRB | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-21 | Done late
71007358 | IRB | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007358 | IRB | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71007358 | IRB | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-07-30 | Done
71007363 | GRL | 1 | Yarn booking | Factory | 2026-04-08 |  | 2026-04-08 | Done
71007363 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-18 | Done
71007363 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-22 | Done
71007363 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007363 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-21 | Done
71007363 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-31 | Done late
71007363 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-31 |  | 2026-05-30 | Done
71007363 | GRL | 8 | Knitting start | Factory | 2026-06-02 |  | 2026-06-03 | Done late
71007363 | GRL | 9 | Linking start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007363 | GRL | 10 | Final inspection | Karbar QA | 2026-07-11 |  | 2026-07-11 | Done
71007363 | GRL | 11 | Ex-factory | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007370 | RSG | 1 | Yarn booking | Factory | 2026-03-26 |  | 2026-03-26 | Done
71007370 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-06 |  | 2026-04-06 | Done
71007370 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-04-11 |  | 2026-04-11 | Done
71007370 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-04-30 |  | 2026-04-30 | Done
71007370 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-10 | Done
71007370 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-16 |  | 2026-05-18 | Done late
71007370 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-05-19 |  | 2026-05-21 | Done late
71007370 | RSG | 8 | Knitting start | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007370 | RSG | 9 | Linking start | Factory | 2026-05-27 |  | 2026-05-26 | Done
71007370 | RSG | 10 | Final inspection | Karbar QA | 2026-06-29 |  | 2026-06-29 | Done
71007370 | RSG | 11 | Ex-factory | Factory | 2026-06-30 |  | 2026-06-30 | Done
71007375 | GRL | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-29 | Done
71007375 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-09 | Done late
71007375 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007375 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-04 | Done late
71007375 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007375 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-17 | Done
71007375 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-23 | Done late
71007375 | GRL | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-23 | Done
71007375 | GRL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007375 | GRL | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007375 | GRL | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007380 | KST | 1 | Yarn booking | Factory | 2026-04-21 |  | 2026-04-21 | Done
71007380 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-30 |  | 2026-05-02 | Done late
71007380 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007380 | KST | 4 | Size set approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-28 | Done late
71007380 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71007380 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-10 |  | 2026-06-10 | Done
71007380 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-06-13 |  | 2026-06-14 | Done late
71007380 | KST | 8 | Knitting start | Factory | 2026-06-15 |  | 2026-06-16 | Done late
71007380 | KST | 9 | Linking start | Factory | 2026-06-21 |  | 2026-06-21 | Done
71007380 | KST | 10 | Final inspection | Karbar QA | 2026-07-23 |  | 2026-07-23 | Done
71007380 | KST | 11 | Ex-factory | Factory | 2026-07-25 |  | 2026-07-25 | Done
71007389 | GRL | 1 | Yarn booking | Factory | 2026-03-29 |  | 2026-03-30 | Done late
71007389 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-08 |  | 2026-04-06 | Done
71007389 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-13 |  | 2026-04-13 | Done
71007389 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-03 |  | 2026-05-03 | Done
71007389 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007389 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-18 |  | 2026-05-18 | Done
71007389 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-21 |  | 2026-05-19 | Done
71007389 | GRL | 8 | Knitting start | Factory | 2026-05-23 |  | 2026-05-24 | Done late
71007389 | GRL | 9 | Linking start | Factory | 2026-05-28 |  | 2026-05-28 | Done
71007389 | GRL | 10 | Final inspection | Karbar QA | 2026-07-01 |  | 2026-07-09 | Done late
71007389 | GRL | 11 | Ex-factory | Factory | 2026-07-02 |  | 2026-07-11 | Done late
71007396 | SND | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-04 | Done
71007396 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71007396 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-22 | Done late
71007396 | SND | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-10 | Done
71007396 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007396 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-25 | Done
71007396 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-28 | Done
71007396 | SND | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-30 | Done
71007396 | SND | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007396 | SND | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007396 | SND | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007402 | SLM | 1 | Yarn booking | Factory | 2026-04-23 |  | 2026-04-23 | Done
71007402 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-02 | Done
71007402 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-10 | Done late
71007402 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-26 | Done
71007402 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-08 | Done
71007402 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-13 |  | 2026-06-14 | Done late
71007402 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-16 |  | 2026-06-18 | Done late
71007402 | SLM | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007402 | SLM | 9 | Linking start | Factory | 2026-06-24 |  | 2026-06-23 | Done
71007402 | SLM | 10 | Final inspection | Karbar QA | 2026-07-27 |  | 2026-07-29 | Done late
71007402 | SLM | 11 | Ex-factory | Factory | 2026-07-28 |  | 2026-07-30 | Done late
71007406 | WTH | 1 | Yarn booking | Factory | 2026-04-25 |  | 2026-04-26 | Done late
71007406 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-06 | Done late
71007406 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-09 | Done
71007406 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-28 | Done
71007406 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-11 | Done late
71007406 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-14 |  | 2026-06-14 | Done
71007406 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-06-17 |  | 2026-06-17 | Done
71007406 | WTH | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007406 | WTH | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-23 | Done
71007406 | WTH | 10 | Final inspection | Karbar QA | 2026-07-28 |  | 2026-07-25 | Done
71007406 | WTH | 11 | Ex-factory | Factory | 2026-07-29 |  | 2026-07-26 | Done
71007412 | RSG | 1 | Yarn booking | Factory | 2026-04-09 |  | 2026-04-11 | Done late
71007412 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-21 | Done late
71007412 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-04-25 |  | 2026-04-25 | Done
71007412 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007412 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-25 | Done
71007412 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-30 |  | 2026-05-30 | Done
71007412 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-06-02 |  | 2026-06-02 | Done
71007412 | RSG | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-06 | Done late
71007412 | RSG | 9 | Linking start | Factory | 2026-06-10 |  | 2026-06-11 | Done late
71007412 | RSG | 10 | Final inspection | Karbar QA | 2026-07-13 |  | 2026-07-13 | Done
71007412 | RSG | 11 | Ex-factory | Factory | 2026-07-14 |  | 2026-07-14 | Done
71007418 | CPL | 1 | Yarn booking | Factory | 2026-04-07 |  | 2026-04-07 | Done
71007418 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-16 |  | 2026-04-15 | Done
71007418 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-23 | Done late
71007418 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-11 | Done
71007418 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007418 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-27 |  | 2026-05-28 | Done late
71007418 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-05-30 |  | 2026-06-01 | Done late
71007418 | CPL | 8 | Knitting start | Factory | 2026-06-01 |  | 2026-06-01 | Done
71007418 | CPL | 9 | Linking start | Factory | 2026-06-07 |  | 2026-06-06 | Done
71007418 | CPL | 10 | Final inspection | Karbar QA | 2026-07-09 |  | 2026-07-07 | Done
71007418 | CPL | 11 | Ex-factory | Factory | 2026-07-11 |  | 2026-07-08 | Done
71007427 | OKH | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-14 | Done
71007427 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-25 | Done
71007427 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-04 | Done late
71007427 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-23 | Done late
71007427 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71007427 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-06 |  | 2026-06-04 | Done
71007427 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-06-09 |  | 2026-06-09 | Done
71007427 | OKH | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007427 | OKH | 9 | Linking start | Factory | 2026-06-17 |  | 2026-06-16 | Done
71007427 | OKH | 10 | Final inspection | Karbar QA | 2026-07-20 |  | 2026-07-20 | Done
71007427 | OKH | 11 | Ex-factory | Factory | 2026-07-21 |  | 2026-07-21 | Done
71007431 | SLM | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-30 | Done
71007431 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-12 | Done late
71007431 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-13 | Done
71007431 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-06 | Done late
71007431 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-15 | Done late
71007431 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-18 | Done
71007431 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-22 |  | 2026-06-20 | Done
71007431 | SLM | 8 | Knitting start | Factory | 2026-06-24 |  | 2026-06-24 | Done
71007431 | SLM | 9 | Linking start | Factory | 2026-06-30 |  | 2026-06-29 | Done
71007431 | SLM | 10 | Final inspection | Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71007431 | SLM | 11 | Ex-factory | Factory | 2026-08-03 |  | 2026-08-03 | Done
71007434 | CLB | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-07 | Done late
71007434 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-16 | Done late
71007434 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-18 | Done
71007434 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-10 | Done
71007434 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007434 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-25 | Done
71007434 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-26 | Done
71007434 | CLB | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71007434 | CLB | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007434 | CLB | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007434 | CLB | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007437 | GRL | 1 | Yarn booking | Factory | 2026-04-11 |  | 2026-04-09 | Done
71007437 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-21 |  | 2026-04-20 | Done
71007437 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-25 | Done
71007437 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-14 | Done
71007437 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-25 | Done
71007437 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-31 |  | 2026-05-30 | Done
71007437 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-03 |  | 2026-06-03 | Done
71007437 | GRL | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007437 | GRL | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-09 | Done
71007437 | GRL | 10 | Final inspection | Karbar QA | 2026-07-14 |  | 2026-07-11 | Done
71007437 | GRL | 11 | Ex-factory | Factory | 2026-07-15 |  | 2026-07-12 | Done
71007442 | SND | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-26 | Done
71007442 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007442 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-10 | Done
71007442 | SND | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-06-01 | Done late
71007442 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-09 | Done
71007442 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-15 | Done
71007442 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-18 | Done
71007442 | SND | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-20 | Done
71007442 | SND | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007442 | SND | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71007442 | SND | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-07-30 | Done
71007446 | GRL | 1 | Yarn booking | Factory | 2026-04-08 |  | 2026-04-08 | Done
71007446 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-18 |  | 2026-04-20 | Done late
71007446 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71007446 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-14 | Done late
71007446 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-25 | Done late
71007446 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-28 |  | 2026-05-28 | Done
71007446 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-05-31 |  | 2026-06-02 | Done late
71007446 | GRL | 8 | Knitting start | Factory | 2026-06-02 |  | 2026-06-02 | Done
71007446 | GRL | 9 | Linking start | Factory | 2026-06-08 |  | 2026-06-07 | Done
71007446 | GRL | 10 | Final inspection | Karbar QA | 2026-07-11 |  | 2026-07-11 | Done
71007446 | GRL | 11 | Ex-factory | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007453 | CPL | 1 | Yarn booking | Factory | 2026-05-05 |  | 2026-05-05 | Done
71007453 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007453 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-21 | Done late
71007453 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-07 | Done
71007453 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-17 | Done
71007453 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-24 |  | 2026-06-23 | Done
71007453 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-06-27 |  | 2026-06-28 | Done late
71007453 | CPL | 8 | Knitting start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71007453 | CPL | 9 | Linking start | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007453 | CPL | 10 | Final inspection | Karbar QA | 2026-08-06 |  | 2026-08-05 | Done
71007453 | CPL | 11 | Ex-factory | Factory | 2026-08-08 |  | 2026-08-06 | Done
71007458 | LTF | 1 | Yarn booking | Factory | 2026-04-11 |  | 2026-04-13 | Done late
71007458 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-21 |  | 2026-04-21 | Done
71007458 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-26 | Done
71007458 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-14 | Done
71007458 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-28 | Done late
71007458 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-31 |  | 2026-06-02 | Done late
71007458 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-06-03 |  | 2026-06-04 | Done late
71007458 | LTF | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-06 | Done late
71007458 | LTF | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007458 | LTF | 10 | Final inspection | Karbar QA | 2026-07-14 |  | 2026-07-12 | Done
71007458 | LTF | 11 | Ex-factory | Factory | 2026-07-15 |  | 2026-07-13 | Done
71007461 | GRL | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-30 | Done
71007461 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-11 | Done
71007461 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-17 | Done late
71007461 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-02 | Done
71007461 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71007461 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-20 |  | 2026-06-21 | Done late
71007461 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-23 |  | 2026-06-22 | Done
71007461 | GRL | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007461 | GRL | 9 | Linking start | Factory | 2026-07-01 |  | 2026-06-30 | Done
71007461 | GRL | 10 | Final inspection | Karbar QA | 2026-08-03 |  | 2026-08-03 | Done
71007461 | GRL | 11 | Ex-factory | Factory | 2026-08-04 |  | 2026-08-04 | Done
71007467 | TLG | 1 | Yarn booking | Factory | 2026-05-03 |  | 2026-05-04 | Done late
71007467 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007467 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-18 | Done
71007467 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-06 | Done
71007467 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-18 | Done late
71007467 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-22 |  | 2026-06-22 | Done
71007467 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-06-25 |  | 2026-06-25 | Done
71007467 | TLG | 8 | Knitting start | Factory | 2026-06-27 |  | 2026-06-27 | Done
71007467 | TLG | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007467 | TLG | 10 | Final inspection | Karbar QA | 2026-08-05 |  | 2026-08-03 | Done
71007467 | TLG | 11 | Ex-factory | Factory | 2026-08-06 |  | 2026-08-04 | Done
71007473 | SND | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-12 | Done
71007473 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-21 | Done
71007473 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007473 | SND | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-18 | Done late
71007473 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007473 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-05-31 | Done
71007473 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-04 | Done
71007473 | SND | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-07 | Done late
71007473 | SND | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007473 | SND | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007473 | SND | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007479 | FNS | 1 | Yarn booking | Factory | 2026-04-19 |  | 2026-04-20 | Done late
71007479 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-29 | Done
71007479 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-06 | Done late
71007479 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007479 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-02 | Done
71007479 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-08 |  | 2026-06-09 | Done late
71007479 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-06-11 |  | 2026-06-11 | Done
71007479 | FNS | 8 | Knitting start | Factory | 2026-06-13 |  | 2026-06-13 | Done
71007479 | FNS | 9 | Linking start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007479 | FNS | 10 | Final inspection | Karbar QA | 2026-07-22 |  | 2026-07-22 | Done
71007479 | FNS | 11 | Ex-factory | Factory | 2026-07-23 |  | 2026-07-23 | Done
71007482 | BLF | 1 | Yarn booking | Factory | 2026-05-02 |  | 2026-05-02 | Done
71007482 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007482 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-17 | Done
71007482 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-07 | Done late
71007482 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-17 | Done late
71007482 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-21 |  | 2026-06-23 | Done late
71007482 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-06-24 |  | 2026-06-23 | Done
71007482 | BLF | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-27 | Done late
71007482 | BLF | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007482 | BLF | 10 | Final inspection | Karbar QA | 2026-08-04 |  | 2026-08-04 | Done
71007482 | BLF | 11 | Ex-factory | Factory | 2026-08-05 |  | 2026-08-05 | Done
71007486 | HMR | 1 | Yarn booking | Factory | 2026-05-09 |  | 2026-05-09 | Done
71007486 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-19 | Done
71007486 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007486 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-14 | Done late
71007486 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-25 | Done late
71007486 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-28 |  | 2026-06-30 | Done late
71007486 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-07-01 |  | 2026-07-02 | Done late
71007486 | HMR | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007486 | HMR | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-07 | Done
71007486 | HMR | 10 | Final inspection | Karbar QA | 2026-08-11 |  | 2026-08-11 | Done
71007486 | HMR | 11 | Ex-factory | Factory | 2026-08-12 |  | 2026-08-12 | Done
71007493 | IRB | 1 | Yarn booking | Factory | 2026-05-05 |  | 2026-05-05 | Done
71007493 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-12 | Done
71007493 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007493 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-09 | Done
71007493 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007493 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-24 |  | 2026-06-22 | Done
71007493 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-27 |  | 2026-06-25 | Done
71007493 | IRB | 8 | Knitting start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71007493 | IRB | 9 | Linking start | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007493 | IRB | 10 | Final inspection | Karbar QA | 2026-08-06 |  | 2026-08-05 | Done
71007493 | IRB | 11 | Ex-factory | Factory | 2026-08-08 |  | 2026-08-06 | Done
71007501 | RSG | 1 | Yarn booking | Factory | 2026-04-11 |  | 2026-04-11 | Done
71007501 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-21 |  | 2026-04-23 | Done late
71007501 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-23 | Done
71007501 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007501 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-26 | Done
71007501 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-31 |  | 2026-05-31 | Done
71007501 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-06-03 |  | 2026-06-02 | Done
71007501 | RSG | 8 | Knitting start | Factory | 2026-06-04 |  | 2026-06-06 | Done late
71007501 | RSG | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007501 | RSG | 10 | Final inspection | Karbar QA | 2026-07-14 |  | 2026-07-14 | Done
71007501 | RSG | 11 | Ex-factory | Factory | 2026-07-15 |  | 2026-07-15 | Done
71007509 | CLB | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-14 | Done late
71007509 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-20 | Done
71007509 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007509 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-14 | Done
71007509 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-28 | Done late
71007509 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-05-30 | Done
71007509 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-03 | Done
71007509 | CLB | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-06 | Done
71007509 | CLB | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007509 | CLB | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007509 | CLB | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007513 | SVP | 1 | Yarn booking | Factory | 2026-04-14 |  | 2026-04-16 | Done late
71007513 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-22 | Done
71007513 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-29 | Done
71007513 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-19 | Done
71007513 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007513 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-03 |  | 2026-06-03 | Done
71007513 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-06-06 |  | 2026-06-04 | Done
71007513 | SVP | 8 | Knitting start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007513 | SVP | 9 | Linking start | Factory | 2026-06-14 |  | 2026-06-13 | Done
71007513 | SVP | 10 | Final inspection | Karbar QA | 2026-07-16 |  | 2026-07-19 | Done late
71007513 | SVP | 11 | Ex-factory | Factory | 2026-07-18 |  | 2026-07-20 | Done late
71007520 | IRB | 1 | Yarn booking | Factory | 2026-04-25 |  | 2026-04-23 | Done
71007520 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-07 | Done late
71007520 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-09 | Done
71007520 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71007520 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-10 | Done late
71007520 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-14 |  | 2026-06-14 | Done
71007520 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-17 |  | 2026-06-17 | Done
71007520 | IRB | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-20 | Done late
71007520 | IRB | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007520 | IRB | 10 | Final inspection | Karbar QA | 2026-07-28 |  | 2026-07-28 | Done
71007520 | IRB | 11 | Ex-factory | Factory | 2026-07-29 |  | 2026-07-29 | Done
71007528 | LTF | 1 | Yarn booking | Factory | 2026-05-05 |  | 2026-05-05 | Done
71007528 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007528 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007528 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-09 | Done
71007528 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007528 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-24 |  | 2026-06-25 | Done late
71007528 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-06-27 |  | 2026-06-25 | Done
71007528 | LTF | 8 | Knitting start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71007528 | LTF | 9 | Linking start | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007528 | LTF | 10 | Final inspection | Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71007528 | LTF | 11 | Ex-factory | Factory | 2026-08-08 |  | 2026-08-08 | Done
71007531 | WSM | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-05 | Done
71007531 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-19 | Done late
71007531 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-20 | Done
71007531 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007531 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71007531 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-28 | Done late
71007531 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-29 | Done
71007531 | WSM | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007531 | WSM | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007531 | WSM | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-08 | Done
71007531 | WSM | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-09 | Done
71007536 | WTH | 1 | Yarn booking | Factory | 2026-05-09 |  | 2026-05-10 | Done late
71007536 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-21 | Done late
71007536 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-25 | Done late
71007536 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-11 | Done
71007536 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-25 | Done late
71007536 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-28 |  | 2026-06-28 | Done
71007536 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-07-01 |  | 2026-06-30 | Done
71007536 | WTH | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007536 | WTH | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-07 | Done
71007536 | WTH | 10 | Final inspection | Karbar QA | 2026-08-11 |  | 2026-08-11 | Done
71007536 | WTH | 11 | Ex-factory | Factory | 2026-08-12 |  | 2026-08-12 | Done
71007542 | CPL | 1 | Yarn booking | Factory | 2026-05-10 |  | 2026-05-12 | Done late
71007542 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007542 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-25 | Done
71007542 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71007542 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-23 | Done
71007542 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-29 |  | 2026-06-27 | Done
71007542 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-02 |  | 2026-07-02 | Done
71007542 | CPL | 8 | Knitting start | Factory | 2026-07-04 |  | 2026-07-05 | Done late
71007542 | CPL | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007542 | CPL | 10 | Final inspection | Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71007542 | CPL | 11 | Ex-factory | Factory | 2026-08-13 |  | 2026-08-13 | Done
71007546 | BLF | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-23 | Done
71007546 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007546 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-09 | Done
71007546 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-30 | Done
71007546 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007546 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-16 | Done late
71007546 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-18 | Done
71007546 | BLF | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-20 | Done
71007546 | BLF | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007546 | BLF | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71007546 | BLF | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-07-30 | Done
71007551 | IRB | 1 | Yarn booking | Factory | 2026-05-03 |  | 2026-05-03 | Done
71007551 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007551 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-18 | Done
71007551 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-07 | Done
71007551 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007551 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-22 |  | 2026-06-24 | Done late
71007551 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-25 |  | 2026-06-23 | Done
71007551 | IRB | 8 | Knitting start | Factory | 2026-06-27 |  | 2026-06-28 | Done late
71007551 | IRB | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007551 | IRB | 10 | Final inspection | Karbar QA | 2026-08-05 |  | 2026-08-17 | Done late
71007551 | IRB | 11 | Ex-factory | Factory | 2026-08-06 |  | 2026-08-18 | Done late
71007554 | KST | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-09 | Done late
71007554 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-18 | Done late
71007554 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-20 | Done
71007554 | KST | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-10 | Done
71007554 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-22 | Done late
71007554 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71007554 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-28 | Done
71007554 | KST | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007554 | KST | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007554 | KST | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-09 | Done
71007554 | KST | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-10 | Done
71007561 | KST | 1 | Yarn booking | Factory | 2026-05-12 |  | 2026-05-14 | Done late
71007561 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007561 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007561 | KST | 4 | Size set approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-16 | Done
71007561 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-24 | Done
71007561 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-01 |  | 2026-07-02 | Done late
71007561 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-07-04 |  | 2026-07-05 | Done late
71007561 | KST | 8 | Knitting start | Factory | 2026-07-06 |  | 2026-07-06 | Done
71007561 | KST | 9 | Linking start | Factory | 2026-07-12 |  | 2026-07-11 | Done
71007561 | KST | 10 | Final inspection | Karbar QA | 2026-08-13 |  | 2026-08-12 | Done
71007561 | KST | 11 | Ex-factory | Factory | 2026-08-15 |  | 2026-08-13 | Done
71007567 | KST | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-26 | Done
71007567 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007567 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-13 | Done late
71007567 | KST | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-28 | Done
71007567 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007567 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-15 | Done
71007567 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-20 | Done late
71007567 | KST | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-20 | Done
71007567 | KST | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007567 | KST | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71007567 | KST | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-07-30 | Done
71007571 | IRB | 1 | Yarn booking | Factory | 2026-04-05 |  | 2026-04-05 | Done
71007571 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-15 |  | 2026-04-15 | Done
71007571 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-20 |  | 2026-04-20 | Done
71007571 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-07 | Done
71007571 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-21 | Done late
71007571 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-05-25 |  | 2026-05-25 | Done
71007571 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-05-28 |  | 2026-05-28 | Done
71007571 | IRB | 8 | Knitting start | Factory | 2026-05-30 |  | 2026-05-30 | Done
71007571 | IRB | 9 | Linking start | Factory | 2026-06-04 |  | 2026-06-04 | Done
71007571 | IRB | 10 | Final inspection | Karbar QA | 2026-07-08 |  | 2026-07-08 | Done
71007571 | IRB | 11 | Ex-factory | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007579 | GRL | 1 | Yarn booking | Factory | 2026-04-12 |  | 2026-04-12 | Done
71007579 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-22 |  | 2026-04-20 | Done
71007579 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-27 | Done
71007579 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007579 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007579 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-01 |  | 2026-06-03 | Done late
71007579 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-04 |  | 2026-06-04 | Done
71007579 | GRL | 8 | Knitting start | Factory | 2026-06-06 |  | 2026-06-06 | Done
71007579 | GRL | 9 | Linking start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007579 | GRL | 10 | Final inspection | Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007579 | GRL | 11 | Ex-factory | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007588 | SND | 1 | Yarn booking | Factory | 2026-05-12 |  | 2026-05-12 | Done
71007588 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007588 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007588 | SND | 4 | Size set approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-14 | Done
71007588 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-27 | Done late
71007588 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-01 |  | 2026-07-01 | Done
71007588 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-04 |  | 2026-07-04 | Done
71007588 | SND | 8 | Knitting start | Factory | 2026-07-06 |  | 2026-07-07 | Done late
71007588 | SND | 9 | Linking start | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007588 | SND | 10 | Final inspection | Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71007588 | SND | 11 | Ex-factory | Factory | 2026-08-15 |  | 2026-08-15 | Done
71007596 | GRL | 1 | Yarn booking | Factory | 2026-04-19 |  | 2026-04-20 | Done late
71007596 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-27 | Done
71007596 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-04 | Done
71007596 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007596 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71007596 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-08 |  | 2026-06-11 | Done late
71007596 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-11 |  | 2026-06-11 | Done
71007596 | GRL | 8 | Knitting start | Factory | 2026-06-13 |  | 2026-06-13 | Done
71007596 | GRL | 9 | Linking start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007596 | GRL | 10 | Final inspection | Karbar QA | 2026-07-22 |  | 2026-07-22 | Done
71007596 | GRL | 11 | Ex-factory | Factory | 2026-07-23 |  | 2026-07-23 | Done
71007602 | TLG | 1 | Yarn booking | Factory | 2026-04-21 |  | 2026-04-19 | Done
71007602 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-30 |  | 2026-05-02 | Done late
71007602 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007602 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-26 | Done
71007602 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71007602 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-10 |  | 2026-06-13 | Done late
71007602 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-06-13 |  | 2026-06-15 | Done late
71007602 | TLG | 8 | Knitting start | Factory | 2026-06-15 |  | 2026-06-15 | Done
71007602 | TLG | 9 | Linking start | Factory | 2026-06-21 |  | 2026-06-20 | Done
71007602 | TLG | 10 | Final inspection | Karbar QA | 2026-07-23 |  | 2026-07-26 | Done late
71007602 | TLG | 11 | Ex-factory | Factory | 2026-07-25 |  | 2026-07-27 | Done late
71007609 | SVP | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-14 | Done
71007609 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-23 | Done
71007609 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71007609 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007609 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-07-01 | Done late
71007609 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-04 |  | 2026-07-05 | Done late
71007609 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-07 |  | 2026-07-07 | Done
71007609 | SVP | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007609 | SVP | 9 | Linking start | Factory | 2026-07-15 |  | 2026-07-14 | Done
71007609 | SVP | 10 | Final inspection | Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71007609 | SVP | 11 | Ex-factory | Factory | 2026-08-18 |  | 2026-08-18 | Done
71007616 | IRB | 1 | Yarn booking | Factory | 2026-04-19 |  | 2026-04-21 | Done late
71007616 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-29 | Done
71007616 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-04 | Done
71007616 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007616 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-04 | Done late
71007616 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-08 |  | 2026-06-11 | Done late
71007616 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-11 |  | 2026-06-11 | Done
71007616 | IRB | 8 | Knitting start | Factory | 2026-06-13 |  | 2026-06-13 | Done
71007616 | IRB | 9 | Linking start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007616 | IRB | 10 | Final inspection | Karbar QA | 2026-07-22 |  | 2026-07-25 | Done late
71007616 | IRB | 11 | Ex-factory | Factory | 2026-07-23 |  | 2026-07-26 | Done late
71007621 | BLF | 1 | Yarn booking | Factory | 2026-05-03 |  | 2026-05-02 | Done
71007621 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007621 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-20 | Done late
71007621 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-04 | Done
71007621 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007621 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-22 |  | 2026-06-22 | Done
71007621 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-06-25 |  | 2026-06-25 | Done
71007621 | BLF | 8 | Knitting start | Factory | 2026-06-27 |  | 2026-06-27 | Done
71007621 | BLF | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007621 | BLF | 10 | Final inspection | Karbar QA | 2026-08-05 |  | 2026-08-06 | Done late
71007621 | BLF | 11 | Ex-factory | Factory | 2026-08-06 |  | 2026-08-08 | Done late
71007624 | WTH | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-17 | Done
71007624 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71007624 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71007624 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-20 | Done
71007624 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71007624 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-06 | Done
71007624 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-07 | Done
71007624 | WTH | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-11 | Done
71007624 | WTH | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007624 | WTH | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-18 | Done
71007624 | WTH | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-19 | Done
71007631 | AMB | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-16 | Done
71007631 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-23 | Done
71007631 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-04-30 |  | 2026-05-02 | Done late
71007631 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007631 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-31 | Done
71007631 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-04 |  | 2026-06-04 | Done
71007631 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-06-08 |  | 2026-06-08 | Done
71007631 | AMB | 8 | Knitting start | Factory | 2026-06-10 |  | 2026-06-10 | Done
71007631 | AMB | 9 | Linking start | Factory | 2026-06-16 |  | 2026-06-15 | Done
71007631 | AMB | 10 | Final inspection | Karbar QA | 2026-07-19 |  | 2026-07-18 | Done
71007631 | AMB | 11 | Ex-factory | Factory | 2026-07-20 |  | 2026-07-19 | Done
71007634 | RSG | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-26 | Done
71007634 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007634 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-09 | Done
71007634 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-30 | Done
71007634 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007634 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-18 | Done late
71007634 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-20 | Done late
71007634 | RSG | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-20 | Done
71007634 | RSG | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007634 | RSG | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-07-26 | Done
71007634 | RSG | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-07-27 | Done
71007642 | GRL | 1 | Yarn booking | Factory | 2026-05-06 |  | 2026-05-07 | Done late
71007642 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-14 | Done
71007642 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007642 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007642 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71007642 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71007642 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-28 |  | 2026-06-30 | Done late
71007642 | GRL | 8 | Knitting start | Factory | 2026-06-30 |  | 2026-07-01 | Done late
71007642 | GRL | 9 | Linking start | Factory | 2026-07-06 |  | 2026-07-06 | Done
71007642 | GRL | 10 | Final inspection | Karbar QA | 2026-08-08 |  | 2026-08-12 | Done late
71007642 | GRL | 11 | Ex-factory | Factory | 2026-08-09 |  | 2026-08-13 | Done late
71007650 | WSM | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-07 | Done
71007650 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-16 | Done
71007650 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-21 | Done
71007650 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007650 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71007650 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-27 |  | 2026-06-27 | Done
71007650 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-30 |  | 2026-07-02 | Done late
71007650 | WSM | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007650 | WSM | 9 | Linking start | Factory | 2026-07-08 |  | 2026-07-07 | Done
71007650 | WSM | 10 | Final inspection | Karbar QA | 2026-08-10 |  | 2026-08-10 | Done
71007650 | WSM | 11 | Ex-factory | Factory | 2026-08-11 |  | 2026-08-11 | Done
71007655 | CPL | 1 | Yarn booking | Factory | 2026-04-14 |  | 2026-04-12 | Done
71007655 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-23 |  | 2026-04-23 | Done
71007655 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-04-29 |  | 2026-04-30 | Done late
71007655 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-19 | Done
71007655 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007655 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-03 |  | 2026-06-06 | Done late
71007655 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-06-06 |  | 2026-06-08 | Done late
71007655 | CPL | 8 | Knitting start | Factory | 2026-06-08 |  | 2026-06-08 | Done
71007655 | CPL | 9 | Linking start | Factory | 2026-06-14 |  | 2026-06-13 | Done
71007655 | CPL | 10 | Final inspection | Karbar QA | 2026-07-16 |  | 2026-07-22 | Done late
71007655 | CPL | 11 | Ex-factory | Factory | 2026-07-18 |  | 2026-07-23 | Done late
71007659 | KST | 1 | Yarn booking | Factory | 2026-04-29 |  | 2026-04-29 | Done
71007659 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-11 | Done late
71007659 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007659 | KST | 4 | Size set approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-04 | Done late
71007659 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-14 | Done late
71007659 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-18 | Done
71007659 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-06-21 |  | 2026-06-23 | Done late
71007659 | KST | 8 | Knitting start | Factory | 2026-06-23 |  | 2026-06-24 | Done late
71007659 | KST | 9 | Linking start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71007659 | KST | 10 | Final inspection | Karbar QA | 2026-08-01 |  | 2026-08-01 | Done
71007659 | KST | 11 | Ex-factory | Factory | 2026-08-02 |  | 2026-08-02 | Done
71007662 | CPL | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-05-02 | Done late
71007662 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-13 | Done late
71007662 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007662 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-02 | Done
71007662 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-17 | Done late
71007662 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-20 |  | 2026-06-21 | Done late
71007662 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-06-23 |  | 2026-06-22 | Done
71007662 | CPL | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-27 | Done late
71007662 | CPL | 9 | Linking start | Factory | 2026-07-01 |  | 2026-07-02 | Done late
71007662 | CPL | 10 | Final inspection | Karbar QA | 2026-08-03 |  | 2026-07-30 | Done
71007662 | CPL | 11 | Ex-factory | Factory | 2026-08-04 |  | 2026-08-01 | Done
71007668 | AMB | 1 | Yarn booking | Factory | 2026-04-21 |  | 2026-04-19 | Done
71007668 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-30 |  | 2026-05-02 | Done late
71007668 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-06 | Done
71007668 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-24 | Done
71007668 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71007668 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-10 |  | 2026-06-13 | Done late
71007668 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-06-13 |  | 2026-06-15 | Done late
71007668 | AMB | 8 | Knitting start | Factory | 2026-06-15 |  | 2026-06-16 | Done late
71007668 | AMB | 9 | Linking start | Factory | 2026-06-21 |  | 2026-06-21 | Done
71007668 | AMB | 10 | Final inspection | Karbar QA | 2026-07-23 |  | 2026-07-22 | Done
71007668 | AMB | 11 | Ex-factory | Factory | 2026-07-25 |  | 2026-07-23 | Done
71007672 | RSG | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-28 | Done
71007672 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-07 | Done
71007672 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007672 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-03 | Done
71007672 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-13 | Done
71007672 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-16 | Done
71007672 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-06-22 |  | 2026-06-22 | Done
71007672 | RSG | 8 | Knitting start | Factory | 2026-06-24 |  | 2026-06-24 | Done
71007672 | RSG | 9 | Linking start | Factory | 2026-06-30 |  | 2026-06-29 | Done
71007672 | RSG | 10 | Final inspection | Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71007672 | RSG | 11 | Ex-factory | Factory | 2026-08-03 |  | 2026-08-03 | Done
71007677 | GRL | 1 | Yarn booking | Factory | 2026-05-05 |  | 2026-05-04 | Done
71007677 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71007677 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007677 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-09 | Done
71007677 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-20 | Done late
71007677 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-24 |  | 2026-06-25 | Done late
71007677 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-27 |  | 2026-06-27 | Done
71007677 | GRL | 8 | Knitting start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71007677 | GRL | 9 | Linking start | Factory | 2026-07-05 |  | 2026-07-04 | Done
71007677 | GRL | 10 | Final inspection | Karbar QA | 2026-08-06 |  | 2026-08-09 | Done late
71007677 | GRL | 11 | Ex-factory | Factory | 2026-08-08 |  | 2026-08-10 | Done late
71007685 | FNS | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-14 | Done
71007685 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-27 |  | 2026-04-29 | Done late
71007685 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-02 |  | 2026-05-02 | Done
71007685 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007685 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-03 | Done late
71007685 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-06 |  | 2026-06-04 | Done
71007685 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-06-09 |  | 2026-06-08 | Done
71007685 | FNS | 8 | Knitting start | Factory | 2026-06-11 |  | 2026-06-11 | Done
71007685 | FNS | 9 | Linking start | Factory | 2026-06-17 |  | 2026-06-16 | Done
71007685 | FNS | 10 | Final inspection | Karbar QA | 2026-07-20 |  | 2026-07-19 | Done
71007685 | FNS | 11 | Ex-factory | Factory | 2026-07-21 |  | 2026-07-20 | Done
71007692 | BRW | 1 | Yarn booking | Factory | 2026-05-02 |  | 2026-04-30 | Done
71007692 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-12 | Done
71007692 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-17 | Done
71007692 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-04 | Done
71007692 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-15 | Done
71007692 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-21 |  | 2026-06-23 | Done late
71007692 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-06-24 |  | 2026-06-25 | Done late
71007692 | BRW | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007692 | BRW | 9 | Linking start | Factory | 2026-07-02 |  | 2026-06-30 | Done
71007692 | BRW | 10 | Final inspection | Karbar QA | 2026-08-04 |  | 2026-08-04 | Done
71007692 | BRW | 11 | Ex-factory | Factory | 2026-08-05 |  | 2026-08-05 | Done
71007698 | SND | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-19 | Done
71007698 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-01 |  | 2026-05-30 | Done
71007698 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-06 | Done
71007698 | SND | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-23 | Done
71007698 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71007698 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-11 |  | 2026-07-09 | Done
71007698 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-14 |  | 2026-07-16 | Done late
71007698 | SND | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71007698 | SND | 9 | Linking start | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71007698 | SND | 10 | Final inspection | Karbar QA | 2026-08-24 |  | 2026-08-24 | Done
71007698 | SND | 11 | Ex-factory | Factory | 2026-08-25 |  | 2026-08-25 | Done
71007701 | BLF | 1 | Yarn booking | Factory | 2026-05-13 |  | 2026-05-11 | Done
71007701 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-21 | Done
71007701 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-27 | Done
71007701 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007701 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71007701 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71007701 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-05 |  | 2026-07-07 | Done late
71007701 | BLF | 8 | Knitting start | Factory | 2026-07-07 |  | 2026-07-07 | Done
71007701 | BLF | 9 | Linking start | Factory | 2026-07-13 |  | 2026-07-12 | Done
71007701 | BLF | 10 | Final inspection | Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71007701 | BLF | 11 | Ex-factory | Factory | 2026-08-16 |  | 2026-08-16 | Done
71007708 | LTF | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-21 | Done
71007708 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-03 | Done late
71007708 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-09 | Done late
71007708 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71007708 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-06 | Done
71007708 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-12 | Done
71007708 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-13 | Done
71007708 | LTF | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007708 | LTF | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71007708 | LTF | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-25 | Done
71007708 | LTF | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-26 | Done
71007717 | TLG | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-16 | Done
71007717 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-26 | Done
71007717 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-04-30 |  | 2026-05-02 | Done late
71007717 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-23 | Done late
71007717 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-05-31 |  | 2026-06-01 | Done late
71007717 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-04 |  | 2026-06-06 | Done late
71007717 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-06-08 |  | 2026-06-10 | Done late
71007717 | TLG | 8 | Knitting start | Factory | 2026-06-10 |  | 2026-06-10 | Done
71007717 | TLG | 9 | Linking start | Factory | 2026-06-16 |  | 2026-06-15 | Done
71007717 | TLG | 10 | Final inspection | Karbar QA | 2026-07-19 |  | 2026-07-19 | Done
71007717 | TLG | 11 | Ex-factory | Factory | 2026-07-20 |  | 2026-07-20 | Done
71007726 | GRL | 1 | Yarn booking | Factory | 2026-04-29 |  | 2026-04-29 | Done
71007726 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-10 | Done late
71007726 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-12 | Done
71007726 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71007726 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-14 | Done late
71007726 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-17 | Done
71007726 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-21 |  | 2026-06-20 | Done
71007726 | GRL | 8 | Knitting start | Factory | 2026-06-23 |  | 2026-06-23 | Done
71007726 | GRL | 9 | Linking start | Factory | 2026-06-29 |  | 2026-06-28 | Done
71007726 | GRL | 10 | Final inspection | Karbar QA | 2026-08-01 |  | 2026-08-10 | Done late
71007726 | GRL | 11 | Ex-factory | Factory | 2026-08-02 |  | 2026-08-11 | Done late
71007733 | MDW | 1 | Yarn booking | Factory | 2026-05-02 |  | 2026-05-02 | Done
71007733 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-12 |  | 2026-05-13 | Done late
71007733 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007733 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-06 | Done
71007733 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-15 | Done
71007733 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-21 |  | 2026-06-23 | Done late
71007733 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-06-24 |  | 2026-06-24 | Done
71007733 | MDW | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-27 | Done late
71007733 | MDW | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007733 | MDW | 10 | Final inspection | Karbar QA | 2026-08-04 |  | 2026-08-04 | Done
71007733 | MDW | 11 | Ex-factory | Factory | 2026-08-05 |  | 2026-08-05 | Done
71007737 | HMR | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-12 | Done
71007737 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007737 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007737 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-20 | Done late
71007737 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-27 | Done
71007737 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71007737 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-07-06 |  | 2026-07-07 | Done late
71007737 | HMR | 8 | Knitting start | Factory | 2026-07-08 |  | 2026-07-08 | Done
71007737 | HMR | 9 | Linking start | Factory | 2026-07-14 |  | 2026-07-13 | Done
71007737 | HMR | 10 | Final inspection | Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71007737 | HMR | 11 | Ex-factory | Factory | 2026-08-17 |  | 2026-08-17 | Done
71007744 | BRW | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-16 | Done late
71007744 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007744 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-30 | Done late
71007744 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007744 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71007744 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-04 | Done late
71007744 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-07-06 |  | 2026-07-07 | Done late
71007744 | BRW | 8 | Knitting start | Factory | 2026-07-08 |  | 2026-07-08 | Done
71007744 | BRW | 9 | Linking start | Factory | 2026-07-14 |  | 2026-07-13 | Done
71007744 | BRW | 10 | Final inspection | Karbar QA | 2026-08-16 |  | 2026-08-12 | Done
71007744 | BRW | 11 | Ex-factory | Factory | 2026-08-17 |  | 2026-08-13 | Done
71007753 | IRB | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-14 | Done
71007753 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-28 | Done late
71007753 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-02 | Done late
71007753 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71007753 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-30 | Done
71007753 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-06 | Done
71007753 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-07 | Done
71007753 | IRB | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-11 | Done
71007753 | IRB | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007753 | IRB | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71007753 | IRB | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-20 | Done
71007760 | RSG | 1 | Yarn booking | Factory | 2026-05-19 |  | 2026-05-18 | Done
71007760 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-26 | Done
71007760 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71007760 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-22 | Done
71007760 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71007760 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-08 |  | 2026-07-08 | Done
71007760 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-07-11 |  | 2026-07-12 | Done late
71007760 | RSG | 8 | Knitting start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71007760 | RSG | 9 | Linking start | Factory | 2026-07-19 |  | 2026-07-18 | Done
71007760 | RSG | 10 | Final inspection | Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71007760 | RSG | 11 | Ex-factory | Factory | 2026-08-22 |  | 2026-08-22 | Done
71007768 | FNS | 1 | Yarn booking | Factory | 2026-04-16 |  | 2026-04-16 | Done
71007768 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-04-26 |  | 2026-04-27 | Done late
71007768 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-04-30 |  | 2026-04-30 | Done
71007768 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-23 | Done late
71007768 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-05-31 |  | 2026-06-01 | Done late
71007768 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-04 |  | 2026-06-04 | Done
71007768 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-06-08 |  | 2026-06-08 | Done
71007768 | FNS | 8 | Knitting start | Factory | 2026-06-10 |  | 2026-06-10 | Done
71007768 | FNS | 9 | Linking start | Factory | 2026-06-16 |  | 2026-06-15 | Done
71007768 | FNS | 10 | Final inspection | Karbar QA | 2026-07-19 |  | 2026-07-19 | Done
71007768 | FNS | 11 | Ex-factory | Factory | 2026-07-20 |  | 2026-07-20 | Done
71007771 | WSM | 1 | Yarn booking | Factory | 2026-04-23 |  | 2026-04-23 | Done
71007771 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-06 | Done late
71007771 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-09 | Done
71007771 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007771 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-07 | Done
71007771 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-13 |  | 2026-06-15 | Done late
71007771 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-16 |  | 2026-06-16 | Done
71007771 | WSM | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-18 | Done
71007771 | WSM | 9 | Linking start | Factory | 2026-06-24 |  | 2026-06-23 | Done
71007771 | WSM | 10 | Final inspection | Karbar QA | 2026-07-27 |  | 2026-07-26 | Done
71007771 | WSM | 11 | Ex-factory | Factory | 2026-07-28 |  | 2026-07-27 | Done
71007775 | IRB | 1 | Yarn booking | Factory | 2026-05-10 |  | 2026-05-10 | Done
71007775 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-21 | Done late
71007775 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-23 | Done
71007775 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-15 | Done late
71007775 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-25 | Done late
71007775 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-29 |  | 2026-06-30 | Done late
71007775 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-02 |  | 2026-07-04 | Done late
71007775 | IRB | 8 | Knitting start | Factory | 2026-07-04 |  | 2026-07-05 | Done late
71007775 | IRB | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007775 | IRB | 10 | Final inspection | Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71007775 | IRB | 11 | Ex-factory | Factory | 2026-08-13 |  | 2026-08-13 | Done
71007780 | GRL | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-19 | Done late
71007780 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007780 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71007780 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-23 | Done late
71007780 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-30 | Done
71007780 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-07 | Done late
71007780 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-08 | Done
71007780 | GRL | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-12 | Done late
71007780 | GRL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007780 | GRL | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71007780 | GRL | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-20 | Done
71007784 | BRW | 1 | Yarn booking | Factory | 2026-05-19 |  | 2026-05-17 | Done
71007784 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-30 | Done late
71007784 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-02 | Done
71007784 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-23 | Done
71007784 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71007784 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-08 |  | 2026-07-07 | Done
71007784 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-07-11 |  | 2026-07-09 | Done
71007784 | BRW | 8 | Knitting start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71007784 | BRW | 9 | Linking start | Factory | 2026-07-19 |  | 2026-07-18 | Done
71007784 | BRW | 10 | Final inspection | Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71007784 | BRW | 11 | Ex-factory | Factory | 2026-08-22 |  | 2026-08-22 | Done
71007790 | SLM | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71007790 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-31 |  | 2026-06-02 | Done late
71007790 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-03 | Done
71007790 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-23 | Done
71007790 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71007790 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-09 |  | 2026-07-07 | Done
71007790 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-13 |  | 2026-07-15 | Done late
71007790 | SLM | 8 | Knitting start | Factory | 2026-07-15 |  | 2026-07-15 | Done
71007790 | SLM | 9 | Linking start | Factory | 2026-07-21 |  | 2026-07-20 | Done
71007790 | SLM | 10 | Final inspection | Karbar QA | 2026-08-23 |  | 2026-08-23 | Done
71007790 | SLM | 11 | Ex-factory | Factory | 2026-08-24 |  | 2026-08-24 | Done
71007797 | WTH | 1 | Yarn booking | Factory | 2026-04-23 |  | 2026-04-23 | Done
71007797 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-04 |  | 2026-05-06 | Done late
71007797 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-09 | Done
71007797 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007797 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-08 | Done
71007797 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-13 |  | 2026-06-13 | Done
71007797 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-06-16 |  | 2026-06-15 | Done
71007797 | WTH | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-20 | Done late
71007797 | WTH | 9 | Linking start | Factory | 2026-06-24 |  | 2026-06-25 | Done late
71007797 | WTH | 10 | Final inspection | Karbar QA | 2026-07-27 |  | 2026-07-25 | Done
71007797 | WTH | 11 | Ex-factory | Factory | 2026-07-28 |  | 2026-07-26 | Done
71007805 | IRB | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-05 | Done
71007805 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-18 | Done
71007805 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-21 | Done
71007805 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007805 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71007805 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-27 |  | 2026-06-27 | Done
71007805 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-06-30 |  | 2026-06-29 | Done
71007805 | IRB | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007805 | IRB | 9 | Linking start | Factory | 2026-07-08 |  | 2026-07-07 | Done
71007805 | IRB | 10 | Final inspection | Karbar QA | 2026-08-10 |  | 2026-08-12 | Done late
71007805 | IRB | 11 | Ex-factory | Factory | 2026-08-11 |  | 2026-08-13 | Done late
71007812 | SLM | 1 | Yarn booking | Factory | 2026-05-09 |  | 2026-05-07 | Done
71007812 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-21 | Done late
71007812 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71007812 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71007812 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-23 | Done
71007812 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-28 |  | 2026-06-28 | Done
71007812 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-01 |  | 2026-06-29 | Done
71007812 | SLM | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007812 | SLM | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-07 | Done
71007812 | SLM | 10 | Final inspection | Karbar QA | 2026-08-11 |  | 2026-08-10 | Done
71007812 | SLM | 11 | Ex-factory | Factory | 2026-08-12 |  | 2026-08-11 | Done
71007821 | CLB | 1 | Yarn booking | Factory | 2026-05-09 |  | 2026-05-07 | Done
71007821 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-20 | Done late
71007821 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-23 | Done
71007821 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71007821 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-24 | Done late
71007821 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-28 |  | 2026-06-25 | Done
71007821 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71007821 | CLB | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007821 | CLB | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-07 | Done
71007821 | CLB | 10 | Final inspection | Karbar QA | 2026-08-11 |  | 2026-08-11 | Done
71007821 | CLB | 11 | Ex-factory | Factory | 2026-08-12 |  | 2026-08-12 | Done
71007828 | KST | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-14 | Done
71007828 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-25 | Done late
71007828 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007828 | KST | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007828 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-29 | Done late
71007828 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71007828 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-07-06 |  | 2026-07-06 | Done
71007828 | KST | 8 | Knitting start | Factory | 2026-07-08 |  | 2026-07-09 | Done late
71007828 | KST | 9 | Linking start | Factory | 2026-07-14 |  | 2026-07-14 | Done
71007828 | KST | 10 | Final inspection | Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71007828 | KST | 11 | Ex-factory | Factory | 2026-08-17 |  | 2026-08-17 | Done
71007834 | AMB | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-25 | Done late
71007834 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-05-31 | Done
71007834 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-07 | Done
71007834 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71007834 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-09 | Done late
71007834 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-14 | Done late
71007834 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-13 | Done
71007834 | AMB | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007834 | AMB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71007834 | AMB | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-25 | Done
71007834 | AMB | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-26 | Done
71007840 | WTH | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-30 | Done
71007840 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-12 | Done late
71007840 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71007840 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71007840 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71007840 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-20 |  | 2026-06-18 | Done
71007840 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-06-23 |  | 2026-06-23 | Done
71007840 | WTH | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007840 | WTH | 9 | Linking start | Factory | 2026-07-01 |  | 2026-06-30 | Done
71007840 | WTH | 10 | Final inspection | Karbar QA | 2026-08-03 |  | 2026-08-05 | Done late
71007840 | WTH | 11 | Ex-factory | Factory | 2026-08-04 |  | 2026-08-06 | Done late
71007849 | WSM | 1 | Yarn booking | Factory | 2026-05-06 |  | 2026-05-06 | Done
71007849 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-18 | Done late
71007849 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-19 | Done
71007849 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-08 | Done
71007849 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71007849 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71007849 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-28 |  | 2026-06-27 | Done
71007849 | WSM | 8 | Knitting start | Factory | 2026-06-30 |  | 2026-06-30 | Done
71007849 | WSM | 9 | Linking start | Factory | 2026-07-06 |  | 2026-07-05 | Done
71007849 | WSM | 10 | Final inspection | Karbar QA | 2026-08-08 |  | 2026-08-08 | Done
71007849 | WSM | 11 | Ex-factory | Factory | 2026-08-09 |  | 2026-08-09 | Done
71007856 | OKH | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-07 | Done
71007856 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007856 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007856 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-10 | Done
71007856 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-22 | Done late
71007856 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-23 | Done
71007856 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-30 | Done late
71007856 | OKH | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007856 | OKH | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007856 | OKH | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-09 | Done
71007856 | OKH | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-10 | Done
71007859 | SVP | 1 | Yarn booking | Factory | 2026-05-27 |  | 2026-05-27 | Done
71007859 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-06 | Done
71007859 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-13 | Done late
71007859 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-29 | Done
71007859 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71007859 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-16 |  | 2026-07-16 | Done
71007859 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-19 |  | 2026-07-18 | Done
71007859 | SVP | 8 | Knitting start | Factory | 2026-07-21 |  | 2026-07-21 | Done
71007859 | SVP | 9 | Linking start | Factory | 2026-07-27 |  | 2026-07-26 | Done
71007859 | SVP | 10 | Final inspection | Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71007859 | SVP | 11 | Ex-factory | Factory | 2026-08-30 |  | 2026-08-30 | Done
71007867 | AMB | 1 | Yarn booking | Factory | 2026-04-26 |  | 2026-04-27 | Done late
71007867 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-06 |  | 2026-05-07 | Done late
71007867 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-10 | Done
71007867 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-31 | Done
71007867 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-11 | Done late
71007867 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-15 |  | 2026-06-15 | Done
71007867 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-06-18 |  | 2026-06-17 | Done
71007867 | AMB | 8 | Knitting start | Factory | 2026-06-20 |  | 2026-06-21 | Done late
71007867 | AMB | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007867 | AMB | 10 | Final inspection | Karbar QA | 2026-07-29 |  | 2026-08-02 | Done late
71007867 | AMB | 11 | Ex-factory | Factory | 2026-07-30 |  | 2026-08-03 | Done late
71007872 | CLB | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-30 | Done
71007872 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-09 | Done
71007872 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-16 | Done late
71007872 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-06 | Done late
71007872 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-13 | Done
71007872 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-18 | Done
71007872 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-06-22 |  | 2026-06-20 | Done
71007872 | CLB | 8 | Knitting start | Factory | 2026-06-24 |  | 2026-06-24 | Done
71007872 | CLB | 9 | Linking start | Factory | 2026-06-30 |  | 2026-06-29 | Done
71007872 | CLB | 10 | Final inspection | Karbar QA | 2026-08-02 |  | 2026-07-30 | Done
71007872 | CLB | 11 | Ex-factory | Factory | 2026-08-03 |  | 2026-08-01 | Done
71007875 | SVP | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-13 | Done
71007875 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-26 | Done late
71007875 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71007875 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71007875 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-28 | Done
71007875 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-04 |  | 2026-07-02 | Done
71007875 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-07 |  | 2026-07-07 | Done
71007875 | SVP | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-11 | Done late
71007875 | SVP | 9 | Linking start | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71007875 | SVP | 10 | Final inspection | Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71007875 | SVP | 11 | Ex-factory | Factory | 2026-08-18 |  | 2026-08-18 | Done
71007884 | BRW | 1 | Yarn booking | Factory | 2026-05-03 |  | 2026-05-04 | Done late
71007884 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007884 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-18 | Done
71007884 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-04 | Done
71007884 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007884 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-22 |  | 2026-06-22 | Done
71007884 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-06-25 |  | 2026-06-25 | Done
71007884 | BRW | 8 | Knitting start | Factory | 2026-06-27 |  | 2026-06-28 | Done late
71007884 | BRW | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007884 | BRW | 10 | Final inspection | Karbar QA | 2026-08-05 |  | 2026-08-05 | Done
71007884 | BRW | 11 | Ex-factory | Factory | 2026-08-06 |  | 2026-08-06 | Done
71007892 | HMR | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-07 | Done
71007892 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-19 | Done late
71007892 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007892 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007892 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71007892 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-28 | Done late
71007892 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-29 | Done
71007892 | HMR | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007892 | HMR | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007892 | HMR | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-05 | Done
71007892 | HMR | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-06 | Done
71007898 | PBB | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-17 | Done
71007898 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71007898 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71007898 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-23 | Done late
71007898 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-30 | Done
71007898 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-06 | Done
71007898 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-09 | Done
71007898 | PBB | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-12 | Done late
71007898 | PBB | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007898 | PBB | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71007898 | PBB | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-20 | Done
71007902 | SVP | 1 | Yarn booking | Factory | 2026-05-27 |  | 2026-05-27 | Done
71007902 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-06 | Done
71007902 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-10 | Done
71007902 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71007902 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-09 | Done
71007902 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-16 |  | 2026-07-15 | Done
71007902 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-19 |  | 2026-07-16 | Done
71007902 | SVP | 8 | Knitting start | Factory | 2026-07-21 |  | 2026-07-21 | Done
71007902 | SVP | 9 | Linking start | Factory | 2026-07-27 |  | 2026-07-26 | Done
71007902 | SVP | 10 | Final inspection | Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71007902 | SVP | 11 | Ex-factory | Factory | 2026-08-30 |  | 2026-08-30 | Done
71007908 | CPL | 1 | Yarn booking | Factory | 2026-04-28 |  | 2026-04-30 | Done late
71007908 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-07 | Done
71007908 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-11 | Done
71007908 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-02 |  | 2026-05-31 | Done
71007908 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-13 | Done late
71007908 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-17 |  | 2026-06-16 | Done
71007908 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-06-20 |  | 2026-06-22 | Done late
71007908 | CPL | 8 | Knitting start | Factory | 2026-06-22 |  | 2026-06-22 | Done
71007908 | CPL | 9 | Linking start | Factory | 2026-06-28 |  | 2026-06-27 | Done
71007908 | CPL | 10 | Final inspection | Karbar QA | 2026-07-30 |  | 2026-07-29 | Done
71007908 | CPL | 11 | Ex-factory | Factory | 2026-08-01 |  | 2026-07-30 | Done
71007915 | TLG | 1 | Yarn booking | Factory | 2026-05-12 |  | 2026-05-11 | Done
71007915 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-19 | Done
71007915 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007915 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-16 | Done
71007915 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-24 | Done
71007915 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-01 |  | 2026-06-29 | Done
71007915 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-04 |  | 2026-07-02 | Done
71007915 | TLG | 8 | Knitting start | Factory | 2026-07-06 |  | 2026-07-07 | Done late
71007915 | TLG | 9 | Linking start | Factory | 2026-07-12 |  | 2026-07-12 | Done
71007915 | TLG | 10 | Final inspection | Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71007915 | TLG | 11 | Ex-factory | Factory | 2026-08-15 |  | 2026-08-15 | Done
71007921 | PBB | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-23 | Done
71007921 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-03 | Done late
71007921 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-09 | Done late
71007921 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71007921 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-07 | Done
71007921 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-14 | Done late
71007921 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-13 | Done
71007921 | PBB | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007921 | PBB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71007921 | PBB | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-25 | Done
71007921 | PBB | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-26 | Done
71007926 | SLM | 1 | Yarn booking | Factory | 2026-04-28 |  | 2026-04-28 | Done
71007926 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-09 | Done late
71007926 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-13 | Done
71007926 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-02 | Done
71007926 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007926 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-17 |  | 2026-06-15 | Done
71007926 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-20 |  | 2026-06-20 | Done
71007926 | SLM | 8 | Knitting start | Factory | 2026-06-22 |  | 2026-06-23 | Done late
71007926 | SLM | 9 | Linking start | Factory | 2026-06-28 |  | 2026-06-28 | Done
71007926 | SLM | 10 | Final inspection | Karbar QA | 2026-07-30 |  | 2026-07-30 | Done
71007926 | SLM | 11 | Ex-factory | Factory | 2026-08-01 |  | 2026-08-01 | Done
71007930 | GRL | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-05 | Done
71007930 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-16 | Done
71007930 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007930 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007930 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-23 | Done late
71007930 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71007930 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-30 | Done late
71007930 | GRL | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007930 | GRL | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007930 | GRL | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-12 | Done late
71007930 | GRL | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-13 | Done late
71007935 | SLM | 1 | Yarn booking | Factory | 2026-05-07 |  | 2026-05-09 | Done late
71007935 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-17 |  | 2026-05-17 | Done
71007935 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71007935 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007935 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71007935 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71007935 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-29 |  | 2026-06-29 | Done
71007935 | SLM | 8 | Knitting start | Factory | 2026-07-01 |  | 2026-07-01 | Done
71007935 | SLM | 9 | Linking start | Factory | 2026-07-07 |  | 2026-07-06 | Done
71007935 | SLM | 10 | Final inspection | Karbar QA | 2026-08-09 |  | 2026-08-09 | Done
71007935 | SLM | 11 | Ex-factory | Factory | 2026-08-10 |  | 2026-08-10 | Done
71007938 | BRW | 1 | Yarn booking | Factory | 2026-04-25 |  | 2026-04-26 | Done late
71007938 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-05 |  | 2026-05-06 | Done late
71007938 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-05-10 |  | 2026-05-12 | Done late
71007938 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71007938 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-09 | Done
71007938 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-14 |  | 2026-06-15 | Done late
71007938 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-06-17 |  | 2026-06-18 | Done late
71007938 | BRW | 8 | Knitting start | Factory | 2026-06-18 |  | 2026-06-20 | Done late
71007938 | BRW | 9 | Linking start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71007938 | BRW | 10 | Final inspection | Karbar QA | 2026-07-28 |  | 2026-07-28 | Done
71007938 | BRW | 11 | Ex-factory | Factory | 2026-07-29 |  | 2026-07-29 | Done
71007946 | OKH | 1 | Yarn booking | Factory | 2026-05-10 |  | 2026-05-09 | Done
71007946 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71007946 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-24 | Done
71007946 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-15 | Done late
71007946 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-23 | Done
71007946 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-29 |  | 2026-07-01 | Done late
71007946 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-07-02 |  | 2026-06-30 | Done
71007946 | OKH | 8 | Knitting start | Factory | 2026-07-04 |  | 2026-07-04 | Done
71007946 | OKH | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71007946 | OKH | 10 | Final inspection | Karbar QA | 2026-08-12 |  | 2026-08-11 | Done
71007946 | OKH | 11 | Ex-factory | Factory | 2026-08-13 |  | 2026-08-12 | Done
71007955 | RVS | 1 | Yarn booking | Factory | 2026-05-13 |  | 2026-05-14 | Done late
71007955 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-24 | Done late
71007955 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71007955 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007955 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-29 | Done late
71007955 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-04 | Done late
71007955 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-07-05 |  | 2026-07-07 | Done late
71007955 | RVS | 8 | Knitting start | Factory | 2026-07-07 |  | 2026-07-08 | Done late
71007955 | RVS | 9 | Linking start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71007955 | RVS | 10 | Final inspection | Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71007955 | RVS | 11 | Ex-factory | Factory | 2026-08-16 |  | 2026-08-16 | Done
71007962 | SND | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-21 | Done
71007962 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-03 | Done late
71007962 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-07 | Done
71007962 | SND | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71007962 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-07 | Done
71007962 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-14 | Done late
71007962 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-16 | Done late
71007962 | SND | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71007962 | SND | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71007962 | SND | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-23 | Done
71007962 | SND | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-24 | Done
71007965 | BLF | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-31 | Done
71007965 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71007965 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-16 | Done late
71007965 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71007965 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71007965 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-20 | Done
71007965 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-23 | Done
71007965 | BLF | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-25 | Done
71007965 | BLF | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71007965 | BLF | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-09-01 | Done
71007965 | BLF | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-02 | Done
71007968 | GRL | 1 | Yarn booking | Factory | 2026-05-03 |  | 2026-05-02 | Done
71007968 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-12 | Done
71007968 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-18 |  | 2026-05-19 | Done late
71007968 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-07 | Done
71007968 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71007968 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-22 |  | 2026-06-23 | Done late
71007968 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-06-25 |  | 2026-06-25 | Done
71007968 | GRL | 8 | Knitting start | Factory | 2026-06-27 |  | 2026-06-28 | Done late
71007968 | GRL | 9 | Linking start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71007968 | GRL | 10 | Final inspection | Karbar QA | 2026-08-05 |  | 2026-08-08 | Done late
71007968 | GRL | 11 | Ex-factory | Factory | 2026-08-06 |  | 2026-08-09 | Done late
71007975 | GRL | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-17 | Done
71007975 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007975 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71007975 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-23 | Done late
71007975 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71007975 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-04 | Done
71007975 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-09 | Done
71007975 | GRL | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-11 | Done
71007975 | GRL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007975 | GRL | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-27 | Done late
71007975 | GRL | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-29 | Done late
71007984 | GRL | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-17 | Done
71007984 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-27 | Done
71007984 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-02 | Done late
71007984 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71007984 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71007984 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-08 | Done late
71007984 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-07 | Done
71007984 | GRL | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-12 | Done late
71007984 | GRL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007984 | GRL | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71007984 | GRL | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-20 | Done
71007990 | SLM | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-25 | Done late
71007990 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-04 | Done late
71007990 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-08 | Done late
71007990 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71007990 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-06 | Done
71007990 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-12 | Done
71007990 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71007990 | SLM | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71007990 | SLM | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71007990 | SLM | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-25 | Done
71007990 | SLM | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-26 | Done
71007994 | PBB | 1 | Yarn booking | Factory | 2026-04-28 |  | 2026-04-28 | Done
71007994 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-07 |  | 2026-05-07 | Done
71007994 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-13 |  | 2026-05-11 | Done
71007994 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-04 | Done late
71007994 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71007994 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-17 |  | 2026-06-18 | Done late
71007994 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-06-20 |  | 2026-06-20 | Done
71007994 | PBB | 8 | Knitting start | Factory | 2026-06-22 |  | 2026-06-23 | Done late
71007994 | PBB | 9 | Linking start | Factory | 2026-06-28 |  | 2026-06-28 | Done
71007994 | PBB | 10 | Final inspection | Karbar QA | 2026-07-30 |  | 2026-07-28 | Done
71007994 | PBB | 11 | Ex-factory | Factory | 2026-08-01 |  | 2026-07-29 | Done
71008003 | WSM | 1 | Yarn booking | Factory | 2026-04-29 |  | 2026-04-29 | Done
71008003 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-09 |  | 2026-05-09 | Done
71008003 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71008003 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71008003 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71008003 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-18 |  | 2026-06-18 | Done
71008003 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-06-21 |  | 2026-06-21 | Done
71008003 | WSM | 8 | Knitting start | Factory | 2026-06-23 |  | 2026-06-23 | Done
71008003 | WSM | 9 | Linking start | Factory | 2026-06-29 |  | 2026-06-28 | Done
71008003 | WSM | 10 | Final inspection | Karbar QA | 2026-08-01 |  | 2026-08-02 | Done late
71008003 | WSM | 11 | Ex-factory | Factory | 2026-08-02 |  | 2026-08-03 | Done late
71008007 | SLM | 1 | Yarn booking | Factory | 2026-04-30 |  | 2026-04-28 | Done
71008007 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-11 |  | 2026-05-09 | Done
71008007 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-14 | Done
71008007 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-02 | Done
71008007 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-17 | Done late
71008007 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-20 |  | 2026-06-20 | Done
71008007 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-23 |  | 2026-06-23 | Done
71008007 | SLM | 8 | Knitting start | Factory | 2026-06-25 |  | 2026-06-25 | Done
71008007 | SLM | 9 | Linking start | Factory | 2026-07-01 |  | 2026-06-30 | Done
71008007 | SLM | 10 | Final inspection | Karbar QA | 2026-08-03 |  | 2026-08-09 | Done late
71008007 | SLM | 11 | Ex-factory | Factory | 2026-08-04 |  | 2026-08-10 | Done late
71008014 | RSG | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-16 | Done late
71008014 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-24 | Done
71008014 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71008014 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008014 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008014 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-04 |  | 2026-07-04 | Done
71008014 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-07-07 |  | 2026-07-07 | Done
71008014 | RSG | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71008014 | RSG | 9 | Linking start | Factory | 2026-07-15 |  | 2026-07-14 | Done
71008014 | RSG | 10 | Final inspection | Karbar QA | 2026-08-17 |  | 2026-08-19 | Done late
71008014 | RSG | 11 | Ex-factory | Factory | 2026-08-18 |  | 2026-08-20 | Done late
71008017 | CPL | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-18 | Done late
71008017 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71008017 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-05-30 | Done
71008017 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71008017 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71008017 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-06 | Done
71008017 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-09 | Done
71008017 | CPL | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-11 | Done
71008017 | CPL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71008017 | CPL | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71008017 | CPL | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-20 | Done
71008020 | GRL | 1 | Yarn booking | Factory | 2026-05-20 |  | 2026-05-21 | Done late
71008020 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71008020 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71008020 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-23 | Done
71008020 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008020 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-09 |  | 2026-07-09 | Done
71008020 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-12 |  | 2026-07-11 | Done
71008020 | GRL | 8 | Knitting start | Factory | 2026-07-14 |  | 2026-07-14 | Done
71008020 | GRL | 9 | Linking start | Factory | 2026-07-20 |  | 2026-07-19 | Done
71008020 | GRL | 10 | Final inspection | Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71008020 | GRL | 11 | Ex-factory | Factory | 2026-08-23 |  | 2026-08-23 | Done
71008026 | BLF | 1 | Yarn booking | Factory | 2026-05-27 |  | 2026-05-26 | Done
71008026 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-04 | Done
71008026 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-09 | Done
71008026 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71008026 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-13 | Done late
71008026 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-16 |  | 2026-07-14 | Done
71008026 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-19 |  | 2026-07-16 | Done
71008026 | BLF | 8 | Knitting start | Factory | 2026-07-21 |  | 2026-07-22 | Done late
71008026 | BLF | 9 | Linking start | Factory | 2026-07-27 |  | 2026-07-27 | Done
71008026 | BLF | 10 | Final inspection | Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71008026 | BLF | 11 | Ex-factory | Factory | 2026-08-30 |  | 2026-08-30 | Done
71008034 | WTH | 1 | Yarn booking | Factory | 2026-05-12 |  | 2026-05-13 | Done late
71008034 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-19 | Done
71008034 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-26 | Done
71008034 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-14 | Done
71008034 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008034 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-01 |  | 2026-07-01 | Done
71008034 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-07-04 |  | 2026-07-02 | Done
71008034 | WTH | 8 | Knitting start | Factory | 2026-07-06 |  | 2026-07-06 | Done
71008034 | WTH | 9 | Linking start | Factory | 2026-07-12 |  | 2026-07-11 | Done
71008034 | WTH | 10 | Final inspection | Karbar QA | 2026-08-13 |  | 2026-08-12 | Done
71008034 | WTH | 11 | Ex-factory | Factory | 2026-08-15 |  | 2026-08-13 | Done
71008039 | WSM | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-12 | Done
71008039 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-25 | Done
71008039 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71008039 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-20 | Done late
71008039 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-28 | Done
71008039 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-04 |  | 2026-07-04 | Done
71008039 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-07-07 |  | 2026-07-06 | Done
71008039 | WSM | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-11 | Done late
71008039 | WSM | 9 | Linking start | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71008039 | WSM | 10 | Final inspection | Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71008039 | WSM | 11 | Ex-factory | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008048 | PBB | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-12 | Done
71008048 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71008048 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71008048 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008048 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-29 | Done late
71008048 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71008048 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-07-06 |  | 2026-07-06 | Done
71008048 | PBB | 8 | Knitting start | Factory | 2026-07-08 |  | 2026-07-09 | Done late
71008048 | PBB | 9 | Linking start | Factory | 2026-07-14 |  | 2026-07-14 | Done
71008048 | PBB | 10 | Final inspection | Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008048 | PBB | 11 | Ex-factory | Factory | 2026-08-17 |  | 2026-08-17 | Done
71008053 | LTF | 1 | Yarn booking | Factory | 2026-05-20 |  | 2026-05-21 | Done late
71008053 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71008053 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-03 | Done
71008053 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-22 | Done
71008053 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008053 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-09 |  | 2026-07-12 | Done late
71008053 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-07-12 |  | 2026-07-14 | Done late
71008053 | LTF | 8 | Knitting start | Factory | 2026-07-14 |  | 2026-07-15 | Done late
71008053 | LTF | 9 | Linking start | Factory | 2026-07-20 |  | 2026-07-20 | Done
71008053 | LTF | 10 | Final inspection | Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71008053 | LTF | 11 | Ex-factory | Factory | 2026-08-23 |  | 2026-08-23 | Done
71008062 | TLG | 1 | Yarn booking | Factory | 2026-05-24 |  | 2026-05-26 | Done late
71008062 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71008062 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-09 | Done late
71008062 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-29 | Done late
71008062 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008062 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-13 |  | 2026-07-15 | Done late
71008062 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-16 |  | 2026-07-18 | Done late
71008062 | TLG | 8 | Knitting start | Factory | 2026-07-18 |  | 2026-07-18 | Done
71008062 | TLG | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008062 | TLG | 10 | Final inspection | Karbar QA | 2026-08-26 |  | 2026-08-25 | Done
71008062 | TLG | 11 | Ex-factory | Factory | 2026-08-27 |  | 2026-08-26 | Done
71008066 | OKH | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008066 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-13 | Done
71008066 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-21 | Done late
71008066 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-07 | Done
71008066 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71008066 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-25 | Done
71008066 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-29 | Done late
71008066 | OKH | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008066 | OKH | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-03 | Done
71008066 | OKH | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71008066 | OKH | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-08 | Done
71008069 | TLG | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-03 | Done
71008069 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-17 | Done late
71008069 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008069 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008069 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-22 | Done late
71008069 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-28 | Done late
71008069 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-28 | Done
71008069 | TLG | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71008069 | TLG | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-04 | Done
71008069 | TLG | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-06 | Done
71008069 | TLG | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-07 | Done
71008072 | SLM | 1 | Yarn booking | Factory | 2026-05-05 |  | 2026-05-05 | Done
71008072 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-14 |  | 2026-05-14 | Done
71008072 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-20 | Done
71008072 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-09 | Done
71008072 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-17 | Done
71008072 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-24 |  | 2026-06-25 | Done late
71008072 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-06-27 |  | 2026-06-25 | Done
71008072 | SLM | 8 | Knitting start | Factory | 2026-06-29 |  | 2026-06-29 | Done
71008072 | SLM | 9 | Linking start | Factory | 2026-07-05 |  | 2026-07-04 | Done
71008072 | SLM | 10 | Final inspection | Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008072 | SLM | 11 | Ex-factory | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008081 | AMB | 1 | Yarn booking | Factory | 2026-05-06 |  | 2026-05-06 | Done
71008081 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-18 | Done late
71008081 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71008081 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-08 | Done
71008081 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-21 | Done late
71008081 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-25 | Done
71008081 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-06-28 |  | 2026-06-30 | Done late
71008081 | AMB | 8 | Knitting start | Factory | 2026-06-30 |  | 2026-06-30 | Done
71008081 | AMB | 9 | Linking start | Factory | 2026-07-06 |  | 2026-07-05 | Done
71008081 | AMB | 10 | Final inspection | Karbar QA | 2026-08-08 |  | 2026-08-08 | Done
71008081 | AMB | 11 | Ex-factory | Factory | 2026-08-09 |  | 2026-08-09 | Done
71008084 | CPL | 1 | Yarn booking | Factory | 2026-05-17 |  | 2026-05-17 | Done
71008084 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-27 |  | 2026-05-28 | Done late
71008084 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71008084 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-22 | Done late
71008084 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71008084 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-06 |  | 2026-07-07 | Done late
71008084 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-09 |  | 2026-07-11 | Done late
71008084 | CPL | 8 | Knitting start | Factory | 2026-07-11 |  | 2026-07-11 | Done
71008084 | CPL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71008084 | CPL | 10 | Final inspection | Karbar QA | 2026-08-19 |  | 2026-08-18 | Done
71008084 | CPL | 11 | Ex-factory | Factory | 2026-08-20 |  | 2026-08-19 | Done
71008092 | RSG | 1 | Yarn booking | Factory | 2026-05-20 |  | 2026-05-20 | Done
71008092 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-28 | Done
71008092 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-06 | Done late
71008092 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-25 | Done late
71008092 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008092 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-09 |  | 2026-07-09 | Done
71008092 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-07-12 |  | 2026-07-12 | Done
71008092 | RSG | 8 | Knitting start | Factory | 2026-07-14 |  | 2026-07-15 | Done late
71008092 | RSG | 9 | Linking start | Factory | 2026-07-20 |  | 2026-07-20 | Done
71008092 | RSG | 10 | Final inspection | Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71008092 | RSG | 11 | Ex-factory | Factory | 2026-08-23 |  | 2026-08-23 | Done
71008097 | CLB | 1 | Yarn booking | Factory | 2026-05-28 |  | 2026-05-26 | Done
71008097 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-08 | Done
71008097 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71008097 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008097 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008097 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-18 |  | 2026-07-16 | Done
71008097 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-07-21 |  | 2026-07-23 | Done late
71008097 | CLB | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008097 | CLB | 9 | Linking start | Factory | 2026-07-29 |  | 2026-07-28 | Done
71008097 | CLB | 10 | Final inspection | Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71008097 | CLB | 11 | Ex-factory | Factory | 2026-09-01 |  | 2026-09-01 | Done
71008103 | PBB | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008103 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-13 | Done
71008103 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008103 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008103 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008103 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-26 | Done late
71008103 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-27 | Done
71008103 | PBB | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71008103 | PBB | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-03 | Done
71008103 | PBB | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-02 | Done
71008103 | PBB | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-03 | Done
71008107 | FNS | 1 | Yarn booking | Factory | 2026-05-13 |  | 2026-05-13 | Done
71008107 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-24 | Done late
71008107 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-27 | Done
71008107 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008107 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71008107 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71008107 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-07-05 |  | 2026-07-05 | Done
71008107 | FNS | 8 | Knitting start | Factory | 2026-07-07 |  | 2026-07-08 | Done late
71008107 | FNS | 9 | Linking start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71008107 | FNS | 10 | Final inspection | Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71008107 | FNS | 11 | Ex-factory | Factory | 2026-08-16 |  | 2026-08-16 | Done
71008113 | SLM | 1 | Yarn booking | Factory | 2026-05-13 |  | 2026-05-13 | Done
71008113 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-23 | Done
71008113 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71008113 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-15 | Done
71008113 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-28 | Done late
71008113 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-01 | Done
71008113 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-05 |  | 2026-07-04 | Done
71008113 | SLM | 8 | Knitting start | Factory | 2026-07-07 |  | 2026-07-07 | Done
71008113 | SLM | 9 | Linking start | Factory | 2026-07-13 |  | 2026-07-12 | Done
71008113 | SLM | 10 | Final inspection | Karbar QA | 2026-08-15 |  | 2026-08-12 | Done
71008113 | SLM | 11 | Ex-factory | Factory | 2026-08-16 |  | 2026-08-13 | Done
71008117 | CLB | 1 | Yarn booking | Factory | 2026-05-24 |  | 2026-05-24 | Done
71008117 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-04 | Done late
71008117 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-10 | Done late
71008117 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008117 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008117 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-13 |  | 2026-07-12 | Done
71008117 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-07-16 |  | 2026-07-16 | Done
71008117 | CLB | 8 | Knitting start | Factory | 2026-07-18 |  | 2026-07-18 | Done
71008117 | CLB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008117 | CLB | 10 | Final inspection | Karbar QA | 2026-08-26 |  | 2026-08-25 | Done
71008117 | CLB | 11 | Ex-factory | Factory | 2026-08-27 |  | 2026-08-26 | Done
71008125 | FNS | 1 | Yarn booking | Factory | 2026-06-03 |  | 2026-06-01 | Done
71008125 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-11 | Done
71008125 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-20 | Done late
71008125 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-06 | Done
71008125 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-19 | Done late
71008125 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-23 | Done
71008125 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-07-26 |  | 2026-07-26 | Done
71008125 | FNS | 8 | Knitting start | Factory | 2026-07-28 |  | 2026-07-29 | Done late
71008125 | FNS | 9 | Linking start | Factory | 2026-08-03 |  | 2026-08-02 | Done
71008125 | FNS | 10 | Final inspection | Karbar QA | 2026-09-05 |  | 2026-09-02 | Done
71008125 | FNS | 11 | Ex-factory | Factory | 2026-09-06 |  | 2026-09-03 | Done
71008132 | KST | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-09 | Done
71008132 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008132 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008132 | KST | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008132 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008132 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71008132 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-03 | Done late
71008132 | KST | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008132 | KST | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008132 | KST | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008132 | KST | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008135 | GRL | 1 | Yarn booking | Factory | 2026-05-16 |  | 2026-05-16 | Done
71008135 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-25 | Done
71008135 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-31 | Done
71008135 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-21 | Done late
71008135 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-29 | Done
71008135 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-05 |  | 2026-07-07 | Done late
71008135 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-08 |  | 2026-07-09 | Done late
71008135 | GRL | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71008135 | GRL | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-14 | Done
71008135 | GRL | 10 | Final inspection | Karbar QA | 2026-08-18 |  | 2026-08-23 | Done late
71008135 | GRL | 11 | Ex-factory | Factory | 2026-08-19 |  | 2026-08-24 | Done late
71008142 | CPL | 1 | Yarn booking | Factory | 2026-05-24 |  | 2026-05-24 | Done
71008142 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71008142 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-10 | Done late
71008142 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-25 | Done
71008142 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71008142 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-13 |  | 2026-07-15 | Done late
71008142 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-16 |  | 2026-07-16 | Done
71008142 | CPL | 8 | Knitting start | Factory | 2026-07-18 |  | 2026-07-19 | Done late
71008142 | CPL | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008142 | CPL | 10 | Final inspection | Karbar QA | 2026-08-26 |  | 2026-08-24 | Done
71008142 | CPL | 11 | Ex-factory | Factory | 2026-08-27 |  | 2026-08-25 | Done
71008147 | SVP | 1 | Yarn booking | Factory | 2026-05-06 |  | 2026-05-05 | Done
71008147 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-16 |  | 2026-05-16 | Done
71008147 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-05-21 |  | 2026-05-21 | Done
71008147 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008147 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008147 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-25 |  | 2026-06-28 | Done late
71008147 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-06-28 |  | 2026-06-29 | Done late
71008147 | SVP | 8 | Knitting start | Factory | 2026-06-30 |  | 2026-06-30 | Done
71008147 | SVP | 9 | Linking start | Factory | 2026-07-06 |  | 2026-07-05 | Done
71008147 | SVP | 10 | Final inspection | Karbar QA | 2026-08-08 |  | 2026-08-05 | Done
71008147 | SVP | 11 | Ex-factory | Factory | 2026-08-09 |  | 2026-08-06 | Done
71008154 | CPL | 1 | Yarn booking | Factory | 2026-05-30 |  | 2026-05-31 | Done late
71008154 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-10 | Done late
71008154 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-13 | Done
71008154 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-06 | Done late
71008154 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-14 | Done
71008154 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-19 |  | 2026-07-21 | Done late
71008154 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-22 |  | 2026-07-20 | Done
71008154 | CPL | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-25 | Done late
71008154 | CPL | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71008154 | CPL | 10 | Final inspection | Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008154 | CPL | 11 | Ex-factory | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008159 | IRB | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-07 | Done
71008159 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008159 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71008159 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-11 | Done
71008159 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008159 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-27 | Done
71008159 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-08-01 | Done late
71008159 | IRB | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008159 | IRB | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008159 | IRB | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008159 | IRB | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008165 | AMB | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-08 | Done
71008165 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008165 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008165 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71008165 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-26 | Done late
71008165 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-28 | Done
71008165 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71008165 | AMB | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008165 | AMB | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008165 | AMB | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008165 | AMB | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008169 | SND | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-10 | Done
71008169 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008169 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008169 | SND | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008169 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008169 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71008169 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71008169 | SND | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008169 | SND | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008169 | SND | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-09 | Done
71008169 | SND | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-10 | Done
71008175 | GRL | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71008175 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71008175 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-07 | Done late
71008175 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-23 | Done
71008175 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-08 | Done late
71008175 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-11 |  | 2026-07-12 | Done late
71008175 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-14 |  | 2026-07-14 | Done
71008175 | GRL | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71008175 | GRL | 9 | Linking start | Factory | 2026-07-22 |  | 2026-07-21 | Done
71008175 | GRL | 10 | Final inspection | Karbar QA | 2026-08-24 |  | 2026-08-23 | Done
71008175 | GRL | 11 | Ex-factory | Factory | 2026-08-25 |  | 2026-08-24 | Done
71008180 | GRL | 1 | Yarn booking | Factory | 2026-05-30 |  | 2026-05-30 | Done
71008180 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-11 | Done late
71008180 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-16 | Done late
71008180 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-06 | Done late
71008180 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-16 | Done late
71008180 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-19 |  | 2026-07-16 | Done
71008180 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-22 |  | 2026-07-21 | Done
71008180 | GRL | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008180 | GRL | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-27 | Done
71008180 | GRL | 10 | Final inspection | Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008180 | GRL | 11 | Ex-factory | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008184 | TLG | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008184 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008184 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008184 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008184 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008184 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-23 | Done
71008184 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-27 | Done
71008184 | TLG | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71008184 | TLG | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-03 | Done
71008184 | TLG | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-09 | Done late
71008184 | TLG | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-10 | Done late
71008188 | BLF | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-07 | Done
71008188 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008188 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-23 | Done late
71008188 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-14 | Done late
71008188 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71008188 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-27 | Done
71008188 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-28 | Done
71008188 | BLF | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008188 | BLF | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008188 | BLF | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-08 | Done
71008188 | BLF | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-09 | Done
71008193 | SLM | 1 | Yarn booking | Factory | 2026-05-09 |  | 2026-05-11 | Done late
71008193 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-19 |  | 2026-05-17 | Done
71008193 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-24 | Done
71008193 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71008193 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-22 | Done
71008193 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-28 |  | 2026-06-28 | Done
71008193 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-01 |  | 2026-07-01 | Done
71008193 | SLM | 8 | Knitting start | Factory | 2026-07-02 |  | 2026-07-02 | Done
71008193 | SLM | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-07 | Done
71008193 | SLM | 10 | Final inspection | Karbar QA | 2026-08-11 |  | 2026-08-18 | Done late
71008193 | SLM | 11 | Ex-factory | Factory | 2026-08-12 |  | 2026-08-19 | Done late
71008200 | CPL | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-02 | Done
71008200 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71008200 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008200 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008200 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-19 | Done
71008200 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-26 | Done late
71008200 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-27 | Done
71008200 | CPL | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71008200 | CPL | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-04 | Done
71008200 | CPL | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71008200 | CPL | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-08 | Done
71008203 | IRB | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-09 | Done
71008203 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008203 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008203 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008203 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008203 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-08-01 | Done late
71008203 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71008203 | IRB | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008203 | IRB | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008203 | IRB | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008203 | IRB | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008208 | OKH | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-09 | Done
71008208 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-23 | Done late
71008208 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71008208 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008208 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71008208 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-01 |  | 2026-08-01 | Done
71008208 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-08-04 |  | 2026-08-04 | Done
71008208 | OKH | 8 | Knitting start | Factory | 2026-08-06 |  | 2026-08-08 | Done late
71008208 | OKH | 9 | Linking start | Factory | 2026-08-12 |  | 2026-08-11 | Done
71008208 | OKH | 10 | Final inspection | Karbar QA | 2026-09-14 |  | 2026-09-12 | Done
71008208 | OKH | 11 | Ex-factory | Factory | 2026-09-15 |  | 2026-09-13 | Done
71008217 | HMR | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-14 | Done
71008217 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-25 | Done late
71008217 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-07-01 | Done late
71008217 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008217 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008217 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-04 | Done late
71008217 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008217 | HMR | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-09 | Done late
71008217 | HMR | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-12 | Done
71008217 | HMR | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71008217 | HMR | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-17 | Done
71008223 | SND | 1 | Yarn booking | Factory | 2026-05-10 |  | 2026-05-10 | Done
71008223 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-20 |  | 2026-05-21 | Done late
71008223 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-23 | Done
71008223 | SND | 4 | Size set approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-16 | Done late
71008223 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-24 | Done
71008223 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-06-29 |  | 2026-06-30 | Done late
71008223 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-02 |  | 2026-07-02 | Done
71008223 | SND | 8 | Knitting start | Factory | 2026-07-04 |  | 2026-07-04 | Done
71008223 | SND | 9 | Linking start | Factory | 2026-07-09 |  | 2026-07-09 | Done
71008223 | SND | 10 | Final inspection | Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71008223 | SND | 11 | Ex-factory | Factory | 2026-08-13 |  | 2026-08-13 | Done
71008227 | OKH | 1 | Yarn booking | Factory | 2026-05-13 |  | 2026-05-14 | Done late
71008227 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-23 |  | 2026-05-23 | Done
71008227 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71008227 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-15 | Done
71008227 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71008227 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71008227 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-07-05 |  | 2026-07-05 | Done
71008227 | OKH | 8 | Knitting start | Factory | 2026-07-07 |  | 2026-07-08 | Done late
71008227 | OKH | 9 | Linking start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71008227 | OKH | 10 | Final inspection | Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71008227 | OKH | 11 | Ex-factory | Factory | 2026-08-16 |  | 2026-08-16 | Done
71008232 | FNS | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-14 | Done
71008232 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-25 |  | 2026-05-25 | Done
71008232 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-05-30 |  | 2026-05-30 | Done
71008232 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-20 | Done late
71008232 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008232 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-04 |  | 2026-07-04 | Done
71008232 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-07-07 |  | 2026-07-05 | Done
71008232 | FNS | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-11 | Done late
71008232 | FNS | 9 | Linking start | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71008232 | FNS | 10 | Final inspection | Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71008232 | FNS | 11 | Ex-factory | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008239 | SVP | 1 | Yarn booking | Factory | 2026-05-19 |  | 2026-05-19 | Done
71008239 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-26 | Done
71008239 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-01 | Done
71008239 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-25 | Done late
71008239 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008239 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-08 |  | 2026-07-09 | Done late
71008239 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-11 |  | 2026-07-13 | Done late
71008239 | SVP | 8 | Knitting start | Factory | 2026-07-13 |  | 2026-07-13 | Done
71008239 | SVP | 9 | Linking start | Factory | 2026-07-19 |  | 2026-07-18 | Done
71008239 | SVP | 10 | Final inspection | Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71008239 | SVP | 11 | Ex-factory | Factory | 2026-08-22 |  | 2026-08-22 | Done
71008246 | RVS | 1 | Yarn booking | Factory | 2026-06-02 |  | 2026-06-02 | Done
71008246 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71008246 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008246 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-07 | Done
71008246 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-18 | Done late
71008246 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-22 |  | 2026-07-25 | Done late
71008246 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-07-25 |  | 2026-07-23 | Done
71008246 | RVS | 8 | Knitting start | Factory | 2026-07-27 |  | 2026-07-28 | Done late
71008246 | RVS | 9 | Linking start | Factory | 2026-08-02 |  | 2026-08-01 | Done
71008246 | RVS | 10 | Final inspection | Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008246 | RVS | 11 | Ex-factory | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008253 | SVP | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-31 | Done
71008253 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008253 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71008253 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-07 | Done late
71008253 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008253 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-20 | Done
71008253 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-23 | Done
71008253 | SVP | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-25 | Done
71008253 | SVP | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008253 | SVP | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-08-31 | Done
71008253 | SVP | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-01 | Done
71008260 | SVP | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008260 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-14 | Done
71008260 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008260 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008260 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71008260 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-26 | Done late
71008260 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-29 | Done late
71008260 | SVP | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008260 | SVP | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-03 | Done
71008260 | SVP | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-05 | Done
71008260 | SVP | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-06 | Done
71008263 | SVP | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-23 | Done
71008263 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-02 | Done
71008263 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-06 | Done
71008263 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71008263 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-09 | Done late
71008263 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-14 | Done late
71008263 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-15 | Done
71008263 | SVP | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71008263 | SVP | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008263 | SVP | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-23 | Done
71008263 | SVP | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-24 | Done
71008271 | IRB | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-11 | Done
71008271 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-24 | Done
71008271 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008271 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-16 | Done
71008271 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-28 | Done
71008271 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-03 | Done
71008271 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008271 | IRB | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008271 | IRB | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008271 | IRB | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-19 | Done late
71008271 | IRB | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-20 | Done late
71008274 | LTF | 1 | Yarn booking | Factory | 2026-05-27 |  | 2026-05-26 | Done
71008274 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-08 | Done late
71008274 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71008274 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71008274 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71008274 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-16 |  | 2026-07-19 | Done late
71008274 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-07-19 |  | 2026-07-18 | Done
71008274 | LTF | 8 | Knitting start | Factory | 2026-07-21 |  | 2026-07-22 | Done late
71008274 | LTF | 9 | Linking start | Factory | 2026-07-27 |  | 2026-07-27 | Done
71008274 | LTF | 10 | Final inspection | Karbar QA | 2026-08-29 |  | 2026-08-26 | Done
71008274 | LTF | 11 | Ex-factory | Factory | 2026-08-30 |  | 2026-08-27 | Done
71008283 | IRB | 1 | Yarn booking | Factory | 2026-05-30 |  | 2026-05-28 | Done
71008283 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-08 | Done
71008283 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008283 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008283 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-13 | Done
71008283 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-19 |  | 2026-07-19 | Done
71008283 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-22 |  | 2026-07-22 | Done
71008283 | IRB | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-25 | Done late
71008283 | IRB | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71008283 | IRB | 10 | Final inspection | Karbar QA | 2026-09-01 |  | 2026-09-05 | Done late
71008283 | IRB | 11 | Ex-factory | Factory | 2026-09-02 |  | 2026-09-06 | Done late
71008289 | CLB | 1 | Yarn booking | Factory | 2026-06-06 |  | 2026-06-08 | Done late
71008289 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-14 | Done
71008289 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-22 | Done late
71008289 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-09 | Done
71008289 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-23 | Done late
71008289 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-26 |  | 2026-07-25 | Done
71008289 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71008289 | CLB | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71008289 | CLB | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-04 | Done
71008289 | CLB | 10 | Final inspection | Karbar QA | 2026-09-08 |  | 2026-09-08 | Done
71008289 | CLB | 11 | Ex-factory | Factory | 2026-09-09 |  | 2026-09-09 | Done
71008297 | HMR | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-09 | Done
71008297 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-21 | Done
71008297 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71008297 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-14 | Done
71008297 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71008297 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-01 |  | 2026-07-30 | Done
71008297 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-04 |  | 2026-08-03 | Done
71008297 | HMR | 8 | Knitting start | Factory | 2026-08-06 |  | 2026-08-08 | Done late
71008297 | HMR | 9 | Linking start | Factory | 2026-08-12 |  | 2026-08-11 | Done
71008297 | HMR | 10 | Final inspection | Karbar QA | 2026-09-14 |  | 2026-09-16 | Done late
71008297 | HMR | 11 | Ex-factory | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71008300 | IRB | 1 | Yarn booking | Factory | 2026-05-24 |  | 2026-05-23 | Done
71008300 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-03 | Done
71008300 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-10 | Done late
71008300 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008300 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008300 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-13 |  | 2026-07-13 | Done
71008300 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-16 |  | 2026-07-15 | Done
71008300 | IRB | 8 | Knitting start | Factory | 2026-07-18 |  | 2026-07-18 | Done
71008300 | IRB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71008300 | IRB | 10 | Final inspection | Karbar QA | 2026-08-26 |  | 2026-09-02 | Done late
71008300 | IRB | 11 | Ex-factory | Factory | 2026-08-27 |  | 2026-09-03 | Done late
71008309 | SVP | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008309 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71008309 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008309 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-08 | Done
71008309 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-22 | Done late
71008309 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-23 | Done
71008309 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-28 | Done
71008309 | SVP | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71008309 | SVP | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-04 | Done
71008309 | SVP | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-08 | Done late
71008309 | SVP | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-09 | Done late
71008316 | RSG | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-02 | Done
71008316 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-13 | Done
71008316 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008316 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008316 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-22 | Done late
71008316 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-25 |  | 2026-07-25 | Done
71008316 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-07-28 |  | 2026-07-30 | Done late
71008316 | RSG | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008316 | RSG | 9 | Linking start | Factory | 2026-08-05 |  | 2026-08-03 | Done
71008316 | RSG | 10 | Final inspection | Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71008316 | RSG | 11 | Ex-factory | Factory | 2026-09-08 |  | 2026-09-08 | Done
71008322 | CLB | 1 | Yarn booking | Factory | 2026-05-14 |  | 2026-05-12 | Done
71008322 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-24 |  | 2026-05-21 | Done
71008322 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-05-28 |  | 2026-05-28 | Done
71008322 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008322 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008322 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-02 |  | 2026-07-02 | Done
71008322 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-07-06 |  | 2026-07-05 | Done
71008322 | CLB | 8 | Knitting start | Factory | 2026-07-08 |  | 2026-07-08 | Done
71008322 | CLB | 9 | Linking start | Factory | 2026-07-14 |  | 2026-07-13 | Done
71008322 | CLB | 10 | Final inspection | Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008322 | CLB | 11 | Ex-factory | Factory | 2026-08-17 |  | 2026-08-17 | Done
71008326 | HMR | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71008326 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71008326 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-08 | Done late
71008326 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-27 | Done late
71008326 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-08 | Done late
71008326 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-11 |  | 2026-07-14 | Done late
71008326 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-07-14 |  | 2026-07-15 | Done late
71008326 | HMR | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71008326 | HMR | 9 | Linking start | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71008326 | HMR | 10 | Final inspection | Karbar QA | 2026-08-24 |  | 2026-08-24 | Done
71008326 | HMR | 11 | Ex-factory | Factory | 2026-08-25 |  | 2026-08-25 | Done
71008329 | AMB | 1 | Yarn booking | Factory | 2026-05-24 |  | 2026-05-25 | Done late
71008329 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-03 |  | 2026-06-04 | Done late
71008329 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-09 | Done late
71008329 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008329 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008329 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-13 |  | 2026-07-14 | Done late
71008329 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-07-16 |  | 2026-07-15 | Done
71008329 | AMB | 8 | Knitting start | Factory | 2026-07-18 |  | 2026-07-18 | Done
71008329 | AMB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008329 | AMB | 10 | Final inspection | Karbar QA | 2026-08-26 |  | 2026-08-26 | Done
71008329 | AMB | 11 | Ex-factory | Factory | 2026-08-27 |  | 2026-08-27 | Done
71008332 | CPL | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-07 | Done
71008332 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008332 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71008332 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-12 | Done
71008332 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-21 | Done
71008332 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-27 | Done
71008332 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-30 | Done
71008332 | CPL | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008332 | CPL | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008332 | CPL | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008332 | CPL | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008337 | RVS | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-10 | Done
71008337 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-20 | Done
71008337 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008337 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-14 | Done
71008337 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-23 | Done
71008337 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71008337 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-02 | Done
71008337 | RVS | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008337 | RVS | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008337 | RVS | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008337 | RVS | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008346 | BLF | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71008346 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71008346 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-06 | Done
71008346 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-27 | Done late
71008346 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-08 | Done late
71008346 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-11 |  | 2026-07-09 | Done
71008346 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-14 |  | 2026-07-14 | Done
71008346 | BLF | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71008346 | BLF | 9 | Linking start | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71008346 | BLF | 10 | Final inspection | Karbar QA | 2026-08-24 |  | 2026-08-27 | Done late
71008346 | BLF | 11 | Ex-factory | Factory | 2026-08-25 |  | 2026-08-29 | Done late
71008353 | IRB | 1 | Yarn booking | Factory | 2026-05-23 |  | 2026-05-25 | Done late
71008353 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-02 |  | 2026-06-03 | Done late
71008353 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-07 |  | 2026-06-08 | Done late
71008353 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71008353 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-06 | Done
71008353 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-12 |  | 2026-07-13 | Done late
71008353 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-15 |  | 2026-07-14 | Done
71008353 | IRB | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71008353 | IRB | 9 | Linking start | Factory | 2026-07-23 |  | 2026-07-21 | Done
71008353 | IRB | 10 | Final inspection | Karbar QA | 2026-08-25 |  | 2026-08-25 | Done
71008353 | IRB | 11 | Ex-factory | Factory | 2026-08-26 |  | 2026-08-26 | Done
71008359 | TLG | 1 | Yarn booking | Factory | 2026-05-26 |  | 2026-05-26 | Done
71008359 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-06 | Done late
71008359 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008359 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-28 | Done
71008359 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008359 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-15 |  | 2026-07-14 | Done
71008359 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-18 |  | 2026-07-18 | Done
71008359 | TLG | 8 | Knitting start | Factory | 2026-07-20 |  | 2026-07-21 | Done late
71008359 | TLG | 9 | Linking start | Factory | 2026-07-26 |  | 2026-07-26 | Done
71008359 | TLG | 10 | Final inspection | Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71008359 | TLG | 11 | Ex-factory | Factory | 2026-08-29 |  | 2026-08-29 | Done
71008367 | SLM | 1 | Yarn booking | Factory | 2026-05-30 |  | 2026-05-28 | Done
71008367 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-07 | Done
71008367 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008367 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-02 | Done
71008367 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-14 | Done
71008367 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-19 |  | 2026-07-21 | Done late
71008367 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-22 |  | 2026-07-23 | Done late
71008367 | SLM | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008367 | SLM | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-27 | Done
71008367 | SLM | 10 | Final inspection | Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008367 | SLM | 11 | Ex-factory | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008371 | RSG | 1 | Yarn booking | Factory | 2026-06-02 |  | 2026-06-02 | Done
71008371 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-13 | Done late
71008371 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-18 | Done late
71008371 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-06 | Done
71008371 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008371 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-22 |  | 2026-07-23 | Done late
71008371 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-07-25 |  | 2026-07-27 | Done late
71008371 | RSG | 8 | Knitting start | Factory | 2026-07-27 |  | 2026-07-28 | Done late
71008371 | RSG | 9 | Linking start | Factory | 2026-08-02 |  | 2026-08-01 | Done
71008371 | RSG | 10 | Final inspection | Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008371 | RSG | 11 | Ex-factory | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008377 | IRB | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-03 | Done
71008377 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-11 | Done
71008377 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008377 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008377 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008377 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-23 | Done
71008377 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-29 | Done late
71008377 | IRB | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-29 | Done
71008377 | IRB | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-02 | Done
71008377 | IRB | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71008377 | IRB | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-07 | Done
71008383 | AMB | 1 | Yarn booking | Factory | 2026-06-23 |  | 2026-06-23 | Done
71008383 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-02 |  | 2026-06-30 | Done
71008383 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71008383 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-30 | Done late
71008383 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-08 | Done late
71008383 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-12 |  | 2026-08-10 | Done
71008383 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71008383 | AMB | 8 | Knitting start | Factory | 2026-08-17 |  | 2026-08-18 | Done late
71008383 | AMB | 9 | Linking start | Factory | 2026-08-23 |  | 2026-08-22 | Done
71008383 | AMB | 10 | Final inspection | Karbar QA | 2026-09-24 |  | 2026-09-24 | Done
71008383 | AMB | 11 | Ex-factory | Factory | 2026-09-26 |  | 2026-09-26 | Done
71008387 | CPL | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71008387 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008387 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-08 | Done
71008387 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71008387 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71008387 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008387 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008387 | CPL | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008387 | CPL | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-22 | Done
71008387 | CPL | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-24 | Done
71008387 | CPL | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-26 | Done
71008394 | TLG | 1 | Yarn booking | Factory | 2026-05-16 |  | 2026-05-18 | Done late
71008394 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-26 |  | 2026-05-26 | Done
71008394 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-28 | Done
71008394 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-18 | Done
71008394 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-06-30 |  | 2026-07-01 | Done late
71008394 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-05 |  | 2026-07-07 | Done late
71008394 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-08 |  | 2026-07-07 | Done
71008394 | TLG | 8 | Knitting start | Factory | 2026-07-09 |  | 2026-07-11 | Done late
71008394 | TLG | 9 | Linking start | Factory | 2026-07-16 |  | 2026-07-16 | Done
71008394 | TLG | 10 | Final inspection | Karbar QA | 2026-08-18 |  | 2026-08-18 | Done
71008394 | TLG | 11 | Ex-factory | Factory | 2026-08-19 |  | 2026-08-19 | Done
71008403 | GRL | 1 | Yarn booking | Factory | 2026-05-28 |  | 2026-05-28 | Done
71008403 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-07 | Done
71008403 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-11 | Done
71008403 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-02 |  | 2026-06-30 | Done
71008403 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-14 | Done late
71008403 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-18 |  | 2026-07-16 | Done
71008403 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-21 |  | 2026-07-23 | Done late
71008403 | GRL | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008403 | GRL | 9 | Linking start | Factory | 2026-07-29 |  | 2026-07-27 | Done
71008403 | GRL | 10 | Final inspection | Karbar QA | 2026-08-31 |  | 2026-09-02 | Done late
71008403 | GRL | 11 | Ex-factory | Factory | 2026-09-01 |  | 2026-09-03 | Done late
71008412 | AMB | 1 | Yarn booking | Factory | 2026-05-28 |  | 2026-05-28 | Done
71008412 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-08 |  | 2026-06-09 | Done late
71008412 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-11 | Done
71008412 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008412 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008412 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-18 |  | 2026-07-18 | Done
71008412 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-07-21 |  | 2026-07-23 | Done late
71008412 | AMB | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008412 | AMB | 9 | Linking start | Factory | 2026-07-29 |  | 2026-07-28 | Done
71008412 | AMB | 10 | Final inspection | Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71008412 | AMB | 11 | Ex-factory | Factory | 2026-09-01 |  | 2026-09-01 | Done
71008421 | MDW | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-10 | Done
71008421 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-20 | Done
71008421 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008421 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-15 | Done
71008421 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71008421 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71008421 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-03 |  | 2026-08-03 | Done
71008421 | MDW | 8 | Knitting start | Factory | 2026-08-05 |  | 2026-08-05 | Done
71008421 | MDW | 9 | Linking start | Factory | 2026-08-11 |  | 2026-08-09 | Done
71008421 | MDW | 10 | Final inspection | Karbar QA | 2026-09-13 |  | 2026-09-15 | Done late
71008421 | MDW | 11 | Ex-factory | Factory | 2026-09-14 |  | 2026-09-16 | Done late
71008430 | GRL | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71008430 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-05 | Done late
71008430 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008430 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008430 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71008430 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008430 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-17 | Done late
71008430 | GRL | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-19 | Done late
71008430 | GRL | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-23 | Done
71008430 | GRL | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-23 | Done
71008430 | GRL | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-24 | Done
71008436 | KST | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-25 | Done late
71008436 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008436 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-08 | Done
71008436 | KST | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71008436 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-09 | Done late
71008436 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-15 | Done late
71008436 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008436 | KST | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008436 | KST | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-22 | Done
71008436 | KST | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-24 | Done
71008436 | KST | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-26 | Done
71008439 | GRL | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-30 | Done
71008439 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-09 | Done
71008439 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-17 | Done late
71008439 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71008439 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008439 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-19 | Done
71008439 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-23 | Done
71008439 | GRL | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-26 | Done late
71008439 | GRL | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-29 | Done
71008439 | GRL | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-09-14 | Done late
71008439 | GRL | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-15 | Done late
71008448 | GRL | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71008448 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-05-31 |  | 2026-05-28 | Done
71008448 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-02 | Done
71008448 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-27 | Done late
71008448 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71008448 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-09 |  | 2026-07-08 | Done
71008448 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-13 |  | 2026-07-12 | Done
71008448 | GRL | 8 | Knitting start | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71008448 | GRL | 9 | Linking start | Factory | 2026-07-21 |  | 2026-07-21 | Done
71008448 | GRL | 10 | Final inspection | Karbar QA | 2026-08-23 |  | 2026-08-25 | Done late
71008448 | GRL | 11 | Ex-factory | Factory | 2026-08-24 |  | 2026-08-26 | Done late
71008454 | SND | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-31 | Done
71008454 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008454 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-13 | Done
71008454 | SND | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-06 | Done late
71008454 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008454 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-23 | Done late
71008454 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-21 | Done
71008454 | SND | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-25 | Done
71008454 | SND | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71008454 | SND | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-09-07 | Done late
71008454 | SND | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-08 | Done late
71008459 | RSG | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-18 | Done
71008459 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008459 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-02 | Done
71008459 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008459 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71008459 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-08 |  | 2026-08-08 | Done
71008459 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-08-11 |  | 2026-08-12 | Done late
71008459 | RSG | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71008459 | RSG | 9 | Linking start | Factory | 2026-08-19 |  | 2026-08-17 | Done
71008459 | RSG | 10 | Final inspection | Karbar QA | 2026-09-21 |  | 2026-09-21 | Done
71008459 | RSG | 11 | Ex-factory | Factory | 2026-09-22 |  | 2026-09-22 | Done
71008467 | TLG | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-13 | Done
71008467 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-24 | Done
71008467 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-07-01 | Done late
71008467 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-18 | Done
71008467 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71008467 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-03 | Done
71008467 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-04 | Done
71008467 | TLG | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008467 | TLG | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008467 | TLG | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71008467 | TLG | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-17 | Done
71008471 | BLF | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-20 | Done late
71008471 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008471 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008471 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008471 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-01 | Done
71008471 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-06 | Done
71008471 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-10 |  | 2026-08-10 | Done
71008471 | BLF | 8 | Knitting start | Factory | 2026-08-12 |  | 2026-08-12 | Done
71008471 | BLF | 9 | Linking start | Factory | 2026-08-18 |  | 2026-08-16 | Done
71008471 | BLF | 10 | Final inspection | Karbar QA | 2026-09-20 |  | 2026-09-16 | Done
71008471 | BLF | 11 | Ex-factory | Factory | 2026-09-21 |  | 2026-09-17 | Done
71008478 | SND | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-21 | Done
71008478 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-29 | Done
71008478 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-08 | Done late
71008478 | SND | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71008478 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71008478 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-10 | Done
71008478 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-15 | Done late
71008478 | SND | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-16 | Done late
71008478 | SND | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-19 | Done
71008478 | SND | 10 | Final inspection | Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71008478 | SND | 11 | Ex-factory | Factory | 2026-09-24 |  | 2026-09-24 | Done
71008486 | WSM | 1 | Yarn booking | Factory | 2026-05-26 |  | 2026-05-26 | Done
71008486 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-06 | Done late
71008486 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-09 | Done
71008486 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-30 | Done
71008486 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008486 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-15 |  | 2026-07-14 | Done
71008486 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-07-18 |  | 2026-07-18 | Done
71008486 | WSM | 8 | Knitting start | Factory | 2026-07-20 |  | 2026-07-21 | Done late
71008486 | WSM | 9 | Linking start | Factory | 2026-07-26 |  | 2026-07-26 | Done
71008486 | WSM | 10 | Final inspection | Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71008486 | WSM | 11 | Ex-factory | Factory | 2026-08-29 |  | 2026-08-29 | Done
71008489 | IRB | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-31 | Done
71008489 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008489 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-13 | Done
71008489 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-04 | Done
71008489 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-14 | Done
71008489 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-23 | Done late
71008489 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-22 | Done
71008489 | IRB | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-25 | Done
71008489 | IRB | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71008489 | IRB | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-09-02 | Done
71008489 | IRB | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008495 | CPL | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-28 | Done
71008495 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008495 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-17 | Done late
71008495 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71008495 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71008495 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-23 | Done late
71008495 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-21 | Done
71008495 | CPL | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-25 | Done
71008495 | CPL | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-28 | Done
71008495 | CPL | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-09-02 | Done
71008495 | CPL | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008504 | GRL | 1 | Yarn booking | Factory | 2026-05-31 |  | 2026-05-31 | Done
71008504 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-11 | Done late
71008504 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-15 |  | 2026-06-15 | Done
71008504 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-06 | Done late
71008504 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008504 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-20 |  | 2026-07-20 | Done
71008504 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-07-23 |  | 2026-07-23 | Done
71008504 | GRL | 8 | Knitting start | Factory | 2026-07-25 |  | 2026-07-26 | Done late
71008504 | GRL | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008504 | GRL | 10 | Final inspection | Karbar QA | 2026-09-02 |  | 2026-08-30 | Done
71008504 | GRL | 11 | Ex-factory | Factory | 2026-09-03 |  | 2026-08-31 | Done
71008509 | TLG | 1 | Yarn booking | Factory | 2026-05-21 |  | 2026-05-21 | Done
71008509 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-01 |  | 2026-06-01 | Done
71008509 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-04 | Done
71008509 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71008509 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71008509 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-11 |  | 2026-07-11 | Done
71008509 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-14 |  | 2026-07-16 | Done late
71008509 | TLG | 8 | Knitting start | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71008509 | TLG | 9 | Linking start | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71008509 | TLG | 10 | Final inspection | Karbar QA | 2026-08-24 |  | 2026-08-24 | Done
71008509 | TLG | 11 | Ex-factory | Factory | 2026-08-25 |  | 2026-08-25 | Done
71008517 | WSM | 1 | Yarn booking | Factory | 2026-06-06 |  | 2026-06-04 | Done
71008517 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-16 | Done
71008517 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-23 | Done late
71008517 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-12 | Done late
71008517 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-20 | Done
71008517 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-26 |  | 2026-07-25 | Done
71008517 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-07-29 |  | 2026-07-29 | Done
71008517 | WSM | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-07-30 | Done
71008517 | WSM | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-03 | Done
71008517 | WSM | 10 | Final inspection | Karbar QA | 2026-09-08 |  | 2026-09-07 | Done
71008517 | WSM | 11 | Ex-factory | Factory | 2026-09-09 |  | 2026-09-08 | Done
71008520 | LTF | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-11 | Done
71008520 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-23 | Done
71008520 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008520 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-20 | Done late
71008520 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008520 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-05 | Done late
71008520 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008520 | LTF | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008520 | LTF | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008520 | LTF | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71008520 | LTF | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-17 | Done
71008523 | MDW | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-24 | Done
71008523 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71008523 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008523 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71008523 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71008523 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008523 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71008523 | MDW | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-19 | Done
71008523 | MDW | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-23 | Done
71008523 | MDW | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71008523 | MDW | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-28 | Done
71008526 | GRL | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-07-01 | Done late
71008526 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008526 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71008526 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71008526 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-12 | Done
71008526 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-18 | Done
71008526 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71008526 | GRL | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-25 | Done late
71008526 | GRL | 9 | Linking start | Factory | 2026-08-30 |  | 2026-08-29 | Done
71008526 | GRL | 10 | Final inspection | Karbar QA | 2026-10-01 |  | 2026-10-04 | Done late
71008526 | GRL | 11 | Ex-factory | Factory | 2026-10-03 |  | 2026-10-05 | Done late
71008531 | LTF | 1 | Yarn booking | Factory | 2026-05-26 |  | 2026-05-26 | Done
71008531 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71008531 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-08 | Done
71008531 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-30 | Done
71008531 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008531 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-15 |  | 2026-07-15 | Done
71008531 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-07-18 |  | 2026-07-18 | Done
71008531 | LTF | 8 | Knitting start | Factory | 2026-07-20 |  | 2026-07-21 | Done late
71008531 | LTF | 9 | Linking start | Factory | 2026-07-26 |  | 2026-07-26 | Done
71008531 | LTF | 10 | Final inspection | Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71008531 | LTF | 11 | Ex-factory | Factory | 2026-08-29 |  | 2026-08-29 | Done
71008536 | SLM | 1 | Yarn booking | Factory | 2026-06-03 |  | 2026-06-03 | Done
71008536 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-13 |  | 2026-06-13 | Done
71008536 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-17 | Done
71008536 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008536 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-20 | Done late
71008536 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-23 | Done
71008536 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-07-26 |  | 2026-07-27 | Done late
71008536 | SLM | 8 | Knitting start | Factory | 2026-07-28 |  | 2026-07-28 | Done
71008536 | SLM | 9 | Linking start | Factory | 2026-08-03 |  | 2026-08-01 | Done
71008536 | SLM | 10 | Final inspection | Karbar QA | 2026-09-05 |  | 2026-09-05 | Done
71008536 | SLM | 11 | Ex-factory | Factory | 2026-09-06 |  | 2026-09-06 | Done
71008545 | SVP | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-07 | Done
71008545 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-16 | Done
71008545 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-23 | Done late
71008545 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-12 | Done
71008545 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-21 | Done
71008545 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-30 | Done late
71008545 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-30 | Done
71008545 | SVP | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008545 | SVP | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008545 | SVP | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008545 | SVP | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008552 | GRL | 1 | Yarn booking | Factory | 2026-06-13 |  | 2026-06-11 | Done
71008552 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-23 |  | 2026-06-23 | Done
71008552 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-28 | Done
71008552 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-19 | Done late
71008552 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-27 | Done
71008552 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-02 |  | 2026-08-02 | Done
71008552 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-05 |  | 2026-08-04 | Done
71008552 | GRL | 8 | Knitting start | Factory | 2026-08-06 |  | 2026-08-06 | Done
71008552 | GRL | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-10 | Done
71008552 | GRL | 10 | Final inspection | Karbar QA | 2026-09-15 |  | 2026-09-27 | Done late
71008552 | GRL | 11 | Ex-factory | Factory | 2026-09-16 |  | 2026-09-28 | Done late
71008558 | TLG | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-14 | Done
71008558 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-24 | Done
71008558 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-07-01 | Done late
71008558 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-20 | Done late
71008558 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008558 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-04 | Done late
71008558 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008558 | TLG | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008558 | TLG | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008558 | TLG | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-13 | Done
71008558 | TLG | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-14 | Done
71008566 | BRW | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-25 | Done
71008566 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71008566 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008566 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71008566 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71008566 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-17 | Done
71008566 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71008566 | BRW | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-22 | Done
71008566 | BRW | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-25 | Done
71008566 | BRW | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71008566 | BRW | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-10-01 | Done
71008572 | RVS | 1 | Yarn booking | Factory | 2026-05-26 |  | 2026-05-24 | Done
71008572 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-04 |  | 2026-06-04 | Done
71008572 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-06-10 |  | 2026-06-10 | Done
71008572 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-06-30 |  | 2026-07-02 | Done late
71008572 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008572 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-15 |  | 2026-07-15 | Done
71008572 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-07-18 |  | 2026-07-20 | Done late
71008572 | RVS | 8 | Knitting start | Factory | 2026-07-20 |  | 2026-07-21 | Done late
71008572 | RVS | 9 | Linking start | Factory | 2026-07-26 |  | 2026-07-26 | Done
71008572 | RVS | 10 | Final inspection | Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71008572 | RVS | 11 | Ex-factory | Factory | 2026-08-29 |  | 2026-08-29 | Done
71008578 | CPL | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-11 | Done
71008578 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-20 | Done
71008578 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-24 | Done
71008578 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008578 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-27 | Done late
71008578 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71008578 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-03 |  | 2026-08-03 | Done
71008578 | CPL | 8 | Knitting start | Factory | 2026-08-05 |  | 2026-08-05 | Done
71008578 | CPL | 9 | Linking start | Factory | 2026-08-11 |  | 2026-08-09 | Done
71008578 | CPL | 10 | Final inspection | Karbar QA | 2026-09-13 |  | 2026-09-10 | Done
71008578 | CPL | 11 | Ex-factory | Factory | 2026-09-14 |  | 2026-09-12 | Done
71008583 | CPL | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-11 | Done
71008583 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71008583 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71008583 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008583 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71008583 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-01 |  | 2026-08-03 | Done late
71008583 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-04 |  | 2026-08-04 | Done
71008583 | CPL | 8 | Knitting start | Factory | 2026-08-06 |  | 2026-08-06 | Done
71008583 | CPL | 9 | Linking start | Factory | 2026-08-12 |  | 2026-08-10 | Done
71008583 | CPL | 10 | Final inspection | Karbar QA | 2026-09-14 |  | 2026-09-10 | Done
71008583 | CPL | 11 | Ex-factory | Factory | 2026-09-15 |  | 2026-09-12 | Done
71008586 | BRW | 1 | Yarn booking | Factory | 2026-06-27 |  | 2026-06-28 | Done late
71008586 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-08 | Done late
71008586 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-12 | Done
71008586 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71008586 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-12 | Done late
71008586 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-16 |  | 2026-08-13 | Done
71008586 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71008586 | BRW | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71008586 | BRW | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-25 | Done
71008586 | BRW | 10 | Final inspection | Karbar QA | 2026-09-29 |  | 2026-09-29 | Done
71008586 | BRW | 11 | Ex-factory | Factory | 2026-09-30 |  | 2026-09-30 | Done
71008592 | CPL | 1 | Yarn booking | Factory | 2026-05-27 |  | 2026-05-28 | Done late
71008592 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-06 |  | 2026-06-04 | Done
71008592 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-09 | Done
71008592 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-01 |  | 2026-06-30 | Done
71008592 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-09 | Done
71008592 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-16 |  | 2026-07-19 | Done late
71008592 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-07-19 |  | 2026-07-19 | Done
71008592 | CPL | 8 | Knitting start | Factory | 2026-07-21 |  | 2026-07-22 | Done late
71008592 | CPL | 9 | Linking start | Factory | 2026-07-27 |  | 2026-07-27 | Done
71008592 | CPL | 10 | Final inspection | Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71008592 | CPL | 11 | Ex-factory | Factory | 2026-08-30 |  | 2026-08-30 | Done
71008599 | OKH | 1 | Yarn booking | Factory | 2026-06-02 |  | 2026-06-01 | Done
71008599 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71008599 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-16 | Done
71008599 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-07 | Done
71008599 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008599 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-22 |  | 2026-07-23 | Done late
71008599 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-07-25 |  | 2026-07-23 | Done
71008599 | OKH | 8 | Knitting start | Factory | 2026-07-27 |  | 2026-07-28 | Done late
71008599 | OKH | 9 | Linking start | Factory | 2026-08-02 |  | 2026-08-01 | Done
71008599 | OKH | 10 | Final inspection | Karbar QA | 2026-09-03 |  | 2026-09-02 | Done
71008599 | OKH | 11 | Ex-factory | Factory | 2026-09-05 |  | 2026-09-03 | Done
71008606 | SVP | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-06 | Done late
71008606 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008606 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-17 | Done
71008606 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008606 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-21 | Done late
71008606 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-26 | Done late
71008606 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-25 | Done
71008606 | SVP | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71008606 | SVP | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-03 | Done
71008606 | SVP | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71008606 | SVP | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-07 | Done
71008610 | BRW | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-07 | Done
71008610 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-18 | Done late
71008610 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-24 | Done late
71008610 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-13 | Done late
71008610 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008610 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-29 | Done late
71008610 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-30 | Done
71008610 | BRW | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008610 | BRW | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008610 | BRW | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008610 | BRW | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008613 | BRW | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71008613 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71008613 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008613 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71008613 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71008613 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008613 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-19 | Done late
71008613 | BRW | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-19 | Done
71008613 | BRW | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-23 | Done
71008613 | BRW | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71008613 | BRW | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-28 | Done
71008617 | IRB | 1 | Yarn booking | Factory | 2026-07-04 |  | 2026-07-04 | Done
71008617 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-16 | Done late
71008617 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-21 | Done late
71008617 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-10 | Done late
71008617 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-18 | Done
71008617 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-23 |  | 2026-08-23 | Done
71008617 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-26 |  | 2026-08-26 | Done
71008617 | IRB | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-29 | Done late
71008617 | IRB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-01 | Done
71008617 | IRB | 10 | Final inspection | Karbar QA | 2026-10-06 |  | 2026-10-08 | Done late
71008617 | IRB | 11 | Ex-factory | Factory | 2026-10-07 |  | 2026-10-10 | Done late
71008621 | IRB | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-04 | Done
71008621 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008621 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-18 | Done
71008621 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008621 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008621 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-23 | Done
71008621 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-27 | Done
71008621 | IRB | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71008621 | IRB | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-03 | Done
71008621 | IRB | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71008621 | IRB | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-07 | Done
71008630 | CPL | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-13 | Done
71008630 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-24 | Done
71008630 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008630 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008630 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008630 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-03 | Done
71008630 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008630 | CPL | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008630 | CPL | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008630 | CPL | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71008630 | CPL | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-17 | Done
71008638 | LTF | 1 | Yarn booking | Factory | 2026-07-04 |  | 2026-07-02 | Done
71008638 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-15 | Done late
71008638 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008638 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71008638 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-19 | Done late
71008638 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-23 |  | 2026-08-23 | Done
71008638 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-26 |  | 2026-08-27 | Done late
71008638 | LTF | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-29 | Done late
71008638 | LTF | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-01 | Done
71008638 | LTF | 10 | Final inspection | Karbar QA | 2026-10-06 |  | 2026-10-06 | Done
71008638 | LTF | 11 | Ex-factory | Factory | 2026-10-07 |  | 2026-10-07 | Done
71008647 | WSM | 1 | Yarn booking | Factory | 2026-05-30 |  | 2026-05-30 | Done
71008647 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-09 |  | 2026-06-11 | Done late
71008647 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-15 | Done late
71008647 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008647 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-13 | Done
71008647 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-19 |  | 2026-07-16 | Done
71008647 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-07-22 |  | 2026-07-22 | Done
71008647 | WSM | 8 | Knitting start | Factory | 2026-07-23 |  | 2026-07-23 | Done
71008647 | WSM | 9 | Linking start | Factory | 2026-07-30 |  | 2026-07-27 | Done
71008647 | WSM | 10 | Final inspection | Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008647 | WSM | 11 | Ex-factory | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008652 | HMR | 1 | Yarn booking | Factory | 2026-06-02 |  | 2026-06-02 | Done
71008652 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-10 | Done
71008652 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008652 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-08 | Done late
71008652 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008652 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-22 |  | 2026-07-23 | Done late
71008652 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-07-25 |  | 2026-07-23 | Done
71008652 | HMR | 8 | Knitting start | Factory | 2026-07-27 |  | 2026-07-28 | Done late
71008652 | HMR | 9 | Linking start | Factory | 2026-08-02 |  | 2026-08-01 | Done
71008652 | HMR | 10 | Final inspection | Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008652 | HMR | 11 | Ex-factory | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008658 | SND | 1 | Yarn booking | Factory | 2026-06-06 |  | 2026-06-07 | Done late
71008658 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-16 |  | 2026-06-16 | Done
71008658 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71008658 | SND | 4 | Size set approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-09 | Done
71008658 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-22 | Done late
71008658 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-26 |  | 2026-07-26 | Done
71008658 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-07-29 |  | 2026-07-27 | Done
71008658 | SND | 8 | Knitting start | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71008658 | SND | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-04 | Done
71008658 | SND | 10 | Final inspection | Karbar QA | 2026-09-08 |  | 2026-09-08 | Done
71008658 | SND | 11 | Ex-factory | Factory | 2026-09-09 |  | 2026-09-09 | Done
71008665 | TLG | 1 | Yarn booking | Factory | 2026-06-23 |  | 2026-06-25 | Done late
71008665 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-02 |  | 2026-06-30 | Done
71008665 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008665 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-30 | Done late
71008665 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-08 | Done late
71008665 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-12 |  | 2026-08-12 | Done
71008665 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-15 |  | 2026-08-15 | Done
71008665 | TLG | 8 | Knitting start | Factory | 2026-08-17 |  | 2026-08-17 | Done
71008665 | TLG | 9 | Linking start | Factory | 2026-08-23 |  | 2026-08-20 | Done
71008665 | TLG | 10 | Final inspection | Karbar QA | 2026-09-24 |  | 2026-09-24 | Done
71008665 | TLG | 11 | Ex-factory | Factory | 2026-09-26 |  | 2026-09-26 | Done
71008669 | PBB | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-24 | Done
71008669 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71008669 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71008669 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71008669 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71008669 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-15 |  | 2026-08-13 | Done
71008669 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-08-18 |  | 2026-08-16 | Done
71008669 | PBB | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71008669 | PBB | 9 | Linking start | Factory | 2026-08-26 |  | 2026-08-25 | Done
71008669 | PBB | 10 | Final inspection | Karbar QA | 2026-09-28 |  | 2026-09-28 | Done
71008669 | PBB | 11 | Ex-factory | Factory | 2026-09-29 |  | 2026-09-29 | Done
71008672 | MDW | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-06-30 | Done
71008672 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71008672 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008672 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-02 | Done
71008672 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71008672 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-19 | Done
71008672 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71008672 | MDW | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-25 | Done late
71008672 | MDW | 9 | Linking start | Factory | 2026-08-30 |  | 2026-08-29 | Done
71008672 | MDW | 10 | Final inspection | Karbar QA | 2026-10-01 |  | 2026-09-30 | Done
71008672 | MDW | 11 | Ex-factory | Factory | 2026-10-03 |  | 2026-10-01 | Done
71008679 | GRL | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-02 | Done
71008679 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71008679 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-21 | Done late
71008679 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71008679 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-18 | Done
71008679 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-08-24 | Done
71008679 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-25 | Done
71008679 | GRL | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-08-29 | Done
71008679 | GRL | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-01 | Done
71008679 | GRL | 10 | Final inspection | Karbar QA | 2026-10-07 |  | 2026-10-13 | Done late
71008679 | GRL | 11 | Ex-factory | Factory | 2026-10-08 |  | 2026-10-14 | Done late
71008686 | MDW | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-25 | Done late
71008686 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-06 | Done late
71008686 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008686 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-28 | Done
71008686 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71008686 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-12 | Done
71008686 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-15 | Done
71008686 | MDW | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-19 | Done late
71008686 | MDW | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-23 | Done
71008686 | MDW | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71008686 | MDW | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-27 | Done
71008692 | SVP | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71008692 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-02 | Done
71008692 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008692 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71008692 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71008692 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008692 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008692 | SVP | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-19 | Done late
71008692 | SVP | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-23 | Done
71008692 | SVP | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71008692 | SVP | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-27 | Done
71008701 | CLB | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-02 | Done
71008701 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008701 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-21 | Done late
71008701 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71008701 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71008701 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-08-27 | Done late
71008701 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-25 | Done
71008701 | CLB | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-08-30 | Done late
71008701 | CLB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-02 | Done
71008701 | CLB | 10 | Final inspection | Karbar QA | 2026-10-07 |  | 2026-10-06 | Done
71008701 | CLB | 11 | Ex-factory | Factory | 2026-10-08 |  | 2026-10-07 | Done
71008707 | TLG | 1 | Yarn booking | Factory | 2026-06-02 |  | 2026-06-02 | Done
71008707 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-11 |  | 2026-06-11 | Done
71008707 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-18 | Done late
71008707 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-07 | Done
71008707 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008707 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-22 |  | 2026-07-22 | Done
71008707 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-07-25 |  | 2026-07-23 | Done
71008707 | TLG | 8 | Knitting start | Factory | 2026-07-27 |  | 2026-07-28 | Done late
71008707 | TLG | 9 | Linking start | Factory | 2026-08-02 |  | 2026-08-01 | Done
71008707 | TLG | 10 | Final inspection | Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008707 | TLG | 11 | Ex-factory | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008712 | PBB | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-18 | Done
71008712 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-30 | Done late
71008712 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008712 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008712 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71008712 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-06 | Done
71008712 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-08-10 |  | 2026-08-10 | Done
71008712 | PBB | 8 | Knitting start | Factory | 2026-08-12 |  | 2026-08-12 | Done
71008712 | PBB | 9 | Linking start | Factory | 2026-08-18 |  | 2026-08-16 | Done
71008712 | PBB | 10 | Final inspection | Karbar QA | 2026-09-20 |  | 2026-09-17 | Done
71008712 | PBB | 11 | Ex-factory | Factory | 2026-09-21 |  | 2026-09-19 | Done
71008716 | CLB | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-18 | Done
71008716 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-27 | Done
71008716 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-05 | Done late
71008716 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008716 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71008716 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-08 |  | 2026-08-08 | Done
71008716 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-11 |  | 2026-08-11 | Done
71008716 | CLB | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71008716 | CLB | 9 | Linking start | Factory | 2026-08-19 |  | 2026-08-17 | Done
71008716 | CLB | 10 | Final inspection | Karbar QA | 2026-09-21 |  | 2026-09-23 | Done late
71008716 | CLB | 11 | Ex-factory | Factory | 2026-09-22 |  | 2026-09-24 | Done late
71008724 | GRL | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71008724 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-07 | Done late
71008724 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008724 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71008724 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71008724 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71008724 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71008724 | GRL | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-20 | Done late
71008724 | GRL | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-24 | Done
71008724 | GRL | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71008724 | GRL | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-28 | Done
71008733 | IRB | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-04 | Done
71008733 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-18 | Done late
71008733 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-22 | Done
71008733 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-12 | Done
71008733 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71008733 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-28 | Done late
71008733 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-29 | Done
71008733 | IRB | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008733 | IRB | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008733 | IRB | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008733 | IRB | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008738 | KST | 1 | Yarn booking | Factory | 2026-06-20 |  | 2026-06-18 | Done
71008738 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-30 |  | 2026-07-02 | Done late
71008738 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-04 | Done
71008738 | KST | 4 | Size set approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008738 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-06 | Done late
71008738 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-09 |  | 2026-08-11 | Done late
71008738 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71008738 | KST | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71008738 | KST | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-17 | Done
71008738 | KST | 10 | Final inspection | Karbar QA | 2026-09-22 |  | 2026-09-21 | Done
71008738 | KST | 11 | Ex-factory | Factory | 2026-09-23 |  | 2026-09-22 | Done
71008741 | GRL | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-06-28 | Done
71008741 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008741 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-13 | Done
71008741 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71008741 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71008741 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-27 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71008741 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-24 | Done late
71008741 | GRL | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-29 | Done late
71008741 | GRL | 9 | Linking start | Factory | 2026-08-30 |  | 2026-09-01 | Done late
71008741 | GRL | 10 | Final inspection | Karbar QA | 2026-10-01 |  |  | Overdue
71008741 | GRL | 11 | Ex-factory | Factory | 2026-10-03 |  |  | Overdue
71008746 | TLG | 1 | Yarn booking | Factory | 2026-07-02 |  | 2026-07-02 | Done
71008746 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008746 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-16 | Done
71008746 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71008746 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71008746 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-22 |  | 2026-08-23 | Done late
71008746 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-25 |  | 2026-08-26 | Done late
71008746 | TLG | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-27 | Done
71008746 | TLG | 9 | Linking start | Factory | 2026-09-02 |  | 2026-08-31 | Done
71008746 | TLG | 10 | Final inspection | Karbar QA | 2026-10-05 |  | 2026-10-05 | Done
71008746 | TLG | 11 | Ex-factory | Factory | 2026-10-06 |  | 2026-10-06 | Done
71008750 | LTF | 1 | Yarn booking | Factory | 2026-07-02 |  | 2026-07-02 | Done
71008750 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008750 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-20 | Done late
71008750 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71008750 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71008750 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-22 |  | 2026-08-25 | Done late
71008750 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-25 |  | 2026-08-23 | Done
71008750 | LTF | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-29 | Done late
71008750 | LTF | 9 | Linking start | Factory | 2026-09-02 |  | 2026-09-01 | Done
71008750 | LTF | 10 | Final inspection | Karbar QA | 2026-10-05 |  | 2026-10-05 | Done
71008750 | LTF | 11 | Ex-factory | Factory | 2026-10-06 |  | 2026-10-06 | Done
71008754 | SLM | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-07 | Done
71008754 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-16 | Done
71008754 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008754 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71008754 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-25 | Done late
71008754 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71008754 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71008754 | SLM | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008754 | SLM | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-06 | Done
71008754 | SLM | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-11 | Done
71008754 | SLM | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-12 | Done
71008757 | BLF | 1 | Yarn booking | Factory | 2026-06-04 |  | 2026-06-06 | Done late
71008757 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-14 |  | 2026-06-14 | Done
71008757 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-06-18 |  | 2026-06-17 | Done
71008757 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008757 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008757 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-23 |  | 2026-07-22 | Done
71008757 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-07-27 |  | 2026-07-27 | Done
71008757 | BLF | 8 | Knitting start | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71008757 | BLF | 9 | Linking start | Factory | 2026-08-04 |  | 2026-08-03 | Done
71008757 | BLF | 10 | Final inspection | Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71008757 | BLF | 11 | Ex-factory | Factory | 2026-09-07 |  | 2026-09-07 | Done
71008766 | SLM | 1 | Yarn booking | Factory | 2026-06-17 |  | 2026-06-17 | Done
71008766 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71008766 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008766 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-20 | Done
71008766 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-02 | Done late
71008766 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-05 | Done
71008766 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-09 |  | 2026-08-08 | Done
71008766 | SLM | 8 | Knitting start | Factory | 2026-08-11 |  | 2026-08-11 | Done
71008766 | SLM | 9 | Linking start | Factory | 2026-08-17 |  | 2026-08-15 | Done
71008766 | SLM | 10 | Final inspection | Karbar QA | 2026-09-19 |  | 2026-09-19 | Done
71008766 | SLM | 11 | Ex-factory | Factory | 2026-09-20 |  | 2026-09-20 | Done
71008775 | LTF | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-18 | Done
71008775 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008775 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008775 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008775 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-05 | Done late
71008775 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-08 |  | 2026-08-08 | Done
71008775 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-11 |  | 2026-08-10 | Done
71008775 | LTF | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71008775 | LTF | 9 | Linking start | Factory | 2026-08-19 |  | 2026-08-18 | Done
71008775 | LTF | 10 | Final inspection | Karbar QA | 2026-09-21 |  | 2026-09-23 | Done late
71008775 | LTF | 11 | Ex-factory | Factory | 2026-09-22 |  | 2026-09-24 | Done late
71008778 | BLF | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-20 | Done late
71008778 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-29 |  | 2026-07-01 | Done late
71008778 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008778 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008778 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71008778 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-08 |  | 2026-08-08 | Done
71008778 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-11 |  | 2026-08-09 | Done
71008778 | BLF | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71008778 | BLF | 9 | Linking start | Factory | 2026-08-19 |  | 2026-08-18 | Done
71008778 | BLF | 10 | Final inspection | Karbar QA | 2026-09-21 |  | 2026-09-20 | Done
71008778 | BLF | 11 | Ex-factory | Factory | 2026-09-22 |  | 2026-09-21 | Done
71008784 | SLM | 1 | Yarn booking | Factory | 2026-06-20 |  | 2026-06-21 | Done late
71008784 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-29 | Done
71008784 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71008784 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008784 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71008784 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-09 |  | 2026-08-10 | Done late
71008784 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71008784 | SLM | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71008784 | SLM | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-17 | Done
71008784 | SLM | 10 | Final inspection | Karbar QA | 2026-09-22 |  | 2026-09-23 | Done late
71008784 | SLM | 11 | Ex-factory | Factory | 2026-09-23 |  | 2026-09-24 | Done late
71008789 | IRB | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-28 | Done
71008789 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71008789 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-14 | Done late
71008789 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-04 | Done late
71008789 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71008789 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-17 | Done
71008789 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71008789 | IRB | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-22 | Done
71008789 | IRB | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-25 | Done
71008789 | IRB | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71008789 | IRB | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-10-01 | Done
71008795 | MDW | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-09 | Done
71008795 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-21 | Done late
71008795 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-23 | Done
71008795 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-14 | Done
71008795 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008795 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-08-01 | Done late
71008795 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-07-30 | Done
71008795 | MDW | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-05 | Done late
71008795 | MDW | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-09 | Done
71008795 | MDW | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008795 | MDW | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008798 | PBB | 1 | Yarn booking | Factory | 2026-07-11 |  | 2026-07-11 | Done
71008798 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-21 | Done
71008798 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-25 | Done
71008798 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-15 | Done
71008798 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71008798 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-30 |  | 2026-08-31 | Done late
71008798 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-02 |  | 2026-09-01 | Done
71008798 | PBB | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008798 | PBB | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-07 | Done
71008798 | PBB | 10 | Final inspection | Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71008798 | PBB | 11 | Ex-factory | Factory | 2026-10-14 |  | 2026-10-14 | Done
71008801 | AMB | 1 | Yarn booking | Factory | 2026-07-02 |  | 2026-06-30 | Done
71008801 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-14 | Done late
71008801 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71008801 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71008801 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71008801 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-22 |  | 2026-08-22 | Done
71008801 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-25 |  | 2026-08-27 | Done late
71008801 | AMB | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-27 | Done
71008801 | AMB | 9 | Linking start | Factory | 2026-09-02 |  | 2026-08-31 | Done
71008801 | AMB | 10 | Final inspection | Karbar QA | 2026-10-05 |  | 2026-10-05 | Done
71008801 | AMB | 11 | Ex-factory | Factory | 2026-10-06 |  | 2026-10-06 | Done
71008806 | SLM | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71008806 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-18 | Done
71008806 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-22 | Done
71008806 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71008806 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71008806 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71008806 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71008806 | SLM | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008806 | SLM | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-06 | Done
71008806 | SLM | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-11 | Done
71008806 | SLM | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-12 | Done
71008810 | WSM | 1 | Yarn booking | Factory | 2026-06-10 |  | 2026-06-10 | Done
71008810 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-20 |  | 2026-06-22 | Done late
71008810 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-23 | Done
71008810 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71008810 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-23 | Done
71008810 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-29 | Done
71008810 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-08-02 |  | 2026-08-03 | Done late
71008810 | WSM | 8 | Knitting start | Factory | 2026-08-04 |  | 2026-08-04 | Done
71008810 | WSM | 9 | Linking start | Factory | 2026-08-10 |  | 2026-08-08 | Done
71008810 | WSM | 10 | Final inspection | Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71008810 | WSM | 11 | Ex-factory | Factory | 2026-09-13 |  | 2026-09-13 | Done
71008817 | TLG | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-14 | Done
71008817 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-25 | Done late
71008817 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71008817 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-21 | Done late
71008817 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008817 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-01 | Done
71008817 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71008817 | TLG | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-08 | Done
71008817 | TLG | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-11 | Done
71008817 | TLG | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-14 | Done
71008817 | TLG | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-15 | Done
71008823 | IRB | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71008823 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71008823 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008823 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-08-01 | Done late
71008823 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-15 | Done late | PP sample rejected once (measurement); resubmitted
71008823 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-18 | Done late | Yarn held at customs 4 days
71008823 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-16 | Done
71008823 | IRB | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-20 | Done late
71008823 | IRB | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-24 | Done
71008823 | IRB | 10 | Final inspection | Karbar QA | 2026-09-27 |  |  | Overdue
71008823 | IRB | 11 | Ex-factory | Factory | 2026-09-28 |  |  | Overdue
71008830 | FNS | 1 | Yarn booking | Factory | 2026-07-01 |  | 2026-06-30 | Done
71008830 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71008830 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71008830 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71008830 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-15 | Done
71008830 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-20 |  | 2026-08-22 | Done late
71008830 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-08-23 |  | 2026-08-24 | Done late
71008830 | FNS | 8 | Knitting start | Factory | 2026-08-25 |  | 2026-08-25 | Done
71008830 | FNS | 9 | Linking start | Factory | 2026-08-31 |  | 2026-08-29 | Done
71008830 | FNS | 10 | Final inspection | Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71008830 | FNS | 11 | Ex-factory | Factory | 2026-10-04 |  | 2026-10-04 | Done
71008837 | SLM | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-07 | Done
71008837 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-18 | Done late
71008837 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008837 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-09 | Done
71008837 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71008837 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-27 | Done late
71008837 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-27 | Done
71008837 | SLM | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71008837 | SLM | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71008837 | SLM | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-06 | Done
71008837 | SLM | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-07 | Done
71008844 | HMR | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-08 | Done
71008844 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-16 | Done
71008844 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-21 | Done
71008844 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-10 | Done
71008844 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71008844 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71008844 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-31 | Done late
71008844 | HMR | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-01 | Done
71008844 | HMR | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-05 | Done
71008844 | HMR | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-10 | Done
71008844 | HMR | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-11 | Done
71008847 | HMR | 1 | Yarn booking | Factory | 2026-07-11 |  | 2026-07-12 | Done late
71008847 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-19 | Done
71008847 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-23 | Done
71008847 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-17 | Done late
71008847 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-27 | Done late
71008847 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-30 |  | 2026-08-30 | Done
71008847 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-02 |  | 2026-09-02 | Done
71008847 | HMR | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008847 | HMR | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-07 | Done
71008847 | HMR | 10 | Final inspection | Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71008847 | HMR | 11 | Ex-factory | Factory | 2026-10-14 |  | 2026-10-14 | Done
71008853 | TLG | 1 | Yarn booking | Factory | 2026-07-11 |  | 2026-07-11 | Done
71008853 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-22 | Done late
71008853 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-23 | Done
71008853 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-13 | Done
71008853 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71008853 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-30 |  | 2026-08-30 | Done
71008853 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-02 |  | 2026-09-01 | Done
71008853 | TLG | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71008853 | TLG | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71008853 | TLG | 10 | Final inspection | Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71008853 | TLG | 11 | Ex-factory | Factory | 2026-10-14 |  | 2026-10-14 | Done
71008860 | SLM | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71008860 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008860 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71008860 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-13 | Done
71008860 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71008860 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-29 | Done
71008860 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008860 | SLM | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008860 | SLM | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71008860 | SLM | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71008860 | SLM | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71008869 | BRW | 1 | Yarn booking | Factory | 2026-06-07 |  | 2026-06-09 | Done late
71008869 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-17 |  | 2026-06-17 | Done
71008869 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-06-22 |  | 2026-06-20 | Done
71008869 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-09 | Done
71008869 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008869 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-27 |  | 2026-07-26 | Done
71008869 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-07-30 |  | 2026-07-30 | Done
71008869 | BRW | 8 | Knitting start | Factory | 2026-08-01 |  | 2026-08-02 | Done late
71008869 | BRW | 9 | Linking start | Factory | 2026-08-06 |  | 2026-08-05 | Done
71008869 | BRW | 10 | Final inspection | Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71008869 | BRW | 11 | Ex-factory | Factory | 2026-09-10 |  | 2026-09-10 | Done
71008874 | AMB | 1 | Yarn booking | Factory | 2026-06-17 |  | 2026-06-17 | Done
71008874 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-27 | Done
71008874 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-04 | Done late
71008874 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008874 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71008874 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-06 | Done
71008874 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-09 |  | 2026-08-09 | Done
71008874 | AMB | 8 | Knitting start | Factory | 2026-08-11 |  | 2026-08-11 | Done
71008874 | AMB | 9 | Linking start | Factory | 2026-08-17 |  | 2026-08-15 | Done
71008874 | AMB | 10 | Final inspection | Karbar QA | 2026-09-19 |  | 2026-09-21 | Done late
71008874 | AMB | 11 | Ex-factory | Factory | 2026-09-20 |  | 2026-09-22 | Done late
71008877 | CLB | 1 | Yarn booking | Factory | 2026-06-17 |  | 2026-06-17 | Done
71008877 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-27 |  | 2026-06-25 | Done
71008877 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008877 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71008877 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-01 | Done
71008877 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-06 | Done
71008877 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-09 |  | 2026-08-09 | Done
71008877 | CLB | 8 | Knitting start | Factory | 2026-08-11 |  | 2026-08-11 | Done
71008877 | CLB | 9 | Linking start | Factory | 2026-08-17 |  | 2026-08-15 | Done
71008877 | CLB | 10 | Final inspection | Karbar QA | 2026-09-19 |  | 2026-09-19 | Done
71008877 | CLB | 11 | Ex-factory | Factory | 2026-09-20 |  | 2026-09-20 | Done
71008885 | SLM | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-23 | Done
71008885 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008885 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008885 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008885 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-10 | Done late
71008885 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-11 | Done
71008885 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-17 | Done late
71008885 | SLM | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008885 | SLM | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-22 | Done
71008885 | SLM | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-27 | Done late
71008885 | SLM | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-28 | Done late
71008893 | AMB | 1 | Yarn booking | Factory | 2026-06-27 |  | 2026-06-25 | Done
71008893 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-07 |  | 2026-07-08 | Done late
71008893 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-12 |  | 2026-07-09 | Done
71008893 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71008893 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-12 | Done late
71008893 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-16 |  | 2026-08-18 | Done late
71008893 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-19 |  | 2026-08-19 | Done
71008893 | AMB | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-20 | Done
71008893 | AMB | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-24 | Done
71008893 | AMB | 10 | Final inspection | Karbar QA | 2026-09-29 |  | 2026-09-27 | Done
71008893 | AMB | 11 | Ex-factory | Factory | 2026-09-30 |  | 2026-09-28 | Done
71008899 | SLM | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-27 | Done
71008899 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71008899 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-12 | Done
71008899 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71008899 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71008899 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-18 | Done late
71008899 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71008899 | SLM | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-23 | Done late
71008899 | SLM | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-26 | Done
71008899 | SLM | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-27 | Done
71008899 | SLM | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-09-28 | Done
71008908 | PBB | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-06 | Done late
71008908 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-13 | Done
71008908 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-19 | Done
71008908 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71008908 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71008908 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-08-22 | Done
71008908 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71008908 | PBB | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-08-30 | Done late
71008908 | PBB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-02 | Done
71008908 | PBB | 10 | Final inspection | Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71008908 | PBB | 11 | Ex-factory | Factory | 2026-10-08 |  | 2026-10-08 | Done
71008915 | SLM | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-05 | Done
71008915 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-18 | Done late
71008915 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008915 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-11 | Done
71008915 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71008915 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-26 | Done
71008915 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71008915 | SLM | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71008915 | SLM | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71008915 | SLM | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-13 | Done late
71008915 | SLM | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-14 | Done late
71008920 | RVS | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-07 | Done
71008920 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71008920 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-21 | Done
71008920 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-11 | Done
71008920 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71008920 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-25 | Done
71008920 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-09-02 | Done late
71008920 | RVS | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-02 | Done
71008920 | RVS | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-06 | Done
71008920 | RVS | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-07 | Done
71008920 | RVS | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-08 | Done
71008927 | IRB | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71008927 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71008927 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008927 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-28 | Done
71008927 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71008927 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-12 | Done
71008927 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71008927 | IRB | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-18 | Done
71008927 | IRB | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-22 | Done
71008927 | IRB | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-27 | Done late
71008927 | IRB | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-28 | Done late
71008932 | RSG | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-28 | Done
71008932 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71008932 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71008932 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71008932 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71008932 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-20 | Done late
71008932 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-18 | Done
71008932 | RSG | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-23 | Done late
71008932 | RSG | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-26 | Done
71008932 | RSG | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71008932 | RSG | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-10-01 | Done
71008938 | HMR | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-07-02 | Done late
71008938 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71008938 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71008938 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71008938 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71008938 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-19 | Done
71008938 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-23 | Done late
71008938 | HMR | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-25 | Done late
71008938 | HMR | 9 | Linking start | Factory | 2026-08-30 |  | 2026-08-29 | Done
71008938 | HMR | 10 | Final inspection | Karbar QA | 2026-10-01 |  | 2026-09-30 | Done
71008938 | HMR | 11 | Ex-factory | Factory | 2026-10-03 |  | 2026-10-01 | Done
71008941 | IRB | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-13 | Done late
71008941 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71008941 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71008941 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-15 | Done
71008941 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-25 | Done
71008941 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-31 | Done
71008941 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71008941 | IRB | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71008941 | IRB | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71008941 | IRB | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71008941 | IRB | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71008950 | CLB | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-18 | Done
71008950 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-28 |  | 2026-06-30 | Done late
71008950 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-02 |  | 2026-07-02 | Done
71008950 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008950 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71008950 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-06 |  | 2026-08-06 | Done
71008950 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-10 |  | 2026-08-08 | Done
71008950 | CLB | 8 | Knitting start | Factory | 2026-08-12 |  | 2026-08-12 | Done
71008950 | CLB | 9 | Linking start | Factory | 2026-08-18 |  | 2026-08-16 | Done
71008950 | CLB | 10 | Final inspection | Karbar QA | 2026-09-20 |  | 2026-09-17 | Done
71008950 | CLB | 11 | Ex-factory | Factory | 2026-09-21 |  | 2026-09-19 | Done
71008953 | SVP | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-07 | Done
71008953 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71008953 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71008953 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-15 | Done late
71008953 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-25 | Done late
71008953 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-08-29 | Done
71008953 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008953 | SVP | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008953 | SVP | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-07 | Done
71008953 | SVP | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-11 | Done
71008953 | SVP | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-12 | Done
71008959 | BLF | 1 | Yarn booking | Factory | 2026-07-14 |  | 2026-07-16 | Done late
71008959 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71008959 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71008959 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-16 | Done
71008959 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71008959 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-02 |  | 2026-09-02 | Done
71008959 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-09-05 |  | 2026-09-05 | Done
71008959 | BLF | 8 | Knitting start | Factory | 2026-09-07 |  | 2026-09-07 | Done
71008959 | BLF | 9 | Linking start | Factory | 2026-09-13 |  | 2026-09-10 | Done
71008959 | BLF | 10 | Final inspection | Karbar QA | 2026-10-15 |  |  | Pending
71008959 | BLF | 11 | Ex-factory | Factory | 2026-10-17 |  |  | Pending
71008967 | PBB | 1 | Yarn booking | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71008967 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-23 | Done
71008967 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71008967 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71008967 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71008967 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-02 | Done
71008967 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71008967 | PBB | 8 | Knitting start | Factory | 2026-09-08 |  | 2026-09-09 | Done late
71008967 | PBB | 9 | Linking start | Factory | 2026-09-14 |  | 2026-09-13 | Done
71008967 | PBB | 10 | Final inspection | Karbar QA | 2026-10-17 |  |  | Pending
71008967 | PBB | 11 | Ex-factory | Factory | 2026-10-18 |  |  | Pending
71008973 | GRL | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71008973 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-29 | Done late
71008973 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71008973 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71008973 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-03 | Done late | PP sample rejected once (measurement); resubmitted
71008973 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-14 | Done late | Lab dip re-approval needed for one colour
71008973 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-07 | Done
71008973 | GRL | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-17 | Done late
71008973 | GRL | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-21 | Done late
71008973 | GRL | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71008973 | GRL | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71008980 | RSG | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-21 | Done
71008980 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71008980 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-04 | Done
71008980 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71008980 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71008980 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-11 | Done late
71008980 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71008980 | RSG | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-15 | Done
71008980 | RSG | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-18 | Done
71008980 | RSG | 10 | Final inspection | Karbar QA | 2026-09-23 |  | 2026-09-24 | Done late
71008980 | RSG | 11 | Ex-factory | Factory | 2026-09-24 |  | 2026-09-26 | Done late
71008985 | BRW | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-11 | Done late
71008985 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71008985 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-27 | Done late
71008985 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-12 | Done
71008985 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71008985 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-09-01 | Done late
71008985 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-09-01 | Done
71008985 | BRW | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71008985 | BRW | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-07 | Done
71008985 | BRW | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71008985 | BRW | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-13 | Done
71008994 | CPL | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-21 | Done
71008994 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71008994 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71008994 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71008994 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71008994 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-13 | Done late
71008994 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71008994 | CPL | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-16 | Done late
71008994 | CPL | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-19 | Done
71008994 | CPL | 10 | Final inspection | Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71008994 | CPL | 11 | Ex-factory | Factory | 2026-09-24 |  | 2026-09-24 | Done
71009000 | SND | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-08 | Done late
71009000 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009000 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009000 | SND | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-11 | Done
71009000 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009000 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-26 | Done
71009000 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71009000 | SND | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71009000 | SND | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71009000 | SND | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71009000 | SND | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-10 | Done
71009007 | CLB | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-11 | Done
71009007 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71009007 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009007 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-16 | Done
71009007 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71009007 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-31 | Done
71009007 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-02 | Done
71009007 | CLB | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009007 | CLB | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009007 | CLB | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009007 | CLB | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009013 | IRB | 1 | Yarn booking | Factory | 2026-07-14 |  | 2026-07-13 | Done
71009013 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-25 | Done late
71009013 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71009013 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-18 | Done
71009013 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009013 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-02 |  | 2026-09-02 | Done
71009013 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-05 |  | 2026-09-07 | Done late
71009013 | IRB | 8 | Knitting start | Factory | 2026-09-07 |  | 2026-09-08 | Done late
71009013 | IRB | 9 | Linking start | Factory | 2026-09-13 |  | 2026-09-12 | Done
71009013 | IRB | 10 | Final inspection | Karbar QA | 2026-10-15 |  |  | Pending
71009013 | IRB | 11 | Ex-factory | Factory | 2026-10-17 |  |  | Pending
71009021 | BLF | 1 | Yarn booking | Factory | 2026-06-18 |  | 2026-06-17 | Done
71009021 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-30 | Done late
71009021 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71009021 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009021 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-04 | Done late
71009021 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-08 |  | 2026-08-09 | Done late
71009021 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-11 |  | 2026-08-10 | Done
71009021 | BLF | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71009021 | BLF | 9 | Linking start | Factory | 2026-08-19 |  | 2026-08-17 | Done
71009021 | BLF | 10 | Final inspection | Karbar QA | 2026-09-21 |  | 2026-09-21 | Done
71009021 | BLF | 11 | Ex-factory | Factory | 2026-09-22 |  | 2026-09-22 | Done
71009027 | GRL | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-22 | Done late
71009027 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71009027 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-07 | Done late
71009027 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-28 | Done late
71009027 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-11 | Done late | PP sample rejected once (measurement); resubmitted
71009027 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-18 | Done late | Lab dip re-approval needed for one colour
71009027 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-12 | Done
71009027 | GRL | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-20 | Done late
71009027 | GRL | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-24 | Done late
71009027 | GRL | 10 | Final inspection | Karbar QA | 2026-09-23 |  |  | Overdue
71009027 | GRL | 11 | Ex-factory | Factory | 2026-09-24 |  |  | Overdue
71009035 | IRB | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71009035 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71009035 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71009035 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71009035 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009035 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-16 | Done late
71009035 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-13 | Done
71009035 | IRB | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-18 | Done
71009035 | IRB | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-22 | Done
71009035 | IRB | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71009035 | IRB | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-27 | Done
71009039 | AMB | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-25 | Done late
71009039 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71009039 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-11 | Done late
71009039 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71009039 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009039 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71009039 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-15 | Done
71009039 | AMB | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-19 | Done late
71009039 | AMB | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-23 | Done
71009039 | AMB | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71009039 | AMB | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-27 | Done
71009046 | TLG | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009046 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009046 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71009046 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-17 | Done late
71009046 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-25 | Done
71009046 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-09-02 | Done late
71009046 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-05 | Done late
71009046 | TLG | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-06 | Done late
71009046 | TLG | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-09 | Done
71009046 | TLG | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009046 | TLG | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009055 | SLM | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-18 | Done
71009055 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-28 | Done
71009055 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009055 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-25 | Done late
71009055 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009055 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-05 | Done
71009055 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009055 | SLM | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-13 | Done late
71009055 | SLM | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-16 | Done
71009055 | SLM | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009055 | SLM | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009063 | SLM | 1 | Yarn booking | Factory | 2026-06-11 |  | 2026-06-11 | Done
71009063 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-21 |  | 2026-06-21 | Done
71009063 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-25 |  | 2026-06-25 | Done
71009063 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009063 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-27 | Done late
71009063 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-07-30 |  | 2026-07-30 | Done
71009063 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-03 |  | 2026-08-03 | Done
71009063 | SLM | 8 | Knitting start | Factory | 2026-08-05 |  | 2026-08-05 | Done
71009063 | SLM | 9 | Linking start | Factory | 2026-08-11 |  | 2026-08-09 | Done
71009063 | SLM | 10 | Final inspection | Karbar QA | 2026-09-13 |  | 2026-09-22 | Done late
71009063 | SLM | 11 | Ex-factory | Factory | 2026-09-14 |  | 2026-09-23 | Done late
71009068 | LTF | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-21 | Done
71009068 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-01 | Done
71009068 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-04 | Done
71009068 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-23 | Done
71009068 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71009068 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-10 | Done
71009068 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71009068 | LTF | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-15 | Done
71009068 | LTF | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-18 | Done
71009068 | LTF | 10 | Final inspection | Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71009068 | LTF | 11 | Ex-factory | Factory | 2026-09-24 |  | 2026-09-24 | Done
71009071 | IRB | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-05 | Done
71009071 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-16 | Done late
71009071 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009071 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71009071 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71009071 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-09-02 | Done late | Lab dip re-approval needed for one colour
71009071 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-26 | Done
71009071 | IRB | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-09-05 | Done late
71009071 | IRB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-08 | Done late
71009071 | IRB | 10 | Final inspection | Karbar QA | 2026-10-07 |  |  | Overdue
71009071 | IRB | 11 | Ex-factory | Factory | 2026-10-08 |  |  | Overdue
71009079 | SLM | 1 | Yarn booking | Factory | 2026-06-14 |  | 2026-06-15 | Done late
71009079 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-24 |  | 2026-06-25 | Done late
71009079 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-06-29 |  | 2026-06-29 | Done
71009079 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-18 | Done
71009079 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71009079 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-03 |  | 2026-08-03 | Done
71009079 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-06 |  | 2026-08-06 | Done
71009079 | SLM | 8 | Knitting start | Factory | 2026-08-08 |  | 2026-08-09 | Done late
71009079 | SLM | 9 | Linking start | Factory | 2026-08-13 |  | 2026-08-12 | Done
71009079 | SLM | 10 | Final inspection | Karbar QA | 2026-09-16 |  | 2026-09-17 | Done late
71009079 | SLM | 11 | Ex-factory | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009085 | GRL | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71009085 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71009085 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71009085 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-28 | Done
71009085 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-11 | Done late
71009085 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71009085 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-17 | Done
71009085 | GRL | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-19 | Done
71009085 | GRL | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-23 | Done
71009085 | GRL | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-24 | Done
71009085 | GRL | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-26 | Done
71009092 | WTH | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009092 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-21 | Done late
71009092 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-23 | Done
71009092 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-11 | Done
71009092 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71009092 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-09-01 | Done late
71009092 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-09-03 | Done late
71009092 | WTH | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71009092 | WTH | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-08 | Done
71009092 | WTH | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009092 | WTH | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009095 | BRW | 1 | Yarn booking | Factory | 2026-06-20 |  | 2026-06-22 | Done late
71009095 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-30 | Done
71009095 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71009095 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71009095 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-05 | Done late
71009095 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-09 |  | 2026-08-09 | Done
71009095 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71009095 | BRW | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-13 | Done
71009095 | BRW | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-17 | Done
71009095 | BRW | 10 | Final inspection | Karbar QA | 2026-09-22 |  | 2026-09-22 | Done
71009095 | BRW | 11 | Ex-factory | Factory | 2026-09-23 |  | 2026-09-23 | Done
71009102 | CPL | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-29 | Done late
71009102 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71009102 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-11 | Done
71009102 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-01 | Done
71009102 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009102 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-18 | Done late
71009102 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-22 | Done late
71009102 | CPL | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-23 | Done late
71009102 | CPL | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-26 | Done
71009102 | CPL | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71009102 | CPL | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-10-01 | Done
71009108 | BRW | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-05 | Done
71009108 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-13 | Done
71009108 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009108 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-06 | Done
71009108 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71009108 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-08-25 | Done late
71009108 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-26 | Done
71009108 | BRW | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-08-29 | Done
71009108 | BRW | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-01 | Done
71009108 | BRW | 10 | Final inspection | Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71009108 | BRW | 11 | Ex-factory | Factory | 2026-10-08 |  | 2026-10-08 | Done
71009117 | CLB | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-06 | Done
71009117 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-18 | Done late
71009117 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-21 | Done
71009117 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-11 | Done
71009117 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-22 | Done late
71009117 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-26 | Done
71009117 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71009117 | CLB | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71009117 | CLB | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71009117 | CLB | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71009117 | CLB | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-10 | Done
71009122 | SLM | 1 | Yarn booking | Factory | 2026-07-11 |  | 2026-07-13 | Done late
71009122 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-19 | Done
71009122 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71009122 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-13 | Done
71009122 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-27 | Done late
71009122 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-30 |  | 2026-08-27 | Done
71009122 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-02 |  | 2026-09-01 | Done
71009122 | SLM | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71009122 | SLM | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-07 | Done
71009122 | SLM | 10 | Final inspection | Karbar QA | 2026-10-13 |  | 2026-10-12 | Done
71009122 | SLM | 11 | Ex-factory | Factory | 2026-10-14 |  | 2026-10-13 | Done
71009129 | GRL | 1 | Yarn booking | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71009129 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71009129 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009129 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71009129 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-06 | Done late
71009129 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-12 | Done late
71009129 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-13 |  | 2026-09-10 | Done
71009129 | GRL | 8 | Knitting start | Factory | 2026-09-15 |  | 2026-09-15 | Done
71009129 | GRL | 9 | Linking start | Factory | 2026-09-21 |  | 2026-09-19 | Done
71009129 | GRL | 10 | Final inspection | Karbar QA | 2026-10-24 |  |  | Pending
71009129 | GRL | 11 | Ex-factory | Factory | 2026-10-25 |  |  | Pending
71009136 | SND | 1 | Yarn booking | Factory | 2026-06-20 |  | 2026-06-20 | Done
71009136 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-06-30 |  | 2026-06-29 | Done
71009136 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-05 | Done
71009136 | SND | 4 | Size set approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71009136 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71009136 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-09 |  | 2026-08-09 | Done
71009136 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-08-12 |  | 2026-08-12 | Done
71009136 | SND | 8 | Knitting start | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71009136 | SND | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-18 | Done
71009136 | SND | 10 | Final inspection | Karbar QA | 2026-09-22 |  | 2026-09-28 | Done late
71009136 | SND | 11 | Ex-factory | Factory | 2026-09-23 |  | 2026-09-29 | Done late
71009142 | KST | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-07 | Done
71009142 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-14 | Done
71009142 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71009142 | KST | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-10 | Done
71009142 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009142 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-27 | Done late
71009142 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-27 | Done
71009142 | KST | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71009142 | KST | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71009142 | KST | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71009142 | KST | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-10 | Done
71009148 | AMB | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009148 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71009148 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009148 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009148 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-09-01 | Done late
71009148 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009148 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71009148 | AMB | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-10 | Done late
71009148 | AMB | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-14 | Done
71009148 | AMB | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009148 | AMB | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009156 | SVP | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-18 | Done late
71009156 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009156 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-02 | Done late
71009156 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-19 | Done
71009156 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-30 | Done
71009156 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-08 | Done late
71009156 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-06 | Done
71009156 | SVP | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71009156 | SVP | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-14 | Done
71009156 | SVP | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71009156 | SVP | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71009161 | SLM | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009161 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71009161 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009161 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009161 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71009161 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-14 | Done late
71009161 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-15 | Done
71009161 | SLM | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009161 | SLM | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-22 | Done
71009161 | SLM | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009161 | SLM | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009166 | KST | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-06-28 | Done
71009166 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71009166 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71009166 | KST | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-02 | Done
71009166 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009166 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-20 | Done late
71009166 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71009166 | KST | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-24 | Done
71009166 | KST | 9 | Linking start | Factory | 2026-08-30 |  | 2026-08-27 | Done
71009166 | KST | 10 | Final inspection | Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71009166 | KST | 11 | Ex-factory | Factory | 2026-10-03 |  | 2026-10-03 | Done
71009169 | IRB | 1 | Yarn booking | Factory | 2026-07-04 |  | 2026-07-06 | Done late
71009169 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-14 |  | 2026-07-15 | Done late
71009169 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71009169 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71009169 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-19 | Done late
71009169 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-23 |  | 2026-08-25 | Done late
71009169 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-08-26 |  | 2026-08-24 | Done
71009169 | IRB | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-27 | Done
71009169 | IRB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-08-31 | Done
71009169 | IRB | 10 | Final inspection | Karbar QA | 2026-10-06 |  | 2026-10-05 | Done
71009169 | IRB | 11 | Ex-factory | Factory | 2026-10-07 |  | 2026-10-06 | Done
71009173 | BLF | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-06 | Done
71009173 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-19 | Done late
71009173 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009173 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71009173 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71009173 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-30 | Done late
71009173 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-29 | Done
71009173 | BLF | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-02 | Done late
71009173 | BLF | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-06 | Done
71009173 | BLF | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-10 | Done
71009173 | BLF | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-11 | Done
71009176 | MDW | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-18 | Done
71009176 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-29 | Done late
71009176 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-03 | Done late
71009176 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71009176 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009176 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-06 | Done
71009176 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71009176 | MDW | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71009176 | MDW | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-14 | Done
71009176 | MDW | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71009176 | MDW | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71009179 | TLG | 1 | Yarn booking | Factory | 2026-07-25 |  | 2026-07-26 | Done late
71009179 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-03 | Done
71009179 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-06 | Done
71009179 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71009179 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-10 | Done late
71009179 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-13 |  | 2026-09-10 | Done
71009179 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71009179 | TLG | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009179 | TLG | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-21 | Done
71009179 | TLG | 10 | Final inspection | Karbar QA | 2026-10-27 |  |  | Pending
71009179 | TLG | 11 | Ex-factory | Factory | 2026-10-28 |  |  | Pending
71009183 | SLM | 1 | Yarn booking | Factory | 2026-07-02 |  | 2026-07-02 | Done
71009183 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-13 | Done
71009183 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009183 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009183 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-22 | Done late | PP sample rejected once (measurement); resubmitted
71009183 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-22 |  | 2026-08-29 | Done late | Yarn held at customs 4 days
71009183 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-25 |  | 2026-08-24 | Done
71009183 | SLM | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-31 | Done late
71009183 | SLM | 9 | Linking start | Factory | 2026-09-02 |  | 2026-09-03 | Done late
71009183 | SLM | 10 | Final inspection | Karbar QA | 2026-10-05 |  |  | Overdue
71009183 | SLM | 11 | Ex-factory | Factory | 2026-10-06 |  |  | Overdue
71009192 | OKH | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-07 | Done
71009192 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009192 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-23 | Done late
71009192 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-09 | Done
71009192 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009192 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-27 | Done late
71009192 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71009192 | OKH | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-08-31 | Done
71009192 | OKH | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-03 | Done
71009192 | OKH | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-07 | Done
71009192 | OKH | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-08 | Done
71009201 | FNS | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-08 | Done
71009201 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009201 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009201 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71009201 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71009201 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009201 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-30 | Done
71009201 | FNS | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-01 | Done
71009201 | FNS | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-05 | Done
71009201 | FNS | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-10 | Done
71009201 | FNS | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-11 | Done
71009208 | GRL | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-07 | Done
71009208 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-21 | Done late
71009208 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009208 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-11 | Done
71009208 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009208 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-29 | Done late
71009208 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71009208 | GRL | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-03 | Done late
71009208 | GRL | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-07 | Done
71009208 | GRL | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-11 | Done
71009208 | GRL | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-12 | Done
71009214 | GRL | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009214 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009214 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009214 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-16 | Done
71009214 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71009214 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-09-01 | Done late
71009214 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71009214 | GRL | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009214 | GRL | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009214 | GRL | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009214 | GRL | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009222 | AMB | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009222 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009222 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-25 | Done
71009222 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-15 | Done
71009222 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71009222 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-31 | Done
71009222 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-05 | Done late
71009222 | AMB | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009222 | AMB | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009222 | AMB | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009222 | AMB | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009230 | MDW | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009230 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-28 | Done late
71009230 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-29 | Done
71009230 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009230 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009230 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009230 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-09 | Done late
71009230 | MDW | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-10 | Done late
71009230 | MDW | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-14 | Done
71009230 | MDW | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009230 | MDW | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009236 | GRL | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-27 | Done late
71009236 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-02 | Done
71009236 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71009236 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009236 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-11 | Done late
71009236 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-15 | Done late
71009236 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-18 | Done late
71009236 | GRL | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-19 | Done
71009236 | GRL | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-23 | Done
71009236 | GRL | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-28 | Done late
71009236 | GRL | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-29 | Done late
71009245 | PBB | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-07 | Done
71009245 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009245 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009245 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71009245 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71009245 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009245 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-29 | Done
71009245 | PBB | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-01 | Done
71009245 | PBB | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-05 | Done
71009245 | PBB | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-10 | Done
71009245 | PBB | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-11 | Done
71009254 | SND | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009254 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009254 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-25 | Done
71009254 | SND | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-16 | Done
71009254 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71009254 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-09-02 | Done late
71009254 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-02 | Done
71009254 | SND | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009254 | SND | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009254 | SND | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009254 | SND | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009263 | LTF | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009263 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009263 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-26 | Done
71009263 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71009263 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-25 | Done
71009263 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-31 | Done
71009263 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71009263 | LTF | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009263 | LTF | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009263 | LTF | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009263 | LTF | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009269 | PBB | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-14 | Done
71009269 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-28 | Done late
71009269 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-08-01 | Done late
71009269 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-19 | Done
71009269 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009269 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009269 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-05 | Done
71009269 | PBB | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-09 | Done
71009269 | PBB | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-13 | Done
71009269 | PBB | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009269 | PBB | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009273 | SVP | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-16 | Done
71009273 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-26 | Done
71009273 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71009273 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71009273 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009273 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-05 | Done
71009273 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71009273 | SVP | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-12 | Done late
71009273 | SVP | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-15 | Done
71009273 | SVP | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71009273 | SVP | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71009281 | HMR | 1 | Yarn booking | Factory | 2026-07-25 |  | 2026-07-25 | Done
71009281 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71009281 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71009281 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-31 | Done late
71009281 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-07 | Done
71009281 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-13 |  | 2026-09-10 | Done
71009281 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71009281 | HMR | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009281 | HMR | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-21 | Done
71009281 | HMR | 10 | Final inspection | Karbar QA | 2026-10-27 |  |  | Pending
71009281 | HMR | 11 | Ex-factory | Factory | 2026-10-28 |  |  | Pending
71009290 | HMR | 1 | Yarn booking | Factory | 2026-06-24 |  | 2026-06-24 | Done
71009290 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-04 |  | 2026-07-04 | Done
71009290 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-08 | Done
71009290 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71009290 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009290 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71009290 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-16 |  | 2026-08-16 | Done
71009290 | HMR | 8 | Knitting start | Factory | 2026-08-18 |  | 2026-08-19 | Done late
71009290 | HMR | 9 | Linking start | Factory | 2026-08-24 |  | 2026-08-23 | Done
71009290 | HMR | 10 | Final inspection | Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71009290 | HMR | 11 | Ex-factory | Factory | 2026-09-27 |  | 2026-09-27 | Done
71009293 | RVS | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-25 | Done
71009293 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71009293 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-11 | Done
71009293 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-04 | Done late
71009293 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009293 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-20 | Done late
71009293 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71009293 | RVS | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-22 | Done
71009293 | RVS | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-25 | Done
71009293 | RVS | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-29 | Done
71009293 | RVS | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-09-30 | Done
71009296 | IRB | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009296 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009296 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009296 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-13 | Done
71009296 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71009296 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-09-01 | Done late
71009296 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71009296 | IRB | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009296 | IRB | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009296 | IRB | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009296 | IRB | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009300 | WTH | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009300 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-27 | Done late
71009300 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-29 | Done
71009300 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009300 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009300 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009300 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71009300 | WTH | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-10 | Done late
71009300 | WTH | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-14 | Done
71009300 | WTH | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009300 | WTH | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009308 | GRL | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71009308 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-04 | Done
71009308 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71009308 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-28 | Done
71009308 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71009308 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-15 |  | 2026-08-15 | Done
71009308 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-08-18 |  | 2026-08-18 | Done
71009308 | GRL | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71009308 | GRL | 9 | Linking start | Factory | 2026-08-26 |  | 2026-08-25 | Done
71009308 | GRL | 10 | Final inspection | Karbar QA | 2026-09-28 |  | 2026-09-29 | Done late
71009308 | GRL | 11 | Ex-factory | Factory | 2026-09-29 |  | 2026-09-30 | Done late
71009313 | WTH | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-24 | Done
71009313 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71009313 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-09 | Done
71009313 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-08-01 | Done late
71009313 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71009313 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-15 |  | 2026-08-13 | Done
71009313 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-08-18 |  | 2026-08-18 | Done
71009313 | WTH | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71009313 | WTH | 9 | Linking start | Factory | 2026-08-26 |  | 2026-08-25 | Done
71009313 | WTH | 10 | Final inspection | Karbar QA | 2026-09-28 |  | 2026-09-28 | Done
71009313 | WTH | 11 | Ex-factory | Factory | 2026-09-29 |  | 2026-09-29 | Done
71009321 | SVP | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009321 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009321 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-26 | Done late
71009321 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009321 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-23 | Done
71009321 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-08-29 | Done
71009321 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-08-31 | Done
71009321 | SVP | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71009321 | SVP | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-07 | Done
71009321 | SVP | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009321 | SVP | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009327 | TLG | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-15 | Done
71009327 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-23 | Done
71009327 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-29 | Done
71009327 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009327 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-09-01 | Done late
71009327 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-05 | Done late
71009327 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-06 | Done
71009327 | TLG | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-10 | Done late
71009327 | TLG | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-14 | Done
71009327 | TLG | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009327 | TLG | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009330 | WTH | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-21 | Done late
71009330 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009330 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71009330 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009330 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009330 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-13 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009330 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-12 | Done late
71009330 | WTH | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-16 | Done late
71009330 | WTH | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-20 | Done late
71009330 | WTH | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009330 | WTH | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009336 | CPL | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-28 | Done late
71009336 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009336 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-11 | Done late
71009336 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009336 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-10 | Done late
71009336 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-15 | Done late
71009336 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009336 | CPL | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-20 | Done late
71009336 | CPL | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-23 | Done
71009336 | CPL | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009336 | CPL | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009340 | IRB | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-26 | Done
71009340 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-03 | Done
71009340 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-09 | Done
71009340 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-09-01 | Done late
71009340 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-08 | Done
71009340 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-12 | Done
71009340 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-19 | Done late
71009340 | IRB | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-20 | Done late
71009340 | IRB | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-23 | Done
71009340 | IRB | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009340 | IRB | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009345 | RVS | 1 | Yarn booking | Factory | 2026-06-21 |  | 2026-06-21 | Done
71009345 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-01 |  | 2026-07-02 | Done late
71009345 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-08 | Done late
71009345 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-23 | Done
71009345 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71009345 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-10 |  | 2026-08-12 | Done late
71009345 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-13 |  | 2026-08-13 | Done
71009345 | RVS | 8 | Knitting start | Factory | 2026-08-15 |  | 2026-08-15 | Done
71009345 | RVS | 9 | Linking start | Factory | 2026-08-20 |  | 2026-08-18 | Done
71009345 | RVS | 10 | Final inspection | Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71009345 | RVS | 11 | Ex-factory | Factory | 2026-09-24 |  | 2026-09-24 | Done
71009349 | PBB | 1 | Yarn booking | Factory | 2026-07-01 |  | 2026-07-01 | Done
71009349 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71009349 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-15 | Done
71009349 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71009349 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-16 | Done late
71009349 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-20 |  | 2026-08-20 | Done
71009349 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-08-23 |  | 2026-08-24 | Done late
71009349 | PBB | 8 | Knitting start | Factory | 2026-08-25 |  | 2026-08-25 | Done
71009349 | PBB | 9 | Linking start | Factory | 2026-08-31 |  | 2026-08-29 | Done
71009349 | PBB | 10 | Final inspection | Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71009349 | PBB | 11 | Ex-factory | Factory | 2026-10-04 |  | 2026-10-04 | Done
71009352 | HMR | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-08 | Done
71009352 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-18 | Done
71009352 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009352 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009352 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009352 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009352 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-08-31 | Done
71009352 | HMR | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-03 | Done late
71009352 | HMR | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-07 | Done
71009352 | HMR | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-07 | Done
71009352 | HMR | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-08 | Done
71009358 | SND | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71009358 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-04 | Done
71009358 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009358 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009358 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-12 | Done late
71009358 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-14 | Done
71009358 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-21 | Done late
71009358 | SND | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-22 | Done late
71009358 | SND | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-26 | Done
71009358 | SND | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009358 | SND | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009366 | RVS | 1 | Yarn booking | Factory | 2026-07-01 |  | 2026-07-02 | Done late
71009366 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71009366 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009366 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71009366 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-13 | Done
71009366 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-20 |  | 2026-08-20 | Done
71009366 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-23 |  | 2026-08-25 | Done late
71009366 | RVS | 8 | Knitting start | Factory | 2026-08-25 |  | 2026-08-25 | Done
71009366 | RVS | 9 | Linking start | Factory | 2026-08-31 |  | 2026-08-29 | Done
71009366 | RVS | 10 | Final inspection | Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71009366 | RVS | 11 | Ex-factory | Factory | 2026-10-04 |  | 2026-10-04 | Done
71009371 | SLM | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-12 | Done
71009371 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-20 | Done
71009371 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009371 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-16 | Done
71009371 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71009371 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-09-05 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009371 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-02 | Done
71009371 | SLM | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-07 | Done late
71009371 | SLM | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71009371 | SLM | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009371 | SLM | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009378 | OKH | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71009378 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-05 |  | 2026-07-04 | Done
71009378 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-09 | Done
71009378 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009378 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71009378 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-13 |  | 2026-08-13 | Done
71009378 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-08-17 |  | 2026-08-15 | Done
71009378 | OKH | 8 | Knitting start | Factory | 2026-08-19 |  | 2026-08-19 | Done
71009378 | OKH | 9 | Linking start | Factory | 2026-08-25 |  | 2026-08-23 | Done
71009378 | OKH | 10 | Final inspection | Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71009378 | OKH | 11 | Ex-factory | Factory | 2026-09-28 |  | 2026-09-28 | Done
71009387 | SLM | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009387 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-22 | Done late
71009387 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-27 | Done late
71009387 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-15 | Done late
71009387 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-25 | Done late
71009387 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-09-01 | Done late
71009387 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-09-02 | Done late
71009387 | SLM | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71009387 | SLM | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-08 | Done
71009387 | SLM | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009387 | SLM | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009396 | TLG | 1 | Yarn booking | Factory | 2026-07-30 |  | 2026-07-30 | Done
71009396 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71009396 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-16 | Done late
71009396 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-02 | Done
71009396 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-15 | Done late
71009396 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-19 |  | 2026-09-19 | Done
71009396 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-22 |  | 2026-09-22 | Done
71009396 | TLG | 8 | Knitting start | Factory | 2026-09-24 |  | 2026-09-24 | Done
71009396 | TLG | 9 | Linking start | Factory | 2026-09-30 |  | 2026-09-28 | Done
71009396 | TLG | 10 | Final inspection | Karbar QA | 2026-11-02 |  |  | Pending
71009396 | TLG | 11 | Ex-factory | Factory | 2026-11-03 |  |  | Pending
71009405 | KST | 1 | Yarn booking | Factory | 2026-06-25 |  | 2026-06-25 | Done
71009405 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-06 |  | 2026-07-06 | Done
71009405 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-12 | Done late
71009405 | KST | 4 | Size set approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009405 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71009405 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-15 |  | 2026-08-15 | Done
71009405 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-08-18 |  | 2026-08-17 | Done
71009405 | KST | 8 | Knitting start | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71009405 | KST | 9 | Linking start | Factory | 2026-08-26 |  | 2026-08-25 | Done
71009405 | KST | 10 | Final inspection | Karbar QA | 2026-09-28 |  | 2026-09-28 | Done
71009405 | KST | 11 | Ex-factory | Factory | 2026-09-29 |  | 2026-09-29 | Done
71009413 | RVS | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-29 | Done late
71009413 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-08 | Done
71009413 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-12 | Done
71009413 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71009413 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009413 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-20 | Done late
71009413 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71009413 | RVS | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-23 | Done late
71009413 | RVS | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-26 | Done
71009413 | RVS | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-27 | Done
71009413 | RVS | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-09-28 | Done
71009419 | RVS | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-08 | Done
71009419 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009419 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-25 | Done late
71009419 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-10 | Done
71009419 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71009419 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009419 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-29 | Done
71009419 | RVS | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-01 | Done
71009419 | RVS | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-05 | Done
71009419 | RVS | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-07 | Done
71009419 | RVS | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-08 | Done
71009425 | GRL | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-18 | Done
71009425 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009425 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009425 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009425 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-03 | Done late
71009425 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-06 | Done
71009425 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-08 | Done
71009425 | GRL | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-12 | Done
71009425 | GRL | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-15 | Done
71009425 | GRL | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009425 | GRL | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009431 | SLM | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-19 | Done
71009431 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009431 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-02 | Done
71009431 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71009431 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009431 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-07 | Done
71009431 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009431 | SLM | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-13 | Done late
71009431 | SLM | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-16 | Done
71009431 | SLM | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009431 | SLM | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009437 | GRL | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-19 | Done
71009437 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009437 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009437 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-24 | Done late
71009437 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009437 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-15 | Done late | Lab dip re-approval needed for one colour
71009437 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-09 | Done
71009437 | GRL | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-17 | Done late
71009437 | GRL | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-21 | Done late
71009437 | GRL | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009437 | GRL | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009446 | HMR | 1 | Yarn booking | Factory | 2026-07-30 |  | 2026-07-28 | Done
71009446 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71009446 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-15 | Done late
71009446 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009446 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71009446 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-17 | Done
71009446 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-21 |  | 2026-09-21 | Done
71009446 | HMR | 8 | Knitting start | Factory | 2026-09-23 |  | 2026-09-24 | Done late
71009446 | HMR | 9 | Linking start | Factory | 2026-09-29 |  | 2026-09-28 | Done
71009446 | HMR | 10 | Final inspection | Karbar QA | 2026-11-01 |  |  | Pending
71009446 | HMR | 11 | Ex-factory | Factory | 2026-11-02 |  |  | Pending
71009453 | BLF | 1 | Yarn booking | Factory | 2026-06-28 |  | 2026-06-28 | Done
71009453 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-08 |  | 2026-07-09 | Done late
71009453 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-11 | Done
71009453 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-01 | Done
71009453 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009453 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-17 |  | 2026-08-20 | Done late
71009453 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-20 |  | 2026-08-20 | Done
71009453 | BLF | 8 | Knitting start | Factory | 2026-08-22 |  | 2026-08-22 | Done
71009453 | BLF | 9 | Linking start | Factory | 2026-08-27 |  | 2026-08-25 | Done
71009453 | BLF | 10 | Final inspection | Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71009453 | BLF | 11 | Ex-factory | Factory | 2026-10-01 |  | 2026-10-01 | Done
71009462 | HMR | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009462 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-21 | Done late
71009462 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-26 | Done late
71009462 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009462 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71009462 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-09-07 | Done late | Yarn held at customs 4 days
71009462 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-08-31 | Done
71009462 | HMR | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-09 | Done late
71009462 | HMR | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-13 | Done late
71009462 | HMR | 10 | Final inspection | Karbar QA | 2026-10-12 |  |  | Overdue
71009462 | HMR | 11 | Ex-factory | Factory | 2026-10-13 |  |  | Overdue
71009470 | IRB | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009470 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009470 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-02 | Done late
71009470 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009470 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-02 | Done late
71009470 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-10 | Done late | Lab dip re-approval needed for one colour
71009470 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-09 | Done late
71009470 | IRB | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-13 | Done late
71009470 | IRB | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-16 | Done
71009470 | IRB | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71009470 | IRB | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71009475 | OKH | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-19 | Done
71009475 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009475 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009475 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71009475 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009475 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-08 | Done late
71009475 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009475 | OKH | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-12 | Done
71009475 | OKH | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-15 | Done
71009475 | OKH | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009475 | OKH | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009478 | OKH | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-27 | Done late
71009478 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009478 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-11 | Done late
71009478 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-29 | Done
71009478 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71009478 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-15 | Done late
71009478 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009478 | OKH | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009478 | OKH | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009478 | OKH | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009478 | OKH | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009481 | CLB | 1 | Yarn booking | Factory | 2026-07-05 |  | 2026-07-05 | Done
71009481 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71009481 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009481 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71009481 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71009481 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-24 |  | 2026-08-27 | Done late
71009481 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-08-27 |  | 2026-08-27 | Done
71009481 | CLB | 8 | Knitting start | Factory | 2026-08-29 |  | 2026-08-30 | Done late
71009481 | CLB | 9 | Linking start | Factory | 2026-09-03 |  | 2026-09-02 | Done
71009481 | CLB | 10 | Final inspection | Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71009481 | CLB | 11 | Ex-factory | Factory | 2026-10-08 |  | 2026-10-08 | Done
71009490 | SLM | 1 | Yarn booking | Factory | 2026-08-04 |  | 2026-08-02 | Done
71009490 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009490 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-18 | Done
71009490 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-08 | Done
71009490 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71009490 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-23 |  | 2026-09-29 | Done late | Yarn held at customs 4 days
71009490 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-26 |  | 2026-09-26 | Done
71009490 | SLM | 8 | Knitting start | Factory | 2026-09-28 |  | 2026-10-01 | Done late
71009490 | SLM | 9 | Linking start | Factory | 2026-10-04 |  | 2026-10-05 | Done late
71009490 | SLM | 10 | Final inspection | Karbar QA | 2026-11-05 |  |  | Pending
71009490 | SLM | 11 | Ex-factory | Factory | 2026-11-07 |  |  | Pending
71009499 | FNS | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-06 | Done
71009499 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009499 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009499 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71009499 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71009499 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009499 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-09-01 | Done late
71009499 | FNS | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-02 | Done late
71009499 | FNS | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-06 | Done
71009499 | FNS | 10 | Final inspection | Karbar QA | 2026-10-10 |  | 2026-10-10 | Done
71009499 | FNS | 11 | Ex-factory | Factory | 2026-10-11 |  | 2026-10-11 | Done
71009505 | SVP | 1 | Yarn booking | Factory | 2026-07-12 |  | 2026-07-14 | Done late
71009505 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-22 | Done
71009505 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-27 | Done
71009505 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71009505 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71009505 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-31 |  | 2026-08-30 | Done
71009505 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-03 |  | 2026-09-03 | Done
71009505 | SVP | 8 | Knitting start | Factory | 2026-09-05 |  | 2026-09-05 | Done
71009505 | SVP | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-08 | Done
71009505 | SVP | 10 | Final inspection | Karbar QA | 2026-10-14 |  |  | Overdue
71009505 | SVP | 11 | Ex-factory | Factory | 2026-10-15 |  |  | Pending
71009509 | SND | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-22 | Done
71009509 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-05 | Done late
71009509 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009509 | SND | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009509 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-06 | Done
71009509 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-14 | Done late
71009509 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-15 | Done
71009509 | SND | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009509 | SND | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-22 | Done
71009509 | SND | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009509 | SND | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009517 | SLM | 1 | Yarn booking | Factory | 2026-07-29 |  | 2026-07-29 | Done
71009517 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71009517 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-12 | Done
71009517 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009517 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71009517 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-24 | Done late | Lab dip re-approval needed for one colour
71009517 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-20 |  | 2026-09-22 | Done late
71009517 | SLM | 8 | Knitting start | Factory | 2026-09-22 |  | 2026-09-27 | Done late
71009517 | SLM | 9 | Linking start | Factory | 2026-09-28 |  | 2026-09-30 | Done late
71009517 | SLM | 10 | Final inspection | Karbar QA | 2026-10-31 |  |  | Pending
71009517 | SLM | 11 | Ex-factory | Factory | 2026-11-01 |  |  | Pending
71009523 | LTF | 1 | Yarn booking | Factory | 2026-07-30 |  | 2026-07-29 | Done
71009523 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-09 | Done
71009523 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009523 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009523 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71009523 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-17 | Done
71009523 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-21 |  | 2026-09-20 | Done
71009523 | LTF | 8 | Knitting start | Factory | 2026-09-23 |  | 2026-09-23 | Done
71009523 | LTF | 9 | Linking start | Factory | 2026-09-29 |  | 2026-09-27 | Done
71009523 | LTF | 10 | Final inspection | Karbar QA | 2026-11-01 |  |  | Pending
71009523 | LTF | 11 | Ex-factory | Factory | 2026-11-02 |  |  | Pending
71009530 | FNS | 1 | Yarn booking | Factory | 2026-08-02 |  | 2026-08-04 | Done late
71009530 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-10 | Done
71009530 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-15 | Done
71009530 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-03 | Done
71009530 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-17 | Done late
71009530 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-21 |  | 2026-09-23 | Done late
71009530 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-09-24 |  | 2026-09-24 | Done
71009530 | FNS | 8 | Knitting start | Factory | 2026-09-26 |  | 2026-09-26 | Done
71009530 | FNS | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-29 | Done
71009530 | FNS | 10 | Final inspection | Karbar QA | 2026-11-04 |  |  | Pending
71009530 | FNS | 11 | Ex-factory | Factory | 2026-11-05 |  |  | Pending
71009539 | TLG | 1 | Yarn booking | Factory | 2026-07-01 |  | 2026-07-02 | Done late
71009539 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-11 |  | 2026-07-11 | Done
71009539 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009539 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71009539 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-13 | Done
71009539 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-20 |  | 2026-08-20 | Done
71009539 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-08-23 |  | 2026-08-22 | Done
71009539 | TLG | 8 | Knitting start | Factory | 2026-08-25 |  | 2026-08-26 | Done late
71009539 | TLG | 9 | Linking start | Factory | 2026-08-31 |  | 2026-08-30 | Done
71009539 | TLG | 10 | Final inspection | Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71009539 | TLG | 11 | Ex-factory | Factory | 2026-10-04 |  | 2026-10-04 | Done
71009547 | SLM | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71009547 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-08 | Done late
71009547 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009547 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009547 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009547 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-23 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009547 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-20 | Done late
71009547 | SLM | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-26 | Done late
71009547 | SLM | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-29 | Done late
71009547 | SLM | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009547 | SLM | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009551 | LTF | 1 | Yarn booking | Factory | 2026-07-21 |  | 2026-07-21 | Done
71009551 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009551 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-03 | Done
71009551 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71009551 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009551 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-09 |  | 2026-09-07 | Done
71009551 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-12 |  | 2026-09-14 | Done late
71009551 | LTF | 8 | Knitting start | Factory | 2026-09-14 |  | 2026-09-14 | Done
71009551 | LTF | 9 | Linking start | Factory | 2026-09-20 |  | 2026-09-17 | Done
71009551 | LTF | 10 | Final inspection | Karbar QA | 2026-10-22 |  |  | Pending
71009551 | LTF | 11 | Ex-factory | Factory | 2026-10-24 |  |  | Pending
71009554 | TLG | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-30 | Done late
71009554 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-08 | Done late
71009554 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009554 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009554 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009554 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-16 | Done
71009554 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-17 | Done
71009554 | TLG | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-22 | Done late
71009554 | TLG | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-26 | Done
71009554 | TLG | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009554 | TLG | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009559 | SVP | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-04 | Done
71009559 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71009559 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009559 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009559 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71009559 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-24 |  | 2026-09-24 | Done
71009559 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-28 |  | 2026-09-28 | Done
71009559 | SVP | 8 | Knitting start | Factory | 2026-09-30 |  | 2026-10-01 | Done late
71009559 | SVP | 9 | Linking start | Factory | 2026-10-06 |  | 2026-10-05 | Done
71009559 | SVP | 10 | Final inspection | Karbar QA | 2026-11-08 |  |  | Pending
71009559 | SVP | 11 | Ex-factory | Factory | 2026-11-09 |  |  | Pending
71009567 | KST | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-06 | Done
71009567 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71009567 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71009567 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-09 | Done
71009567 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-22 | Done late
71009567 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-26 |  | 2026-09-28 | Done late
71009567 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-09-29 |  | 2026-09-29 | Done
71009567 | KST | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71009567 | KST | 9 | Linking start | Factory | 2026-10-07 |  | 2026-10-06 | Done
71009567 | KST | 10 | Final inspection | Karbar QA | 2026-11-09 |  |  | Pending
71009567 | KST | 11 | Ex-factory | Factory | 2026-11-10 |  |  | Pending
71009573 | GRL | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-06 | Done
71009573 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71009573 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71009573 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-08 | Done
71009573 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71009573 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-26 |  | 2026-09-27 | Done late
71009573 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-29 |  | 2026-09-28 | Done
71009573 | GRL | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71009573 | GRL | 9 | Linking start | Factory | 2026-10-07 |  | 2026-10-06 | Done
71009573 | GRL | 10 | Final inspection | Karbar QA | 2026-11-09 |  |  | Pending
71009573 | GRL | 11 | Ex-factory | Factory | 2026-11-10 |  |  | Pending
71009582 | BLF | 1 | Yarn booking | Factory | 2026-06-30 |  | 2026-07-01 | Done late
71009582 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-09 |  | 2026-07-08 | Done
71009582 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-15 |  | 2026-07-15 | Done
71009582 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-04 | Done
71009582 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009582 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-19 |  | 2026-08-18 | Done
71009582 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-08-22 |  | 2026-08-22 | Done
71009582 | BLF | 8 | Knitting start | Factory | 2026-08-24 |  | 2026-08-24 | Done
71009582 | BLF | 9 | Linking start | Factory | 2026-08-30 |  | 2026-08-27 | Done
71009582 | BLF | 10 | Final inspection | Karbar QA | 2026-10-01 |  | 2026-09-30 | Done
71009582 | BLF | 11 | Ex-factory | Factory | 2026-10-03 |  | 2026-10-01 | Done
71009586 | MDW | 1 | Yarn booking | Factory | 2026-07-02 |  | 2026-06-30 | Done
71009586 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-13 |  | 2026-07-15 | Done late
71009586 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-18 | Done
71009586 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009586 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-19 | Done late
71009586 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-22 |  | 2026-08-20 | Done
71009586 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-08-25 |  | 2026-08-24 | Done
71009586 | MDW | 8 | Knitting start | Factory | 2026-08-27 |  | 2026-08-27 | Done
71009586 | MDW | 9 | Linking start | Factory | 2026-09-02 |  | 2026-08-31 | Done
71009586 | MDW | 10 | Final inspection | Karbar QA | 2026-10-05 |  | 2026-10-05 | Done
71009586 | MDW | 11 | Ex-factory | Factory | 2026-10-06 |  | 2026-10-06 | Done
71009594 | LTF | 1 | Yarn booking | Factory | 2026-07-14 |  | 2026-07-12 | Done
71009594 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009594 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71009594 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-18 | Done
71009594 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-29 | Done late
71009594 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-02 |  | 2026-09-02 | Done
71009594 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-05 |  | 2026-09-05 | Done
71009594 | LTF | 8 | Knitting start | Factory | 2026-09-07 |  | 2026-09-07 | Done
71009594 | LTF | 9 | Linking start | Factory | 2026-09-13 |  | 2026-09-10 | Done
71009594 | LTF | 10 | Final inspection | Karbar QA | 2026-10-15 |  |  | Pending
71009594 | LTF | 11 | Ex-factory | Factory | 2026-10-17 |  |  | Pending
71009600 | IRB | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009600 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-27 | Done late
71009600 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009600 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009600 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-09-01 | Done late
71009600 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-12 | Done late | Lab dip re-approval needed for one colour
71009600 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71009600 | IRB | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-14 | Done late
71009600 | IRB | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71009600 | IRB | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009600 | IRB | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009605 | TLG | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-19 | Done late
71009605 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-27 | Done
71009605 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71009605 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71009605 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-08-31 | Done
71009605 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-08 | Done late
71009605 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71009605 | TLG | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71009605 | TLG | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-14 | Done
71009605 | TLG | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71009605 | TLG | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71009613 | WSM | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-18 | Done
71009613 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-28 | Done
71009613 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-04 | Done late
71009613 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71009613 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-03 | Done late
71009613 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-15 | Done late | Yarn held at customs 4 days
71009613 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-10 | Done late
71009613 | WSM | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-17 | Done late
71009613 | WSM | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-21 | Done late
71009613 | WSM | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71009613 | WSM | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71009618 | BLF | 1 | Yarn booking | Factory | 2026-07-25 |  | 2026-07-25 | Done
71009618 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-06 | Done late
71009618 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-08 | Done
71009618 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-27 | Done
71009618 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-08 | Done
71009618 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-13 |  | 2026-09-13 | Done
71009618 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71009618 | BLF | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009618 | BLF | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009618 | BLF | 10 | Final inspection | Karbar QA | 2026-10-27 |  |  | Pending
71009618 | BLF | 11 | Ex-factory | Factory | 2026-10-28 |  |  | Pending
71009622 | SLM | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-08 | Done
71009622 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-20 | Done late
71009622 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-20 | Done
71009622 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71009622 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-24 | Done late
71009622 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-26 | Done
71009622 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-29 | Done
71009622 | SLM | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71009622 | SLM | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71009622 | SLM | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71009622 | SLM | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71009626 | HMR | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-11 | Done late
71009626 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71009626 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71009626 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-15 | Done late
71009626 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71009626 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-28 | Done
71009626 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71009626 | HMR | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71009626 | HMR | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71009626 | HMR | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71009626 | HMR | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71009631 | GRL | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009631 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-28 | Done late
71009631 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009631 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009631 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-09-01 | Done late
71009631 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-12 | Done late | Yarn held at customs 4 days
71009631 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-07 | Done
71009631 | GRL | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-14 | Done late
71009631 | GRL | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71009631 | GRL | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009631 | GRL | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009634 | WTH | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-20 | Done late
71009634 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-27 | Done
71009634 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-02 | Done
71009634 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009634 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-01 | Done
71009634 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-07 | Done
71009634 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009634 | WTH | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-13 | Done late
71009634 | WTH | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-16 | Done
71009634 | WTH | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009634 | WTH | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009642 | AMB | 1 | Yarn booking | Factory | 2026-07-22 |  | 2026-07-22 | Done
71009642 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-01 | Done
71009642 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009642 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71009642 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71009642 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-10 | Done
71009642 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-13 |  | 2026-09-10 | Done
71009642 | AMB | 8 | Knitting start | Factory | 2026-09-15 |  | 2026-09-16 | Done late
71009642 | AMB | 9 | Linking start | Factory | 2026-09-21 |  | 2026-09-20 | Done
71009642 | AMB | 10 | Final inspection | Karbar QA | 2026-10-24 |  |  | Pending
71009642 | AMB | 11 | Ex-factory | Factory | 2026-10-25 |  |  | Pending
71009649 | KST | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009649 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71009649 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-09 | Done late
71009649 | KST | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009649 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-06 | Done
71009649 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-15 | Done late
71009649 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-16 | Done late
71009649 | KST | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009649 | KST | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-22 | Done
71009649 | KST | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009649 | KST | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009654 | IRB | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-26 | Done
71009654 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-03 | Done
71009654 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-12 | Done late
71009654 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009654 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71009654 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-14 | Done
71009654 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-16 | Done
71009654 | IRB | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009654 | IRB | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009654 | IRB | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009654 | IRB | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009661 | RSG | 1 | Yarn booking | Factory | 2026-07-11 |  | 2026-07-09 | Done
71009661 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-21 |  | 2026-07-21 | Done
71009661 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71009661 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-13 | Done
71009661 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71009661 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-30 |  | 2026-08-31 | Done late
71009661 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-09-02 |  | 2026-09-01 | Done
71009661 | RSG | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-03 | Done
71009661 | RSG | 9 | Linking start | Factory | 2026-09-10 |  | 2026-09-07 | Done
71009661 | RSG | 10 | Final inspection | Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71009661 | RSG | 11 | Ex-factory | Factory | 2026-10-14 |  | 2026-10-14 | Done
71009664 | SLM | 1 | Yarn booking | Factory | 2026-07-15 |  | 2026-07-16 | Done late
71009664 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-26 | Done late
71009664 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009664 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71009664 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-30 | Done late
71009664 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-01 | Done
71009664 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-06 |  | 2026-09-07 | Done late
71009664 | SLM | 8 | Knitting start | Factory | 2026-09-08 |  | 2026-09-08 | Done
71009664 | SLM | 9 | Linking start | Factory | 2026-09-14 |  | 2026-09-12 | Done
71009664 | SLM | 10 | Final inspection | Karbar QA | 2026-10-17 |  |  | Pending
71009664 | SLM | 11 | Ex-factory | Factory | 2026-10-18 |  |  | Pending
71009668 | RSG | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009668 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009668 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009668 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009668 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71009668 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71009668 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-15 | Done
71009668 | RSG | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009668 | RSG | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71009668 | RSG | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009668 | RSG | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009676 | TLG | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-15 | Done
71009676 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-25 | Done
71009676 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-01 | Done
71009676 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009676 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-02 | Done late
71009676 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-06 | Done late
71009676 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-06 | Done
71009676 | TLG | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-12 | Done late
71009676 | TLG | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-15 | Done
71009676 | TLG | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71009676 | TLG | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71009680 | SVP | 1 | Yarn booking | Factory | 2026-07-22 |  | 2026-07-22 | Done
71009680 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-03 | Done late
71009680 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-05 | Done
71009680 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-24 | Done
71009680 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-03 | Done
71009680 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-08 | Done
71009680 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-13 |  | 2026-09-15 | Done late
71009680 | SVP | 8 | Knitting start | Factory | 2026-09-15 |  | 2026-09-16 | Done late
71009680 | SVP | 9 | Linking start | Factory | 2026-09-21 |  | 2026-09-20 | Done
71009680 | SVP | 10 | Final inspection | Karbar QA | 2026-10-24 |  |  | Pending
71009680 | SVP | 11 | Ex-factory | Factory | 2026-10-25 |  |  | Pending
71009689 | BLF | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-10 | Done late
71009689 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71009689 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71009689 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-15 | Done late
71009689 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71009689 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-26 | Done
71009689 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-03 | Done late
71009689 | BLF | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71009689 | BLF | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71009689 | BLF | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71009689 | BLF | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71009698 | CPL | 1 | Yarn booking | Factory | 2026-07-08 |  | 2026-07-09 | Done late
71009698 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-18 |  | 2026-07-19 | Done late
71009698 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009698 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71009698 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-26 | Done late | PP sample rejected once (measurement); resubmitted
71009698 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-31 | Done late | Yarn held at customs 4 days
71009698 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-08-30 |  | 2026-08-31 | Done late
71009698 | CPL | 8 | Knitting start | Factory | 2026-09-01 |  | 2026-09-02 | Done late
71009698 | CPL | 9 | Linking start | Factory | 2026-09-07 |  | 2026-09-06 | Done
71009698 | CPL | 10 | Final inspection | Karbar QA | 2026-10-10 |  |  | Overdue
71009698 | CPL | 11 | Ex-factory | Factory | 2026-10-11 |  |  | Overdue
71009703 | SLM | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009703 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-19 |  | 2026-07-19 | Done
71009703 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-25 | Done late
71009703 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-11 | Done
71009703 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009703 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-27 |  | 2026-08-27 | Done
71009703 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-08-31 |  | 2026-09-02 | Done late
71009703 | SLM | 8 | Knitting start | Factory | 2026-09-02 |  | 2026-09-02 | Done
71009703 | SLM | 9 | Linking start | Factory | 2026-09-08 |  | 2026-09-06 | Done
71009703 | SLM | 10 | Final inspection | Karbar QA | 2026-10-11 |  | 2026-10-11 | Done
71009703 | SLM | 11 | Ex-factory | Factory | 2026-10-12 |  | 2026-10-12 | Done
71009712 | CPL | 1 | Yarn booking | Factory | 2026-07-15 |  | 2026-07-15 | Done
71009712 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71009712 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-28 | Done
71009712 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-18 | Done
71009712 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-30 | Done late
71009712 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009712 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71009712 | CPL | 8 | Knitting start | Factory | 2026-09-08 |  | 2026-09-08 | Done
71009712 | CPL | 9 | Linking start | Factory | 2026-09-14 |  | 2026-09-12 | Done
71009712 | CPL | 10 | Final inspection | Karbar QA | 2026-10-17 |  |  | Pending
71009712 | CPL | 11 | Ex-factory | Factory | 2026-10-18 |  |  | Pending
71009719 | GRL | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-19 | Done
71009719 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71009719 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009719 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-20 | Done
71009719 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-03 | Done late
71009719 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-09 | Done late
71009719 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009719 | GRL | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-12 | Done
71009719 | GRL | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-15 | Done
71009719 | GRL | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009719 | GRL | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009724 | TLG | 1 | Yarn booking | Factory | 2026-08-05 |  | 2026-08-05 | Done
71009724 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-15 | Done
71009724 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009724 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71009724 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-21 | Done late
71009724 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-24 |  | 2026-09-24 | Done
71009724 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-27 |  | 2026-09-29 | Done late
71009724 | TLG | 8 | Knitting start | Factory | 2026-09-29 |  | 2026-09-30 | Done late
71009724 | TLG | 9 | Linking start | Factory | 2026-10-05 |  | 2026-10-04 | Done
71009724 | TLG | 10 | Final inspection | Karbar QA | 2026-11-07 |  |  | Pending
71009724 | TLG | 11 | Ex-factory | Factory | 2026-11-08 |  |  | Pending
71009730 | SVP | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009730 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009730 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71009730 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009730 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-23 | Done
71009730 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-08-29 | Done
71009730 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-09-02 | Done late
71009730 | SVP | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71009730 | SVP | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-08 | Done
71009730 | SVP | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009730 | SVP | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009736 | PBB | 1 | Yarn booking | Factory | 2026-07-09 |  | 2026-07-09 | Done
71009736 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-20 |  | 2026-07-20 | Done
71009736 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-25 | Done
71009736 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-12 | Done
71009736 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71009736 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-29 |  | 2026-08-30 | Done late
71009736 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-01 |  | 2026-08-30 | Done
71009736 | PBB | 8 | Knitting start | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71009736 | PBB | 9 | Linking start | Factory | 2026-09-09 |  | 2026-09-08 | Done
71009736 | PBB | 10 | Final inspection | Karbar QA | 2026-10-12 |  | 2026-10-11 | Done
71009736 | PBB | 11 | Ex-factory | Factory | 2026-10-13 |  | 2026-10-12 | Done
71009741 | IRB | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-18 | Done
71009741 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-28 | Done
71009741 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-03 | Done late
71009741 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71009741 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-06 | Done late | PP sample rejected once (measurement); resubmitted
71009741 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-14 | Done late | Lab dip re-approval needed for one colour
71009741 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71009741 | IRB | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-17 | Done late
71009741 | IRB | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-21 | Done late
71009741 | IRB | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71009741 | IRB | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71009748 | WTH | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009748 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009748 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71009748 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009748 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71009748 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71009748 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-14 | Done
71009748 | WTH | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009748 | WTH | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71009748 | WTH | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009748 | WTH | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009756 | RVS | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-25 | Done
71009756 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71009756 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-12 | Done late
71009756 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-27 | Done
71009756 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-10 | Done late
71009756 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-15 | Done late
71009756 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009756 | RVS | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009756 | RVS | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009756 | RVS | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009756 | RVS | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009759 | TLG | 1 | Yarn booking | Factory | 2026-08-05 |  | 2026-08-05 | Done
71009759 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-15 | Done
71009759 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-19 | Done
71009759 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-07 | Done
71009759 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-17 | Done
71009759 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-24 |  | 2026-09-27 | Done late
71009759 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71009759 | TLG | 8 | Knitting start | Factory | 2026-09-29 |  | 2026-09-29 | Done
71009759 | TLG | 9 | Linking start | Factory | 2026-10-05 |  | 2026-10-03 | Done
71009759 | TLG | 10 | Final inspection | Karbar QA | 2026-11-07 |  |  | Pending
71009759 | TLG | 11 | Ex-factory | Factory | 2026-11-08 |  |  | Pending
71009763 | MDW | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-08 | Done
71009763 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-16 | Done
71009763 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-25 | Done late
71009763 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-13 | Done late
71009763 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-22 | Done
71009763 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-27 | Done
71009763 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71009763 | MDW | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71009763 | MDW | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71009763 | MDW | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71009763 | MDW | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71009770 | LTF | 1 | Yarn booking | Factory | 2026-07-07 |  | 2026-07-07 | Done
71009770 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-16 |  | 2026-07-16 | Done
71009770 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-07-22 |  | 2026-07-20 | Done
71009770 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-11 | Done
71009770 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-22 | Done late
71009770 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-08-26 |  | 2026-08-27 | Done late
71009770 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-08-29 |  | 2026-08-29 | Done
71009770 | LTF | 8 | Knitting start | Factory | 2026-08-31 |  | 2026-09-01 | Done late
71009770 | LTF | 9 | Linking start | Factory | 2026-09-06 |  | 2026-09-05 | Done
71009770 | LTF | 10 | Final inspection | Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71009770 | LTF | 11 | Ex-factory | Factory | 2026-10-10 |  | 2026-10-10 | Done
71009779 | IRB | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-27 | Done late
71009779 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009779 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-09 | Done
71009779 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009779 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71009779 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-14 | Done
71009779 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-16 | Done
71009779 | IRB | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009779 | IRB | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009779 | IRB | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009779 | IRB | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009785 | BLF | 1 | Yarn booking | Factory | 2026-07-30 |  | 2026-07-30 | Done
71009785 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-10 | Done late
71009785 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009785 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009785 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71009785 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-17 | Done
71009785 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-09-21 |  | 2026-09-22 | Done late
71009785 | BLF | 8 | Knitting start | Factory | 2026-09-23 |  | 2026-09-23 | Done
71009785 | BLF | 9 | Linking start | Factory | 2026-09-29 |  | 2026-09-27 | Done
71009785 | BLF | 10 | Final inspection | Karbar QA | 2026-11-01 |  |  | Pending
71009785 | BLF | 11 | Ex-factory | Factory | 2026-11-02 |  |  | Pending
71009789 | GRL | 1 | Yarn booking | Factory | 2026-08-11 |  | 2026-08-11 | Done
71009789 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-19 | Done
71009789 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71009789 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-13 | Done
71009789 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71009789 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-30 |  | 2026-10-08 | Done late | Yarn held at customs 4 days
71009789 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-03 |  | 2026-10-01 | Done
71009789 | GRL | 8 | Knitting start | Factory | 2026-10-05 |  | 2026-10-10 | Done late
71009789 | GRL | 9 | Linking start | Factory | 2026-10-11 |  | 2026-10-13 | Done late
71009789 | GRL | 10 | Final inspection | Karbar QA | 2026-11-12 |  |  | Pending
71009789 | GRL | 11 | Ex-factory | Factory | 2026-11-14 |  |  | Pending
71009797 | MDW | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-12 | Done
71009797 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009797 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009797 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71009797 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71009797 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-03 | Done late
71009797 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-07 | Done late
71009797 | MDW | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-08 | Done late
71009797 | MDW | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-12 | Done
71009797 | MDW | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71009797 | MDW | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71009802 | KST | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-13 | Done
71009802 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71009802 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009802 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71009802 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-29 | Done late
71009802 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-01 | Done
71009802 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-03 | Done
71009802 | KST | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-08 | Done late
71009802 | KST | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-12 | Done
71009802 | KST | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71009802 | KST | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71009811 | TLG | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-15 | Done
71009811 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71009811 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71009811 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-22 | Done late
71009811 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-31 | Done
71009811 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-07 | Done late
71009811 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-10 | Done late
71009811 | TLG | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-12 | Done late
71009811 | TLG | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-15 | Done
71009811 | TLG | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71009811 | TLG | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71009816 | LTF | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009816 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009816 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-10 | Done late
71009816 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009816 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71009816 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-20 | Done late | Lab dip re-approval needed for one colour
71009816 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-17 | Done late
71009816 | LTF | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-22 | Done late
71009816 | LTF | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-26 | Done late
71009816 | LTF | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009816 | LTF | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009823 | TLG | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-23 | Done
71009823 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009823 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-12 | Done late
71009823 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009823 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-10 | Done late
71009823 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-14 | Done
71009823 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009823 | TLG | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-20 | Done late
71009823 | TLG | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-23 | Done
71009823 | TLG | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009823 | TLG | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009828 | FNS | 1 | Yarn booking | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71009828 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009828 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009828 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71009828 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71009828 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-17 | Done
71009828 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-09-20 |  | 2026-09-20 | Done
71009828 | FNS | 8 | Knitting start | Factory | 2026-09-22 |  | 2026-09-22 | Done
71009828 | FNS | 9 | Linking start | Factory | 2026-09-28 |  | 2026-09-26 | Done
71009828 | FNS | 10 | Final inspection | Karbar QA | 2026-10-31 |  |  | Pending
71009828 | FNS | 11 | Ex-factory | Factory | 2026-11-01 |  |  | Pending
71009831 | SLM | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-30 | Done late
71009831 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009831 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71009831 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-08-30 | Done
71009831 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009831 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-24 | Done late | Yarn held at customs 4 days
71009831 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-17 | Done
71009831 | SLM | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-26 | Done late
71009831 | SLM | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-29 | Done late
71009831 | SLM | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009831 | SLM | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009840 | WSM | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71009840 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009840 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71009840 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-02 | Done late
71009840 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009840 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-14 | Done
71009840 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-17 | Done
71009840 | WSM | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-21 | Done
71009840 | WSM | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-24 | Done
71009840 | WSM | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009840 | WSM | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009845 | WSM | 1 | Yarn booking | Factory | 2026-07-29 |  | 2026-07-29 | Done
71009845 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009845 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71009845 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-09-02 |  | 2026-08-31 | Done
71009845 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71009845 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-20 | Done late
71009845 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-09-20 |  | 2026-09-20 | Done
71009845 | WSM | 8 | Knitting start | Factory | 2026-09-22 |  | 2026-09-22 | Done
71009845 | WSM | 9 | Linking start | Factory | 2026-09-28 |  | 2026-09-26 | Done
71009845 | WSM | 10 | Final inspection | Karbar QA | 2026-10-31 |  |  | Pending
71009845 | WSM | 11 | Ex-factory | Factory | 2026-11-01 |  |  | Pending
71009854 | HMR | 1 | Yarn booking | Factory | 2026-08-01 |  | 2026-08-03 | Done late
71009854 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-11 | Done
71009854 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71009854 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71009854 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-15 | Done
71009854 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-20 |  | 2026-09-19 | Done
71009854 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71009854 | HMR | 8 | Knitting start | Factory | 2026-09-24 |  | 2026-09-24 | Done
71009854 | HMR | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-28 | Done
71009854 | HMR | 10 | Final inspection | Karbar QA | 2026-11-03 |  |  | Pending
71009854 | HMR | 11 | Ex-factory | Factory | 2026-11-04 |  |  | Pending
71009861 | GRL | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-10 | Done late
71009861 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-17 | Done
71009861 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71009861 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-12 | Done
71009861 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-24 | Done late
71009861 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-29 | Done late
71009861 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71009861 | GRL | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71009861 | GRL | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71009861 | GRL | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71009861 | GRL | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71009864 | AMB | 1 | Yarn booking | Factory | 2026-07-14 |  | 2026-07-16 | Done late
71009864 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-23 |  | 2026-07-23 | Done
71009864 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-29 | Done
71009864 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-17 | Done
71009864 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009864 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-02 |  | 2026-09-03 | Done late
71009864 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-05 |  | 2026-09-05 | Done
71009864 | AMB | 8 | Knitting start | Factory | 2026-09-07 |  | 2026-09-08 | Done late
71009864 | AMB | 9 | Linking start | Factory | 2026-09-13 |  | 2026-09-12 | Done
71009864 | AMB | 10 | Final inspection | Karbar QA | 2026-10-15 |  |  | Pending
71009864 | AMB | 11 | Ex-factory | Factory | 2026-10-17 |  |  | Pending
71009873 | KST | 1 | Yarn booking | Factory | 2026-08-19 |  | 2026-08-20 | Done late
71009873 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71009873 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009873 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-24 | Done late
71009873 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-04 | Done late
71009873 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71009873 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-11 |  | 2026-10-11 | Done
71009873 | KST | 8 | Knitting start | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009873 | KST | 9 | Linking start | Factory | 2026-10-19 |  |  | Pending
71009873 | KST | 10 | Final inspection | Karbar QA | 2026-11-21 |  |  | Pending
71009873 | KST | 11 | Ex-factory | Factory | 2026-11-22 |  |  | Pending
71009876 | OKH | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-19 | Done
71009876 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009876 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009876 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71009876 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-04 | Done
71009876 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-10 | Done late
71009876 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009876 | OKH | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71009876 | OKH | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71009876 | OKH | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71009876 | OKH | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71009879 | LTF | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-28 | Done late
71009879 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009879 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-11 | Done late
71009879 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71009879 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-08 | Done
71009879 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-16 | Done late
71009879 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-15 | Done
71009879 | LTF | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009879 | LTF | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009879 | LTF | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009879 | LTF | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009888 | GRL | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-27 | Done late
71009888 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-04 | Done
71009888 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71009888 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-27 | Done
71009888 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71009888 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-14 | Done
71009888 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009888 | GRL | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-19 | Done
71009888 | GRL | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-22 | Done
71009888 | GRL | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009888 | GRL | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009893 | FNS | 1 | Yarn booking | Factory | 2026-07-15 |  | 2026-07-14 | Done
71009893 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-25 |  | 2026-07-26 | Done late
71009893 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-28 | Done
71009893 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-18 | Done
71009893 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-27 | Done
71009893 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-03 | Done
71009893 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-09-06 |  | 2026-09-06 | Done
71009893 | FNS | 8 | Knitting start | Factory | 2026-09-08 |  | 2026-09-08 | Done
71009893 | FNS | 9 | Linking start | Factory | 2026-09-14 |  | 2026-09-12 | Done
71009893 | FNS | 10 | Final inspection | Karbar QA | 2026-10-17 |  |  | Pending
71009893 | FNS | 11 | Ex-factory | Factory | 2026-10-18 |  |  | Pending
71009899 | OKH | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009899 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71009899 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009899 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009899 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-08 | Done late
71009899 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-13 | Done late
71009899 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-17 | Done late
71009899 | OKH | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009899 | OKH | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71009899 | OKH | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009899 | OKH | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009905 | CLB | 1 | Yarn booking | Factory | 2026-08-02 |  | 2026-08-03 | Done late
71009905 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71009905 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71009905 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71009905 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71009905 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-21 |  | 2026-09-19 | Done
71009905 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-09-24 |  | 2026-09-24 | Done
71009905 | CLB | 8 | Knitting start | Factory | 2026-09-26 |  | 2026-09-26 | Done
71009905 | CLB | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-29 | Done
71009905 | CLB | 10 | Final inspection | Karbar QA | 2026-11-04 |  |  | Pending
71009905 | CLB | 11 | Ex-factory | Factory | 2026-11-05 |  |  | Pending
71009910 | SND | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-08 | Done
71009910 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-18 | Done
71009910 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-20 | Done
71009910 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71009910 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-23 | Done late
71009910 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-27 | Done
71009910 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71009910 | SND | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71009910 | SND | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71009910 | SND | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71009910 | SND | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71009918 | TLG | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71009918 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71009918 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-26 | Done
71009918 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71009918 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-26 | Done
71009918 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-01 | Done
71009918 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-05 | Done
71009918 | TLG | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-07 | Done
71009918 | TLG | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-11 | Done
71009918 | TLG | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71009918 | TLG | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71009921 | BRW | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-16 | Done
71009921 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-27 |  | 2026-07-28 | Done late
71009921 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-02 | Done late
71009921 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009921 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-02 | Done late
71009921 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-05 |  | 2026-09-08 | Done late
71009921 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-09-08 |  | 2026-09-10 | Done late
71009921 | BRW | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71009921 | BRW | 9 | Linking start | Factory | 2026-09-16 |  | 2026-09-14 | Done
71009921 | BRW | 10 | Final inspection | Karbar QA | 2026-10-19 |  |  | Pending
71009921 | BRW | 11 | Ex-factory | Factory | 2026-10-20 |  |  | Pending
71009928 | PBB | 1 | Yarn booking | Factory | 2026-07-21 |  | 2026-07-23 | Done late
71009928 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-30 |  | 2026-08-01 | Done late
71009928 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-06 | Done late
71009928 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-23 | Done
71009928 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009928 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-09 |  | 2026-09-10 | Done late
71009928 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71009928 | PBB | 8 | Knitting start | Factory | 2026-09-14 |  | 2026-09-15 | Done late
71009928 | PBB | 9 | Linking start | Factory | 2026-09-20 |  | 2026-09-19 | Done
71009928 | PBB | 10 | Final inspection | Karbar QA | 2026-10-22 |  |  | Pending
71009928 | PBB | 11 | Ex-factory | Factory | 2026-10-24 |  |  | Pending
71009933 | TLG | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009933 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-02 | Done
71009933 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71009933 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-25 | Done
71009933 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-06 | Done
71009933 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71009933 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-17 | Done late
71009933 | TLG | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71009933 | TLG | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-22 | Done
71009933 | TLG | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009933 | TLG | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71009941 | FNS | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-06 | Done
71009941 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-17 | Done late
71009941 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-18 | Done
71009941 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009941 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71009941 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-24 |  | 2026-09-30 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009941 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-09-28 |  | 2026-09-30 | Done late
71009941 | FNS | 8 | Knitting start | Factory | 2026-09-30 |  | 2026-10-03 | Done late
71009941 | FNS | 9 | Linking start | Factory | 2026-10-06 |  | 2026-10-06 | Done
71009941 | FNS | 10 | Final inspection | Karbar QA | 2026-11-08 |  |  | Pending
71009941 | FNS | 11 | Ex-factory | Factory | 2026-11-09 |  |  | Pending
71009945 | GRL | 1 | Yarn booking | Factory | 2026-07-16 |  | 2026-07-14 | Done
71009945 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-26 |  | 2026-07-26 | Done
71009945 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-07-30 |  | 2026-08-01 | Done late
71009945 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71009945 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71009945 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-03 |  | 2026-09-12 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009945 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-07 |  | 2026-09-09 | Done late
71009945 | GRL | 8 | Knitting start | Factory | 2026-09-09 |  | 2026-09-14 | Done late
71009945 | GRL | 9 | Linking start | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71009945 | GRL | 10 | Final inspection | Karbar QA | 2026-10-18 |  |  | Pending
71009945 | GRL | 11 | Ex-factory | Factory | 2026-10-19 |  |  | Pending
71009949 | IRB | 1 | Yarn booking | Factory | 2026-07-19 |  | 2026-07-18 | Done
71009949 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-29 |  | 2026-07-30 | Done late
71009949 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-04 | Done late
71009949 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-24 | Done late
71009949 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-03 | Done late
71009949 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-07 |  | 2026-09-05 | Done
71009949 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-10 |  | 2026-09-10 | Done
71009949 | IRB | 8 | Knitting start | Factory | 2026-09-12 |  | 2026-09-12 | Done
71009949 | IRB | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-15 | Done
71009949 | IRB | 10 | Final inspection | Karbar QA | 2026-10-21 |  |  | Pending
71009949 | IRB | 11 | Ex-factory | Factory | 2026-10-22 |  |  | Pending
71009955 | SLM | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-26 | Done
71009955 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009955 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-11 | Done late
71009955 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-29 | Done
71009955 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-14 | Done late | PP sample rejected once (measurement); resubmitted
71009955 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-22 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71009955 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71009955 | SLM | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-24 | Done late
71009955 | SLM | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-28 | Done late
71009955 | SLM | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71009955 | SLM | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71009961 | AMB | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71009961 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-05 | Done
71009961 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-10 | Done
71009961 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009961 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71009961 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-17 | Done late
71009961 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-17 | Done
71009961 | AMB | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-22 | Done late
71009961 | AMB | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-26 | Done
71009961 | AMB | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009961 | AMB | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009965 | BRW | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71009965 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009965 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009965 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71009965 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-06 | Done late
71009965 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71009965 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71009965 | BRW | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71009965 | BRW | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71009965 | BRW | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71009965 | BRW | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71009974 | TLG | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71009974 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71009974 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-13 | Done late
71009974 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71009974 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-09 | Done
71009974 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-17 | Done late
71009974 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-19 | Done
71009974 | TLG | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-21 | Done
71009974 | TLG | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-24 | Done
71009974 | TLG | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71009974 | TLG | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71009980 | CLB | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-13 | Done
71009980 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71009980 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009980 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71009980 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71009980 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-01 | Done
71009980 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-06 | Done late
71009980 | CLB | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-07 | Done
71009980 | CLB | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-11 | Done
71009980 | CLB | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71009980 | CLB | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71009983 | WTH | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-13 | Done
71009983 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-20 | Done
71009983 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-25 | Done
71009983 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71009983 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-10-01 | Done late | PP sample rejected once (measurement); resubmitted
71009983 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-07 | Done late | Lab dip re-approval needed for one colour
71009983 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-06 | Done late
71009983 | WTH | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-10 | Done late
71009983 | WTH | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-13 | Done
71009983 | WTH | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71009983 | WTH | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71009991 | RSG | 1 | Yarn booking | Factory | 2026-08-15 |  | 2026-08-13 | Done
71009991 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71009991 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71009991 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71009991 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-09-29 |  | 2026-10-01 | Done late
71009991 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-04 |  | 2026-10-06 | Done late
71009991 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71009991 | RSG | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-10 | Done late
71009991 | RSG | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-13 | Done
71009991 | RSG | 10 | Final inspection | Karbar QA | 2026-11-17 |  |  | Pending
71009991 | RSG | 11 | Ex-factory | Factory | 2026-11-18 |  |  | Pending
71009995 | TLG | 1 | Yarn booking | Factory | 2026-07-21 |  | 2026-07-21 | Done
71009995 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-30 |  | 2026-07-30 | Done
71009995 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71009995 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-27 | Done late
71009995 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71009995 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-09 |  | 2026-09-09 | Done
71009995 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-12 |  | 2026-09-12 | Done
71009995 | TLG | 8 | Knitting start | Factory | 2026-09-14 |  | 2026-09-14 | Done
71009995 | TLG | 9 | Linking start | Factory | 2026-09-20 |  | 2026-09-17 | Done
71009995 | TLG | 10 | Final inspection | Karbar QA | 2026-10-22 |  |  | Pending
71009995 | TLG | 11 | Ex-factory | Factory | 2026-10-24 |  |  | Pending
71009999 | BLF | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71009999 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71009999 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-09 | Done late
71009999 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71009999 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-09 | Done late
71009999 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-10 | Done
71009999 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-16 | Done late
71009999 | BLF | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71009999 | BLF | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71009999 | BLF | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71009999 | BLF | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71010004 | MDW | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71010004 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-03 | Done
71010004 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-09 | Done late
71010004 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010004 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010004 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71010004 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-15 | Done
71010004 | MDW | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71010004 | MDW | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71010004 | MDW | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71010004 | MDW | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71010013 | IRB | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-27 | Done late
71010013 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71010013 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71010013 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71010013 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010013 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-21 | Done late | Dyed yarn delayed at spinner (shade re-dye)
71010013 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71010013 | IRB | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-23 | Done late
71010013 | IRB | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-27 | Done late
71010013 | IRB | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71010013 | IRB | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71010019 | KST | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010019 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-02 | Done late
71010019 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-03 | Done
71010019 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-22 | Done
71010019 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71010019 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-10 |  | 2026-10-08 | Done
71010019 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-13 |  | 2026-10-12 | Done
71010019 | KST | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010019 | KST | 9 | Linking start | Factory | 2026-10-21 |  |  | Pending
71010019 | KST | 10 | Final inspection | Karbar QA | 2026-11-23 |  |  | Pending
71010019 | KST | 11 | Ex-factory | Factory | 2026-11-24 |  |  | Pending
71010023 | TLG | 1 | Yarn booking | Factory | 2026-07-18 |  | 2026-07-18 | Done
71010023 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-07-28 |  | 2026-07-28 | Done
71010023 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71010023 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71010023 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-03 | Done late
71010023 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-06 |  | 2026-09-03 | Done
71010023 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-09-09 |  | 2026-09-09 | Done
71010023 | TLG | 8 | Knitting start | Factory | 2026-09-10 |  | 2026-09-10 | Done
71010023 | TLG | 9 | Linking start | Factory | 2026-09-17 |  | 2026-09-14 | Done
71010023 | TLG | 10 | Final inspection | Karbar QA | 2026-10-20 |  |  | Pending
71010023 | TLG | 11 | Ex-factory | Factory | 2026-10-21 |  |  | Pending
71010028 | GRL | 1 | Yarn booking | Factory | 2026-07-22 |  | 2026-07-22 | Done
71010028 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-01 |  | 2026-07-30 | Done
71010028 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-05 | Done
71010028 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71010028 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-10 | Done late | PP sample rejected once (measurement); resubmitted
71010028 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-17 | Done late | Lab dip re-approval needed for one colour
71010028 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-13 |  | 2026-09-13 | Done
71010028 | GRL | 8 | Knitting start | Factory | 2026-09-15 |  | 2026-09-20 | Done late
71010028 | GRL | 9 | Linking start | Factory | 2026-09-21 |  | 2026-09-23 | Done late
71010028 | GRL | 10 | Final inspection | Karbar QA | 2026-10-24 |  |  | Pending
71010028 | GRL | 11 | Ex-factory | Factory | 2026-10-25 |  |  | Pending
71010035 | FNS | 1 | Yarn booking | Factory | 2026-07-28 |  | 2026-07-28 | Done
71010035 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71010035 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71010035 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71010035 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71010035 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-16 |  | 2026-09-17 | Done late
71010035 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-09-19 |  | 2026-09-17 | Done
71010035 | FNS | 8 | Knitting start | Factory | 2026-09-21 |  | 2026-09-21 | Done
71010035 | FNS | 9 | Linking start | Factory | 2026-09-27 |  | 2026-09-24 | Done
71010035 | FNS | 10 | Final inspection | Karbar QA | 2026-10-29 |  |  | Pending
71010035 | FNS | 11 | Ex-factory | Factory | 2026-10-31 |  |  | Pending
71010041 | BRW | 1 | Yarn booking | Factory | 2026-08-02 |  | 2026-08-02 | Done
71010041 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-12 | Done
71010041 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-18 | Done late
71010041 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010041 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010041 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-21 |  | 2026-09-22 | Done late
71010041 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-09-24 |  | 2026-09-23 | Done
71010041 | BRW | 8 | Knitting start | Factory | 2026-09-26 |  | 2026-09-27 | Done late
71010041 | BRW | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-30 | Done
71010041 | BRW | 10 | Final inspection | Karbar QA | 2026-11-04 |  |  | Pending
71010041 | BRW | 11 | Ex-factory | Factory | 2026-11-05 |  |  | Pending
71010048 | PBB | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-06 | Done
71010048 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-20 | Done late
71010048 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71010048 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71010048 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-22 | Done
71010048 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-29 | Done late
71010048 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-10-01 | Done late
71010048 | PBB | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71010048 | PBB | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71010048 | PBB | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71010048 | PBB | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71010056 | KST | 1 | Yarn booking | Factory | 2026-08-12 |  | 2026-08-13 | Done late
71010056 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71010056 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-25 | Done
71010056 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-15 | Done
71010056 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-27 | Done late
71010056 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-09-29 | Done
71010056 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-04 |  | 2026-10-03 | Done
71010056 | KST | 8 | Knitting start | Factory | 2026-10-06 |  | 2026-10-07 | Done late
71010056 | KST | 9 | Linking start | Factory | 2026-10-12 |  | 2026-10-11 | Done
71010056 | KST | 10 | Final inspection | Karbar QA | 2026-11-14 |  |  | Pending
71010056 | KST | 11 | Ex-factory | Factory | 2026-11-15 |  |  | Pending
71010063 | TLG | 1 | Yarn booking | Factory | 2026-08-25 |  | 2026-08-27 | Done late
71010063 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-05 | Done late
71010063 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-08 | Done
71010063 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71010063 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-08 | Done
71010063 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-14 |  | 2026-10-14 | Done
71010063 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-10-17 |  |  | Pending
71010063 | TLG | 8 | Knitting start | Factory | 2026-10-19 |  |  | Pending
71010063 | TLG | 9 | Linking start | Factory | 2026-10-25 |  |  | Pending
71010063 | TLG | 10 | Final inspection | Karbar QA | 2026-11-26 |  |  | Pending
71010063 | TLG | 11 | Ex-factory | Factory | 2026-11-28 |  |  | Pending
71010071 | SVP | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71010071 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71010071 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-04 | Done
71010071 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-26 | Done
71010071 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-08 | Done late
71010071 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-10 | Done
71010071 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-09-14 |  | 2026-09-15 | Done late
71010071 | SVP | 8 | Knitting start | Factory | 2026-09-16 |  | 2026-09-16 | Done
71010071 | SVP | 9 | Linking start | Factory | 2026-09-22 |  | 2026-09-20 | Done
71010071 | SVP | 10 | Final inspection | Karbar QA | 2026-10-25 |  |  | Pending
71010071 | SVP | 11 | Ex-factory | Factory | 2026-10-26 |  |  | Pending
71010074 | HMR | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71010074 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-02 |  | 2026-08-02 | Done
71010074 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-06 | Done
71010074 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010074 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010074 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-10 | Done
71010074 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-14 |  | 2026-09-14 | Done
71010074 | HMR | 8 | Knitting start | Factory | 2026-09-16 |  | 2026-09-16 | Done
71010074 | HMR | 9 | Linking start | Factory | 2026-09-22 |  | 2026-09-20 | Done
71010074 | HMR | 10 | Final inspection | Karbar QA | 2026-10-25 |  |  | Pending
71010074 | HMR | 11 | Ex-factory | Factory | 2026-10-26 |  |  | Pending
71010078 | HMR | 1 | Yarn booking | Factory | 2026-07-30 |  | 2026-08-01 | Done late
71010078 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-11 | Done late
71010078 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-16 | Done late
71010078 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010078 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-15 | Done late
71010078 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-19 |  | 2026-09-17 | Done
71010078 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-09-22 |  | 2026-09-21 | Done
71010078 | HMR | 8 | Knitting start | Factory | 2026-09-24 |  | 2026-09-26 | Done late
71010078 | HMR | 9 | Linking start | Factory | 2026-09-30 |  | 2026-09-29 | Done
71010078 | HMR | 10 | Final inspection | Karbar QA | 2026-11-02 |  |  | Pending
71010078 | HMR | 11 | Ex-factory | Factory | 2026-11-03 |  |  | Pending
71010082 | BLF | 1 | Yarn booking | Factory | 2026-08-15 |  | 2026-08-16 | Done late
71010082 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-24 | Done
71010082 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71010082 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-21 | Done late
71010082 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71010082 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-04 |  | 2026-10-01 | Done
71010082 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71010082 | BLF | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010082 | BLF | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-12 | Done
71010082 | BLF | 10 | Final inspection | Karbar QA | 2026-11-17 |  |  | Pending
71010082 | BLF | 11 | Ex-factory | Factory | 2026-11-18 |  |  | Pending
71010086 | AMB | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-18 | Done
71010086 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71010086 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-05 | Done late
71010086 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010086 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-04 | Done
71010086 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71010086 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71010086 | AMB | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71010086 | AMB | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010086 | AMB | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010086 | AMB | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010094 | BLF | 1 | Yarn booking | Factory | 2026-08-25 |  | 2026-08-25 | Done
71010094 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010094 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010094 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-28 | Done
71010094 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-08 | Done
71010094 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-14 |  | 2026-10-14 | Done
71010094 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-17 |  |  | Pending
71010094 | BLF | 8 | Knitting start | Factory | 2026-10-19 |  |  | Pending
71010094 | BLF | 9 | Linking start | Factory | 2026-10-25 |  |  | Pending
71010094 | BLF | 10 | Final inspection | Karbar QA | 2026-11-26 |  |  | Pending
71010094 | BLF | 11 | Ex-factory | Factory | 2026-11-28 |  |  | Pending
71010103 | BLF | 1 | Yarn booking | Factory | 2026-07-22 |  | 2026-07-23 | Done late
71010103 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-01 |  | 2026-08-02 | Done late
71010103 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-06 |  | 2026-08-08 | Done late
71010103 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71010103 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-06 | Done late
71010103 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-10 |  | 2026-09-10 | Done
71010103 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-09-13 |  | 2026-09-13 | Done
71010103 | BLF | 8 | Knitting start | Factory | 2026-09-15 |  | 2026-09-15 | Done
71010103 | BLF | 9 | Linking start | Factory | 2026-09-21 |  | 2026-09-19 | Done
71010103 | BLF | 10 | Final inspection | Karbar QA | 2026-10-24 |  |  | Pending
71010103 | BLF | 11 | Ex-factory | Factory | 2026-10-25 |  |  | Pending
71010108 | IRB | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-25 | Done late
71010108 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71010108 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71010108 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010108 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-09 | Done late
71010108 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71010108 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-13 | Done
71010108 | IRB | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71010108 | IRB | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-21 | Done
71010108 | IRB | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71010108 | IRB | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71010112 | SLM | 1 | Yarn booking | Factory | 2026-07-23 |  | 2026-07-23 | Done
71010112 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-03 |  | 2026-08-01 | Done
71010112 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-09 | Done late
71010112 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-25 | Done
71010112 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010112 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-12 |  | 2026-09-12 | Done
71010112 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-09-15 |  | 2026-09-15 | Done
71010112 | SLM | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71010112 | SLM | 9 | Linking start | Factory | 2026-09-23 |  | 2026-09-22 | Done
71010112 | SLM | 10 | Final inspection | Karbar QA | 2026-10-26 |  |  | Pending
71010112 | SLM | 11 | Ex-factory | Factory | 2026-10-27 |  |  | Pending
71010120 | GRL | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-08 | Done late
71010120 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-17 | Done
71010120 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-23 | Done late
71010120 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71010120 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-22 | Done late
71010120 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-26 |  | 2026-10-04 | Done late | Yarn held at customs 4 days
71010120 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-29 |  | 2026-09-29 | Done
71010120 | GRL | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-06 | Done late
71010120 | GRL | 9 | Linking start | Factory | 2026-10-07 |  | 2026-10-10 | Done late
71010120 | GRL | 10 | Final inspection | Karbar QA | 2026-11-09 |  |  | Pending
71010120 | GRL | 11 | Ex-factory | Factory | 2026-11-10 |  |  | Pending
71010128 | AMB | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-23 | Done
71010128 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-03 | Done late
71010128 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-08 | Done late
71010128 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-24 | Done
71010128 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-06 | Done
71010128 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-13 | Done late
71010128 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  | 2026-10-14 | Done
71010128 | AMB | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010128 | AMB | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010128 | AMB | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010128 | AMB | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010135 | LTF | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-27 | Done
71010135 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010135 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71010135 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-09-30 | Done
71010135 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010135 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010135 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010135 | LTF | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010135 | LTF | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010135 | LTF | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010135 | LTF | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010139 | AMB | 1 | Yarn booking | Factory | 2026-07-29 |  | 2026-07-29 | Done
71010139 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-06 | Done
71010139 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71010139 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-01 | Done
71010139 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71010139 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-20 | Done late
71010139 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-09-20 |  | 2026-09-20 | Done
71010139 | AMB | 8 | Knitting start | Factory | 2026-09-22 |  | 2026-09-22 | Done
71010139 | AMB | 9 | Linking start | Factory | 2026-09-28 |  | 2026-09-26 | Done
71010139 | AMB | 10 | Final inspection | Karbar QA | 2026-10-31 |  |  | Pending
71010139 | AMB | 11 | Ex-factory | Factory | 2026-11-01 |  |  | Pending
71010145 | OKH | 1 | Yarn booking | Factory | 2026-07-29 |  | 2026-07-30 | Done late
71010145 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-08 |  | 2026-08-08 | Done
71010145 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71010145 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-01 | Done
71010145 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-13 | Done late
71010145 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-17 |  | 2026-09-17 | Done
71010145 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-09-20 |  | 2026-09-20 | Done
71010145 | OKH | 8 | Knitting start | Factory | 2026-09-22 |  | 2026-09-23 | Done late
71010145 | OKH | 9 | Linking start | Factory | 2026-09-28 |  | 2026-09-27 | Done
71010145 | OKH | 10 | Final inspection | Karbar QA | 2026-10-31 |  |  | Pending
71010145 | OKH | 11 | Ex-factory | Factory | 2026-11-01 |  |  | Pending
71010153 | IRB | 1 | Yarn booking | Factory | 2026-08-01 |  | 2026-08-01 | Done
71010153 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-12 | Done late
71010153 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71010153 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-07 | Done late
71010153 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-17 | Done late
71010153 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-20 |  | 2026-09-22 | Done late
71010153 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-09-23 |  | 2026-09-23 | Done
71010153 | IRB | 8 | Knitting start | Factory | 2026-09-24 |  | 2026-09-26 | Done late
71010153 | IRB | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-29 | Done
71010153 | IRB | 10 | Final inspection | Karbar QA | 2026-11-03 |  |  | Pending
71010153 | IRB | 11 | Ex-factory | Factory | 2026-11-04 |  |  | Pending
71010162 | KST | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-10 | Done late
71010162 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71010162 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-22 | Done
71010162 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71010162 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010162 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-30 | Done late
71010162 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-09-30 | Done
71010162 | KST | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71010162 | KST | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71010162 | KST | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010162 | KST | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010170 | BLF | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-11 | Done late
71010170 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71010170 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-23 | Done
71010170 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-12 | Done
71010170 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-22 | Done
71010170 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-29 | Done late
71010170 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-09-29 | Done
71010170 | BLF | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71010170 | BLF | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-07 | Done
71010170 | BLF | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010170 | BLF | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010174 | BRW | 1 | Yarn booking | Factory | 2026-08-12 |  | 2026-08-12 | Done
71010174 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-20 | Done
71010174 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010174 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010174 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-28 | Done late
71010174 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-04 | Done late
71010174 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-04 |  | 2026-10-04 | Done
71010174 | BRW | 8 | Knitting start | Factory | 2026-10-06 |  | 2026-10-06 | Done
71010174 | BRW | 9 | Linking start | Factory | 2026-10-12 |  | 2026-10-10 | Done
71010174 | BRW | 10 | Final inspection | Karbar QA | 2026-11-14 |  |  | Pending
71010174 | BRW | 11 | Ex-factory | Factory | 2026-11-15 |  |  | Pending
71010180 | HMR | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71010180 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71010180 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010180 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71010180 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-30 | Done late
71010180 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-01 | Done
71010180 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-05 | Done
71010180 | HMR | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-10 | Done late
71010180 | HMR | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-13 | Done
71010180 | HMR | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010180 | HMR | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010188 | SND | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-15 | Done late
71010188 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-25 | Done late
71010188 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-31 | Done late
71010188 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-16 | Done
71010188 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-27 | Done
71010188 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-03 | Done
71010188 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-06 | Done
71010188 | SND | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010188 | SND | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-12 | Done
71010188 | SND | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010188 | SND | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010193 | RSG | 1 | Yarn booking | Factory | 2026-08-15 |  | 2026-08-15 | Done
71010193 | RSG | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-23 | Done
71010193 | RSG | 3 | Fit sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-27 | Done
71010193 | RSG | 4 | Size set approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71010193 | RSG | 5 | PP sample approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71010193 | RSG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-04 |  | 2026-10-03 | Done
71010193 | RSG | 7 | PP meeting | Factory + Karbar QA | 2026-10-07 |  | 2026-10-06 | Done
71010193 | RSG | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010193 | RSG | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-12 | Done
71010193 | RSG | 10 | Final inspection | Karbar QA | 2026-11-17 |  |  | Pending
71010193 | RSG | 11 | Ex-factory | Factory | 2026-11-18 |  |  | Pending
71010198 | CPL | 1 | Yarn booking | Factory | 2026-08-16 |  | 2026-08-15 | Done
71010198 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-25 | Done
71010198 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-31 | Done
71010198 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010198 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-29 | Done
71010198 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-05 |  | 2026-10-07 | Done late
71010198 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71010198 | CPL | 8 | Knitting start | Factory | 2026-10-10 |  | 2026-10-11 | Done late
71010198 | CPL | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-14 | Done
71010198 | CPL | 10 | Final inspection | Karbar QA | 2026-11-18 |  |  | Pending
71010198 | CPL | 11 | Ex-factory | Factory | 2026-11-19 |  |  | Pending
71010202 | IRB | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010202 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-27 | Done
71010202 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010202 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010202 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-05 | Done late
71010202 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-07 | Done
71010202 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-13 | Done late
71010202 | IRB | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71010202 | IRB | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010202 | IRB | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010202 | IRB | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010210 | CLB | 1 | Yarn booking | Factory | 2026-07-25 |  | 2026-07-26 | Done late
71010210 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-04 |  | 2026-08-02 | Done
71010210 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-09 |  | 2026-08-11 | Done late
71010210 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010210 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-08 | Done
71010210 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-13 |  | 2026-09-15 | Done late
71010210 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-09-16 |  | 2026-09-16 | Done
71010210 | CLB | 8 | Knitting start | Factory | 2026-09-17 |  | 2026-09-17 | Done
71010210 | CLB | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-21 | Done
71010210 | CLB | 10 | Final inspection | Karbar QA | 2026-10-27 |  |  | Pending
71010210 | CLB | 11 | Ex-factory | Factory | 2026-10-28 |  |  | Pending
71010217 | GRL | 1 | Yarn booking | Factory | 2026-08-01 |  | 2026-08-01 | Done
71010217 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-11 |  | 2026-08-13 | Done late
71010217 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-16 |  | 2026-08-18 | Done late
71010217 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71010217 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-17 | Done late
71010217 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-20 |  | 2026-09-24 | Done late | Yarn held at customs 4 days
71010217 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-23 |  | 2026-09-21 | Done
71010217 | GRL | 8 | Knitting start | Factory | 2026-09-24 |  | 2026-09-27 | Done late
71010217 | GRL | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-30 | Done
71010217 | GRL | 10 | Final inspection | Karbar QA | 2026-11-03 |  |  | Pending
71010217 | GRL | 11 | Ex-factory | Factory | 2026-11-04 |  |  | Pending
71010221 | LTF | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-09 | Done late
71010221 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-20 | Done late
71010221 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71010221 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71010221 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-23 | Done late
71010221 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-27 | Done
71010221 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71010221 | LTF | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71010221 | LTF | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71010221 | LTF | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71010221 | LTF | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71010229 | KST | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-10 | Done late
71010229 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71010229 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71010229 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-10 | Done
71010229 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010229 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-28 | Done
71010229 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010229 | KST | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71010229 | KST | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71010229 | KST | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010229 | KST | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010238 | GRL | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-06 | Done
71010238 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71010238 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-25 | Done late
71010238 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-10 | Done
71010238 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-24 | Done late
71010238 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-29 | Done late
71010238 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010238 | GRL | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71010238 | GRL | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-07 | Done
71010238 | GRL | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010238 | GRL | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010244 | GRL | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-26 | Done
71010244 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-03 | Done
71010244 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-10 | Done
71010244 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-29 | Done
71010244 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-10 | Done late
71010244 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-15 | Done late
71010244 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-16 | Done
71010244 | GRL | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-20 | Done late
71010244 | GRL | 9 | Linking start | Factory | 2026-09-24 |  | 2026-09-23 | Done
71010244 | GRL | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71010244 | GRL | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71010250 | BRW | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-13 | Done
71010250 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-20 | Done
71010250 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-25 | Done
71010250 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-15 | Done
71010250 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71010250 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-01 | Done
71010250 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-07 | Done late
71010250 | BRW | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-07 | Done
71010250 | BRW | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-11 | Done
71010250 | BRW | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71010250 | BRW | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71010256 | RVS | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-11 | Done
71010256 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71010256 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010256 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010256 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010256 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-04 | Done late
71010256 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-04 | Done
71010256 | RVS | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010256 | RVS | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-12 | Done
71010256 | RVS | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010256 | RVS | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010261 | FNS | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-22 | Done
71010261 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-02 | Done late
71010261 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-07 | Done late
71010261 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-28 | Done late
71010261 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-06 | Done
71010261 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-13 | Done late
71010261 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  |  | Overdue
71010261 | FNS | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010261 | FNS | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010261 | FNS | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010261 | FNS | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010267 | HMR | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-22 | Done
71010267 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71010267 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-05 | Done
71010267 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-28 | Done late
71010267 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-08 | Done late
71010267 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-13 | Done late
71010267 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  |  | Overdue
71010267 | HMR | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010267 | HMR | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010267 | HMR | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010267 | HMR | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010274 | GRL | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-20 | Done
71010274 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71010274 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010274 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-24 | Done
71010274 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010274 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  |  | Overdue
71010274 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  |  | Pending
71010274 | GRL | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010274 | GRL | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010274 | GRL | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010274 | GRL | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010279 | GRL | 1 | Yarn booking | Factory | 2026-08-26 |  | 2026-08-26 | Done
71010279 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-03 | Done
71010279 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-08 | Done
71010279 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-29 | Done
71010279 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-11 | Done late
71010279 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-15 |  |  | Pending
71010279 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-18 |  |  | Pending
71010279 | GRL | 8 | Knitting start | Factory | 2026-10-20 |  |  | Pending
71010279 | GRL | 9 | Linking start | Factory | 2026-10-26 |  |  | Pending
71010279 | GRL | 10 | Final inspection | Karbar QA | 2026-11-28 |  |  | Pending
71010279 | GRL | 11 | Ex-factory | Factory | 2026-11-29 |  |  | Pending
71010283 | BLF | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-27 | Done
71010283 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010283 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71010283 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010283 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010283 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010283 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010283 | BLF | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010283 | BLF | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010283 | BLF | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010283 | BLF | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010289 | KST | 1 | Yarn booking | Factory | 2026-09-02 |  | 2026-09-03 | Done late
71010289 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71010289 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-15 | Done
71010289 | KST | 4 | Size set approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71010289 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71010289 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-22 |  |  | Pending
71010289 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-25 |  |  | Pending
71010289 | KST | 8 | Knitting start | Factory | 2026-10-27 |  |  | Pending
71010289 | KST | 9 | Linking start | Factory | 2026-11-02 |  |  | Pending
71010289 | KST | 10 | Final inspection | Karbar QA | 2026-12-05 |  |  | Pending
71010289 | KST | 11 | Ex-factory | Factory | 2026-12-06 |  |  | Pending
71010297 | KST | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-10 | Done late
71010297 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-17 | Done
71010297 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-22 | Done
71010297 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-14 | Done late
71010297 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-24 | Done late
71010297 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-28 | Done late
71010297 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-29 | Done
71010297 | KST | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71010297 | KST | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71010297 | KST | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71010297 | KST | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71010305 | GRL | 1 | Yarn booking | Factory | 2026-07-26 |  | 2026-07-27 | Done late
71010305 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-05 |  | 2026-08-05 | Done
71010305 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-10 |  | 2026-08-08 | Done
71010305 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71010305 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-10 | Done late
71010305 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-14 |  | 2026-09-22 | Done late | Yarn held at customs 4 days
71010305 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-09-17 |  | 2026-09-17 | Done
71010305 | GRL | 8 | Knitting start | Factory | 2026-09-19 |  | 2026-09-24 | Done late
71010305 | GRL | 9 | Linking start | Factory | 2026-09-24 |  | 2026-10-07 | Done late | Linking machines tied up on other POs; 13 M/C allocated from 7 Oct
71010305 | GRL | 10 | Final inspection | Karbar QA | 2026-10-28 |  |  | Pending
71010305 | GRL | 11 | Ex-factory | Factory | 2026-10-29 |  |  | Pending
71010309 | KST | 1 | Yarn booking | Factory | 2026-08-04 |  | 2026-08-04 | Done
71010309 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-13 |  | 2026-08-13 | Done
71010309 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-18 | Done
71010309 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-08 |  | 2026-09-08 | Done
71010309 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010309 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-23 |  | 2026-09-24 | Done late
71010309 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-09-26 |  | 2026-09-24 | Done
71010309 | KST | 8 | Knitting start | Factory | 2026-09-28 |  | 2026-09-29 | Done late
71010309 | KST | 9 | Linking start | Factory | 2026-10-04 |  | 2026-10-03 | Done
71010309 | KST | 10 | Final inspection | Karbar QA | 2026-11-05 |  |  | Pending
71010309 | KST | 11 | Ex-factory | Factory | 2026-11-07 |  |  | Pending
71010318 | MDW | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-22 | Done late
71010318 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-31 | Done
71010318 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71010318 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-22 | Done
71010318 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-06 | Done late
71010318 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-10 |  | 2026-10-08 | Done
71010318 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71010318 | MDW | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010318 | MDW | 9 | Linking start | Factory | 2026-10-21 |  |  | Pending
71010318 | MDW | 10 | Final inspection | Karbar QA | 2026-11-23 |  |  | Pending
71010318 | MDW | 11 | Ex-factory | Factory | 2026-11-24 |  |  | Pending
71010321 | CPL | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-06 | Done
71010321 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-16 | Done
71010321 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71010321 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71010321 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71010321 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-26 |  | 2026-09-28 | Done late
71010321 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-09-29 |  | 2026-09-28 | Done
71010321 | CPL | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71010321 | CPL | 9 | Linking start | Factory | 2026-10-07 |  | 2026-10-05 | Done
71010321 | CPL | 10 | Final inspection | Karbar QA | 2026-11-09 |  |  | Pending
71010321 | CPL | 11 | Ex-factory | Factory | 2026-11-10 |  |  | Pending
71010325 | GRL | 1 | Yarn booking | Factory | 2026-08-16 |  | 2026-08-16 | Done
71010325 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71010325 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-02 | Done late
71010325 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010325 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71010325 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-05 |  | 2026-10-08 | Done late | Yarn held at customs 4 days
71010325 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71010325 | GRL | 8 | Knitting start | Factory | 2026-10-10 |  | 2026-10-10 | Done
71010325 | GRL | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-13 | Done
71010325 | GRL | 10 | Final inspection | Karbar QA | 2026-11-18 |  |  | Pending
71010325 | GRL | 11 | Ex-factory | Factory | 2026-11-19 |  |  | Pending
71010334 | RVS | 1 | Yarn booking | Factory | 2026-08-25 |  | 2026-08-25 | Done
71010334 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-02 | Done
71010334 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-08 | Done
71010334 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-27 | Done
71010334 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-08 | Done
71010334 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-14 |  |  | Overdue
71010334 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-10-17 |  |  | Pending
71010334 | RVS | 8 | Knitting start | Factory | 2026-10-19 |  |  | Pending
71010334 | RVS | 9 | Linking start | Factory | 2026-10-25 |  |  | Pending
71010334 | RVS | 10 | Final inspection | Karbar QA | 2026-11-26 |  |  | Pending
71010334 | RVS | 11 | Ex-factory | Factory | 2026-11-28 |  |  | Pending
71010343 | MDW | 1 | Yarn booking | Factory | 2026-09-03 |  | 2026-09-03 | Done
71010343 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-14 | Done late
71010343 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010343 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-08 | Done
71010343 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010343 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-22 |  |  | Pending
71010343 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-10-26 |  |  | Pending
71010343 | MDW | 8 | Knitting start | Factory | 2026-10-28 |  |  | Pending
71010343 | MDW | 9 | Linking start | Factory | 2026-11-03 |  |  | Pending
71010343 | MDW | 10 | Final inspection | Karbar QA | 2026-12-06 |  |  | Pending
71010343 | MDW | 11 | Ex-factory | Factory | 2026-12-07 |  |  | Pending
71010350 | BRW | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-10 | Done late
71010350 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-16 | Done
71010350 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71010350 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71010350 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-22 | Done
71010350 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-27 | Done
71010350 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-10-01 | Done late
71010350 | BRW | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71010350 | BRW | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71010350 | BRW | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71010350 | BRW | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71010354 | HMR | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-08 | Done
71010354 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71010354 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71010354 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-14 | Done late
71010354 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010354 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-10-04 | Done late | Lab dip re-approval needed for one colour
71010354 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010354 | HMR | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-06 | Done late
71010354 | HMR | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-10 | Done late
71010354 | HMR | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010354 | HMR | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010357 | AMB | 1 | Yarn booking | Factory | 2026-08-19 |  | 2026-08-17 | Done
71010357 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010357 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010357 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-21 | Done
71010357 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-03 | Done
71010357 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-11 | Done late
71010357 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-11 |  | 2026-10-12 | Done late
71010357 | AMB | 8 | Knitting start | Factory | 2026-10-13 |  | 2026-10-14 | Done late
71010357 | AMB | 9 | Linking start | Factory | 2026-10-19 |  |  | Pending
71010357 | AMB | 10 | Final inspection | Karbar QA | 2026-11-21 |  |  | Pending
71010357 | AMB | 11 | Ex-factory | Factory | 2026-11-22 |  |  | Pending
71010360 | GRL | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-22 | Done
71010360 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-08-31 | Done
71010360 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010360 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-24 | Done
71010360 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-11 | Done late | PP sample rejected once (measurement); resubmitted
71010360 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 | 2026-10-19 |  | Overdue | Dyed yarn delayed at spinner (shade re-dye)
71010360 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  | 2026-10-14 | Done
71010360 | GRL | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010360 | GRL | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010360 | GRL | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010360 | GRL | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010369 | TLG | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-29 | Done late
71010369 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010369 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-14 | Done late
71010369 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010369 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-13 | Done late
71010369 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010369 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010369 | TLG | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010369 | TLG | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010369 | TLG | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010369 | TLG | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010377 | SVP | 1 | Yarn booking | Factory | 2026-08-30 |  | 2026-08-30 | Done
71010377 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010377 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-14 | Done
71010377 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-06 | Done late
71010377 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-10-14 |  |  | Overdue
71010377 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-19 |  |  | Pending
71010377 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-10-22 |  |  | Pending
71010377 | SVP | 8 | Knitting start | Factory | 2026-10-24 |  |  | Pending
71010377 | SVP | 9 | Linking start | Factory | 2026-10-29 |  |  | Pending
71010377 | SVP | 10 | Final inspection | Karbar QA | 2026-12-02 |  |  | Pending
71010377 | SVP | 11 | Ex-factory | Factory | 2026-12-03 |  |  | Pending
71010380 | PBB | 1 | Yarn booking | Factory | 2026-08-02 |  | 2026-08-04 | Done late
71010380 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-12 |  | 2026-08-11 | Done
71010380 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-15 | Done
71010380 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010380 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-17 | Done late
71010380 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-21 |  | 2026-09-23 | Done late
71010380 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-09-24 |  | 2026-09-22 | Done
71010380 | PBB | 8 | Knitting start | Factory | 2026-09-26 |  | 2026-09-26 | Done
71010380 | PBB | 9 | Linking start | Factory | 2026-10-01 |  | 2026-09-29 | Done
71010380 | PBB | 10 | Final inspection | Karbar QA | 2026-11-04 |  |  | Pending
71010380 | PBB | 11 | Ex-factory | Factory | 2026-11-05 |  |  | Pending
71010389 | IRB | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-06 | Done
71010389 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-17 | Done
71010389 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-25 | Done late
71010389 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-14 | Done late
71010389 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-22 | Done
71010389 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-29 | Done late
71010389 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010389 | IRB | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71010389 | IRB | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-07 | Done
71010389 | IRB | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010389 | IRB | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010394 | TLG | 1 | Yarn booking | Factory | 2026-08-30 |  | 2026-08-30 | Done
71010394 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010394 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-16 | Done late
71010394 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-06 | Done late
71010394 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-14 | Done
71010394 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-19 |  |  | Pending
71010394 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-10-22 |  |  | Pending
71010394 | TLG | 8 | Knitting start | Factory | 2026-10-24 |  |  | Pending
71010394 | TLG | 9 | Linking start | Factory | 2026-10-29 |  |  | Pending
71010394 | TLG | 10 | Final inspection | Karbar QA | 2026-12-02 |  |  | Pending
71010394 | TLG | 11 | Ex-factory | Factory | 2026-12-03 |  |  | Pending
71010398 | AMB | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-07 | Done late
71010398 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-15 | Done
71010398 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71010398 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71010398 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71010398 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 |  |  | Pending
71010398 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71010398 | AMB | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71010398 | AMB | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010398 | AMB | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71010398 | AMB | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71010402 | FNS | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-22 | Done
71010402 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71010402 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-08 | Done late
71010402 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-29 | Done late
71010402 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010402 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-12 | Done
71010402 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  |  | Pending
71010402 | FNS | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010402 | FNS | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010402 | FNS | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010402 | FNS | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010407 | MDW | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-05 | Done
71010407 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-17 | Done late
71010407 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010407 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-08 | Done
71010407 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010407 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010407 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010407 | MDW | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010407 | MDW | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010407 | MDW | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010407 | MDW | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010412 | LTF | 1 | Yarn booking | Factory | 2026-08-05 |  | 2026-08-05 | Done
71010412 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-15 |  | 2026-08-15 | Done
71010412 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71010412 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010412 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-20 | Done late
71010412 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-24 |  | 2026-09-24 | Done
71010412 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-09-27 |  | 2026-09-27 | Done
71010412 | LTF | 8 | Knitting start | Factory | 2026-09-29 |  | 2026-09-29 | Done
71010412 | LTF | 9 | Linking start | Factory | 2026-10-05 |  | 2026-10-03 | Done
71010412 | LTF | 10 | Final inspection | Karbar QA | 2026-11-07 |  |  | Pending
71010412 | LTF | 11 | Ex-factory | Factory | 2026-11-08 |  |  | Pending
71010417 | SLM | 1 | Yarn booking | Factory | 2026-08-11 |  | 2026-08-10 | Done
71010417 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71010417 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71010417 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-14 | Done
71010417 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010417 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-30 |  | 2026-09-30 | Done
71010417 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71010417 | SLM | 8 | Knitting start | Factory | 2026-10-05 |  | 2026-10-05 | Done
71010417 | SLM | 9 | Linking start | Factory | 2026-10-11 |  | 2026-10-08 | Done
71010417 | SLM | 10 | Final inspection | Karbar QA | 2026-11-12 |  |  | Pending
71010417 | SLM | 11 | Ex-factory | Factory | 2026-11-14 |  |  | Pending
71010426 | GRL | 1 | Yarn booking | Factory | 2026-08-15 |  | 2026-08-15 | Done
71010426 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-24 | Done
71010426 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71010426 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-17 | Done
71010426 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71010426 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-04 |  | 2026-10-05 | Done late
71010426 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-07 |  | 2026-10-06 | Done
71010426 | GRL | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010426 | GRL | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-12 | Done
71010426 | GRL | 10 | Final inspection | Karbar QA | 2026-11-17 |  |  | Pending
71010426 | GRL | 11 | Ex-factory | Factory | 2026-11-18 |  |  | Pending
71010430 | SLM | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-27 | Done
71010430 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010430 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71010430 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010430 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-12 | Done late
71010430 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-15 |  |  | Pending
71010430 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-19 |  |  | Pending
71010430 | SLM | 8 | Knitting start | Factory | 2026-10-21 |  |  | Pending
71010430 | SLM | 9 | Linking start | Factory | 2026-10-27 |  |  | Pending
71010430 | SLM | 10 | Final inspection | Karbar QA | 2026-11-29 |  |  | Pending
71010430 | SLM | 11 | Ex-factory | Factory | 2026-11-30 |  |  | Pending
71010435 | BRW | 1 | Yarn booking | Factory | 2026-09-01 |  | 2026-09-01 | Done
71010435 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-12 | Done late
71010435 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-15 | Done
71010435 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-04 | Done
71010435 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71010435 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-21 |  |  | Pending
71010435 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-24 |  |  | Pending
71010435 | BRW | 8 | Knitting start | Factory | 2026-10-26 |  |  | Pending
71010435 | BRW | 9 | Linking start | Factory | 2026-11-01 |  |  | Pending
71010435 | BRW | 10 | Final inspection | Karbar QA | 2026-12-03 |  |  | Pending
71010435 | BRW | 11 | Ex-factory | Factory | 2026-12-05 |  |  | Pending
71010441 | CLB | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-09 | Done late
71010441 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-16 | Done
71010441 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-22 | Done
71010441 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-13 | Done
71010441 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010441 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 |  |  | Pending
71010441 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71010441 | CLB | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71010441 | CLB | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71010441 | CLB | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71010441 | CLB | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71010449 | WTH | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-07 | Done
71010449 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010449 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010449 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-11 | Done
71010449 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010449 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 |  |  | Pending
71010449 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71010449 | WTH | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71010449 | WTH | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71010449 | WTH | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71010449 | WTH | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71010455 | FNS | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-12 | Done
71010455 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-22 | Done
71010455 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010455 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010455 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-30 | Done late
71010455 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-03 | Done
71010455 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-06 | Done
71010455 | FNS | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010455 | FNS | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-12 | Done
71010455 | FNS | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010455 | FNS | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010464 | SND | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-24 | Done late
71010464 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-02 | Done late
71010464 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010464 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-26 | Done
71010464 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-08 | Done late
71010464 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-11 | Done
71010464 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  | 2026-10-12 | Done
71010464 | SND | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010464 | SND | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010464 | SND | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010464 | SND | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010472 | PBB | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-24 | Done late
71010472 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-08-31 | Done
71010472 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010472 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71010472 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71010472 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-11 | Done
71010472 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  | 2026-10-13 | Done
71010472 | PBB | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010472 | PBB | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010472 | PBB | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010472 | PBB | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010478 | WSM | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-12 | Done late
71010478 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-19 | Done
71010478 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010478 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  | 2026-10-14 | Done
71010478 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010478 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 |  |  | Pending
71010478 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-02 |  |  | Pending
71010478 | WSM | 8 | Knitting start | Factory | 2026-11-04 |  |  | Pending
71010478 | WSM | 9 | Linking start | Factory | 2026-11-10 |  |  | Pending
71010478 | WSM | 10 | Final inspection | Karbar QA | 2026-12-13 |  |  | Pending
71010478 | WSM | 11 | Ex-factory | Factory | 2026-12-14 |  |  | Pending
71010487 | SVP | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-09 | Done
71010487 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71010487 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71010487 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71010487 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-24 | Done late
71010487 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-10-01 | Done late
71010487 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010487 | SVP | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71010487 | SVP | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-07 | Done
71010487 | SVP | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010487 | SVP | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010494 | WTH | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-24 | Done late
71010494 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71010494 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010494 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71010494 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010494 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-12 | Done
71010494 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  |  | Pending
71010494 | WTH | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010494 | WTH | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010494 | WTH | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010494 | WTH | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010503 | CPL | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-06 | Done late
71010503 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-15 | Done
71010503 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010503 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010503 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010503 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010503 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010503 | CPL | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010503 | CPL | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010503 | CPL | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010503 | CPL | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010509 | IRB | 1 | Yarn booking | Factory | 2026-08-16 |  | 2026-08-13 | Done
71010509 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71010509 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-29 | Done
71010509 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010509 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-29 | Done
71010509 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-05 |  | 2026-10-06 | Done late
71010509 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-08 |  | 2026-10-08 | Done
71010509 | IRB | 8 | Knitting start | Factory | 2026-10-10 |  | 2026-10-10 | Done
71010509 | IRB | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-13 | Done
71010509 | IRB | 10 | Final inspection | Karbar QA | 2026-11-18 |  |  | Pending
71010509 | IRB | 11 | Ex-factory | Factory | 2026-11-19 |  |  | Pending
71010513 | KST | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-06 | Done
71010513 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010513 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-19 | Done
71010513 | KST | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-08 | Done
71010513 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71010513 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 |  |  | Pending
71010513 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71010513 | KST | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71010513 | KST | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010513 | KST | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71010513 | KST | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71010517 | PBB | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-12 | Done
71010517 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-23 | Done
71010517 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010517 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-15 | Done
71010517 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71010517 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-04 | Done late
71010517 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-10-05 |  | 2026-10-07 | Done late
71010517 | PBB | 8 | Knitting start | Factory | 2026-10-07 |  | 2026-10-08 | Done late
71010517 | PBB | 9 | Linking start | Factory | 2026-10-13 |  | 2026-10-12 | Done
71010517 | PBB | 10 | Final inspection | Karbar QA | 2026-11-15 |  |  | Pending
71010517 | PBB | 11 | Ex-factory | Factory | 2026-11-16 |  |  | Pending
71010524 | CLB | 1 | Yarn booking | Factory | 2026-08-15 |  | 2026-08-16 | Done late
71010524 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-25 |  | 2026-08-25 | Done
71010524 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-29 | Done
71010524 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71010524 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71010524 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-04 |  | 2026-10-04 | Done
71010524 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-07 |  | 2026-10-07 | Done
71010524 | CLB | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010524 | CLB | 9 | Linking start | Factory | 2026-10-15 |  | 2026-10-12 | Done
71010524 | CLB | 10 | Final inspection | Karbar QA | 2026-11-17 |  |  | Pending
71010524 | CLB | 11 | Ex-factory | Factory | 2026-11-18 |  |  | Pending
71010527 | SLM | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-20 | Done
71010527 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-09-01 | Done
71010527 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-08 | Done late
71010527 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-26 | Done
71010527 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-06 | Done
71010527 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-13 | Done late
71010527 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  | 2026-10-14 | Done
71010527 | SLM | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010527 | SLM | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010527 | SLM | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010527 | SLM | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010530 | SLM | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-05 | Done
71010530 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-15 | Done
71010530 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010530 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-12 | Done late
71010530 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010530 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010530 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010530 | SLM | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010530 | SLM | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010530 | SLM | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010530 | SLM | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010534 | BRW | 1 | Yarn booking | Factory | 2026-08-08 |  | 2026-08-09 | Done late
71010534 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-18 |  | 2026-08-18 | Done
71010534 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-23 |  | 2026-08-24 | Done late
71010534 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-14 | Done late
71010534 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-22 | Done
71010534 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-27 |  | 2026-09-29 | Done late
71010534 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-09-30 |  | 2026-09-30 | Done
71010534 | BRW | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-01 | Done
71010534 | BRW | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-05 | Done
71010534 | BRW | 10 | Final inspection | Karbar QA | 2026-11-10 |  |  | Pending
71010534 | BRW | 11 | Ex-factory | Factory | 2026-11-11 |  |  | Pending
71010537 | BRW | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-09 | Done
71010537 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-19 | Done
71010537 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71010537 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71010537 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010537 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-29 | Done late
71010537 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-10-01 | Done
71010537 | BRW | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-03 | Done
71010537 | BRW | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-06 | Done
71010537 | BRW | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010537 | BRW | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010543 | GRL | 1 | Yarn booking | Factory | 2026-08-12 |  | 2026-08-13 | Done late
71010543 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71010543 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-29 | Done late
71010543 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010543 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-28 | Done late
71010543 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-01 | Done
71010543 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-04 |  | 2026-10-04 | Done
71010543 | GRL | 8 | Knitting start | Factory | 2026-10-06 |  | 2026-10-07 | Done late
71010543 | GRL | 9 | Linking start | Factory | 2026-10-12 |  | 2026-10-11 | Done
71010543 | GRL | 10 | Final inspection | Karbar QA | 2026-11-14 |  |  | Pending
71010543 | GRL | 11 | Ex-factory | Factory | 2026-11-15 |  |  | Pending
71010548 | OKH | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-12 | Done
71010548 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71010548 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010548 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-16 | Done
71010548 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010548 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-01 | Done
71010548 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-06 | Done
71010548 | OKH | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010548 | OKH | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-12 | Done
71010548 | OKH | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010548 | OKH | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010553 | BRW | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010553 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-31 |  | 2026-08-31 | Done
71010553 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-06 | Done late
71010553 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010553 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-06 | Done late
71010553 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-10 |  | 2026-10-10 | Done
71010553 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-10-13 |  | 2026-10-13 | Done
71010553 | BRW | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010553 | BRW | 9 | Linking start | Factory | 2026-10-21 |  |  | Pending
71010553 | BRW | 10 | Final inspection | Karbar QA | 2026-11-23 |  |  | Pending
71010553 | BRW | 11 | Ex-factory | Factory | 2026-11-24 |  |  | Pending
71010556 | HMR | 1 | Yarn booking | Factory | 2026-09-09 |  | 2026-09-09 | Done
71010556 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71010556 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-26 | Done late
71010556 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-13 | Done
71010556 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71010556 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 |  |  | Pending
71010556 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-11-01 |  |  | Pending
71010556 | HMR | 8 | Knitting start | Factory | 2026-11-03 |  |  | Pending
71010556 | HMR | 9 | Linking start | Factory | 2026-11-09 |  |  | Pending
71010556 | HMR | 10 | Final inspection | Karbar QA | 2026-12-12 |  |  | Pending
71010556 | HMR | 11 | Ex-factory | Factory | 2026-12-13 |  |  | Pending
71010563 | TLG | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-08 | Done
71010563 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-22 | Done late
71010563 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010563 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71010563 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010563 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 |  |  | Pending
71010563 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-11-02 |  |  | Pending
71010563 | TLG | 8 | Knitting start | Factory | 2026-11-04 |  |  | Pending
71010563 | TLG | 9 | Linking start | Factory | 2026-11-10 |  |  | Pending
71010563 | TLG | 10 | Final inspection | Karbar QA | 2026-12-13 |  |  | Pending
71010563 | TLG | 11 | Ex-factory | Factory | 2026-12-14 |  |  | Pending
71010570 | KST | 1 | Yarn booking | Factory | 2026-08-19 |  | 2026-08-20 | Done late
71010570 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-27 | Done
71010570 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-05 | Done late
71010570 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010570 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-01 | Done
71010570 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71010570 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-11 |  | 2026-10-12 | Done late
71010570 | KST | 8 | Knitting start | Factory | 2026-10-13 |  | 2026-10-14 | Done late
71010570 | KST | 9 | Linking start | Factory | 2026-10-19 |  |  | Pending
71010570 | KST | 10 | Final inspection | Karbar QA | 2026-11-21 |  |  | Pending
71010570 | KST | 11 | Ex-factory | Factory | 2026-11-22 |  |  | Pending
71010573 | FNS | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-27 | Done
71010573 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-03 | Done
71010573 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-12 | Done late
71010573 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-09-29 | Done
71010573 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-10 | Done
71010573 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-15 |  |  | Pending
71010573 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-10-19 |  |  | Pending
71010573 | FNS | 8 | Knitting start | Factory | 2026-10-21 |  |  | Pending
71010573 | FNS | 9 | Linking start | Factory | 2026-10-27 |  |  | Pending
71010573 | FNS | 10 | Final inspection | Karbar QA | 2026-11-29 |  |  | Pending
71010573 | FNS | 11 | Ex-factory | Factory | 2026-11-30 |  |  | Pending
71010581 | TLG | 1 | Yarn booking | Factory | 2026-08-30 |  | 2026-08-27 | Done
71010581 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010581 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-16 | Done late
71010581 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-05 | Done late
71010581 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-14 |  |  | Overdue
71010581 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-19 |  |  | Pending
71010581 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-10-22 |  |  | Pending
71010581 | TLG | 8 | Knitting start | Factory | 2026-10-24 |  |  | Pending
71010581 | TLG | 9 | Linking start | Factory | 2026-10-29 |  |  | Pending
71010581 | TLG | 10 | Final inspection | Karbar QA | 2026-12-02 |  |  | Pending
71010581 | TLG | 11 | Ex-factory | Factory | 2026-12-03 |  |  | Pending
71010590 | GRL | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-07 | Done late
71010590 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-16 | Done late
71010590 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-17 | Done
71010590 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010590 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010590 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010590 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010590 | GRL | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010590 | GRL | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010590 | GRL | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010590 | GRL | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010595 | BLF | 1 | Yarn booking | Factory | 2026-09-13 |  | 2026-09-10 | Done
71010595 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-21 | Done
71010595 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-26 | Done
71010595 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010595 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71010595 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-02 |  |  | Pending
71010595 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-11-05 |  |  | Pending
71010595 | BLF | 8 | Knitting start | Factory | 2026-11-07 |  |  | Pending
71010595 | BLF | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71010595 | BLF | 10 | Final inspection | Karbar QA | 2026-12-16 |  |  | Pending
71010595 | BLF | 11 | Ex-factory | Factory | 2026-12-17 |  |  | Pending
71010600 | OKH | 1 | Yarn booking | Factory | 2026-08-06 |  | 2026-08-06 | Done
71010600 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-17 |  | 2026-08-16 | Done
71010600 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-22 | Done
71010600 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-10 | Done
71010600 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71010600 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-26 |  | 2026-09-27 | Done late
71010600 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-09-29 |  | 2026-09-27 | Done
71010600 | OKH | 8 | Knitting start | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71010600 | OKH | 9 | Linking start | Factory | 2026-10-07 |  | 2026-10-06 | Done
71010600 | OKH | 10 | Final inspection | Karbar QA | 2026-11-09 |  |  | Pending
71010600 | OKH | 11 | Ex-factory | Factory | 2026-11-10 |  |  | Pending
71010605 | WTH | 1 | Yarn booking | Factory | 2026-08-11 |  | 2026-08-13 | Done late
71010605 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71010605 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71010605 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-17 | Done late
71010605 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010605 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-30 |  | 2026-09-30 | Done
71010605 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-03 |  | 2026-10-01 | Done
71010605 | WTH | 8 | Knitting start | Factory | 2026-10-05 |  | 2026-10-05 | Done
71010605 | WTH | 9 | Linking start | Factory | 2026-10-11 |  | 2026-10-08 | Done
71010605 | WTH | 10 | Final inspection | Karbar QA | 2026-11-12 |  |  | Pending
71010605 | WTH | 11 | Ex-factory | Factory | 2026-11-14 |  |  | Pending
71010614 | WTH | 1 | Yarn booking | Factory | 2026-08-13 |  | 2026-08-11 | Done
71010614 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-26 | Done late
71010614 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-30 | Done late
71010614 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010614 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010614 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-03 |  | 2026-10-01 | Done
71010614 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-06 |  | 2026-10-07 | Done late
71010614 | WTH | 8 | Knitting start | Factory | 2026-10-08 |  | 2026-10-08 | Done
71010614 | WTH | 9 | Linking start | Factory | 2026-10-14 |  | 2026-10-12 | Done
71010614 | WTH | 10 | Final inspection | Karbar QA | 2026-11-16 |  |  | Pending
71010614 | WTH | 11 | Ex-factory | Factory | 2026-11-17 |  |  | Pending
71010621 | GRL | 1 | Yarn booking | Factory | 2026-08-19 |  | 2026-08-18 | Done
71010621 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-29 | Done
71010621 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010621 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-24 | Done late
71010621 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-03 | Done
71010621 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-10 | Done late
71010621 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-11 |  | 2026-10-12 | Done late
71010621 | GRL | 8 | Knitting start | Factory | 2026-10-13 |  | 2026-10-13 | Done
71010621 | GRL | 9 | Linking start | Factory | 2026-10-19 |  |  | Pending
71010621 | GRL | 10 | Final inspection | Karbar QA | 2026-11-21 |  |  | Pending
71010621 | GRL | 11 | Ex-factory | Factory | 2026-11-22 |  |  | Pending
71010630 | CLB | 1 | Yarn booking | Factory | 2026-08-19 |  | 2026-08-20 | Done late
71010630 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-29 |  | 2026-08-27 | Done
71010630 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010630 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010630 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-01 | Done
71010630 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71010630 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-11 |  | 2026-10-12 | Done late
71010630 | CLB | 8 | Knitting start | Factory | 2026-10-13 |  | 2026-10-14 | Done late
71010630 | CLB | 9 | Linking start | Factory | 2026-10-19 |  |  | Pending
71010630 | CLB | 10 | Final inspection | Karbar QA | 2026-11-21 |  |  | Pending
71010630 | CLB | 11 | Ex-factory | Factory | 2026-11-22 |  |  | Pending
71010634 | IRB | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010634 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-01 | Done late
71010634 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71010634 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010634 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71010634 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-10 |  | 2026-10-10 | Done
71010634 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-13 |  | 2026-10-11 | Done
71010634 | IRB | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010634 | IRB | 9 | Linking start | Factory | 2026-10-21 |  |  | Pending
71010634 | IRB | 10 | Final inspection | Karbar QA | 2026-11-23 |  |  | Pending
71010634 | IRB | 11 | Ex-factory | Factory | 2026-11-24 |  |  | Pending
71010637 | HMR | 1 | Yarn booking | Factory | 2026-08-25 |  | 2026-08-25 | Done
71010637 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010637 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-07 | Done
71010637 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-30 | Done late
71010637 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71010637 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-14 |  | 2026-10-14 | Done
71010637 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-17 |  |  | Pending
71010637 | HMR | 8 | Knitting start | Factory | 2026-10-19 |  |  | Pending
71010637 | HMR | 9 | Linking start | Factory | 2026-10-25 |  |  | Pending
71010637 | HMR | 10 | Final inspection | Karbar QA | 2026-11-26 |  |  | Pending
71010637 | HMR | 11 | Ex-factory | Factory | 2026-11-28 |  |  | Pending
71010640 | WTH | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-12 | Done late
71010640 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-23 | Done late
71010640 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-24 | Done
71010640 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71010640 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71010640 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-31 |  |  | Pending
71010640 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-11-03 |  |  | Pending
71010640 | WTH | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71010640 | WTH | 9 | Linking start | Factory | 2026-11-11 |  |  | Pending
71010640 | WTH | 10 | Final inspection | Karbar QA | 2026-12-14 |  |  | Pending
71010640 | WTH | 11 | Ex-factory | Factory | 2026-12-15 |  |  | Pending
71010648 | SND | 1 | Yarn booking | Factory | 2026-09-13 |  | 2026-09-14 | Done late
71010648 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010648 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010648 | SND | 4 | Size set approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010648 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71010648 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-02 |  |  | Pending
71010648 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-11-05 |  |  | Pending
71010648 | SND | 8 | Knitting start | Factory | 2026-11-07 |  |  | Pending
71010648 | SND | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71010648 | SND | 10 | Final inspection | Karbar QA | 2026-12-16 |  |  | Pending
71010648 | SND | 11 | Ex-factory | Factory | 2026-12-17 |  |  | Pending
71010654 | KST | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-22 | Done
71010654 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71010654 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-05 | Done
71010654 | KST | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-26 | Done
71010654 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010654 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-12 | Done
71010654 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  |  | Pending
71010654 | KST | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010654 | KST | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010654 | KST | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010654 | KST | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010657 | SVP | 1 | Yarn booking | Factory | 2026-09-13 |  | 2026-09-12 | Done
71010657 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010657 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010657 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010657 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71010657 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-02 |  |  | Pending
71010657 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-11-05 |  |  | Pending
71010657 | SVP | 8 | Knitting start | Factory | 2026-11-07 |  |  | Pending
71010657 | SVP | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71010657 | SVP | 10 | Final inspection | Karbar QA | 2026-12-16 |  |  | Pending
71010657 | SVP | 11 | Ex-factory | Factory | 2026-12-17 |  |  | Pending
71010664 | OKH | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71010664 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71010664 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010664 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010664 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010664 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 |  |  | Pending
71010664 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-11-09 |  |  | Pending
71010664 | OKH | 8 | Knitting start | Factory | 2026-11-11 |  |  | Pending
71010664 | OKH | 9 | Linking start | Factory | 2026-11-17 |  |  | Pending
71010664 | OKH | 10 | Final inspection | Karbar QA | 2026-12-20 |  |  | Pending
71010664 | OKH | 11 | Ex-factory | Factory | 2026-12-21 |  |  | Pending
71010672 | IRB | 1 | Yarn booking | Factory | 2026-08-09 |  | 2026-08-09 | Done
71010672 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-19 |  | 2026-08-20 | Done late
71010672 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-24 |  | 2026-08-24 | Done
71010672 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71010672 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010672 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-28 |  | 2026-09-28 | Done
71010672 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-01 |  | 2026-09-30 | Done
71010672 | IRB | 8 | Knitting start | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71010672 | IRB | 9 | Linking start | Factory | 2026-10-08 |  | 2026-10-07 | Done
71010672 | IRB | 10 | Final inspection | Karbar QA | 2026-11-11 |  |  | Pending
71010672 | IRB | 11 | Ex-factory | Factory | 2026-11-12 |  |  | Pending
71010677 | SND | 1 | Yarn booking | Factory | 2026-08-11 |  | 2026-08-13 | Done late
71010677 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-20 |  | 2026-08-20 | Done
71010677 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-27 | Done late
71010677 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-15 | Done
71010677 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010677 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-09-30 |  | 2026-10-01 | Done late
71010677 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-10-03 |  | 2026-10-03 | Done
71010677 | SND | 8 | Knitting start | Factory | 2026-10-05 |  | 2026-10-06 | Done late
71010677 | SND | 9 | Linking start | Factory | 2026-10-11 |  | 2026-10-10 | Done
71010677 | SND | 10 | Final inspection | Karbar QA | 2026-11-12 |  |  | Pending
71010677 | SND | 11 | Ex-factory | Factory | 2026-11-14 |  |  | Pending
71010686 | IRB | 1 | Yarn booking | Factory | 2026-08-16 |  | 2026-08-16 | Done
71010686 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-26 |  | 2026-08-26 | Done
71010686 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-08-31 |  | 2026-09-01 | Done late
71010686 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-22 | Done late
71010686 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71010686 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-05 | 2026-10-12 |  | Overdue | Supplier capacity issue - partial lot only
71010686 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-08 |  | 2026-10-07 | Done
71010686 | IRB | 8 | Knitting start | Factory | 2026-10-10 |  |  | Overdue
71010686 | IRB | 9 | Linking start | Factory | 2026-10-15 |  |  | Pending
71010686 | IRB | 10 | Final inspection | Karbar QA | 2026-11-18 |  |  | Pending
71010686 | IRB | 11 | Ex-factory | Factory | 2026-11-19 |  |  | Pending
71010695 | SLM | 1 | Yarn booking | Factory | 2026-09-01 |  | 2026-09-03 | Done late
71010695 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-08 | Done
71010695 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-14 | Done
71010695 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-08 | Done late
71010695 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-15 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71010695 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-21 | 2026-10-29 |  | Pending | Supplier capacity issue - partial lot only
71010695 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-24 |  |  | Pending
71010695 | SLM | 8 | Knitting start | Factory | 2026-10-26 |  |  | Pending
71010695 | SLM | 9 | Linking start | Factory | 2026-11-01 |  |  | Pending
71010695 | SLM | 10 | Final inspection | Karbar QA | 2026-12-03 |  |  | Pending
71010695 | SLM | 11 | Ex-factory | Factory | 2026-12-05 |  |  | Pending
71010701 | SND | 1 | Yarn booking | Factory | 2026-08-23 |  | 2026-08-20 | Done
71010701 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-02 |  | 2026-09-02 | Done
71010701 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010701 | SND | 4 | Size set approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71010701 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010701 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-12 |  | 2026-10-12 | Done
71010701 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-10-15 |  |  | Pending
71010701 | SND | 8 | Knitting start | Factory | 2026-10-17 |  |  | Pending
71010701 | SND | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010701 | SND | 10 | Final inspection | Karbar QA | 2026-11-25 |  |  | Pending
71010701 | SND | 11 | Ex-factory | Factory | 2026-11-26 |  |  | Pending
71010707 | GRL | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-07 | Done late
71010707 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-17 | Done late
71010707 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71010707 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71010707 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71010707 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 | 2026-11-04 |  | Pending | Yarn shipment rolled to next vessel
71010707 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71010707 | GRL | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71010707 | GRL | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010707 | GRL | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71010707 | GRL | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71010712 | OKH | 1 | Yarn booking | Factory | 2026-08-12 |  | 2026-08-12 | Done
71010712 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-22 |  | 2026-08-24 | Done late
71010712 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-08-27 |  | 2026-08-27 | Done
71010712 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-15 | Done
71010712 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-28 | Done late
71010712 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-01 |  | 2026-10-04 | Done late
71010712 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-10-04 |  | 2026-10-04 | Done
71010712 | OKH | 8 | Knitting start | Factory | 2026-10-06 |  | 2026-10-06 | Done
71010712 | OKH | 9 | Linking start | Factory | 2026-10-12 |  | 2026-10-10 | Done
71010712 | OKH | 10 | Final inspection | Karbar QA | 2026-11-14 |  |  | Pending
71010712 | OKH | 11 | Ex-factory | Factory | 2026-11-15 |  |  | Pending
71010721 | GRL | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010721 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-30 | Done
71010721 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-02 | Done
71010721 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010721 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-04 | Done
71010721 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 | 2026-10-17 |  | Overdue | Supplier capacity issue - partial lot only
71010721 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71010721 | GRL | 8 | Knitting start | Factory | 2026-10-14 |  |  | Overdue
71010721 | GRL | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010721 | GRL | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010721 | GRL | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010725 | WTH | 1 | Yarn booking | Factory | 2026-09-03 |  | 2026-09-03 | Done
71010725 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-14 | Done
71010725 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71010725 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-08 | Done
71010725 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-10-19 |  |  | Pending
71010725 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-24 |  |  | Pending
71010725 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-27 |  |  | Pending
71010725 | WTH | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010725 | WTH | 9 | Linking start | Factory | 2026-11-04 |  |  | Pending
71010725 | WTH | 10 | Final inspection | Karbar QA | 2026-12-07 |  |  | Pending
71010725 | WTH | 11 | Ex-factory | Factory | 2026-12-08 |  |  | Pending
71010732 | SLM | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-08 | Done
71010732 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010732 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010732 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-12 | Done
71010732 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010732 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 |  |  | Pending
71010732 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71010732 | SLM | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71010732 | SLM | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71010732 | SLM | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71010732 | SLM | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71010741 | CLB | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-19 | Done
71010741 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-29 | Done
71010741 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-02 | Done
71010741 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010741 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-06 | Done late
71010741 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-07 | Done
71010741 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71010741 | CLB | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71010741 | CLB | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010741 | CLB | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010741 | CLB | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010747 | LTF | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-18 | Done
71010747 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71010747 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010747 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010747 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-05 | Done late
71010747 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-11 | Done late
71010747 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-10 | Done
71010747 | LTF | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71010747 | LTF | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010747 | LTF | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010747 | LTF | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010756 | HMR | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-06 | Done
71010756 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-17 | Done late
71010756 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-23 | Done late
71010756 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71010756 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71010756 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 |  |  | Pending
71010756 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71010756 | HMR | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71010756 | HMR | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010756 | HMR | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71010756 | HMR | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71010759 | SLM | 1 | Yarn booking | Factory | 2026-08-20 |  | 2026-08-20 | Done
71010759 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-08-30 |  | 2026-08-31 | Done late
71010759 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-03 | Done
71010759 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010759 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-04 | Done
71010759 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-08 |  | 2026-10-08 | Done
71010759 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-12 |  | 2026-10-12 | Done
71010759 | SLM | 8 | Knitting start | Factory | 2026-10-14 |  | 2026-10-14 | Done
71010759 | SLM | 9 | Linking start | Factory | 2026-10-20 |  |  | Pending
71010759 | SLM | 10 | Final inspection | Karbar QA | 2026-11-22 |  |  | Pending
71010759 | SLM | 11 | Ex-factory | Factory | 2026-11-23 |  |  | Pending
71010768 | OKH | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-06 | Done late
71010768 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-14 | Done
71010768 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010768 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010768 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010768 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010768 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010768 | OKH | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010768 | OKH | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010768 | OKH | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010768 | OKH | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010777 | TLG | 1 | Yarn booking | Factory | 2026-09-09 |  | 2026-09-08 | Done
71010777 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-17 | Done
71010777 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010777 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-13 | Done
71010777 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71010777 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 |  |  | Pending
71010777 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-11-01 |  |  | Pending
71010777 | TLG | 8 | Knitting start | Factory | 2026-11-03 |  |  | Pending
71010777 | TLG | 9 | Linking start | Factory | 2026-11-09 |  |  | Pending
71010777 | TLG | 10 | Final inspection | Karbar QA | 2026-12-12 |  |  | Pending
71010777 | TLG | 11 | Ex-factory | Factory | 2026-12-13 |  |  | Pending
71010780 | CLB | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-20 | Done
71010780 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-08-30 | Done
71010780 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010780 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-26 | Done
71010780 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-07 | Done late
71010780 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-10 | Done
71010780 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  | 2026-10-14 | Done
71010780 | CLB | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010780 | CLB | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010780 | CLB | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010780 | CLB | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010787 | LTF | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-08 | Done
71010787 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-15 | Done
71010787 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-22 | Done
71010787 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-11 | Done
71010787 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71010787 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 | 2026-11-04 |  | Pending | Supplier capacity issue - partial lot only
71010787 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71010787 | LTF | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71010787 | LTF | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71010787 | LTF | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71010787 | LTF | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71010792 | CLB | 1 | Yarn booking | Factory | 2026-09-27 |  | 2026-09-26 | Done
71010792 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010792 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010792 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010792 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71010792 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-16 |  |  | Pending
71010792 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-11-19 |  |  | Pending
71010792 | CLB | 8 | Knitting start | Factory | 2026-11-21 |  |  | Pending
71010792 | CLB | 9 | Linking start | Factory | 2026-11-26 |  |  | Pending
71010792 | CLB | 10 | Final inspection | Karbar QA | 2026-12-30 |  |  | Pending
71010792 | CLB | 11 | Ex-factory | Factory | 2026-12-31 |  |  | Pending
71010795 | RVS | 1 | Yarn booking | Factory | 2026-08-22 |  | 2026-08-20 | Done
71010795 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-01 |  | 2026-08-31 | Done
71010795 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010795 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-24 | Done
71010795 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-06 | Done
71010795 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-11 |  | 2026-10-12 | Done late
71010795 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-10-14 |  | 2026-10-14 | Done
71010795 | RVS | 8 | Knitting start | Factory | 2026-10-15 |  |  | Pending
71010795 | RVS | 9 | Linking start | Factory | 2026-10-22 |  |  | Pending
71010795 | RVS | 10 | Final inspection | Karbar QA | 2026-11-24 |  |  | Pending
71010795 | RVS | 11 | Ex-factory | Factory | 2026-11-25 |  |  | Pending
71010798 | FNS | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-25 | Done
71010798 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-06 |  | 2026-09-06 | Done
71010798 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-09 | Done
71010798 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010798 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71010798 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-15 |  |  | Pending
71010798 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-10-19 |  |  | Pending
71010798 | FNS | 8 | Knitting start | Factory | 2026-10-21 |  |  | Pending
71010798 | FNS | 9 | Linking start | Factory | 2026-10-27 |  |  | Pending
71010798 | FNS | 10 | Final inspection | Karbar QA | 2026-11-29 |  |  | Pending
71010798 | FNS | 11 | Ex-factory | Factory | 2026-11-30 |  |  | Pending
71010802 | WSM | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-22 | Done late
71010802 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-10-01 | Done late
71010802 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-03 | Done
71010802 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010802 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71010802 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71010802 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71010802 | WSM | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71010802 | WSM | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71010802 | WSM | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71010802 | WSM | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71010806 | GRL | 1 | Yarn booking | Factory | 2026-09-27 |  | 2026-09-27 | Done
71010806 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010806 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-14 | Done late
71010806 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010806 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-11 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71010806 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-16 | 2026-11-25 |  | Pending | Yarn shipment rolled to next vessel
71010806 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-19 |  |  | Pending
71010806 | GRL | 8 | Knitting start | Factory | 2026-11-21 |  |  | Pending
71010806 | GRL | 9 | Linking start | Factory | 2026-11-26 |  |  | Pending
71010806 | GRL | 10 | Final inspection | Karbar QA | 2026-12-30 |  |  | Pending
71010806 | GRL | 11 | Ex-factory | Factory | 2026-12-31 |  |  | Pending
71010811 | WSM | 1 | Yarn booking | Factory | 2026-09-03 |  | 2026-09-03 | Done
71010811 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-16 | Done late
71010811 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-21 | Done late
71010811 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71010811 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-10-19 |  |  | Pending
71010811 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-24 |  |  | Pending
71010811 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-10-27 |  |  | Pending
71010811 | WSM | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010811 | WSM | 9 | Linking start | Factory | 2026-11-04 |  |  | Pending
71010811 | WSM | 10 | Final inspection | Karbar QA | 2026-12-07 |  |  | Pending
71010811 | WSM | 11 | Ex-factory | Factory | 2026-12-08 |  |  | Pending
71010817 | WSM | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-09 | Done late
71010817 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-19 | Done late
71010817 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-21 | Done
71010817 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-14 | Done late
71010817 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010817 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 |  |  | Pending
71010817 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71010817 | WSM | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71010817 | WSM | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71010817 | WSM | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71010817 | WSM | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71010821 | TLG | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-17 | Done
71010821 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-28 | Done
71010821 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-01 | Done
71010821 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010821 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71010821 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-07 |  |  | Pending
71010821 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-11-10 |  |  | Pending
71010821 | TLG | 8 | Knitting start | Factory | 2026-11-12 |  |  | Pending
71010821 | TLG | 9 | Linking start | Factory | 2026-11-18 |  |  | Pending
71010821 | TLG | 10 | Final inspection | Karbar QA | 2026-12-21 |  |  | Pending
71010821 | TLG | 11 | Ex-factory | Factory | 2026-12-22 |  |  | Pending
71010830 | RVS | 1 | Yarn booking | Factory | 2026-09-03 |  | 2026-09-02 | Done
71010830 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-12 | Done
71010830 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-19 |  | 2026-09-19 | Done
71010830 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71010830 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-19 |  |  | Pending
71010830 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-24 | 2026-10-29 |  | Pending | Supplier capacity issue - partial lot only
71010830 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-10-27 |  |  | Pending
71010830 | RVS | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010830 | RVS | 9 | Linking start | Factory | 2026-11-04 |  |  | Pending
71010830 | RVS | 10 | Final inspection | Karbar QA | 2026-12-07 |  |  | Pending
71010830 | RVS | 11 | Ex-factory | Factory | 2026-12-08 |  |  | Pending
71010833 | GRL | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-03 | Done
71010833 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-16 | Done late
71010833 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010833 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010833 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010833 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010833 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010833 | GRL | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010833 | GRL | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010833 | GRL | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010833 | GRL | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010842 | AMB | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-10 | Done
71010842 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71010842 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71010842 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  | 2026-10-13 | Done
71010842 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010842 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 |  |  | Pending
71010842 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-02 |  |  | Pending
71010842 | AMB | 8 | Knitting start | Factory | 2026-11-04 |  |  | Pending
71010842 | AMB | 9 | Linking start | Factory | 2026-11-10 |  |  | Pending
71010842 | AMB | 10 | Final inspection | Karbar QA | 2026-12-13 |  |  | Pending
71010842 | AMB | 11 | Ex-factory | Factory | 2026-12-14 |  |  | Pending
71010849 | BRW | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-20 | Done
71010849 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71010849 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-06 | Done late
71010849 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010849 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71010849 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71010849 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71010849 | BRW | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71010849 | BRW | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71010849 | BRW | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71010849 | BRW | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71010853 | SLM | 1 | Yarn booking | Factory | 2026-08-25 |  | 2026-08-27 | Done late
71010853 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-03 |  | 2026-09-01 | Done
71010853 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010853 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-28 | Done
71010853 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-12 | Done late | PP sample rejected once (measurement); resubmitted
71010853 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-14 | 2026-10-20 |  | Overdue | Yarn shipment rolled to next vessel
71010853 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-10-17 |  |  | Pending
71010853 | SLM | 8 | Knitting start | Factory | 2026-10-19 |  |  | Pending
71010853 | SLM | 9 | Linking start | Factory | 2026-10-25 |  |  | Pending
71010853 | SLM | 10 | Final inspection | Karbar QA | 2026-11-26 |  |  | Pending
71010853 | SLM | 11 | Ex-factory | Factory | 2026-11-28 |  |  | Pending
71010859 | OKH | 1 | Yarn booking | Factory | 2026-08-30 |  | 2026-08-27 | Done
71010859 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010859 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-14 | Done
71010859 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-05 | Done late
71010859 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-10-14 |  |  | Overdue
71010859 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-19 |  |  | Pending
71010859 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-10-22 |  |  | Pending
71010859 | OKH | 8 | Knitting start | Factory | 2026-10-24 |  |  | Pending
71010859 | OKH | 9 | Linking start | Factory | 2026-10-29 |  |  | Pending
71010859 | OKH | 10 | Final inspection | Karbar QA | 2026-12-02 |  |  | Pending
71010859 | OKH | 11 | Ex-factory | Factory | 2026-12-03 |  |  | Pending
71010863 | CLB | 1 | Yarn booking | Factory | 2026-09-13 |  | 2026-09-14 | Done late
71010863 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-23 | Done
71010863 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-30 | Done late
71010863 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010863 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71010863 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-02 |  |  | Pending
71010863 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-11-05 |  |  | Pending
71010863 | CLB | 8 | Knitting start | Factory | 2026-11-07 |  |  | Pending
71010863 | CLB | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71010863 | CLB | 10 | Final inspection | Karbar QA | 2026-12-16 |  |  | Pending
71010863 | CLB | 11 | Ex-factory | Factory | 2026-12-17 |  |  | Pending
71010870 | FNS | 1 | Yarn booking | Factory | 2026-09-29 |  | 2026-09-28 | Done
71010870 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71010870 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-14 | Done
71010870 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-11-03 |  |  | Pending
71010870 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71010870 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-18 |  |  | Pending
71010870 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-11-21 |  |  | Pending
71010870 | FNS | 8 | Knitting start | Factory | 2026-11-23 |  |  | Pending
71010870 | FNS | 9 | Linking start | Factory | 2026-11-29 |  |  | Pending
71010870 | FNS | 10 | Final inspection | Karbar QA | 2026-12-31 |  |  | Pending
71010870 | FNS | 11 | Ex-factory | Factory | 2027-01-02 |  |  | Pending
71010877 | RVS | 1 | Yarn booking | Factory | 2026-08-30 |  | 2026-08-30 | Done
71010877 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-09 |  | 2026-09-09 | Done
71010877 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-14 |  | 2026-09-13 | Done
71010877 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-04 | Done
71010877 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-14 | Done
71010877 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-19 |  |  | Pending
71010877 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-10-22 |  |  | Pending
71010877 | RVS | 8 | Knitting start | Factory | 2026-10-24 |  |  | Pending
71010877 | RVS | 9 | Linking start | Factory | 2026-10-29 |  |  | Pending
71010877 | RVS | 10 | Final inspection | Karbar QA | 2026-12-02 |  |  | Pending
71010877 | RVS | 11 | Ex-factory | Factory | 2026-12-03 |  |  | Pending
71010883 | AMB | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-20 | Done
71010883 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-28 | Done
71010883 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71010883 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010883 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71010883 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71010883 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71010883 | AMB | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71010883 | AMB | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71010883 | AMB | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71010883 | AMB | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71010892 | AMB | 1 | Yarn booking | Factory | 2026-09-22 |  | 2026-09-21 | Done
71010892 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-01 |  | 2026-09-30 | Done
71010892 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-05 | Done
71010892 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71010892 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71010892 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-11 |  |  | Pending
71010892 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-14 |  |  | Pending
71010892 | AMB | 8 | Knitting start | Factory | 2026-11-16 |  |  | Pending
71010892 | AMB | 9 | Linking start | Factory | 2026-11-22 |  |  | Pending
71010892 | AMB | 10 | Final inspection | Karbar QA | 2026-12-24 |  |  | Pending
71010892 | AMB | 11 | Ex-factory | Factory | 2026-12-26 |  |  | Pending
71010898 | AMB | 1 | Yarn booking | Factory | 2026-08-26 |  | 2026-08-24 | Done
71010898 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-05 |  | 2026-09-05 | Done
71010898 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-09 | Done
71010898 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-09-30 |  | 2026-10-01 | Done late
71010898 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010898 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-15 |  |  | Pending
71010898 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-18 |  |  | Pending
71010898 | AMB | 8 | Knitting start | Factory | 2026-10-20 |  |  | Pending
71010898 | AMB | 9 | Linking start | Factory | 2026-10-26 |  |  | Pending
71010898 | AMB | 10 | Final inspection | Karbar QA | 2026-11-28 |  |  | Pending
71010898 | AMB | 11 | Ex-factory | Factory | 2026-11-29 |  |  | Pending
71010901 | MDW | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-26 | Done
71010901 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010901 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-13 | Done late
71010901 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-03 | Done late
71010901 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-11 | Done
71010901 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010901 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010901 | MDW | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010901 | MDW | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010901 | MDW | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010901 | MDW | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010907 | CLB | 1 | Yarn booking | Factory | 2026-09-03 |  | 2026-09-05 | Done late
71010907 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-13 |  | 2026-09-13 | Done
71010907 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-17 | Done
71010907 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-06 | Done
71010907 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71010907 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-22 |  |  | Pending
71010907 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-10-26 |  |  | Pending
71010907 | CLB | 8 | Knitting start | Factory | 2026-10-28 |  |  | Pending
71010907 | CLB | 9 | Linking start | Factory | 2026-11-03 |  |  | Pending
71010907 | CLB | 10 | Final inspection | Karbar QA | 2026-12-06 |  |  | Pending
71010907 | CLB | 11 | Ex-factory | Factory | 2026-12-07 |  |  | Pending
71010912 | LTF | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-06 | Done
71010912 | LTF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010912 | LTF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-20 | Done
71010912 | LTF | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71010912 | LTF | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71010912 | LTF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 |  |  | Pending
71010912 | LTF | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71010912 | LTF | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71010912 | LTF | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010912 | LTF | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71010912 | LTF | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71010918 | CPL | 1 | Yarn booking | Factory | 2026-09-12 |  | 2026-09-10 | Done
71010918 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-24 | Done late
71010918 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-29 | Done late
71010918 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71010918 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71010918 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-01 |  |  | Pending
71010918 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-11-04 |  |  | Pending
71010918 | CPL | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71010918 | CPL | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71010918 | CPL | 10 | Final inspection | Karbar QA | 2026-12-15 |  |  | Pending
71010918 | CPL | 11 | Ex-factory | Factory | 2026-12-16 |  |  | Pending
71010922 | KST | 1 | Yarn booking | Factory | 2026-09-24 |  | 2026-09-22 | Done
71010922 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-06 | Done late
71010922 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-08 | Done
71010922 | KST | 4 | Size set approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71010922 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71010922 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-14 |  |  | Pending
71010922 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-11-17 |  |  | Pending
71010922 | KST | 8 | Knitting start | Factory | 2026-11-19 |  |  | Pending
71010922 | KST | 9 | Linking start | Factory | 2026-11-25 |  |  | Pending
71010922 | KST | 10 | Final inspection | Karbar QA | 2026-12-28 |  |  | Pending
71010922 | KST | 11 | Ex-factory | Factory | 2026-12-29 |  |  | Pending
71010929 | GRL | 1 | Yarn booking | Factory | 2026-09-27 |  | 2026-09-26 | Done
71010929 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-08 | Done late
71010929 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-14 | Done late
71010929 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010929 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71010929 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-16 |  |  | Pending
71010929 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-19 |  |  | Pending
71010929 | GRL | 8 | Knitting start | Factory | 2026-11-21 |  |  | Pending
71010929 | GRL | 9 | Linking start | Factory | 2026-11-26 |  |  | Pending
71010929 | GRL | 10 | Final inspection | Karbar QA | 2026-12-30 |  |  | Pending
71010929 | GRL | 11 | Ex-factory | Factory | 2026-12-31 |  |  | Pending
71010938 | TLG | 1 | Yarn booking | Factory | 2026-09-27 |  | 2026-09-27 | Done
71010938 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71010938 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010938 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010938 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71010938 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-16 |  |  | Pending
71010938 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-11-19 |  |  | Pending
71010938 | TLG | 8 | Knitting start | Factory | 2026-11-21 |  |  | Pending
71010938 | TLG | 9 | Linking start | Factory | 2026-11-26 |  |  | Pending
71010938 | TLG | 10 | Final inspection | Karbar QA | 2026-12-30 |  |  | Pending
71010938 | TLG | 11 | Ex-factory | Factory | 2026-12-31 |  |  | Pending
71010942 | GRL | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-29 | Done late
71010942 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-06 | Done
71010942 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-12 | Done
71010942 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-09-29 | Done
71010942 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010942 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010942 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010942 | GRL | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010942 | GRL | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010942 | GRL | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010942 | GRL | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010946 | PBB | 1 | Yarn booking | Factory | 2026-08-27 |  | 2026-08-27 | Done
71010946 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-07 |  | 2026-09-07 | Done
71010946 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-12 |  | 2026-09-10 | Done
71010946 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010946 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010946 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-17 |  |  | Pending
71010946 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-10-20 |  |  | Pending
71010946 | PBB | 8 | Knitting start | Factory | 2026-10-22 |  |  | Pending
71010946 | PBB | 9 | Linking start | Factory | 2026-10-28 |  |  | Pending
71010946 | PBB | 10 | Final inspection | Karbar QA | 2026-11-30 |  |  | Pending
71010946 | PBB | 11 | Ex-factory | Factory | 2026-12-01 |  |  | Pending
71010952 | RVS | 1 | Yarn booking | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71010952 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71010952 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71010952 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010952 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71010952 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-04 |  |  | Pending
71010952 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-11-07 |  |  | Pending
71010952 | RVS | 8 | Knitting start | Factory | 2026-11-09 |  |  | Pending
71010952 | RVS | 9 | Linking start | Factory | 2026-11-15 |  |  | Pending
71010952 | RVS | 10 | Final inspection | Karbar QA | 2026-12-17 |  |  | Pending
71010952 | RVS | 11 | Ex-factory | Factory | 2026-12-19 |  |  | Pending
71010955 | SND | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-19 | Done late
71010955 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-28 | Done late
71010955 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010955 | SND | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010955 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010955 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 |  |  | Pending
71010955 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-11-09 |  |  | Pending
71010955 | SND | 8 | Knitting start | Factory | 2026-11-11 |  |  | Pending
71010955 | SND | 9 | Linking start | Factory | 2026-11-17 |  |  | Pending
71010955 | SND | 10 | Final inspection | Karbar QA | 2026-12-20 |  |  | Pending
71010955 | SND | 11 | Ex-factory | Factory | 2026-12-21 |  |  | Pending
71010960 | WSM | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-17 | Done
71010960 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71010960 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71010960 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71010960 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71010960 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 |  |  | Pending
71010960 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-09 |  |  | Pending
71010960 | WSM | 8 | Knitting start | Factory | 2026-11-11 |  |  | Pending
71010960 | WSM | 9 | Linking start | Factory | 2026-11-17 |  |  | Pending
71010960 | WSM | 10 | Final inspection | Karbar QA | 2026-12-20 |  |  | Pending
71010960 | WSM | 11 | Ex-factory | Factory | 2026-12-21 |  |  | Pending
71010969 | SVP | 1 | Yarn booking | Factory | 2026-09-19 |  | 2026-09-19 | Done
71010969 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-27 | Done
71010969 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-01 | Done
71010969 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71010969 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-11-03 |  |  | Pending
71010969 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-08 |  |  | Pending
71010969 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-11-11 |  |  | Pending
71010969 | SVP | 8 | Knitting start | Factory | 2026-11-12 |  |  | Pending
71010969 | SVP | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71010969 | SVP | 10 | Final inspection | Karbar QA | 2026-12-22 |  |  | Pending
71010969 | SVP | 11 | Ex-factory | Factory | 2026-12-23 |  |  | Pending
71010975 | AMB | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-17 | Done
71010975 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-28 | Done
71010975 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-06 | Done late
71010975 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71010975 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71010975 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71010975 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71010975 | AMB | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71010975 | AMB | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71010975 | AMB | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71010975 | AMB | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71010981 | AMB | 1 | Yarn booking | Factory | 2026-09-01 |  | 2026-09-03 | Done late
71010981 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-10 |  | 2026-09-09 | Done
71010981 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71010981 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-06 | Done
71010981 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-15 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71010981 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-21 | 2026-10-29 |  | Pending | Supplier capacity issue - partial lot only
71010981 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-24 |  |  | Pending
71010981 | AMB | 8 | Knitting start | Factory | 2026-10-26 |  |  | Pending
71010981 | AMB | 9 | Linking start | Factory | 2026-11-01 |  |  | Pending
71010981 | AMB | 10 | Final inspection | Karbar QA | 2026-12-03 |  |  | Pending
71010981 | AMB | 11 | Ex-factory | Factory | 2026-12-05 |  |  | Pending
71010989 | WTH | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-07 | Done late
71010989 | WTH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-15 | Done
71010989 | WTH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-22 | Done late
71010989 | WTH | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71010989 | WTH | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71010989 | WTH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71010989 | WTH | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71010989 | WTH | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71010989 | WTH | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71010989 | WTH | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71010989 | WTH | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71010994 | SLM | 1 | Yarn booking | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71010994 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-13 | Done late
71010994 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71010994 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71010994 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71010994 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-21 |  |  | Pending
71010994 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-24 |  |  | Pending
71010994 | SLM | 8 | Knitting start | Factory | 2026-11-26 |  |  | Pending
71010994 | SLM | 9 | Linking start | Factory | 2026-12-02 |  |  | Pending
71010994 | SLM | 10 | Final inspection | Karbar QA | 2027-01-04 |  |  | Pending
71010994 | SLM | 11 | Ex-factory | Factory | 2027-01-05 |  |  | Pending
71010999 | WSM | 1 | Yarn booking | Factory | 2026-10-01 |  | 2026-10-01 | Done
71010999 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-12 | Done
71010999 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71010999 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71010999 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71010999 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-21 |  |  | Pending
71010999 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-24 |  |  | Pending
71010999 | WSM | 8 | Knitting start | Factory | 2026-11-26 |  |  | Pending
71010999 | WSM | 9 | Linking start | Factory | 2026-12-02 |  |  | Pending
71010999 | WSM | 10 | Final inspection | Karbar QA | 2027-01-04 |  |  | Pending
71010999 | WSM | 11 | Ex-factory | Factory | 2027-01-05 |  |  | Pending
71011003 | MDW | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-10 | Done
71011003 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71011003 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-27 | Done late
71011003 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71011003 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011003 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-31 |  |  | Pending
71011003 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-11-03 |  |  | Pending
71011003 | MDW | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71011003 | MDW | 9 | Linking start | Factory | 2026-11-11 |  |  | Pending
71011003 | MDW | 10 | Final inspection | Karbar QA | 2026-12-14 |  |  | Pending
71011003 | MDW | 11 | Ex-factory | Factory | 2026-12-15 |  |  | Pending
71011008 | CLB | 1 | Yarn booking | Factory | 2026-09-15 |  | 2026-09-15 | Done
71011008 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71011008 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-10-01 | Done late
71011008 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011008 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011008 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-04 |  |  | Pending
71011008 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-11-07 |  |  | Pending
71011008 | CLB | 8 | Knitting start | Factory | 2026-11-09 |  |  | Pending
71011008 | CLB | 9 | Linking start | Factory | 2026-11-15 |  |  | Pending
71011008 | CLB | 10 | Final inspection | Karbar QA | 2026-12-17 |  |  | Pending
71011008 | CLB | 11 | Ex-factory | Factory | 2026-12-19 |  |  | Pending
71011014 | MDW | 1 | Yarn booking | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71011014 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-12 |  | 2026-10-11 | Done
71011014 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011014 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011014 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011014 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-21 |  |  | Pending
71011014 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-11-24 |  |  | Pending
71011014 | MDW | 8 | Knitting start | Factory | 2026-11-26 |  |  | Pending
71011014 | MDW | 9 | Linking start | Factory | 2026-12-02 |  |  | Pending
71011014 | MDW | 10 | Final inspection | Karbar QA | 2027-01-04 |  |  | Pending
71011014 | MDW | 11 | Ex-factory | Factory | 2027-01-05 |  |  | Pending
71011018 | CPL | 1 | Yarn booking | Factory | 2026-10-10 |  | 2026-10-11 | Done late
71011018 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011018 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011018 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-14 |  |  | Pending
71011018 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011018 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-29 |  |  | Pending
71011018 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-02 |  |  | Pending
71011018 | CPL | 8 | Knitting start | Factory | 2026-12-03 |  |  | Pending
71011018 | CPL | 9 | Linking start | Factory | 2026-12-10 |  |  | Pending
71011018 | CPL | 10 | Final inspection | Karbar QA | 2027-01-12 |  |  | Pending
71011018 | CPL | 11 | Ex-factory | Factory | 2027-01-13 |  |  | Pending
71011021 | BLF | 1 | Yarn booking | Factory | 2026-09-06 |  | 2026-09-08 | Done late
71011021 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-16 |  | 2026-09-16 | Done
71011021 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-21 |  | 2026-09-21 | Done
71011021 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-11 | Done
71011021 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71011021 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-26 |  |  | Pending
71011021 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-10-29 |  |  | Pending
71011021 | BLF | 8 | Knitting start | Factory | 2026-10-31 |  |  | Pending
71011021 | BLF | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71011021 | BLF | 10 | Final inspection | Karbar QA | 2026-12-09 |  |  | Pending
71011021 | BLF | 11 | Ex-factory | Factory | 2026-12-10 |  |  | Pending
71011029 | GRL | 1 | Yarn booking | Factory | 2026-09-12 |  | 2026-09-12 | Done
71011029 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-23 | Done late
71011029 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-29 | Done late
71011029 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011029 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011029 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-01 | 2026-11-09 |  | Pending | Dyed yarn delayed at spinner (shade re-dye)
71011029 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-04 |  |  | Pending
71011029 | GRL | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71011029 | GRL | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71011029 | GRL | 10 | Final inspection | Karbar QA | 2026-12-15 |  |  | Pending
71011029 | GRL | 11 | Ex-factory | Factory | 2026-12-16 |  |  | Pending
71011032 | SLM | 1 | Yarn booking | Factory | 2026-09-22 |  | 2026-09-22 | Done
71011032 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71011032 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71011032 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011032 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71011032 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-11 | 2026-11-17 |  | Pending | Supplier capacity issue - partial lot only
71011032 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-14 |  |  | Pending
71011032 | SLM | 8 | Knitting start | Factory | 2026-11-16 |  |  | Pending
71011032 | SLM | 9 | Linking start | Factory | 2026-11-22 |  |  | Pending
71011032 | SLM | 10 | Final inspection | Karbar QA | 2026-12-24 |  |  | Pending
71011032 | SLM | 11 | Ex-factory | Factory | 2026-12-26 |  |  | Pending
71011036 | GRL | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-07 | Done
71011036 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011036 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011036 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011036 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011036 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011036 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011036 | GRL | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011036 | GRL | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011036 | GRL | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011036 | GRL | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011040 | KST | 1 | Yarn booking | Factory | 2026-09-10 |  | 2026-09-10 | Done
71011040 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-20 | Done
71011040 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71011040 | KST | 4 | Size set approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71011040 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending | PP sample rejected once (measurement); resubmitted
71011040 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-29 | 2026-11-04 |  | Pending | Supplier capacity issue - partial lot only
71011040 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-11-02 |  |  | Pending
71011040 | KST | 8 | Knitting start | Factory | 2026-11-04 |  |  | Pending
71011040 | KST | 9 | Linking start | Factory | 2026-11-10 |  |  | Pending
71011040 | KST | 10 | Final inspection | Karbar QA | 2026-12-13 |  |  | Pending
71011040 | KST | 11 | Ex-factory | Factory | 2026-12-14 |  |  | Pending
71011048 | BLF | 1 | Yarn booking | Factory | 2026-09-15 |  | 2026-09-13 | Done
71011048 | BLF | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-24 | Done
71011048 | BLF | 3 | Fit sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71011048 | BLF | 4 | Size set approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011048 | BLF | 5 | PP sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011048 | BLF | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-04 | 2026-11-12 |  | Pending | Yarn shipment rolled to next vessel
71011048 | BLF | 7 | PP meeting | Factory + Karbar QA | 2026-11-07 |  |  | Pending
71011048 | BLF | 8 | Knitting start | Factory | 2026-11-09 |  |  | Pending
71011048 | BLF | 9 | Linking start | Factory | 2026-11-15 |  |  | Pending
71011048 | BLF | 10 | Final inspection | Karbar QA | 2026-12-17 |  |  | Pending
71011048 | BLF | 11 | Ex-factory | Factory | 2026-12-19 |  |  | Pending
71011052 | AMB | 1 | Yarn booking | Factory | 2026-09-05 |  | 2026-09-07 | Done late
71011052 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-15 |  | 2026-09-14 | Done
71011052 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-20 |  | 2026-09-21 | Done late
71011052 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-12 | Done late
71011052 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011052 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-25 |  |  | Pending
71011052 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-10-28 |  |  | Pending
71011052 | AMB | 8 | Knitting start | Factory | 2026-10-29 |  |  | Pending
71011052 | AMB | 9 | Linking start | Factory | 2026-11-05 |  |  | Pending
71011052 | AMB | 10 | Final inspection | Karbar QA | 2026-12-08 |  |  | Pending
71011052 | AMB | 11 | Ex-factory | Factory | 2026-12-09 |  |  | Pending
71011056 | WSM | 1 | Yarn booking | Factory | 2026-09-15 |  | 2026-09-15 | Done
71011056 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-23 | Done
71011056 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-28 | Done
71011056 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011056 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011056 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-04 |  |  | Pending
71011056 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-07 |  |  | Pending
71011056 | WSM | 8 | Knitting start | Factory | 2026-11-09 |  |  | Pending
71011056 | WSM | 9 | Linking start | Factory | 2026-11-15 |  |  | Pending
71011056 | WSM | 10 | Final inspection | Karbar QA | 2026-12-17 |  |  | Pending
71011056 | WSM | 11 | Ex-factory | Factory | 2026-12-19 |  |  | Pending
71011063 | BRW | 1 | Yarn booking | Factory | 2026-09-19 |  | 2026-09-19 | Done
71011063 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-29 |  | 2026-10-01 | Done late
71011063 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-05 | Done late
71011063 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71011063 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-11-03 |  |  | Pending
71011063 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-08 |  |  | Pending
71011063 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-11 |  |  | Pending
71011063 | BRW | 8 | Knitting start | Factory | 2026-11-12 |  |  | Pending
71011063 | BRW | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71011063 | BRW | 10 | Final inspection | Karbar QA | 2026-12-22 |  |  | Pending
71011063 | BRW | 11 | Ex-factory | Factory | 2026-12-23 |  |  | Pending
71011069 | IRB | 1 | Yarn booking | Factory | 2026-09-08 |  | 2026-09-06 | Done
71011069 | IRB | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-17 |  | 2026-09-16 | Done
71011069 | IRB | 3 | Fit sample approval | Karbar Merchandising | 2026-09-23 |  | 2026-09-21 | Done
71011069 | IRB | 4 | Size set approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-11 | Done
71011069 | IRB | 5 | PP sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011069 | IRB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-10-28 |  |  | Pending
71011069 | IRB | 7 | PP meeting | Factory + Karbar QA | 2026-10-31 |  |  | Pending
71011069 | IRB | 8 | Knitting start | Factory | 2026-11-02 |  |  | Pending
71011069 | IRB | 9 | Linking start | Factory | 2026-11-08 |  |  | Pending
71011069 | IRB | 10 | Final inspection | Karbar QA | 2026-12-10 |  |  | Pending
71011069 | IRB | 11 | Ex-factory | Factory | 2026-12-12 |  |  | Pending
71011076 | RVS | 1 | Yarn booking | Factory | 2026-09-12 |  | 2026-09-12 | Done
71011076 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-22 | Done
71011076 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71011076 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011076 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011076 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-01 |  |  | Pending
71011076 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-11-04 |  |  | Pending
71011076 | RVS | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71011076 | RVS | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71011076 | RVS | 10 | Final inspection | Karbar QA | 2026-12-15 |  |  | Pending
71011076 | RVS | 11 | Ex-factory | Factory | 2026-12-16 |  |  | Pending
71011084 | GRL | 1 | Yarn booking | Factory | 2026-10-14 |  |  | Overdue
71011084 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71011084 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011084 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011084 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-28 |  |  | Pending
71011084 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-03 |  |  | Pending
71011084 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-06 |  |  | Pending
71011084 | GRL | 8 | Knitting start | Factory | 2026-12-08 |  |  | Pending
71011084 | GRL | 9 | Linking start | Factory | 2026-12-14 |  |  | Pending
71011084 | GRL | 10 | Final inspection | Karbar QA | 2027-01-16 |  |  | Pending
71011084 | GRL | 11 | Ex-factory | Factory | 2027-01-17 |  |  | Pending
71011091 | RVS | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-17 | Done
71011091 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-26 | Done
71011091 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-03 | Done late
71011091 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011091 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011091 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 |  |  | Pending
71011091 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-11-09 |  |  | Pending
71011091 | RVS | 8 | Knitting start | Factory | 2026-11-11 |  |  | Pending
71011091 | RVS | 9 | Linking start | Factory | 2026-11-17 |  |  | Pending
71011091 | RVS | 10 | Final inspection | Karbar QA | 2026-12-20 |  |  | Pending
71011091 | RVS | 11 | Ex-factory | Factory | 2026-12-21 |  |  | Pending
71011097 | SVP | 1 | Yarn booking | Factory | 2026-09-19 |  | 2026-09-17 | Done
71011097 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-29 |  | 2026-09-29 | Done
71011097 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-10-04 |  | 2026-10-01 | Done
71011097 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-10-24 |  |  | Pending
71011097 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-11-03 |  |  | Pending
71011097 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-08 |  |  | Pending
71011097 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-11-11 |  |  | Pending
71011097 | SVP | 8 | Knitting start | Factory | 2026-11-12 |  |  | Pending
71011097 | SVP | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71011097 | SVP | 10 | Final inspection | Karbar QA | 2026-12-22 |  |  | Pending
71011097 | SVP | 11 | Ex-factory | Factory | 2026-12-23 |  |  | Pending
71011101 | FNS | 1 | Yarn booking | Factory | 2026-10-03 |  | 2026-10-04 | Done late
71011101 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-12 | Done
71011101 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71011101 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011101 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011101 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-22 |  |  | Pending
71011101 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-11-25 |  |  | Pending
71011101 | FNS | 8 | Knitting start | Factory | 2026-11-26 |  |  | Pending
71011101 | FNS | 9 | Linking start | Factory | 2026-12-03 |  |  | Pending
71011101 | FNS | 10 | Final inspection | Karbar QA | 2027-01-05 |  |  | Pending
71011101 | FNS | 11 | Ex-factory | Factory | 2027-01-06 |  |  | Pending
71011106 | BRW | 1 | Yarn booking | Factory | 2026-09-22 |  | 2026-09-20 | Done
71011106 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71011106 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71011106 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011106 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011106 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-11 |  |  | Pending
71011106 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-14 |  |  | Pending
71011106 | BRW | 8 | Knitting start | Factory | 2026-11-16 |  |  | Pending
71011106 | BRW | 9 | Linking start | Factory | 2026-11-22 |  |  | Pending
71011106 | BRW | 10 | Final inspection | Karbar QA | 2026-12-24 |  |  | Pending
71011106 | BRW | 11 | Ex-factory | Factory | 2026-12-26 |  |  | Pending
71011115 | OKH | 1 | Yarn booking | Factory | 2026-09-12 |  | 2026-09-14 | Done late
71011115 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-24 | Done late
71011115 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71011115 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011115 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011115 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-01 |  |  | Pending
71011115 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-11-04 |  |  | Pending
71011115 | OKH | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71011115 | OKH | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71011115 | OKH | 10 | Final inspection | Karbar QA | 2026-12-15 |  |  | Pending
71011115 | OKH | 11 | Ex-factory | Factory | 2026-12-16 |  |  | Pending
71011120 | SND | 1 | Yarn booking | Factory | 2026-09-12 |  | 2026-09-10 | Done
71011120 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-22 |  | 2026-09-21 | Done
71011120 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71011120 | SND | 4 | Size set approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011120 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011120 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-01 |  |  | Pending
71011120 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-11-04 |  |  | Pending
71011120 | SND | 8 | Knitting start | Factory | 2026-11-05 |  |  | Pending
71011120 | SND | 9 | Linking start | Factory | 2026-11-12 |  |  | Pending
71011120 | SND | 10 | Final inspection | Karbar QA | 2026-12-15 |  |  | Pending
71011120 | SND | 11 | Ex-factory | Factory | 2026-12-16 |  |  | Pending
71011127 | GRL | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-17 | Done
71011127 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-27 |  | 2026-09-27 | Done
71011127 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71011127 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011127 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011127 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 | 2026-11-11 |  | Pending | Yarn shipment rolled to next vessel
71011127 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-09 |  |  | Pending
71011127 | GRL | 8 | Knitting start | Factory | 2026-11-11 |  |  | Pending
71011127 | GRL | 9 | Linking start | Factory | 2026-11-17 |  |  | Pending
71011127 | GRL | 10 | Final inspection | Karbar QA | 2026-12-20 |  |  | Pending
71011127 | GRL | 11 | Ex-factory | Factory | 2026-12-21 |  |  | Pending
71011136 | GRL | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-17 | Done
71011136 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71011136 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71011136 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011136 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011136 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71011136 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71011136 | GRL | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71011136 | GRL | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71011136 | GRL | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71011136 | GRL | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71011139 | BRW | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-17 | Done
71011139 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-28 | Done
71011139 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-03 | Done
71011139 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011139 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011139 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71011139 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71011139 | BRW | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71011139 | BRW | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71011139 | BRW | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71011139 | BRW | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71011146 | SLM | 1 | Yarn booking | Factory | 2026-10-04 |  | 2026-10-01 | Done
71011146 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-13 | Done
71011146 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-19 |  |  | Pending
71011146 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-08 |  |  | Pending
71011146 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011146 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-23 |  |  | Pending
71011146 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-26 |  |  | Pending
71011146 | SLM | 8 | Knitting start | Factory | 2026-11-28 |  |  | Pending
71011146 | SLM | 9 | Linking start | Factory | 2026-12-03 |  |  | Pending
71011146 | SLM | 10 | Final inspection | Karbar QA | 2027-01-06 |  |  | Pending
71011146 | SLM | 11 | Ex-factory | Factory | 2027-01-07 |  |  | Pending
71011153 | OKH | 1 | Yarn booking | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71011153 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-13 | Done late
71011153 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-10-15 |  | 2026-10-13 | Done
71011153 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011153 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011153 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-19 |  |  | Pending
71011153 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-11-23 |  |  | Pending
71011153 | OKH | 8 | Knitting start | Factory | 2026-11-25 |  |  | Pending
71011153 | OKH | 9 | Linking start | Factory | 2026-12-01 |  |  | Pending
71011153 | OKH | 10 | Final inspection | Karbar QA | 2027-01-03 |  |  | Pending
71011153 | OKH | 11 | Ex-factory | Factory | 2027-01-04 |  |  | Pending
71011161 | CPL | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-07 | Done
71011161 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011161 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011161 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011161 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011161 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011161 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011161 | CPL | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011161 | CPL | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011161 | CPL | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011161 | CPL | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011165 | GRL | 1 | Yarn booking | Factory | 2026-10-13 |  | 2026-10-12 | Done
71011165 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011165 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011165 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011165 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011165 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-02 |  |  | Pending
71011165 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-05 |  |  | Pending
71011165 | GRL | 8 | Knitting start | Factory | 2026-12-07 |  |  | Pending
71011165 | GRL | 9 | Linking start | Factory | 2026-12-13 |  |  | Pending
71011165 | GRL | 10 | Final inspection | Karbar QA | 2027-01-14 |  |  | Pending
71011165 | GRL | 11 | Ex-factory | Factory | 2027-01-16 |  |  | Pending
71011168 | OKH | 1 | Yarn booking | Factory | 2026-09-23 |  | 2026-09-23 | Done
71011168 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-03 | Done
71011168 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-07 | Done
71011168 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011168 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011168 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-12 |  |  | Pending
71011168 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-11-15 |  |  | Pending
71011168 | OKH | 8 | Knitting start | Factory | 2026-11-17 |  |  | Pending
71011168 | OKH | 9 | Linking start | Factory | 2026-11-23 |  |  | Pending
71011168 | OKH | 10 | Final inspection | Karbar QA | 2026-12-26 |  |  | Pending
71011168 | OKH | 11 | Ex-factory | Factory | 2026-12-27 |  |  | Pending
71011171 | FNS | 1 | Yarn booking | Factory | 2026-09-17 |  | 2026-09-17 | Done
71011171 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-28 |  | 2026-09-30 | Done late
71011171 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-03 | Done
71011171 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011171 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011171 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-07 |  |  | Pending
71011171 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-11-10 |  |  | Pending
71011171 | FNS | 8 | Knitting start | Factory | 2026-11-12 |  |  | Pending
71011171 | FNS | 9 | Linking start | Factory | 2026-11-18 |  |  | Pending
71011171 | FNS | 10 | Final inspection | Karbar QA | 2026-12-21 |  |  | Pending
71011171 | FNS | 11 | Ex-factory | Factory | 2026-12-22 |  |  | Pending
71011176 | TLG | 1 | Yarn booking | Factory | 2026-09-24 |  | 2026-09-22 | Done
71011176 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-04 | Done
71011176 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-12 | Done late
71011176 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011176 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71011176 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-14 |  |  | Pending
71011176 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-11-17 |  |  | Pending
71011176 | TLG | 8 | Knitting start | Factory | 2026-11-19 |  |  | Pending
71011176 | TLG | 9 | Linking start | Factory | 2026-11-25 |  |  | Pending
71011176 | TLG | 10 | Final inspection | Karbar QA | 2026-12-28 |  |  | Pending
71011176 | TLG | 11 | Ex-factory | Factory | 2026-12-29 |  |  | Pending
71011179 | SVP | 1 | Yarn booking | Factory | 2026-10-03 |  | 2026-10-01 | Done
71011179 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-13 |  | 2026-10-13 | Done
71011179 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71011179 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011179 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011179 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-22 |  |  | Pending
71011179 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-11-25 |  |  | Pending
71011179 | SVP | 8 | Knitting start | Factory | 2026-11-26 |  |  | Pending
71011179 | SVP | 9 | Linking start | Factory | 2026-12-03 |  |  | Pending
71011179 | SVP | 10 | Final inspection | Karbar QA | 2027-01-05 |  |  | Pending
71011179 | SVP | 11 | Ex-factory | Factory | 2027-01-06 |  |  | Pending
71011183 | SLM | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-05 | Done
71011183 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011183 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011183 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011183 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011183 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011183 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011183 | SLM | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011183 | SLM | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011183 | SLM | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011183 | SLM | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011186 | AMB | 1 | Yarn booking | Factory | 2026-10-08 |  | 2026-10-10 | Done late
71011186 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71011186 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011186 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011186 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011186 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011186 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-30 |  |  | Pending
71011186 | AMB | 8 | Knitting start | Factory | 2026-12-02 |  |  | Pending
71011186 | AMB | 9 | Linking start | Factory | 2026-12-08 |  |  | Pending
71011186 | AMB | 10 | Final inspection | Karbar QA | 2027-01-10 |  |  | Pending
71011186 | AMB | 11 | Ex-factory | Factory | 2027-01-11 |  |  | Pending
71011190 | SLM | 1 | Yarn booking | Factory | 2026-10-10 |  | 2026-10-10 | Done
71011190 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011190 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011190 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-14 |  |  | Pending
71011190 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011190 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-29 |  |  | Pending
71011190 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-12-02 |  |  | Pending
71011190 | SLM | 8 | Knitting start | Factory | 2026-12-03 |  |  | Pending
71011190 | SLM | 9 | Linking start | Factory | 2026-12-10 |  |  | Pending
71011190 | SLM | 10 | Final inspection | Karbar QA | 2027-01-12 |  |  | Pending
71011190 | SLM | 11 | Ex-factory | Factory | 2027-01-13 |  |  | Pending
71011193 | HMR | 1 | Yarn booking | Factory | 2026-09-15 |  | 2026-09-17 | Done late
71011193 | HMR | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-24 |  | 2026-09-22 | Done
71011193 | HMR | 3 | Fit sample approval | Karbar Merchandising | 2026-09-30 |  | 2026-10-01 | Done late
71011193 | HMR | 4 | Size set approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011193 | HMR | 5 | PP sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011193 | HMR | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-04 |  |  | Pending
71011193 | HMR | 7 | PP meeting | Factory + Karbar QA | 2026-11-07 |  |  | Pending
71011193 | HMR | 8 | Knitting start | Factory | 2026-11-09 |  |  | Pending
71011193 | HMR | 9 | Linking start | Factory | 2026-11-15 |  |  | Pending
71011193 | HMR | 10 | Final inspection | Karbar QA | 2026-12-17 |  |  | Pending
71011193 | HMR | 11 | Ex-factory | Factory | 2026-12-19 |  |  | Pending
71011196 | BRW | 1 | Yarn booking | Factory | 2026-09-16 |  | 2026-09-16 | Done
71011196 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-26 |  | 2026-09-26 | Done
71011196 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-01 |  | 2026-09-30 | Done
71011196 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71011196 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011196 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-05 |  |  | Pending
71011196 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-08 |  |  | Pending
71011196 | BRW | 8 | Knitting start | Factory | 2026-11-10 |  |  | Pending
71011196 | BRW | 9 | Linking start | Factory | 2026-11-16 |  |  | Pending
71011196 | BRW | 10 | Final inspection | Karbar QA | 2026-12-19 |  |  | Pending
71011196 | BRW | 11 | Ex-factory | Factory | 2026-12-20 |  |  | Pending
71011202 | PBB | 1 | Yarn booking | Factory | 2026-09-22 |  | 2026-09-22 | Done
71011202 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-03 | Done late
71011202 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-07 | Done
71011202 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011202 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011202 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-11 |  |  | Pending
71011202 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-11-14 |  |  | Pending
71011202 | PBB | 8 | Knitting start | Factory | 2026-11-16 |  |  | Pending
71011202 | PBB | 9 | Linking start | Factory | 2026-11-22 |  |  | Pending
71011202 | PBB | 10 | Final inspection | Karbar QA | 2026-12-24 |  |  | Pending
71011202 | PBB | 11 | Ex-factory | Factory | 2026-12-26 |  |  | Pending
71011208 | SND | 1 | Yarn booking | Factory | 2026-09-24 |  | 2026-09-22 | Done
71011208 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71011208 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-08 | Done
71011208 | SND | 4 | Size set approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011208 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71011208 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-14 |  |  | Pending
71011208 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-11-17 |  |  | Pending
71011208 | SND | 8 | Knitting start | Factory | 2026-11-19 |  |  | Pending
71011208 | SND | 9 | Linking start | Factory | 2026-11-25 |  |  | Pending
71011208 | SND | 10 | Final inspection | Karbar QA | 2026-12-28 |  |  | Pending
71011208 | SND | 11 | Ex-factory | Factory | 2026-12-29 |  |  | Pending
71011215 | GRL | 1 | Yarn booking | Factory | 2026-10-13 |  | 2026-10-12 | Done
71011215 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011215 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011215 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011215 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011215 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-02 |  |  | Pending
71011215 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-05 |  |  | Pending
71011215 | GRL | 8 | Knitting start | Factory | 2026-12-07 |  |  | Pending
71011215 | GRL | 9 | Linking start | Factory | 2026-12-13 |  |  | Pending
71011215 | GRL | 10 | Final inspection | Karbar QA | 2027-01-14 |  |  | Pending
71011215 | GRL | 11 | Ex-factory | Factory | 2027-01-16 |  |  | Pending
71011222 | RVS | 1 | Yarn booking | Factory | 2026-10-20 |  |  | Pending
71011222 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011222 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011222 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011222 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011222 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-09 |  |  | Pending
71011222 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-12-12 |  |  | Pending
71011222 | RVS | 8 | Knitting start | Factory | 2026-12-14 |  |  | Pending
71011222 | RVS | 9 | Linking start | Factory | 2026-12-20 |  |  | Pending
71011222 | RVS | 10 | Final inspection | Karbar QA | 2027-01-21 |  |  | Pending
71011222 | RVS | 11 | Ex-factory | Factory | 2027-01-23 |  |  | Pending
71011230 | OKH | 1 | Yarn booking | Factory | 2026-09-24 |  | 2026-09-24 | Done
71011230 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-05 | Done
71011230 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-10-10 |  | 2026-10-10 | Done
71011230 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011230 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71011230 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-14 |  |  | Pending
71011230 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-11-17 |  |  | Pending
71011230 | OKH | 8 | Knitting start | Factory | 2026-11-19 |  |  | Pending
71011230 | OKH | 9 | Linking start | Factory | 2026-11-25 |  |  | Pending
71011230 | OKH | 10 | Final inspection | Karbar QA | 2026-12-28 |  |  | Pending
71011230 | OKH | 11 | Ex-factory | Factory | 2026-12-29 |  |  | Pending
71011239 | AMB | 1 | Yarn booking | Factory | 2026-10-17 |  |  | Pending
71011239 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011239 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011239 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011239 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-12-01 |  |  | Pending
71011239 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-06 |  |  | Pending
71011239 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-12-09 |  |  | Pending
71011239 | AMB | 8 | Knitting start | Factory | 2026-12-10 |  |  | Pending
71011239 | AMB | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011239 | AMB | 10 | Final inspection | Karbar QA | 2027-01-19 |  |  | Pending
71011239 | AMB | 11 | Ex-factory | Factory | 2027-01-20 |  |  | Pending
71011243 | CLB | 1 | Yarn booking | Factory | 2026-10-20 |  |  | Pending
71011243 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011243 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011243 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011243 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011243 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-09 |  |  | Pending
71011243 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-12-12 |  |  | Pending
71011243 | CLB | 8 | Knitting start | Factory | 2026-12-14 |  |  | Pending
71011243 | CLB | 9 | Linking start | Factory | 2026-12-20 |  |  | Pending
71011243 | CLB | 10 | Final inspection | Karbar QA | 2027-01-21 |  |  | Pending
71011243 | CLB | 11 | Ex-factory | Factory | 2027-01-23 |  |  | Pending
71011247 | TLG | 1 | Yarn booking | Factory | 2026-10-21 |  |  | Pending
71011247 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011247 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011247 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011247 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-12-05 |  |  | Pending
71011247 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011247 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-12-13 |  |  | Pending
71011247 | TLG | 8 | Knitting start | Factory | 2026-12-15 |  |  | Pending
71011247 | TLG | 9 | Linking start | Factory | 2026-12-21 |  |  | Pending
71011247 | TLG | 10 | Final inspection | Karbar QA | 2027-01-23 |  |  | Pending
71011247 | TLG | 11 | Ex-factory | Factory | 2027-01-24 |  |  | Pending
71011253 | WSM | 1 | Yarn booking | Factory | 2026-09-20 |  | 2026-09-20 | Done
71011253 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-09-30 |  | 2026-09-30 | Done
71011253 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-05 |  | 2026-10-03 | Done
71011253 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011253 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011253 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-09 |  |  | Pending
71011253 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-11-12 |  |  | Pending
71011253 | WSM | 8 | Knitting start | Factory | 2026-11-14 |  |  | Pending
71011253 | WSM | 9 | Linking start | Factory | 2026-11-19 |  |  | Pending
71011253 | WSM | 10 | Final inspection | Karbar QA | 2026-12-23 |  |  | Pending
71011253 | WSM | 11 | Ex-factory | Factory | 2026-12-24 |  |  | Pending
71011261 | SLM | 1 | Yarn booking | Factory | 2026-10-08 |  | 2026-10-07 | Done
71011261 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71011261 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011261 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011261 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011261 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011261 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-30 |  |  | Pending
71011261 | SLM | 8 | Knitting start | Factory | 2026-12-02 |  |  | Pending
71011261 | SLM | 9 | Linking start | Factory | 2026-12-08 |  |  | Pending
71011261 | SLM | 10 | Final inspection | Karbar QA | 2027-01-10 |  |  | Pending
71011261 | SLM | 11 | Ex-factory | Factory | 2027-01-11 |  |  | Pending
71011267 | GRL | 1 | Yarn booking | Factory | 2026-10-21 |  |  | Pending
71011267 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011267 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011267 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011267 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-05 |  |  | Pending
71011267 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011267 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-13 |  |  | Pending
71011267 | GRL | 8 | Knitting start | Factory | 2026-12-15 |  |  | Pending
71011267 | GRL | 9 | Linking start | Factory | 2026-12-21 |  |  | Pending
71011267 | GRL | 10 | Final inspection | Karbar QA | 2027-01-23 |  |  | Pending
71011267 | GRL | 11 | Ex-factory | Factory | 2027-01-24 |  |  | Pending
71011276 | CPL | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011276 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011276 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011276 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011276 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-07 |  |  | Pending
71011276 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-12 |  |  | Pending
71011276 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-15 |  |  | Pending
71011276 | CPL | 8 | Knitting start | Factory | 2026-12-17 |  |  | Pending
71011276 | CPL | 9 | Linking start | Factory | 2026-12-23 |  |  | Pending
71011276 | CPL | 10 | Final inspection | Karbar QA | 2027-01-25 |  |  | Pending
71011276 | CPL | 11 | Ex-factory | Factory | 2027-01-26 |  |  | Pending
71011284 | SLM | 1 | Yarn booking | Factory | 2026-09-22 |  | 2026-09-22 | Done
71011284 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-01 |  | 2026-10-01 | Done
71011284 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-07 |  | 2026-10-06 | Done
71011284 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011284 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011284 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-11 |  |  | Pending
71011284 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-11-14 |  |  | Pending
71011284 | SLM | 8 | Knitting start | Factory | 2026-11-16 |  |  | Pending
71011284 | SLM | 9 | Linking start | Factory | 2026-11-22 |  |  | Pending
71011284 | SLM | 10 | Final inspection | Karbar QA | 2026-12-24 |  |  | Pending
71011284 | SLM | 11 | Ex-factory | Factory | 2026-12-26 |  |  | Pending
71011289 | MDW | 1 | Yarn booking | Factory | 2026-09-23 |  | 2026-09-23 | Done
71011289 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-03 |  | 2026-10-03 | Done
71011289 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71011289 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011289 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011289 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-12 |  |  | Pending
71011289 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-11-15 |  |  | Pending
71011289 | MDW | 8 | Knitting start | Factory | 2026-11-17 |  |  | Pending
71011289 | MDW | 9 | Linking start | Factory | 2026-11-23 |  |  | Pending
71011289 | MDW | 10 | Final inspection | Karbar QA | 2026-12-26 |  |  | Pending
71011289 | MDW | 11 | Ex-factory | Factory | 2026-12-27 |  |  | Pending
71011292 | SLM | 1 | Yarn booking | Factory | 2026-10-15 |  |  | Pending
71011292 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011292 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011292 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011292 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011292 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-05 |  |  | Pending
71011292 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-12-08 |  |  | Pending
71011292 | SLM | 8 | Knitting start | Factory | 2026-12-10 |  |  | Pending
71011292 | SLM | 9 | Linking start | Factory | 2026-12-16 |  |  | Pending
71011292 | SLM | 10 | Final inspection | Karbar QA | 2027-01-18 |  |  | Pending
71011292 | SLM | 11 | Ex-factory | Factory | 2027-01-19 |  |  | Pending
71011298 | GRL | 1 | Yarn booking | Factory | 2026-10-27 |  |  | Pending
71011298 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011298 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011298 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-12-01 |  |  | Pending
71011298 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011298 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-16 |  |  | Pending
71011298 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-19 |  |  | Pending
71011298 | GRL | 8 | Knitting start | Factory | 2026-12-21 |  |  | Pending
71011298 | GRL | 9 | Linking start | Factory | 2026-12-27 |  |  | Pending
71011298 | GRL | 10 | Final inspection | Karbar QA | 2027-01-28 |  |  | Pending
71011298 | GRL | 11 | Ex-factory | Factory | 2027-01-30 |  |  | Pending
71011305 | GRL | 1 | Yarn booking | Factory | 2026-09-29 |  | 2026-09-27 | Done
71011305 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-08 |  | 2026-10-10 | Done late
71011305 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-14 |  | 2026-10-14 | Done
71011305 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-03 |  |  | Pending
71011305 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011305 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-18 |  |  | Pending
71011305 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-11-21 |  |  | Pending
71011305 | GRL | 8 | Knitting start | Factory | 2026-11-23 |  |  | Pending
71011305 | GRL | 9 | Linking start | Factory | 2026-11-29 |  |  | Pending
71011305 | GRL | 10 | Final inspection | Karbar QA | 2026-12-31 |  |  | Pending
71011305 | GRL | 11 | Ex-factory | Factory | 2027-01-02 |  |  | Pending
71011309 | CPL | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011309 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011309 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011309 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011309 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011309 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011309 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011309 | CPL | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011309 | CPL | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011309 | CPL | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011309 | CPL | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011317 | CPL | 1 | Yarn booking | Factory | 2026-10-20 |  |  | Pending
71011317 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011317 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011317 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011317 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011317 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-09 |  |  | Pending
71011317 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-12 |  |  | Pending
71011317 | CPL | 8 | Knitting start | Factory | 2026-12-14 |  |  | Pending
71011317 | CPL | 9 | Linking start | Factory | 2026-12-20 |  |  | Pending
71011317 | CPL | 10 | Final inspection | Karbar QA | 2027-01-21 |  |  | Pending
71011317 | CPL | 11 | Ex-factory | Factory | 2027-01-23 |  |  | Pending
71011323 | PBB | 1 | Yarn booking | Factory | 2026-10-29 |  |  | Pending
71011323 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71011323 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-14 |  |  | Pending
71011323 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011323 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-12-14 |  |  | Pending
71011323 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-19 |  |  | Pending
71011323 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-12-22 |  |  | Pending
71011323 | PBB | 8 | Knitting start | Factory | 2026-12-24 |  |  | Pending
71011323 | PBB | 9 | Linking start | Factory | 2026-12-30 |  |  | Pending
71011323 | PBB | 10 | Final inspection | Karbar QA | 2027-02-01 |  |  | Pending
71011323 | PBB | 11 | Ex-factory | Factory | 2027-02-02 |  |  | Pending
71011327 | SND | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011327 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011327 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011327 | SND | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011327 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011327 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011327 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-12-14 |  |  | Pending
71011327 | SND | 8 | Knitting start | Factory | 2026-12-16 |  |  | Pending
71011327 | SND | 9 | Linking start | Factory | 2026-12-22 |  |  | Pending
71011327 | SND | 10 | Final inspection | Karbar QA | 2027-01-24 |  |  | Pending
71011327 | SND | 11 | Ex-factory | Factory | 2027-01-25 |  |  | Pending
71011335 | AMB | 1 | Yarn booking | Factory | 2026-10-01 |  | 2026-10-03 | Done late
71011335 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-12 | Done late
71011335 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-15 |  |  | Pending
71011335 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011335 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011335 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-19 |  |  | Pending
71011335 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-11-23 |  |  | Pending
71011335 | AMB | 8 | Knitting start | Factory | 2026-11-25 |  |  | Pending
71011335 | AMB | 9 | Linking start | Factory | 2026-12-01 |  |  | Pending
71011335 | AMB | 10 | Final inspection | Karbar QA | 2027-01-03 |  |  | Pending
71011335 | AMB | 11 | Ex-factory | Factory | 2027-01-04 |  |  | Pending
71011338 | MDW | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-08 | Done late
71011338 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011338 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011338 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011338 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011338 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011338 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011338 | MDW | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011338 | MDW | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011338 | MDW | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011338 | MDW | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011345 | OKH | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011345 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011345 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011345 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011345 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011345 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011345 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011345 | OKH | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011345 | OKH | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011345 | OKH | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011345 | OKH | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011352 | RVS | 1 | Yarn booking | Factory | 2026-09-26 |  | 2026-09-26 | Done
71011352 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-06 |  | 2026-10-05 | Done
71011352 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-11 |  | 2026-10-08 | Done
71011352 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011352 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-11-10 |  |  | Pending
71011352 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-15 |  |  | Pending
71011352 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-11-18 |  |  | Pending
71011352 | RVS | 8 | Knitting start | Factory | 2026-11-19 |  |  | Pending
71011352 | RVS | 9 | Linking start | Factory | 2026-11-26 |  |  | Pending
71011352 | RVS | 10 | Final inspection | Karbar QA | 2026-12-29 |  |  | Pending
71011352 | RVS | 11 | Ex-factory | Factory | 2026-12-30 |  |  | Pending
71011356 | PBB | 1 | Yarn booking | Factory | 2026-10-13 |  | 2026-10-13 | Done
71011356 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011356 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011356 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011356 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011356 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-02 |  |  | Pending
71011356 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-12-05 |  |  | Pending
71011356 | PBB | 8 | Knitting start | Factory | 2026-12-07 |  |  | Pending
71011356 | PBB | 9 | Linking start | Factory | 2026-12-13 |  |  | Pending
71011356 | PBB | 10 | Final inspection | Karbar QA | 2027-01-14 |  |  | Pending
71011356 | PBB | 11 | Ex-factory | Factory | 2027-01-16 |  |  | Pending
71011363 | WSM | 1 | Yarn booking | Factory | 2026-10-15 |  |  | Pending
71011363 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011363 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011363 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011363 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011363 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-05 |  |  | Pending
71011363 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-12-08 |  |  | Pending
71011363 | WSM | 8 | Knitting start | Factory | 2026-12-10 |  |  | Pending
71011363 | WSM | 9 | Linking start | Factory | 2026-12-16 |  |  | Pending
71011363 | WSM | 10 | Final inspection | Karbar QA | 2027-01-18 |  |  | Pending
71011363 | WSM | 11 | Ex-factory | Factory | 2027-01-19 |  |  | Pending
71011372 | MDW | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-06 | Done
71011372 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011372 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011372 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011372 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011372 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011372 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011372 | MDW | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011372 | MDW | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011372 | MDW | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011372 | MDW | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011377 | GRL | 1 | Yarn booking | Factory | 2026-10-11 |  | 2026-10-11 | Done
71011377 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71011377 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011377 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011377 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011377 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-30 |  |  | Pending
71011377 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-03 |  |  | Pending
71011377 | GRL | 8 | Knitting start | Factory | 2026-12-05 |  |  | Pending
71011377 | GRL | 9 | Linking start | Factory | 2026-12-10 |  |  | Pending
71011377 | GRL | 10 | Final inspection | Karbar QA | 2027-01-13 |  |  | Pending
71011377 | GRL | 11 | Ex-factory | Factory | 2027-01-14 |  |  | Pending
71011382 | AMB | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011382 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011382 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011382 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011382 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011382 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011382 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011382 | AMB | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011382 | AMB | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011382 | AMB | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011382 | AMB | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011386 | GRL | 1 | Yarn booking | Factory | 2026-10-10 |  | 2026-10-08 | Done
71011386 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-20 |  |  | Pending
71011386 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011386 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-14 |  |  | Pending
71011386 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011386 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-29 |  |  | Pending
71011386 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-02 |  |  | Pending
71011386 | GRL | 8 | Knitting start | Factory | 2026-12-03 |  |  | Pending
71011386 | GRL | 9 | Linking start | Factory | 2026-12-10 |  |  | Pending
71011386 | GRL | 10 | Final inspection | Karbar QA | 2027-01-12 |  |  | Pending
71011386 | GRL | 11 | Ex-factory | Factory | 2027-01-13 |  |  | Pending
71011394 | FNS | 1 | Yarn booking | Factory | 2026-10-15 |  |  | Pending
71011394 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-25 |  |  | Pending
71011394 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011394 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011394 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-11-29 |  |  | Pending
71011394 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-03 |  |  | Pending
71011394 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-12-07 |  |  | Pending
71011394 | FNS | 8 | Knitting start | Factory | 2026-12-09 |  |  | Pending
71011394 | FNS | 9 | Linking start | Factory | 2026-12-15 |  |  | Pending
71011394 | FNS | 10 | Final inspection | Karbar QA | 2027-01-17 |  |  | Pending
71011394 | FNS | 11 | Ex-factory | Factory | 2027-01-18 |  |  | Pending
71011403 | CPL | 1 | Yarn booking | Factory | 2026-10-07 |  | 2026-10-07 | Done
71011403 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-17 |  |  | Pending
71011403 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011403 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011403 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011403 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011403 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-11-29 |  |  | Pending
71011403 | CPL | 8 | Knitting start | Factory | 2026-12-01 |  |  | Pending
71011403 | CPL | 9 | Linking start | Factory | 2026-12-07 |  |  | Pending
71011403 | CPL | 10 | Final inspection | Karbar QA | 2027-01-09 |  |  | Pending
71011403 | CPL | 11 | Ex-factory | Factory | 2027-01-10 |  |  | Pending
71011410 | CPL | 1 | Yarn booking | Factory | 2026-10-13 |  | 2026-10-13 | Done
71011410 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011410 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011410 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011410 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011410 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-02 |  |  | Pending
71011410 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-05 |  |  | Pending
71011410 | CPL | 8 | Knitting start | Factory | 2026-12-07 |  |  | Pending
71011410 | CPL | 9 | Linking start | Factory | 2026-12-13 |  |  | Pending
71011410 | CPL | 10 | Final inspection | Karbar QA | 2027-01-14 |  |  | Pending
71011410 | CPL | 11 | Ex-factory | Factory | 2027-01-16 |  |  | Pending
71011418 | FNS | 1 | Yarn booking | Factory | 2026-10-28 |  |  | Pending
71011418 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011418 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011418 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011418 | FNS | 5 | PP sample approval | Karbar Merchandising | 2026-12-12 |  |  | Pending
71011418 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-17 |  |  | Pending
71011418 | FNS | 7 | PP meeting | Factory + Karbar QA | 2026-12-20 |  |  | Pending
71011418 | FNS | 8 | Knitting start | Factory | 2026-12-22 |  |  | Pending
71011418 | FNS | 9 | Linking start | Factory | 2026-12-28 |  |  | Pending
71011418 | FNS | 10 | Final inspection | Karbar QA | 2027-01-30 |  |  | Pending
71011418 | FNS | 11 | Ex-factory | Factory | 2027-01-31 |  |  | Pending
71011424 | BRW | 1 | Yarn booking | Factory | 2026-10-08 |  | 2026-10-08 | Done
71011424 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-18 |  |  | Pending
71011424 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-10-22 |  |  | Pending
71011424 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011424 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011424 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-26 |  |  | Pending
71011424 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-11-30 |  |  | Pending
71011424 | BRW | 8 | Knitting start | Factory | 2026-12-02 |  |  | Pending
71011424 | BRW | 9 | Linking start | Factory | 2026-12-08 |  |  | Pending
71011424 | BRW | 10 | Final inspection | Karbar QA | 2027-01-10 |  |  | Pending
71011424 | BRW | 11 | Ex-factory | Factory | 2027-01-11 |  |  | Pending
71011430 | RVS | 1 | Yarn booking | Factory | 2026-10-28 |  |  | Pending
71011430 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011430 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011430 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011430 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-12-12 |  |  | Pending
71011430 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-17 |  |  | Pending
71011430 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-12-20 |  |  | Pending
71011430 | RVS | 8 | Knitting start | Factory | 2026-12-22 |  |  | Pending
71011430 | RVS | 9 | Linking start | Factory | 2026-12-28 |  |  | Pending
71011430 | RVS | 10 | Final inspection | Karbar QA | 2027-01-30 |  |  | Pending
71011430 | RVS | 11 | Ex-factory | Factory | 2027-01-31 |  |  | Pending
71011433 | GRL | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011433 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011433 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011433 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011433 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011433 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011433 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011433 | GRL | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011433 | GRL | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011433 | GRL | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011433 | GRL | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011436 | MDW | 1 | Yarn booking | Factory | 2026-10-20 |  |  | Pending
71011436 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-29 |  |  | Pending
71011436 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011436 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-11-24 |  |  | Pending
71011436 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011436 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-09 |  |  | Pending
71011436 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-12-12 |  |  | Pending
71011436 | MDW | 8 | Knitting start | Factory | 2026-12-14 |  |  | Pending
71011436 | MDW | 9 | Linking start | Factory | 2026-12-20 |  |  | Pending
71011436 | MDW | 10 | Final inspection | Karbar QA | 2027-01-21 |  |  | Pending
71011436 | MDW | 11 | Ex-factory | Factory | 2027-01-23 |  |  | Pending
71011442 | KST | 1 | Yarn booking | Factory | 2026-11-10 |  |  | Pending
71011442 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011442 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011442 | KST | 4 | Size set approval | Karbar Merchandising | 2026-12-15 |  |  | Pending
71011442 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-12-24 |  |  | Pending
71011442 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-30 |  |  | Pending
71011442 | KST | 7 | PP meeting | Factory + Karbar QA | 2027-01-02 |  |  | Pending
71011442 | KST | 8 | Knitting start | Factory | 2027-01-04 |  |  | Pending
71011442 | KST | 9 | Linking start | Factory | 2027-01-10 |  |  | Pending
71011442 | KST | 10 | Final inspection | Karbar QA | 2027-02-11 |  |  | Pending
71011442 | KST | 11 | Ex-factory | Factory | 2027-02-13 |  |  | Pending
71011447 | TLG | 1 | Yarn booking | Factory | 2026-10-11 |  | 2026-10-10 | Done
71011447 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-21 |  |  | Pending
71011447 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011447 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011447 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011447 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-11-30 |  |  | Pending
71011447 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-12-03 |  |  | Pending
71011447 | TLG | 8 | Knitting start | Factory | 2026-12-05 |  |  | Pending
71011447 | TLG | 9 | Linking start | Factory | 2026-12-10 |  |  | Pending
71011447 | TLG | 10 | Final inspection | Karbar QA | 2027-01-13 |  |  | Pending
71011447 | TLG | 11 | Ex-factory | Factory | 2027-01-14 |  |  | Pending
71011456 | SND | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011456 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011456 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011456 | SND | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011456 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011456 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011456 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-12-14 |  |  | Pending
71011456 | SND | 8 | Knitting start | Factory | 2026-12-16 |  |  | Pending
71011456 | SND | 9 | Linking start | Factory | 2026-12-22 |  |  | Pending
71011456 | SND | 10 | Final inspection | Karbar QA | 2027-01-24 |  |  | Pending
71011456 | SND | 11 | Ex-factory | Factory | 2027-01-25 |  |  | Pending
71011461 | CLB | 1 | Yarn booking | Factory | 2026-10-28 |  |  | Pending
71011461 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011461 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011461 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011461 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-12-12 |  |  | Pending
71011461 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-17 |  |  | Pending
71011461 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-12-20 |  |  | Pending
71011461 | CLB | 8 | Knitting start | Factory | 2026-12-22 |  |  | Pending
71011461 | CLB | 9 | Linking start | Factory | 2026-12-28 |  |  | Pending
71011461 | CLB | 10 | Final inspection | Karbar QA | 2027-01-30 |  |  | Pending
71011461 | CLB | 11 | Ex-factory | Factory | 2027-01-31 |  |  | Pending
71011470 | GRL | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011470 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011470 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011470 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011470 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011470 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011470 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011470 | GRL | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011470 | GRL | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011470 | GRL | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011470 | GRL | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011473 | GRL | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011473 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011473 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011473 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011473 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011473 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011473 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011473 | GRL | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011473 | GRL | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011473 | GRL | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011473 | GRL | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011480 | TLG | 1 | Yarn booking | Factory | 2026-10-17 |  |  | Pending
71011480 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-27 |  |  | Pending
71011480 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011480 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011480 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-12-01 |  |  | Pending
71011480 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-06 |  |  | Pending
71011480 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-12-09 |  |  | Pending
71011480 | TLG | 8 | Knitting start | Factory | 2026-12-10 |  |  | Pending
71011480 | TLG | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011480 | TLG | 10 | Final inspection | Karbar QA | 2027-01-19 |  |  | Pending
71011480 | TLG | 11 | Ex-factory | Factory | 2027-01-20 |  |  | Pending
71011487 | SND | 1 | Yarn booking | Factory | 2026-11-05 |  |  | Pending
71011487 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011487 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011487 | SND | 4 | Size set approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011487 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011487 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-24 |  |  | Pending
71011487 | SND | 7 | PP meeting | Factory + Karbar QA | 2026-12-28 |  |  | Pending
71011487 | SND | 8 | Knitting start | Factory | 2026-12-30 |  |  | Pending
71011487 | SND | 9 | Linking start | Factory | 2027-01-05 |  |  | Pending
71011487 | SND | 10 | Final inspection | Karbar QA | 2027-02-07 |  |  | Pending
71011487 | SND | 11 | Ex-factory | Factory | 2027-02-08 |  |  | Pending
71011493 | MDW | 1 | Yarn booking | Factory | 2026-11-05 |  |  | Pending
71011493 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011493 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011493 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011493 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011493 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-24 |  |  | Pending
71011493 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-12-28 |  |  | Pending
71011493 | MDW | 8 | Knitting start | Factory | 2026-12-30 |  |  | Pending
71011493 | MDW | 9 | Linking start | Factory | 2027-01-05 |  |  | Pending
71011493 | MDW | 10 | Final inspection | Karbar QA | 2027-02-07 |  |  | Pending
71011493 | MDW | 11 | Ex-factory | Factory | 2027-02-08 |  |  | Pending
71011502 | TLG | 1 | Yarn booking | Factory | 2026-11-05 |  |  | Pending
71011502 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011502 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011502 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011502 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-12-21 |  |  | Pending
71011502 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-26 |  |  | Pending
71011502 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-12-29 |  |  | Pending
71011502 | TLG | 8 | Knitting start | Factory | 2026-12-31 |  |  | Pending
71011502 | TLG | 9 | Linking start | Factory | 2027-01-06 |  |  | Pending
71011502 | TLG | 10 | Final inspection | Karbar QA | 2027-02-08 |  |  | Pending
71011502 | TLG | 11 | Ex-factory | Factory | 2027-02-09 |  |  | Pending
71011507 | OKH | 1 | Yarn booking | Factory | 2026-10-25 |  |  | Pending
71011507 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-04 |  |  | Pending
71011507 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-11-09 |  |  | Pending
71011507 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-11-29 |  |  | Pending
71011507 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-12-09 |  |  | Pending
71011507 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-14 |  |  | Pending
71011507 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-12-17 |  |  | Pending
71011507 | OKH | 8 | Knitting start | Factory | 2026-12-19 |  |  | Pending
71011507 | OKH | 9 | Linking start | Factory | 2026-12-24 |  |  | Pending
71011507 | OKH | 10 | Final inspection | Karbar QA | 2027-01-27 |  |  | Pending
71011507 | OKH | 11 | Ex-factory | Factory | 2027-01-28 |  |  | Pending
71011512 | WSM | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011512 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011512 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011512 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011512 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011512 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011512 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-12-14 |  |  | Pending
71011512 | WSM | 8 | Knitting start | Factory | 2026-12-16 |  |  | Pending
71011512 | WSM | 9 | Linking start | Factory | 2026-12-22 |  |  | Pending
71011512 | WSM | 10 | Final inspection | Karbar QA | 2027-01-24 |  |  | Pending
71011512 | WSM | 11 | Ex-factory | Factory | 2027-01-25 |  |  | Pending
71011518 | RVS | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011518 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011518 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011518 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011518 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011518 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011518 | RVS | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011518 | RVS | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011518 | RVS | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011518 | RVS | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011518 | RVS | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011524 | WSM | 1 | Yarn booking | Factory | 2026-11-03 |  |  | Pending
71011524 | WSM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011524 | WSM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011524 | WSM | 4 | Size set approval | Karbar Merchandising | 2026-12-08 |  |  | Pending
71011524 | WSM | 5 | PP sample approval | Karbar Merchandising | 2026-12-17 |  |  | Pending
71011524 | WSM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-23 |  |  | Pending
71011524 | WSM | 7 | PP meeting | Factory + Karbar QA | 2026-12-26 |  |  | Pending
71011524 | WSM | 8 | Knitting start | Factory | 2026-12-28 |  |  | Pending
71011524 | WSM | 9 | Linking start | Factory | 2027-01-03 |  |  | Pending
71011524 | WSM | 10 | Final inspection | Karbar QA | 2027-02-04 |  |  | Pending
71011524 | WSM | 11 | Ex-factory | Factory | 2027-02-06 |  |  | Pending
71011530 | CPL | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011530 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011530 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011530 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011530 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011530 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011530 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011530 | CPL | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011530 | CPL | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011530 | CPL | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011530 | CPL | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011534 | FNS | 1 | Yarn booking | Factory | 2026-11-22 |  |  | Pending
71011534 | FNS | 2 | Yarn shade approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011534 | FNS | 3 | Fit sample approval | Karbar Merchandising | 2026-12-07 |  |  | Pending
71011534 | FNS | 4 | Size set approval | Karbar Merchandising | 2026-12-27 |  |  | Pending
71011534 | FNS | 5 | PP sample approval | Karbar Merchandising | 2027-01-06 |  |  | Pending
71011534 | FNS | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-11 |  |  | Pending
71011534 | FNS | 7 | PP meeting | Factory + Karbar QA | 2027-01-14 |  |  | Pending
71011534 | FNS | 8 | Knitting start | Factory | 2027-01-16 |  |  | Pending
71011534 | FNS | 9 | Linking start | Factory | 2027-01-21 |  |  | Pending
71011534 | FNS | 10 | Final inspection | Karbar QA | 2027-02-24 |  |  | Pending
71011534 | FNS | 11 | Ex-factory | Factory | 2027-02-25 |  |  | Pending
71011537 | BRW | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011537 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011537 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011537 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011537 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-12-07 |  |  | Pending
71011537 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-12 |  |  | Pending
71011537 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-12-15 |  |  | Pending
71011537 | BRW | 8 | Knitting start | Factory | 2026-12-17 |  |  | Pending
71011537 | BRW | 9 | Linking start | Factory | 2026-12-23 |  |  | Pending
71011537 | BRW | 10 | Final inspection | Karbar QA | 2027-01-25 |  |  | Pending
71011537 | BRW | 11 | Ex-factory | Factory | 2027-01-26 |  |  | Pending
71011546 | SLM | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011546 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011546 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011546 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011546 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011546 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011546 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011546 | SLM | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011546 | SLM | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011546 | SLM | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011546 | SLM | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011553 | AMB | 1 | Yarn booking | Factory | 2026-10-15 |  |  | Pending
71011553 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-26 |  |  | Pending
71011553 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-10-31 |  |  | Pending
71011553 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011553 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011553 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-05 |  |  | Pending
71011553 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-12-08 |  |  | Pending
71011553 | AMB | 8 | Knitting start | Factory | 2026-12-10 |  |  | Pending
71011553 | AMB | 9 | Linking start | Factory | 2026-12-16 |  |  | Pending
71011553 | AMB | 10 | Final inspection | Karbar QA | 2027-01-18 |  |  | Pending
71011553 | AMB | 11 | Ex-factory | Factory | 2027-01-19 |  |  | Pending
71011562 | MDW | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011562 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011562 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011562 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011562 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011562 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011562 | MDW | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011562 | MDW | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011562 | MDW | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011562 | MDW | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011562 | MDW | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011565 | BRW | 1 | Yarn booking | Factory | 2026-10-18 |  |  | Pending
71011565 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-10-28 |  |  | Pending
71011565 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-02 |  |  | Pending
71011565 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011565 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011565 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-07 |  |  | Pending
71011565 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-12-10 |  |  | Pending
71011565 | BRW | 8 | Knitting start | Factory | 2026-12-12 |  |  | Pending
71011565 | BRW | 9 | Linking start | Factory | 2026-12-17 |  |  | Pending
71011565 | BRW | 10 | Final inspection | Karbar QA | 2027-01-20 |  |  | Pending
71011565 | BRW | 11 | Ex-factory | Factory | 2027-01-21 |  |  | Pending
71011572 | SVP | 1 | Yarn booking | Factory | 2026-11-01 |  |  | Pending
71011572 | SVP | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-11 |  |  | Pending
71011572 | SVP | 3 | Fit sample approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011572 | SVP | 4 | Size set approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011572 | SVP | 5 | PP sample approval | Karbar Merchandising | 2026-12-16 |  |  | Pending
71011572 | SVP | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-21 |  |  | Pending
71011572 | SVP | 7 | PP meeting | Factory + Karbar QA | 2026-12-24 |  |  | Pending
71011572 | SVP | 8 | Knitting start | Factory | 2026-12-26 |  |  | Pending
71011572 | SVP | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011572 | SVP | 10 | Final inspection | Karbar QA | 2027-02-03 |  |  | Pending
71011572 | SVP | 11 | Ex-factory | Factory | 2027-02-04 |  |  | Pending
71011575 | OKH | 1 | Yarn booking | Factory | 2026-10-22 |  |  | Pending
71011575 | OKH | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-01 |  |  | Pending
71011575 | OKH | 3 | Fit sample approval | Karbar Merchandising | 2026-11-05 |  |  | Pending
71011575 | OKH | 4 | Size set approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011575 | OKH | 5 | PP sample approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011575 | OKH | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-10 |  |  | Pending
71011575 | OKH | 7 | PP meeting | Factory + Karbar QA | 2026-12-14 |  |  | Pending
71011575 | OKH | 8 | Knitting start | Factory | 2026-12-16 |  |  | Pending
71011575 | OKH | 9 | Linking start | Factory | 2026-12-22 |  |  | Pending
71011575 | OKH | 10 | Final inspection | Karbar QA | 2027-01-24 |  |  | Pending
71011575 | OKH | 11 | Ex-factory | Factory | 2027-01-25 |  |  | Pending
71011580 | BRW | 1 | Yarn booking | Factory | 2026-10-28 |  |  | Pending
71011580 | BRW | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-07 |  |  | Pending
71011580 | BRW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011580 | BRW | 4 | Size set approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011580 | BRW | 5 | PP sample approval | Karbar Merchandising | 2026-12-12 |  |  | Pending
71011580 | BRW | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-17 |  |  | Pending
71011580 | BRW | 7 | PP meeting | Factory + Karbar QA | 2026-12-20 |  |  | Pending
71011580 | BRW | 8 | Knitting start | Factory | 2026-12-22 |  |  | Pending
71011580 | BRW | 9 | Linking start | Factory | 2026-12-28 |  |  | Pending
71011580 | BRW | 10 | Final inspection | Karbar QA | 2027-01-30 |  |  | Pending
71011580 | BRW | 11 | Ex-factory | Factory | 2027-01-31 |  |  | Pending
71011586 | GRL | 1 | Yarn booking | Factory | 2026-11-22 |  |  | Pending
71011586 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011586 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-12-07 |  |  | Pending
71011586 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-12-27 |  |  | Pending
71011586 | GRL | 5 | PP sample approval | Karbar Merchandising | 2027-01-06 |  |  | Pending
71011586 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-11 |  |  | Pending
71011586 | GRL | 7 | PP meeting | Factory + Karbar QA | 2027-01-14 |  |  | Pending
71011586 | GRL | 8 | Knitting start | Factory | 2027-01-16 |  |  | Pending
71011586 | GRL | 9 | Linking start | Factory | 2027-01-21 |  |  | Pending
71011586 | GRL | 10 | Final inspection | Karbar QA | 2027-02-24 |  |  | Pending
71011586 | GRL | 11 | Ex-factory | Factory | 2027-02-25 |  |  | Pending
71011593 | SLM | 1 | Yarn booking | Factory | 2026-11-15 |  |  | Pending
71011593 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011593 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011593 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011593 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011593 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-04 |  |  | Pending
71011593 | SLM | 7 | PP meeting | Factory + Karbar QA | 2027-01-07 |  |  | Pending
71011593 | SLM | 8 | Knitting start | Factory | 2027-01-09 |  |  | Pending
71011593 | SLM | 9 | Linking start | Factory | 2027-01-14 |  |  | Pending
71011593 | SLM | 10 | Final inspection | Karbar QA | 2027-02-17 |  |  | Pending
71011593 | SLM | 11 | Ex-factory | Factory | 2027-02-18 |  |  | Pending
71011598 | MDW | 1 | Yarn booking | Factory | 2026-11-15 |  |  | Pending
71011598 | MDW | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011598 | MDW | 3 | Fit sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011598 | MDW | 4 | Size set approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011598 | MDW | 5 | PP sample approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011598 | MDW | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-04 |  |  | Pending
71011598 | MDW | 7 | PP meeting | Factory + Karbar QA | 2027-01-07 |  |  | Pending
71011598 | MDW | 8 | Knitting start | Factory | 2027-01-09 |  |  | Pending
71011598 | MDW | 9 | Linking start | Factory | 2027-01-14 |  |  | Pending
71011598 | MDW | 10 | Final inspection | Karbar QA | 2027-02-17 |  |  | Pending
71011598 | MDW | 11 | Ex-factory | Factory | 2027-02-18 |  |  | Pending
71011601 | TLG | 1 | Yarn booking | Factory | 2026-10-31 |  |  | Pending
71011601 | TLG | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-10 |  |  | Pending
71011601 | TLG | 3 | Fit sample approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011601 | TLG | 4 | Size set approval | Karbar Merchandising | 2026-12-05 |  |  | Pending
71011601 | TLG | 5 | PP sample approval | Karbar Merchandising | 2026-12-15 |  |  | Pending
71011601 | TLG | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-20 |  |  | Pending
71011601 | TLG | 7 | PP meeting | Factory + Karbar QA | 2026-12-23 |  |  | Pending
71011601 | TLG | 8 | Knitting start | Factory | 2026-12-24 |  |  | Pending
71011601 | TLG | 9 | Linking start | Factory | 2026-12-31 |  |  | Pending
71011601 | TLG | 10 | Final inspection | Karbar QA | 2027-02-02 |  |  | Pending
71011601 | TLG | 11 | Ex-factory | Factory | 2027-02-03 |  |  | Pending
71011609 | SLM | 1 | Yarn booking | Factory | 2026-11-05 |  |  | Pending
71011609 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-16 |  |  | Pending
71011609 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-21 |  |  | Pending
71011609 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011609 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-12-21 |  |  | Pending
71011609 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-26 |  |  | Pending
71011609 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-12-29 |  |  | Pending
71011609 | SLM | 8 | Knitting start | Factory | 2026-12-31 |  |  | Pending
71011609 | SLM | 9 | Linking start | Factory | 2027-01-06 |  |  | Pending
71011609 | SLM | 10 | Final inspection | Karbar QA | 2027-02-08 |  |  | Pending
71011609 | SLM | 11 | Ex-factory | Factory | 2027-02-09 |  |  | Pending
71011618 | AMB | 1 | Yarn booking | Factory | 2026-11-03 |  |  | Pending
71011618 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011618 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011618 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-12-08 |  |  | Pending
71011618 | AMB | 5 | PP sample approval | Karbar Merchandising | 2026-12-17 |  |  | Pending
71011618 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-23 |  |  | Pending
71011618 | AMB | 7 | PP meeting | Factory + Karbar QA | 2026-12-26 |  |  | Pending
71011618 | AMB | 8 | Knitting start | Factory | 2026-12-28 |  |  | Pending
71011618 | AMB | 9 | Linking start | Factory | 2027-01-03 |  |  | Pending
71011618 | AMB | 10 | Final inspection | Karbar QA | 2027-02-04 |  |  | Pending
71011618 | AMB | 11 | Ex-factory | Factory | 2027-02-06 |  |  | Pending
71011627 | GRL | 1 | Yarn booking | Factory | 2026-10-29 |  |  | Pending
71011627 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-08 |  |  | Pending
71011627 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-12 |  |  | Pending
71011627 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011627 | GRL | 5 | PP sample approval | Karbar Merchandising | 2026-12-13 |  |  | Pending
71011627 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-17 |  |  | Pending
71011627 | GRL | 7 | PP meeting | Factory + Karbar QA | 2026-12-21 |  |  | Pending
71011627 | GRL | 8 | Knitting start | Factory | 2026-12-23 |  |  | Pending
71011627 | GRL | 9 | Linking start | Factory | 2026-12-29 |  |  | Pending
71011627 | GRL | 10 | Final inspection | Karbar QA | 2027-01-31 |  |  | Pending
71011627 | GRL | 11 | Ex-factory | Factory | 2027-02-01 |  |  | Pending
71011636 | PBB | 1 | Yarn booking | Factory | 2026-11-04 |  |  | Pending
71011636 | PBB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-14 |  |  | Pending
71011636 | PBB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011636 | PBB | 4 | Size set approval | Karbar Merchandising | 2026-12-09 |  |  | Pending
71011636 | PBB | 5 | PP sample approval | Karbar Merchandising | 2026-12-19 |  |  | Pending
71011636 | PBB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-24 |  |  | Pending
71011636 | PBB | 7 | PP meeting | Factory + Karbar QA | 2026-12-27 |  |  | Pending
71011636 | PBB | 8 | Knitting start | Factory | 2026-12-29 |  |  | Pending
71011636 | PBB | 9 | Linking start | Factory | 2027-01-04 |  |  | Pending
71011636 | PBB | 10 | Final inspection | Karbar QA | 2027-02-06 |  |  | Pending
71011636 | PBB | 11 | Ex-factory | Factory | 2027-02-07 |  |  | Pending
71011645 | CLB | 1 | Yarn booking | Factory | 2026-11-08 |  |  | Pending
71011645 | CLB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011645 | CLB | 3 | Fit sample approval | Karbar Merchandising | 2026-11-23 |  |  | Pending
71011645 | CLB | 4 | Size set approval | Karbar Merchandising | 2026-12-13 |  |  | Pending
71011645 | CLB | 5 | PP sample approval | Karbar Merchandising | 2026-12-23 |  |  | Pending
71011645 | CLB | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-28 |  |  | Pending
71011645 | CLB | 7 | PP meeting | Factory + Karbar QA | 2026-12-31 |  |  | Pending
71011645 | CLB | 8 | Knitting start | Factory | 2027-01-02 |  |  | Pending
71011645 | CLB | 9 | Linking start | Factory | 2027-01-07 |  |  | Pending
71011645 | CLB | 10 | Final inspection | Karbar QA | 2027-02-10 |  |  | Pending
71011645 | CLB | 11 | Ex-factory | Factory | 2027-02-11 |  |  | Pending
71011648 | RVS | 1 | Yarn booking | Factory | 2026-11-15 |  |  | Pending
71011648 | RVS | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011648 | RVS | 3 | Fit sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011648 | RVS | 4 | Size set approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011648 | RVS | 5 | PP sample approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011648 | RVS | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-04 |  |  | Pending
71011648 | RVS | 7 | PP meeting | Factory + Karbar QA | 2027-01-07 |  |  | Pending
71011648 | RVS | 8 | Knitting start | Factory | 2027-01-09 |  |  | Pending
71011648 | RVS | 9 | Linking start | Factory | 2027-01-14 |  |  | Pending
71011648 | RVS | 10 | Final inspection | Karbar QA | 2027-02-17 |  |  | Pending
71011648 | RVS | 11 | Ex-factory | Factory | 2027-02-18 |  |  | Pending
71011657 | AMB | 1 | Yarn booking | Factory | 2026-11-19 |  |  | Pending
71011657 | AMB | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-29 |  |  | Pending
71011657 | AMB | 3 | Fit sample approval | Karbar Merchandising | 2026-12-03 |  |  | Pending
71011657 | AMB | 4 | Size set approval | Karbar Merchandising | 2026-12-24 |  |  | Pending
71011657 | AMB | 5 | PP sample approval | Karbar Merchandising | 2027-01-03 |  |  | Pending
71011657 | AMB | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-07 |  |  | Pending
71011657 | AMB | 7 | PP meeting | Factory + Karbar QA | 2027-01-11 |  |  | Pending
71011657 | AMB | 8 | Knitting start | Factory | 2027-01-13 |  |  | Pending
71011657 | AMB | 9 | Linking start | Factory | 2027-01-19 |  |  | Pending
71011657 | AMB | 10 | Final inspection | Karbar QA | 2027-02-21 |  |  | Pending
71011657 | AMB | 11 | Ex-factory | Factory | 2027-02-22 |  |  | Pending
71011660 | SLM | 1 | Yarn booking | Factory | 2026-11-17 |  |  | Pending
71011660 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-26 |  |  | Pending
71011660 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011660 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-12-22 |  |  | Pending
71011660 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-12-31 |  |  | Pending
71011660 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-06 |  |  | Pending
71011660 | SLM | 7 | PP meeting | Factory + Karbar QA | 2027-01-09 |  |  | Pending
71011660 | SLM | 8 | Knitting start | Factory | 2027-01-11 |  |  | Pending
71011660 | SLM | 9 | Linking start | Factory | 2027-01-17 |  |  | Pending
71011660 | SLM | 10 | Final inspection | Karbar QA | 2027-02-18 |  |  | Pending
71011660 | SLM | 11 | Ex-factory | Factory | 2027-02-20 |  |  | Pending
71011663 | CPL | 1 | Yarn booking | Factory | 2026-11-08 |  |  | Pending
71011663 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-18 |  |  | Pending
71011663 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-23 |  |  | Pending
71011663 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-12-13 |  |  | Pending
71011663 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-23 |  |  | Pending
71011663 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-28 |  |  | Pending
71011663 | CPL | 7 | PP meeting | Factory + Karbar QA | 2026-12-31 |  |  | Pending
71011663 | CPL | 8 | Knitting start | Factory | 2027-01-02 |  |  | Pending
71011663 | CPL | 9 | Linking start | Factory | 2027-01-07 |  |  | Pending
71011663 | CPL | 10 | Final inspection | Karbar QA | 2027-02-10 |  |  | Pending
71011663 | CPL | 11 | Ex-factory | Factory | 2027-02-11 |  |  | Pending
71011666 | KST | 1 | Yarn booking | Factory | 2026-11-07 |  |  | Pending
71011666 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-17 |  |  | Pending
71011666 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-11-22 |  |  | Pending
71011666 | KST | 4 | Size set approval | Karbar Merchandising | 2026-12-12 |  |  | Pending
71011666 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-12-22 |  |  | Pending
71011666 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-27 |  |  | Pending
71011666 | KST | 7 | PP meeting | Factory + Karbar QA | 2026-12-30 |  |  | Pending
71011666 | KST | 8 | Knitting start | Factory | 2026-12-31 |  |  | Pending
71011666 | KST | 9 | Linking start | Factory | 2027-01-07 |  |  | Pending
71011666 | KST | 10 | Final inspection | Karbar QA | 2027-02-09 |  |  | Pending
71011666 | KST | 11 | Ex-factory | Factory | 2027-02-10 |  |  | Pending
71011670 | SLM | 1 | Yarn booking | Factory | 2026-11-05 |  |  | Pending
71011670 | SLM | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-15 |  |  | Pending
71011670 | SLM | 3 | Fit sample approval | Karbar Merchandising | 2026-11-19 |  |  | Pending
71011670 | SLM | 4 | Size set approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011670 | SLM | 5 | PP sample approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011670 | SLM | 6 | Yarn in-house | Factory / Yarn supplier | 2026-12-24 |  |  | Pending
71011670 | SLM | 7 | PP meeting | Factory + Karbar QA | 2026-12-28 |  |  | Pending
71011670 | SLM | 8 | Knitting start | Factory | 2026-12-30 |  |  | Pending
71011670 | SLM | 9 | Linking start | Factory | 2027-01-05 |  |  | Pending
71011670 | SLM | 10 | Final inspection | Karbar QA | 2027-02-07 |  |  | Pending
71011670 | SLM | 11 | Ex-factory | Factory | 2027-02-08 |  |  | Pending
71011675 | KST | 1 | Yarn booking | Factory | 2026-11-12 |  |  | Pending
71011675 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-23 |  |  | Pending
71011675 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-11-28 |  |  | Pending
71011675 | KST | 4 | Size set approval | Karbar Merchandising | 2026-12-17 |  |  | Pending
71011675 | KST | 5 | PP sample approval | Karbar Merchandising | 2026-12-28 |  |  | Pending
71011675 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-02 |  |  | Pending
71011675 | KST | 7 | PP meeting | Factory + Karbar QA | 2027-01-05 |  |  | Pending
71011675 | KST | 8 | Knitting start | Factory | 2027-01-07 |  |  | Pending
71011675 | KST | 9 | Linking start | Factory | 2027-01-13 |  |  | Pending
71011675 | KST | 10 | Final inspection | Karbar QA | 2027-02-15 |  |  | Pending
71011675 | KST | 11 | Ex-factory | Factory | 2027-02-16 |  |  | Pending
71011678 | KST | 1 | Yarn booking | Factory | 2026-11-22 |  |  | Pending
71011678 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-12-02 |  |  | Pending
71011678 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-12-07 |  |  | Pending
71011678 | KST | 4 | Size set approval | Karbar Merchandising | 2026-12-27 |  |  | Pending
71011678 | KST | 5 | PP sample approval | Karbar Merchandising | 2027-01-06 |  |  | Pending
71011678 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-11 |  |  | Pending
71011678 | KST | 7 | PP meeting | Factory + Karbar QA | 2027-01-14 |  |  | Pending
71011678 | KST | 8 | Knitting start | Factory | 2027-01-16 |  |  | Pending
71011678 | KST | 9 | Linking start | Factory | 2027-01-21 |  |  | Pending
71011678 | KST | 10 | Final inspection | Karbar QA | 2027-02-24 |  |  | Pending
71011678 | KST | 11 | Ex-factory | Factory | 2027-02-25 |  |  | Pending
71011686 | SND | 1 | Yarn booking | Factory | 2026-11-15 |  |  | Pending
71011686 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011686 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011686 | SND | 4 | Size set approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011686 | SND | 5 | PP sample approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011686 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-04 |  |  | Pending
71011686 | SND | 7 | PP meeting | Factory + Karbar QA | 2027-01-07 |  |  | Pending
71011686 | SND | 8 | Knitting start | Factory | 2027-01-09 |  |  | Pending
71011686 | SND | 9 | Linking start | Factory | 2027-01-14 |  |  | Pending
71011686 | SND | 10 | Final inspection | Karbar QA | 2027-02-17 |  |  | Pending
71011686 | SND | 11 | Ex-factory | Factory | 2027-02-18 |  |  | Pending
71011691 | CPL | 1 | Yarn booking | Factory | 2026-11-15 |  |  | Pending
71011691 | CPL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-25 |  |  | Pending
71011691 | CPL | 3 | Fit sample approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011691 | CPL | 4 | Size set approval | Karbar Merchandising | 2026-12-20 |  |  | Pending
71011691 | CPL | 5 | PP sample approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011691 | CPL | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-04 |  |  | Pending
71011691 | CPL | 7 | PP meeting | Factory + Karbar QA | 2027-01-07 |  |  | Pending
71011691 | CPL | 8 | Knitting start | Factory | 2027-01-09 |  |  | Pending
71011691 | CPL | 9 | Linking start | Factory | 2027-01-14 |  |  | Pending
71011691 | CPL | 10 | Final inspection | Karbar QA | 2027-02-17 |  |  | Pending
71011691 | CPL | 11 | Ex-factory | Factory | 2027-02-18 |  |  | Pending
71011698 | SND | 1 | Yarn booking | Factory | 2026-11-25 |  |  | Pending
71011698 | SND | 2 | Yarn shade approval | Karbar Merchandising | 2026-12-05 |  |  | Pending
71011698 | SND | 3 | Fit sample approval | Karbar Merchandising | 2026-12-10 |  |  | Pending
71011698 | SND | 4 | Size set approval | Karbar Merchandising | 2026-12-30 |  |  | Pending
71011698 | SND | 5 | PP sample approval | Karbar Merchandising | 2027-01-09 |  |  | Pending
71011698 | SND | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-14 |  |  | Pending
71011698 | SND | 7 | PP meeting | Factory + Karbar QA | 2027-01-17 |  |  | Pending
71011698 | SND | 8 | Knitting start | Factory | 2027-01-19 |  |  | Pending
71011698 | SND | 9 | Linking start | Factory | 2027-01-25 |  |  | Pending
71011698 | SND | 10 | Final inspection | Karbar QA | 2027-02-27 |  |  | Pending
71011698 | SND | 11 | Ex-factory | Factory | 2027-02-28 |  |  | Pending
71011705 | GRL | 1 | Yarn booking | Factory | 2026-11-19 |  |  | Pending
71011705 | GRL | 2 | Yarn shade approval | Karbar Merchandising | 2026-11-30 |  |  | Pending
71011705 | GRL | 3 | Fit sample approval | Karbar Merchandising | 2026-12-05 |  |  | Pending
71011705 | GRL | 4 | Size set approval | Karbar Merchandising | 2026-12-24 |  |  | Pending
71011705 | GRL | 5 | PP sample approval | Karbar Merchandising | 2027-01-04 |  |  | Pending
71011705 | GRL | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-09 |  |  | Pending
71011705 | GRL | 7 | PP meeting | Factory + Karbar QA | 2027-01-12 |  |  | Pending
71011705 | GRL | 8 | Knitting start | Factory | 2027-01-14 |  |  | Pending
71011705 | GRL | 9 | Linking start | Factory | 2027-01-20 |  |  | Pending
71011705 | GRL | 10 | Final inspection | Karbar QA | 2027-02-22 |  |  | Pending
71011705 | GRL | 11 | Ex-factory | Factory | 2027-02-23 |  |  | Pending
71011710 | KST | 1 | Yarn booking | Factory | 2026-11-21 |  |  | Pending
71011710 | KST | 2 | Yarn shade approval | Karbar Merchandising | 2026-12-01 |  |  | Pending
71011710 | KST | 3 | Fit sample approval | Karbar Merchandising | 2026-12-06 |  |  | Pending
71011710 | KST | 4 | Size set approval | Karbar Merchandising | 2026-12-26 |  |  | Pending
71011710 | KST | 5 | PP sample approval | Karbar Merchandising | 2027-01-05 |  |  | Pending
71011710 | KST | 6 | Yarn in-house | Factory / Yarn supplier | 2027-01-10 |  |  | Pending
71011710 | KST | 7 | PP meeting | Factory + Karbar QA | 2027-01-13 |  |  | Pending
71011710 | KST | 8 | Knitting start | Factory | 2027-01-14 |  |  | Pending
71011710 | KST | 9 | Linking start | Factory | 2027-01-21 |  |  | Pending
71011710 | KST | 10 | Final inspection | Karbar QA | 2027-02-23 |  |  | Pending
71011710 | KST | 11 | Ex-factory | Factory | 2027-02-24 |  |  | Pending

## Columns
Sheet | Column | Type | Required | Description | Example
T&A Calendar | PO No | Text | Yes | Links to the Order Book. | 71004521
T&A Calendar | Factory Code | Text | Yes | Factory that owns the milestone. | GRL
T&A Calendar | Seq | Integer | Yes | Milestone order, 1 to 11. | 6
T&A Calendar | Milestone | Text | Yes | Yarn booking, Yarn shade approval, Fit sample approval, Size set approval, PP sample approval, Yarn in-house, PP meeting, Knitting start, Linking start, Final inspection, Ex-factory. | Yarn in-house
T&A Calendar | Responsible | Text | Yes | Who must complete it. | Factory / Yarn supplier
T&A Calendar | Planned Date | Date | Yes | Date from the T&A template (days before ex-factory). | 14-Sep-2026
T&A Calendar | Revised Date | Date | No | New committed date when the factory has warned of a delay. | 20-Oct-2026
T&A Calendar | Actual Date | Date | No | Date it happened. Blank while pending. | 22-Sep-2026
T&A Calendar | Status | Text | Yes | Done, Done late, Pending or Overdue (as of the report date). | Done late
T&A Calendar | Remarks | Text | No | Reason for a delay. | Dyed yarn delayed at spinner